## Ribbon View
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-07-01 | 2026-08-01 | 2026-08-01 | 2026-09-01 | 2026-09-01 | 2026-10-01 | 2026-10-01 | 2026-11-01 | 2026-11-01 | Status Date | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Avg Float | Max Float | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | EAC | AC (ACWP) | %Spent | %Spent (EAC) | VAC | BAC | SV(t) | SPI(t) | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Overrun | Work Underrun | Work Overrun | Total Work | Actual Work | Remaining Work | Work Discrepancy | Baseline Work | Summarized Work | Work per Day | Missing Resources | Resources | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Float Ratio™ | New Activity & Critical - Created (Snapshot) | Critical | Non-Critical | CP - Float Ratio™ | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Duration Variance (Original & Actual) | Duration Variance (Actual) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Score
Ribbons | Hard_File_updated3 | [10 empty] | 2026-10-12 | 7 | 2.12 | 35 | 0 | 35 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 1 | 60 | x | 0.11 | 0.47 | -7 | 43 | -12530 | -56725 | 0.49 | 0.81 | 180407 | 150211 | 238883 | 1.23 | 0.6 | -0.21 | 110440 | 53715 | 66245 | 91% | 54% | 44% | 37% | -58607 | 121800 | 1395 | 779 | 72% | 56% | -310 | 1085 | -84 | 1.25 | 10 | 14246 | 91461 | 180407 | 67703 | 112704 | 58607 | 121800 | 1093 | 0 | 0 | 9 | 56 | 366 | 1395 | 779 | 616 | 310 | 1085 | 0 | 8 | 22 | 73 | 0.08 | 24 | 2 | N/A | 22 | 0.08 | 2 | N/A | 2026-10-12 | 0.33 | 6 | 2 | N/A | 4 | 0.33 | 2 | N/A | 2026-10-12 | 0.23 | 26 | 6 | 20 | 0.23 | 6 | 0 | 2026-10-12 | 0 | N/A | N/A | 0.4 | 5 | 2 | 3 | 0.4 | 2 | 0 | 2026-10-12 | 0.47 | 68 | 32 | 36 | 0.47 | 32 | N/A | 2026-10-12 | 0.53 | 19 | 10 | 9 | 0.53 | 10 | N/A | 2026-10-12 | 35 | 5 | 30 | 0 | 1:06 | 11 | 0 | 0 | 35 | -5.59 | 0 | 35 | 18 | -11.9 | 7 | 3 | 8 | 95 | 53 | 53 | 42 | 42 | 0 | 100% | 0 | 100% | 0 | 0 | 1.25 | 9 | 5 | 95 | 53 | 53 | 2
Ribbons | Hard_File_updated3 | [11 empty] | 7% |  | 66% | 0% | 66% | 4% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 71% | 0% | 0% | 0% | 2% | 88% | [5 empty] | -23% | -51% | [15 empty] | -48% | [5 empty] | -29% |  |  |  | 11% | 8% | 51% | 123% | 38% | 62% | 48% | 91% |  | 0% | 0% | 9% | 4% | 26% | N/A | 56% | 44% | 29% |  |  |  | 23% | 77% |  |  | 8% | 0% | 92% |  | 8% |  |  |  |  | 33% | 0% | 67% |  | 33% |  |  |  |  | 23% | 77% |  | 23% | [7 empty] | 40% | 60% |  | 40% |  |  |  |  | 47% | 53% |  | 47% |  |  |  |  | 53% | 47% |  | 53% |  |  | 66% | 45% | 71% | 0% | 0.17 | 21% | 0% | 0% | 66% |  |  | 66% | 34% |  | 13% | 6% | 15% | 100% |  |  |  |  | 0% |  | 0% |  | 0% | 0% |  | 12% | 7% | 100% | 56% | 56%
Ribbons | Hard_File_updated2 | [10 empty] | 2026-09-10 | 9 | 2.07 | 53 | 0 | 53 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 43 | 0 | 30 | 0 | 1 | 33 | ✓ | 0.93 | 0.59 | 9 | 62 | -14405 | -14540 | 0.77 | 0.78 | 146859 | 172063 | 203647 | 1.21 | 1.01 | 0.24 | 64240 | 49700 | 64105 | 48% | 48% | 37% | 44% | -13459 | 133400 | 1399 | 753 | 60% | 54% | -154 | 1245 | -73 | 1.14 | 6 | 7446 | 36613 | 146859 | 63763 | 83096 | 13459 | 133400 | 907 | 0 | 0 | 5 | 32 | 186 | 1399 | 753 | 646 | 154 | 1245 | 0 | 9 | 27 | 83 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 0.59 | 44 | 26 | 18 | 0.59 | 26 | N/A | 2026-09-10 | 0.62 | 13 | 8 | 5 | 0.62 | 8 | N/A | 2026-09-10 | 53 | 10 | 43 | 0 | 1:04 | 16 | 5 | 0 | 53 | 5.74 | 0 | 53 | 23 | -1.33 | 8 | 4 | 11 | 110 | 76 | 76 | 34 | 34 | 0 | 100% | 0 | 100% | 0 | 0 | 1.14 | 6 | 5 | 110 | 76 | 76 | 1
Ribbons | Hard_File_updated2 | [11 empty] | 8% |  | 70% | 0% | 70% | 2% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 74% | 0% | 52% | 0% | 2% | 75% | [5 empty] | -29% | -23% | [15 empty] | -10% | [5 empty] | -12% |  |  |  | 5% | 5% | 25% | 100% | 43% | 57% | 10% | 100% |  | 0% | 0% | 5% | 2% | 13% | N/A | 54% | 46% | 12% |  |  |  | 25% | 75% |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  |  |  | 59% | 41% |  | 59% |  |  |  |  | 62% | 38% |  | 62% |  |  | 70% | 56% | 74% | 0% | 0.23 | 21% | 7% | 0% | 70% |  |  | 70% | 30% |  | 11% | 5% | 14% | 100% |  |  |  |  | 0% |  | 0% |  | 0% | 0% |  | 7% | 6% | 100% | 69% | 69%
Phase Analyzer | Status Date | 2026-07-01: 2026-09-10; 2026-08-01: 2026-09-10; 2026-09-01: 2026-09-10; 2026-10-01: 2026-09-10; 2026-11-01: 2026-09-10
Phase Analyzer | WBS | 2026-07-01: 2; 2026-08-01: 2; 2026-09-01: 6; 2026-10-01: 6; 2026-11-01: 8
Phase Analyzer | New Activity - Created (Snapshot) | 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0
Phase Analyzer | Longest Path - Critical Activities and Milestones | 0 | ( N/A ) | 0 | 0% | 17 | 100% | 28 | 93% | 10 | 100%
Phase Analyzer | Critical Milestones (To-Go) | 0 | ( N/A ) | 0 | 0% | 3 | 100% | 4 | 67% | 3 | 100%
Phase Analyzer | Critical Tasks (To-Go) | 0 | ( N/A ) | 0 | 0% | 14 | 100% | 24 | 100% | 7 | 100%
Phase Analyzer | Critical Tasks (In Progress) | 0 | ( N/A ) | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Critical Milestone-to-Task Ratio (To-Go) | N/A | N/A | N/A | N/A | 1:05 | 0.21 | 1:06 | 0.17 | 1:02 | 0.43
Phase Analyzer | High Float 10% | N/A | ( N/A ) | 15 | 71% | 0 | 0% | 1 | 3% | 0 | 0%
Phase Analyzer | High Float 44d | 0 | ( N/A ) | 5 | 24% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Zero Days Float | 0 | ( N/A ) | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Negative Float | 0 | ( N/A ) | 0 | 0% | 16 | 100% | 27 | 93% | 10 | 100%
Phase Analyzer | Avg Float | 2026-07-01: N/A; 2026-08-01: 35; 2026-09-01: -2; 2026-10-01: -1; 2026-11-01: -1
Phase Analyzer | Max Float | 2026-07-01: N/A; 2026-08-01: 62; 2026-09-01: -2; 2026-10-01: 13; 2026-11-01: -1
Phase Analyzer | Float Ratio™ | 2026-07-01: N/A; 2026-08-01: 24.1; 2026-09-01: -1.84; 2026-10-01: -1.11; 2026-11-01: -1.22
Phase Analyzer | New Activity & Critical - Created (Snapshot) | 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0
Phase Analyzer | Critical | 0 | ( N/A ) | 0 | 0% | 17 | 100% | 28 | 93% | 10 | 100%
Phase Analyzer | Non-Critical | 0 | ( N/A ) | 21 | 100% | 0 | 0% | 2 | 7% | 0 | 0%
Phase Analyzer | CP - Float Ratio™ | 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: -1.84; 2026-10-01: -1.11; 2026-11-01: -1.22
Phase Analyzer | 0 to 20 Days Float | 0 | ( N/A ) | 6 | 29% | 0 | 0% | 2 | 7% | 0 | 0%
Phase Analyzer | 20 to 30 days float | 0 | ( N/A ) | 4 | 19% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | More than 30 days float | 0 | ( N/A ) | 11 | 52% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Schedule Baseline Activities | 18 | 257% | 92 | 200% | 44 | 220% | 66 | 220% | 12 | 120%
Phase Analyzer | Scheduled/Baselined to Start | 2026-07-01: 2; 2026-08-01: 36; 2026-09-01: 34; 2026-10-01: 62; 2026-11-01: 10
Phase Analyzer | Scheduled/Baselined to Finish | 2026-07-01: 0; 2026-08-01: 38; 2026-09-01: 30; 2026-10-01: 64; 2026-11-01: 12
Phase Analyzer | Start/ed | 2026-07-01: 7; 2026-08-01: 24; 2026-09-01: 3; 2026-10-01: 0; 2026-11-01: 0
Phase Analyzer | Finish/ed | 2026-07-01: 6; 2026-08-01: 25; 2026-09-01: 3; 2026-10-01: 0; 2026-11-01: 0
Phase Analyzer | Start/ed on Time | 8 | 44% | 58 | 66% | 25 | 60% | 26 | 42% | 5 | 50%
Phase Analyzer | Start/ed Late | 10 | 56% | 24 | 27% | 16 | 38% | 35 | 56% | 5 | 50%
Phase Analyzer | Finish Compliance™ (Phase) | 2026-07-01: 57%; 2026-08-01: 70%; 2026-09-01: 65%; 2026-10-01: 41%; 2026-11-01: 50%
Phase Analyzer | Started Delayed (>30 days) | 0 | 0% | 0 | 0% | 0 | 0% | N/A | ( N/A ) | N/A | ( N/A )
Phase Analyzer | Duration Variance (Original & Actual) | N/A | 0% | N/A | 0% | 2 | 6% | 0 | 0% | 0 | 0%
Phase Analyzer | Duration Variance (Actual) | N/A | 0% | N/A | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Phase Analyzer | Score | 2026-07-01: 100; 2026-08-01: 77; 2026-09-01: 47; 2026-10-01: 35; 2026-11-01: 23

## Ribbon Analysis
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Status Date | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Avg Float | Max Float | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | EAC | AC (ACWP) | %Spent | %Spent (EAC) | VAC | BAC | SV(t) | SPI(t) | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Overrun | Work Underrun | Work Overrun | Total Work | Actual Work | Remaining Work | Work Discrepancy | Baseline Work | Summarized Work | Work per Day | Missing Resources | Resources | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Float Ratio™ | New Activity & Critical - Created (Snapshot) | Critical | Non-Critical | CP - Float Ratio™ | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Duration Variance (Original & Actual) | Duration Variance (Actual) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Score
Ribbons | Hard_File_updated3 | 2026-10-12 | 7 | 2.12 | 35 | 0 | 35 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 1 | 60 | x | 0.11 | 0.47 | -7 | 43 | -12530 | -56725 | 0.49 | 0.81 | 180407 | 150211 | 238883 | 1.23 | 0.6 | -0.21 | 110440 | 53715 | 66245 | 91% | 54% | 44% | 37% | -58607 | 121800 | 1395 | 779 | 72% | 56% | -310 | 1085 | -84 | 1.25 | 10 | 14246 | 91461 | 180407 | 67703 | 112704 | 58607 | 121800 | 1093 | 0 | 0 | 9 | 56 | 366 | 1395 | 779 | 616 | 310 | 1085 | 0 | 8 | 22 | 73 | 0.08 | 24 | 2 | N/A | 22 | 0.08 | 2 | N/A | 2026-10-12 | 0.33 | 6 | 2 | N/A | 4 | 0.33 | 2 | N/A | 2026-10-12 | 0.23 | 26 | 6 | 20 | 0.23 | 6 | 0 | 2026-10-12 | 0 | N/A | N/A | 0.4 | 5 | 2 | 3 | 0.4 | 2 | 0 | 2026-10-12 | 0.47 | 68 | 32 | 36 | 0.47 | 32 | N/A | 2026-10-12 | 0.53 | 19 | 10 | 9 | 0.53 | 10 | N/A | 2026-10-12 | 35 | 5 | 30 | 0 | 1:06 | 11 | 0 | 0 | 35 | -5.59 | 0 | 35 | 18 | -11.9 | 7 | 3 | 8 | 95 | 53 | 53 | 42 | 42 | 0 | 100% | 0 | 100% | 0 | 0 | 1.25 | 9 | 5 | 95 | 53 | 53 | 2
Ribbons | Hard_File_updated2 | 2026-09-10 | 9 | 2.07 | 53 | 0 | 53 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 43 | 0 | 30 | 0 | 1 | 33 | ✓ | 0.93 | 0.59 | 9 | 62 | -14405 | -14540 | 0.77 | 0.78 | 146859 | 172063 | 203647 | 1.21 | 1.01 | 0.24 | 64240 | 49700 | 64105 | 48% | 48% | 37% | 44% | -13459 | 133400 | 1399 | 753 | 60% | 54% | -154 | 1245 | -73 | 1.14 | 6 | 7446 | 36613 | 146859 | 63763 | 83096 | 13459 | 133400 | 907 | 0 | 0 | 5 | 32 | 186 | 1399 | 753 | 646 | 154 | 1245 | 0 | 9 | 27 | 83 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-09-10 | 0.59 | 44 | 26 | 18 | 0.59 | 26 | N/A | 2026-09-10 | 0.62 | 13 | 8 | 5 | 0.62 | 8 | N/A | 2026-09-10 | 53 | 10 | 43 | 0 | 1:04 | 16 | 5 | 0 | 53 | 5.74 | 0 | 53 | 23 | -1.33 | 8 | 4 | 11 | 110 | 76 | 76 | 34 | 34 | 0 | 100% | 0 | 100% | 0 | 0 | 1.14 | 6 | 5 | 110 | 76 | 76 | 1
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Status Date | Missing Logic | Logic Density™ | Critical | Hard Constraints | Negative Float | Insufficient Detail™ | Number of Lags | Number of Leads | Merge Hotspot | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Avg Float | Max Float | CV | SV | SPI | CPI | EAC | EAC(CPI) | EAC(Composite) | TCPI(BAC) | TCPI(EAC) | TCPI(EAC) to CPI | PV (BCWS) | EV (BCWP) | AC (ACWP) | %Schedule | %Spent | %Complete | %Spent (EAC) | VAC | BAC | EAC | AC (ACWP) | %Spent | %Spent (EAC) | VAC | BAC | SV(t) | SPI(t) | Overrun | $ Cost Underrun | $ Cost Overrun | $ Total Cost | $ Actual Cost | $ Remaining Cost | $ Cost Discrepancy | $ Budget Cost | $ Cost per Day | Negative Planned Cost | Negative Actual Cost | Overrun | Work Underrun | Work Overrun | Total Work | Actual Work | Remaining Work | Work Discrepancy | Baseline Work | Summarized Work | Work per Day | Missing Resources | Resources | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Float Ratio™ | New Activity & Critical - Created (Snapshot) | Critical | Non-Critical | CP - Float Ratio™ | 0 to 20 Days Float | 20 to 30 days float | More than 30 days float | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Duration Variance (Original & Actual) | Duration Variance (Actual) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Score
Ribbons | Hard_File_updated3 |  | 7% |  | 66% | 0% | 66% | 4% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 71% | 0% | 0% | 0% | 2% | 88% | [5 empty] | -23% | -51% | [15 empty] | -48% | [5 empty] | -29% |  |  |  | 11% | 8% | 51% | 123% | 38% | 62% | 48% | 91% |  | 0% | 0% | 9% | 4% | 26% | N/A | 56% | 44% | 29% |  |  |  | 23% | 77% |  |  | 8% | 0% | 92% |  | 8% |  |  |  |  | 33% | 0% | 67% |  | 33% |  |  |  |  | 23% | 77% |  | 23% | [7 empty] | 40% | 60% |  | 40% |  |  |  |  | 47% | 53% |  | 47% |  |  |  |  | 53% | 47% |  | 53% |  |  | 66% | 45% | 71% | 0% | 0.17 | 21% | 0% | 0% | 66% |  |  | 66% | 34% |  | 13% | 6% | 15% | 100% |  |  |  |  | 0% |  | 0% |  | 0% | 0% |  | 12% | 7% | 100% | 56% | 56%
Ribbons | Hard_File_updated2 |  | 8% |  | 70% | 0% | 70% | 2% | 0% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 74% | 0% | 52% | 0% | 2% | 75% | [5 empty] | -29% | -23% | [15 empty] | -10% | [5 empty] | -12% |  |  |  | 5% | 5% | 25% | 100% | 43% | 57% | 10% | 100% |  | 0% | 0% | 5% | 2% | 13% | N/A | 54% | 46% | 12% |  |  |  | 25% | 75% |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  |  |  | 59% | 41% |  | 59% |  |  |  |  | 62% | 38% |  | 62% |  |  | 70% | 56% | 74% | 0% | 0.23 | 21% | 7% | 0% | 70% |  |  | 70% | 30% |  | 11% | 5% | 14% | 100% |  |  |  |  | 0% |  | 0% |  | 0% | 0% |  | 7% | 6% | 100% | 69% | 69%

## Hard_File_updated21
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View | Hard_File_updated2: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 1 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 1 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 3 | 1 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
7. Negative Float
Activities that are incomplete and have total float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
9. Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
Overrun
Number of activities where total cost is greater than budgeted cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
$ Cost Underrun
A currency measure of the difference between total budgeted cost and total cost of all under-budget activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
$ Cost Overrun
A currency measure of the difference between total budgeted cost and total cost of all over-budget activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
$ Actual Cost
A currency measure of the actual amount paid or incurred, as opposed to estimated cost or standard cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
$ Cost Discrepancy
A currency measure of the difference between budgeted and current cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
Overrun
Number of activities where total work is greater than budgeted work.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
Work Underrun
A measure of the difference between total budgeted work and actual work of all activities that have total work less than budgeted work.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
Work Overrun
A measure of the difference between total budgeted work and actual work of all activities that have total work greater than budgeted work.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
Actual Work
Calculation of the actual work completed for all activities within a grouping
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
Remaining Work
Calculation of total remaining work for all activities within a grouping
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
Work Discrepancy
A calculation of the difference between budgeted and current work
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
Missing Resources
Number of activities that are not carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Resources
Number of activities that are carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
BEI - Total Milestones
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
BEI - Complete Milestones
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
BEI - Incomplete Milestones
The total number (cumulative) of milestones that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
BEI - Complete Milestones (adjusted)
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE | FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE | FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE | FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE | FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE | FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Start/ed
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
Finish/ed
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE | 2 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
Scheduled Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Scheduled to Start
Number of activities that are scheduled to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Scheduled to Finish
Number of activities that are scheduled to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1

## Hard_File_updated32
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View | Hard_File_updated3: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 1 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 1 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 1 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 1 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 1 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
Critical
Number of critical activities
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Insufficient Detail™
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
Merge Hotspot
The total number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 3 | 1 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
7. Negative Float
Activities that are incomplete and have total float less than 0 working days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
Overrun
Number of activities where total cost is greater than budgeted cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
$ Cost Underrun
A currency measure of the difference between total budgeted cost and total cost of all under-budget activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
$ Cost Overrun
A currency measure of the difference between total budgeted cost and total cost of all over-budget activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
$ Actual Cost
A currency measure of the actual amount paid or incurred, as opposed to estimated cost or standard cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
$ Cost Discrepancy
A currency measure of the difference between budgeted and current cost.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
Overrun
Number of activities where total work is greater than budgeted work.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
Work Underrun
A measure of the difference between total budgeted work and actual work of all activities that have total work less than budgeted work.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
Work Overrun
A measure of the difference between total budgeted work and actual work of all activities that have total work greater than budgeted work.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
Actual Work
Calculation of the actual work completed for all activities within a grouping
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
Remaining Work
Calculation of total remaining work for all activities within a grouping
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Work Discrepancy
A calculation of the difference between budgeted and current work
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
Missing Resources
Number of activities that are not carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
Resources
Number of activities that are carrying resources
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
HMI - Total Tasks
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
HMI - Complete Tasks
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
HMI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
HMI - Complete Tasks (adjusted)
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for tasks baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
HMI - Total Milestones
The total number of milestones baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
HMI - Complete Milestones
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
HMI - Incomplete Milestones
The total number of milestones that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
HMI - Complete Milestones (adjusted)
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for milestones baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
CEI - Total Tasks
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 1 | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 1 | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 1 | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 1 | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 1 | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 0 | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 0 | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 0 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 0 | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 0 | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 0 | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 0 | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 0 | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 0 | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 0 | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 0 | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 0 | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 0 | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 0 | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 0 | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 0 | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 0 | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 0 | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 0 | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 0 | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
CEI - Complete Tasks
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 1 | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 1 | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 1 | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 1 | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 1 | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
CEI - Incomplete Tasks
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
CEI - Complete Tasks (adjusted)
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned activities that were completed within the measured timeframe.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
CEI - Total Milestones
The number of milestones forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
CEI - Complete Milestones
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
CEI - Incomplete Milestones
The number of milestones that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
CEI - Complete Milestones (adjusted)
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned milestones that were completed within the measured timeframe.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
BEI - Total Milestones
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
BEI - Complete Milestones
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
BEI - Incomplete Milestones
The total number (cumulative) of milestones that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
BEI - Complete Milestones (adjusted)
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE | TRUE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE | TRUE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE | TRUE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE | FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE | FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE | FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE | FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE | FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE | TRUE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Start/ed
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
Finish/ed
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE | 1 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
Scheduled Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated3 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated3 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Scheduled to Start
Number of activities that are scheduled to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
Scheduled to Finish
Number of activities that are scheduled to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27

## Phase Analysis
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01
Phase Analyzer | Status Date | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10
Phase Analyzer | WBS | 2 | 2 | 6 | 6 | 8
Phase Analyzer | New Activity - Created (Snapshot) | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Longest Path - Critical Activities and Milestones | 0 | 0 | 17 | 28 | 10
Phase Analyzer | Critical Milestones (To-Go) | 0 | 0 | 3 | 4 | 3
Phase Analyzer | Critical Tasks (To-Go) | 0 | 0 | 14 | 24 | 7
Phase Analyzer | Critical Tasks (In Progress) | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Critical Milestone-to-Task Ratio (To-Go) | N/A | N/A | 1:05 | 1:06 | 1:02
Phase Analyzer | High Float 10% | N/A | 15 | 0 | 1 | 0
Phase Analyzer | High Float 44d | 0 | 5 | 0 | 0 | 0
Phase Analyzer | Zero Days Float | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Negative Float | 0 | 0 | 16 | 27 | 10
Phase Analyzer | Avg Float | N/A | 35 | -2 | -1 | -1
Phase Analyzer | Max Float | N/A | 62 | -2 | 13 | -1
Phase Analyzer | Float Ratio™ | N/A | 24.1 | -1.84 | -1.11 | -1.22
Phase Analyzer | New Activity & Critical - Created (Snapshot) | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Critical | 0 | 0 | 17 | 28 | 10
Phase Analyzer | Non-Critical | 0 | 21 | 0 | 2 | 0
Phase Analyzer | CP - Float Ratio™ | N/A | N/A | -1.84 | -1.11 | -1.22
Phase Analyzer | 0 to 20 Days Float | 0 | 6 | 0 | 2 | 0
Phase Analyzer | 20 to 30 days float | 0 | 4 | 0 | 0 | 0
Phase Analyzer | More than 30 days float | 0 | 11 | 0 | 0 | 0
Phase Analyzer | Schedule Baseline Activities | 18 | 92 | 44 | 66 | 12
Phase Analyzer | Scheduled/Baselined to Start | 2 | 36 | 34 | 62 | 10
Phase Analyzer | Scheduled/Baselined to Finish | 0 | 38 | 30 | 64 | 12
Phase Analyzer | Start/ed | 7 | 24 | 3 | 0 | 0
Phase Analyzer | Finish/ed | 6 | 25 | 3 | 0 | 0
Phase Analyzer | Start/ed on Time | 8 | 58 | 25 | 26 | 5
Phase Analyzer | Start/ed Late | 10 | 24 | 16 | 35 | 5
Phase Analyzer | Finish Compliance™ (Phase) | 57% | 70% | 65% | 41% | 50%
Phase Analyzer | Started Delayed (>30 days) | 0 | 0 | 0 | N/A | N/A
Phase Analyzer | Duration Variance (Original & Actual) | N/A | N/A | 2 | 0 | 0
Phase Analyzer | Duration Variance (Actual) | N/A | N/A | 0 | 0 | 0
Phase Analyzer | Score | 100 | 77 | 47 | 35 | 23
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line
|  | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01
Phase Analyzer | Status Date
Phase Analyzer | WBS
Phase Analyzer | New Activity - Created (Snapshot)
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare
Phase Analyzer | Longest Path - Critical Activities and Milestones | ( N/A ) | 0% | 100% | 93% | 100%
Phase Analyzer | Critical Milestones (To-Go) | ( N/A ) | 0% | 100% | 67% | 100%
Phase Analyzer | Critical Tasks (To-Go) | ( N/A ) | 0% | 100% | 100% | 100%
Phase Analyzer | Critical Tasks (In Progress) | ( N/A ) | ( N/A ) | 0% | 0% | 0%
Phase Analyzer | Critical Milestone-to-Task Ratio (To-Go) | N/A | N/A | 0.21 | 0.17 | 0.43
Phase Analyzer | High Float 10% | ( N/A ) | 71% | 0% | 3% | 0%
Phase Analyzer | High Float 44d | ( N/A ) | 24% | 0% | 0% | 0%
Phase Analyzer | Zero Days Float | ( N/A ) | 0% | 0% | 0% | 0%
Phase Analyzer | Negative Float | ( N/A ) | 0% | 100% | 93% | 100%
Phase Analyzer | Avg Float
Phase Analyzer | Max Float
Phase Analyzer | Float Ratio™
Phase Analyzer | New Activity & Critical - Created (Snapshot)
Phase Analyzer | Critical | ( N/A ) | 0% | 100% | 93% | 100%
Phase Analyzer | Non-Critical | ( N/A ) | 100% | 0% | 7% | 0%
Phase Analyzer | CP - Float Ratio™
Phase Analyzer | 0 to 20 Days Float | ( N/A ) | 29% | 0% | 7% | 0%
Phase Analyzer | 20 to 30 days float | ( N/A ) | 19% | 0% | 0% | 0%
Phase Analyzer | More than 30 days float | ( N/A ) | 52% | 0% | 0% | 0%
Phase Analyzer | Schedule Baseline Activities | 257% | 200% | 220% | 220% | 120%
Phase Analyzer | Scheduled/Baselined to Start
Phase Analyzer | Scheduled/Baselined to Finish
Phase Analyzer | Start/ed
Phase Analyzer | Finish/ed
Phase Analyzer | Start/ed on Time | 44% | 66% | 60% | 42% | 50%
Phase Analyzer | Start/ed Late | 56% | 27% | 38% | 56% | 50%
Phase Analyzer | Finish Compliance™ (Phase)
Phase Analyzer | Started Delayed (>30 days) | 0% | 0% | 0% | ( N/A ) | ( N/A )
Phase Analyzer | Duration Variance (Original & Actual) | 0% | 0% | 6% | 0% | 0%
Phase Analyzer | Duration Variance (Actual) | 0% | 0% | 0% | 0% | 0%
Phase Analyzer | Score

## 7-2026 Details
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
7/2026: Detailed View | 7/2026: Detailed View | 7/2026: Detailed View | 7/2026: Detailed View | 7/2026: Detailed View | 7/2026: Detailed View | 7/2026: Detailed View | 7/2026: Detailed View | 7/2026: Detailed View
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
Start/ed
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Finish/ed
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated2 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated2 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
Start/ed on Time
Number of activities starting or that have started within the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated2 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated2 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated3 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated3 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Start/ed Late
Number of activities starting or that have started after the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 1 |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated2 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 94 | Determine solutions for product points | Hard_File_updated3 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated3 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 | 3 |  | 157 | Document product review results | Hard_File_updated3 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0

## 8-2026 Details
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View | 8/2026: Detailed View
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE | FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE | FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE | FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE | FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE | FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE | FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
20 to 30 days float
Total number of activities with positive float of more than 20 and less than or equal to 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
More than 30 days float
Total number of activities with positive float of more than 30 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 180 | Online support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 180 | Online support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
Start/ed
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
Finish/ed
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated2 | 1 | 0 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 157 | Document product review results | Hard_File_updated2 | 3 | 0 | 2026-08-18 | 2026-08-19 | 2026-07-23 | 2026-07-24 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-07-31 | Milestone | Complete | 100 | 0
FALSE |  | 211 | Review output of product review phase | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-07-31 | 2026-08-01 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
Start/ed on Time
Number of activities starting or that have started within the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated2 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated2 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated2 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated2 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated2 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 44
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 44
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 44
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 56
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 188 | Identify service delivery options | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-22 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 12
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 12
FALSE |  | 179 | Phone support | Hard_File_updated2 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 12
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated2 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 44
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 54
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated2 | 1 | 1 | 2026-08-06 | 2026-08-07 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 62
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated2 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 26
FALSE |  | 385 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated2 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-24 | 2026-08-24 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 26
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated2 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 44
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-18 | 2026-08-18 | Normal | Complete | 100 | 0
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Complete | 100 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated3 | 1 | 0 | 2026-08-25 | 2026-08-26 | 2026-08-20 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-21 | 2026-08-21 | Milestone | Complete | 100 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated3 | 2 | 0 | 2026-08-26 | 2026-08-27 | 2026-08-21 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-22 | 2026-08-22 | Normal | Complete | 100 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated3 | 1 | 0 | 2026-08-27 | 2026-08-28 | 2026-08-24 | 2026-08-24 | Normal | Complete | 100 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-30 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Milestone | Complete | 100 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated3 | 1 | 0 | 2026-08-28 | 2026-08-29 | 2026-08-25 | 2026-08-25 | Normal | Complete | 100 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated3 | 1 | 0 | 2026-08-29 | 2026-08-30 | 2026-08-26 | 2026-08-26 | Normal | Complete | 100 | 0
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-18 | 2026-08-18 | 2026-08-14 | 2026-08-14 | Milestone | Complete | 100 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-17 | 2026-08-17 | Milestone | Complete | 100 | 0
Start/ed Late
Number of activities starting or that have started after the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 5
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-14 | 2026-10-14 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 42
FALSE |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 178 | On-site support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE |  | 179 | Phone support | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 42
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 43
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-16 | 2026-10-16 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 40
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated3 | 1 | 1 | 2026-10-12 | 2026-10-13 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 27
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | -25
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE | 5 | 5 |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 2 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated2 | 3 | 3 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 44
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE | 5 | 2 |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE | 1 | 0 |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE | 1 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 1 | 0 |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE | 1 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE | 1 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE | 2 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated2 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE | 5 | 5 |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated2 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated2 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 4 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated3 | 4 | 0 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-20 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated3 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 1 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated3 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE | 5 | 2 |  | 290 | Review expertise of potential vendors | Hard_File_updated3 | 2 | 0 | 2026-09-04 | 2026-09-07 | 2026-08-31 | 2026-09-07 | Normal | Complete | 100 | 0
FALSE | 1 | 0 |  | 321 | Determine technology budget | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 5
FALSE | 1 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 5
FALSE | 15 | 18 |  | 187 | Determine required skill sets for various support options | Hard_File_updated3 | 18 | 0 | 2026-08-05 | 2026-08-18 | 2026-08-05 | 2026-08-14 | Normal | Complete | 100 | 0
FALSE | 1 | 0 |  | 188 | Identify service delivery options | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-14 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 42
FALSE | 1 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 42
FALSE | 1 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated3 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 5
FALSE | 2 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated3 | 2 | 2 | 2026-10-15 | 2026-10-16 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 5
FALSE | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated3 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 1 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 385 | Determine success metrics | Hard_File_updated3 | 12 | 12 | 2026-10-13 | 2026-11-04 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated3 | 5 | 5 | 2026-11-04 | 2026-11-06 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated3 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 5

## 9-2026 Details
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View | 9/2026: Detailed View
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
Start/ed
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
Finish/ed
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated2 | 1 | 0 | 2026-09-02 | 2026-09-02 | 2026-08-27 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated2 | 1 | 0 | 2026-09-03 | 2026-09-03 | 2026-08-28 | 2026-08-28 | Normal | Complete | 100 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated2 | 5 | 0 | 2026-09-04 | 2026-09-10 | 2026-08-31 | 2026-09-04 | Normal | Complete | 100 | 0
Start/ed on Time
Number of activities starting or that have started within the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated2 | 1 | 1 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated2 | 2 | 2 | 2026-09-22 | 2026-09-24 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -2
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated2 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -2
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated2 | 1 | 1 | 2026-09-21 | 2026-09-21 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -2
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated2 | 1 | 1 | 2026-09-22 | 2026-09-22 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -2
FALSE |  | 291 | Review cost | Hard_File_updated2 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | -2
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated2 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | -2
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated2 | 1 | 1 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | -2
FALSE |  | 295 | Review service levels | Hard_File_updated2 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | -2
FALSE |  | 296 | Review customer references | Hard_File_updated2 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | -2
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-09-17 | 2026-09-17 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | -2
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated2 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -2
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated2 | 0 | 0 | 2026-09-28 | 2026-09-28 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -2
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated2 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -2
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated2 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -2
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated3 | 1 | 0 | 2026-09-25 | 2026-09-25 | 2026-09-14 | 2026-09-14 | Normal | Complete | 100 | 0
FALSE |  | 291 | Review cost | Hard_File_updated3 | 1 | 0 | 2026-09-08 | 2026-09-08 | 2026-09-07 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated3 | 1 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-10 | 2026-09-10 | Normal | Complete | 100 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated3 | 1 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Normal | Complete | 100 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated3 | 1 | 0 | 2026-09-09 | 2026-09-09 | 2026-09-08 | 2026-09-08 | Normal | Complete | 100 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated3 | 1 | 0 | 2026-09-10 | 2026-09-10 | 2026-09-09 | 2026-09-09 | Normal | Complete | 100 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-09-14 | 2026-09-14 | 2026-09-11 | 2026-09-11 | Milestone | Complete | 100 | 0
Start/ed Late
Number of activities starting or that have started after the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated3 | 0 | 0 | 2026-10-21 | 2026-10-21 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | -18
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -18
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | 1 | 0 |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | 4 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | 4 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE | 1 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE | 4 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | 1 | 0 |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | 4 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | 4 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated3 | 2 | 2 | 2026-11-02 | 2026-11-04 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | -16
FALSE | 1 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated3 | 1 | 1 | 2026-10-13 | 2026-10-13 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated3 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated3 | 6 | 6 | 2026-10-13 | 2026-10-21 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated3 | 3 | 3 | 2026-10-22 | 2026-10-27 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated3 | 1 | 1 | 2026-10-21 | 2026-10-22 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated3 | 1 | 1 | 2026-10-27 | 2026-10-28 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -18
FALSE | 1 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 223 | Assemble content development team | Hard_File_updated3 | 1 | 1 | 2026-11-09 | 2026-11-09 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -25
FALSE | 4 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27

## 10-2026 Details
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View | 10/2026: Detailed View
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE | TRUE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE | TRUE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
Non-Critical
Number of non-critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
0 to 20 Days Float
Number of activities with positive float of more than zero and less than or equal to 20 days.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated2 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | -2
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-01 | 2026-10-01 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | -2
FALSE |  | 223 | Assemble content development team | Hard_File_updated2 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-04 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE |  | 13 | Determine success metrics | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-04 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-08 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -39
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-08 | 2026-12-08 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -27
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-09 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-09 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-02 | 2026-12-02 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 7
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -27
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -27
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated2 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-08-12 | 2026-08-12 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 62
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-04 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE |  | 13 | Determine success metrics | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-04 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-08 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -39
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-08 | 2026-12-08 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -27
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-09 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated3 | 4 | 4 | 2026-10-19 | 2026-11-05 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 27
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-02 | 2026-12-02 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 7
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -27
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -27
Start/ed on Time
Number of activities starting or that have started within the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-10-29 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 13 | Determine success metrics | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-29 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -1
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -1
FALSE |  | 262 | Train additional trainers | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-12 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -1
FALSE |  | 264 | Create proficiency exams | Hard_File_updated2 | 4 | 4 | 2026-10-09 | 2026-10-11 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -2
FALSE |  | 269 | Prepare training venues | Hard_File_updated2 | 1 | 1 | 2026-10-12 | 2026-10-14 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -1
FALSE |  | 270 | Create communications plan | Hard_File_updated2 | 3 | 3 | 2026-10-14 | 2026-10-16 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -1
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated2 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -1
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated2 | 1 | 1 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -2
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated2 | 1 | 1 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -1
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-08 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -2
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 229 | Acquire final content approval | Hard_File_updated2 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -1
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated2 | 1 | 1 | 2026-10-06 | 2026-10-07 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 257 | Develop beta content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-07 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 258 | Revise and update content | Hard_File_updated2 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -2
FALSE |  | 253 | Create content development schedule | Hard_File_updated2 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -2
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-09 | 2026-10-09 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -1
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-20 | 2026-10-20 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 13
FALSE |  | 34 | Train new resources | Hard_File_updated2 | 1 | 1 | 2026-10-22 | 2026-10-22 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -1
FALSE |  | 49 | Hire new resources | Hard_File_updated2 | 1 | 1 | 2026-10-21 | 2026-10-21 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -1
FALSE |  | 389 | Certify new resources | Hard_File_updated2 | 3 | 3 | 2026-10-23 | 2026-10-27 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -1
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-27 | 2026-10-27 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 8
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated2 | 1 | 1 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -1
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-10-28 | 2026-10-28 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -1
Start/ed Late
Number of activities starting or that have started after the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-04 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE |  | 13 | Determine success metrics | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-04 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-08 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -39
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-08 | 2026-12-08 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -27
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-09 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-09 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | -27
FALSE |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE |  | 269 | Prepare training venues | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-19 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | -27
FALSE |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-12 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 258 | Revise and update content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-13 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | -25
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 12
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 27
FALSE |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-02 | 2026-12-02 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 7
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -27
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | -27
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | 4 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | 1 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-04 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-08 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -39
FALSE | 1 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-09 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE | 4 | 0 |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE | 3 | 0 |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE | 3 | 0 |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -27
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | 4 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated2 | 4 | 4 | 2026-08-07 | 2026-08-12 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 62
FALSE | 1 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-04 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated3 | 1 | 1 | 2026-12-04 | 2026-12-08 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -39
FALSE | 1 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated3 | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-09 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 262 | Train additional trainers | Hard_File_updated3 | 1 | 1 | 2026-11-18 | 2026-11-18 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | -27
FALSE | 4 | 0 |  | 264 | Create proficiency exams | Hard_File_updated3 | 4 | 4 | 2026-11-16 | 2026-11-18 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | -27
FALSE | 3 | 0 |  | 270 | Create communications plan | Hard_File_updated3 | 3 | 3 | 2026-11-19 | 2026-11-23 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated3 | 1 | 1 | 2026-11-24 | 2026-11-24 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated3 | 1 | 1 | 2026-11-16 | 2026-11-16 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | -26
FALSE | 1 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated3 | 1 | 1 | 2026-11-25 | 2026-11-25 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-13 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 229 | Acquire final content approval | Hard_File_updated3 | 1 | 1 | 2026-11-13 | 2026-11-16 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 257 | Develop beta content | Hard_File_updated3 | 1 | 1 | 2026-11-12 | 2026-11-12 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated3 | 1 | 1 | 2026-11-10 | 2026-11-10 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 253 | Create content development schedule | Hard_File_updated3 | 1 | 1 | 2026-11-11 | 2026-11-11 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | -25
FALSE | 1 | 0 |  | 34 | Train new resources | Hard_File_updated3 | 1 | 1 | 2026-11-27 | 2026-11-27 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 49 | Hire new resources | Hard_File_updated3 | 1 | 1 | 2026-11-26 | 2026-11-26 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | -27
FALSE | 3 | 0 |  | 389 | Certify new resources | Hard_File_updated3 | 3 | 3 | 2026-11-30 | 2026-12-02 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated3 | 1 | 1 | 2026-12-03 | 2026-12-03 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | -27

## 11-2026 Details
Fuse® Analyst Report
Workbook: Hard_File_update2 vs update3_Fuse - 282 Activities
Quick Add Metrics
Created on: 7/9/2026
Created by: dpolitte
11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View | 11/2026: Detailed View
Longest Path - Critical Activities and Milestones
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical Milestones (To-Go)
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical Tasks (To-Go)
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
Negative Float
Number of activities with total finish float less than 0 working days.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Critical
Number of critical activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
CP - Float Ratio™
Average float divided by average remaining duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
Schedule Baseline Activities
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated2 | 1 | 1 | 2026-10-29 | 2026-11-02 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | -3
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-02 | 2026-11-02 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | -1
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated2 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Scheduled/Baselined to Start
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-10 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated3 | 1 | 1 | 2026-12-10 | 2026-12-10 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -27
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated3 | 6 | 2 | 2026-12-10 | 2026-12-12 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -37
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-12 | 2026-12-12 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -26
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-12 | 2026-12-12 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -26
Scheduled/Baselined to Finish
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-03 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-09 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-10 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated3 | 1 | 1 | 2026-12-10 | 2026-12-10 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -27
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated3 | 6 | 2 | 2026-12-10 | 2026-12-12 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -37
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-12 | 2026-12-12 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -26
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-12 | 2026-12-12 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -26
Start/ed on Time
Number of activities starting or that have started within the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated2 | 1 | 1 | 2026-11-03 | 2026-11-04 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -1
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated2 | 1 | 1 | 2026-11-04 | 2026-11-04 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -1
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated2 | 6 | 2 | 2026-11-04 | 2026-11-06 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -1
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated2 | 0 | 0 | 2026-11-06 | 2026-11-06 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -1
Start/ed Late
Number of activities starting or that have started after the expected baselined period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-10 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated3 | 1 | 1 | 2026-12-10 | 2026-12-10 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -27
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated3 | 6 | 2 | 2026-12-10 | 2026-12-12 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -37
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-12 | 2026-12-12 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -26
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated3 | 0 | 0 | 2026-12-12 | 2026-12-12 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | -26
Duration Variance (Original & Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-09 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated3 | 1 | 1 | 2026-12-10 | 2026-12-10 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -27
FALSE | 6 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated3 | 6 | 2 | 2026-12-10 | 2026-12-12 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -37
Duration Variance (Actual)
Excluded | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated3 | 1 | 1 | 2026-12-09 | 2026-12-09 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | -27
FALSE | 1 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated3 | 1 | 1 | 2026-12-10 | 2026-12-10 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | -27
FALSE | 6 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated3 | 6 | 2 | 2026-12-10 | 2026-12-12 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | -37