## Projects
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects
Name | Start | Start | Finish | Finish | Time Now | Time Now | Baseline Start | Baseline Start | Baseline Finish | Baseline Finish | Activities | Activities | Budget Duration | Budget Duration | Actual Duration | Actual Duration | Remaining Duration | Remaining Duration | Total Duration | Total Duration | Budget Cost | Budget Cost | Actual Cost | Actual Cost | Remaining Cost | Remaining Cost | Total Cost | Total Cost
Hard_File_updated |  | 2026-07-08 08:00 |  | 2026-11-05 12:00 |  | 2026-08-11 17:00 |  | 2026-07-08 08:00 |  | 2026-11-05 12:00 |  | 141 |  | 120.1667 |  | 25 |  | 62 |  | 86 |  | 133400 |  | 20800 |  | 116600 |  | 137400
Hard_File_updated2 | = | 2026-07-08 08:00 | p | 2026-11-06 17:00 | p | 2026-09-10 17:00 | = | 2026-07-08 08:00 | = | 2026-11-05 12:00 | = | 141 | = | 120.1667 | p | 47 | q | 41 | p | 88 | = | 133400 | p | 63763 | q | 83096 | p | 146859

## Activities
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2

## Relationships
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Relationships - 1 (1%) | Relationships - 1 (1%) | Relationships - 1 (1%) | Relationships - 1 (1%) | Relationships - 1 (1%) | Relationships - 1 (1%) | Relationships - 1 (1%) | Relationships - 1 (1%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Hard_File_updated | Hard_File_updated2
387 | Business Performance Planning COMPLETE | False | 223 | Assemble content development team | True | O | FinishToStart (0)

## Leads-Lags
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%) | Leads/Lags - 1 (1%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Hard_File_updated Relationship Type | Hard_File_updated2 Relationship Type | Hard_File_updated Lead/Lag | Hard_File_updated2 Lead/Lag
387 | Business Performance Planning COMPLETE | False | 223 | Assemble content development team | True | O | FinishToStart | O | 0

## Resources
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%) | Resources - 32 (33%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Resource | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | Customer Service Team | 8 | q | 0
2 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | Customer Service Team | 8 | q | 0
3 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
4 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 4 | q | 0
5 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
6 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | Content Developer | 4 | q | 0
7 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 4 | q | 0
8 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
9 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | Content Developer | 8 | q | 0
10 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 40 | q | 20
11 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
12 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
13 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 55 | q | 0
14 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
15 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
16 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
17 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
18 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
19 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
20 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
21 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | Content Developer | 8 | q | 0
22 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | Customer Service Team | 48 | q | 0
23 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | Customer Service Team | 8 | q | 1.4545
24 | 210 | Review anticipated skill sets of support resources | Normal | 0 | 4.2.1.2 | 4.2.1.2 |  | 2 | 1.88 | Path 02 | Cleaning | O |  | 0.52
25 | 210 | Review anticipated skill sets of support resources | Normal | 0 | 4.2.1.2 | 4.2.1.2 |  | 2 | 1.88 | Path 02 | Logistics Apprentice | O |  | 0
26 | 210 | Review anticipated skill sets of support resources | Normal | 0 | 4.2.1.2 | 4.2.1.2 |  | 2 | 1.88 | Path 02 | AI Token Time | O |  | 0
27 | 211 | Review output of product review phase | Normal | 0 | 4.2.1.1 | 4.2.1.1 |  | 2 | 4.88 | Path 02 | Cleaning | O |  | 0
28 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | Cleaning | O |  | 0.052634
29 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | Trainer Apprentice | O |  | 0
30 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | Logistics Apprentice | O |  | 0
31 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | Content Developer | O |  | 1.4545
32 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | Trainer | O |  | 5.0909

## Calendars
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars
Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated |  |  | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar
Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated |  |  | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 24 Hours
Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated |  |  | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 16 Hour Work Days
Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated |  |  | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Standard+Sat.
Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated |  |  | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ASIT_REFERENCE
Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated |  |  | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: SSI 24 Hour
Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated | Hard_File_updated |  |  | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00

## Calendar Exceptions
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Calendar: Standard
Hard_File_updated | Hard_File_updated2
Calendar: Used for Microsoft Project 98 Baseline Calendar
Hard_File_updated | Hard_File_updated2
Calendar: 24 Hours
Hard_File_updated | Hard_File_updated2
Calendar: 16 Hour Work Days
Hard_File_updated | Hard_File_updated2
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-01-01 | 2019-01-01
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-05-25 | 2020-05-25
2020-07-06 | 2020-07-06
2020-09-07 | 2020-09-07
2020-11-26 | 2020-11-26
2021-01-18 | 2021-01-18
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
Calendar: Standard+Sat.
Hard_File_updated | Hard_File_updated2
Calendar: ASIT_REFERENCE
Hard_File_updated | Hard_File_updated2
Calendar: SSI 24 Hour
Hard_File_updated | Hard_File_updated2

## ID
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Description
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Activity-Type
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%) | Activity Type - 1 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | Normal |  |  |  | Milestone

## Baseline-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Original-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%) | Original Duration - 31 (22%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 8 | q | -1 | (-12%) | 7
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 4 | q | -1 | (-25%) | 3
3 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 29 | p | 2 | -7% | 31
4 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 29 | p | 2 | -7% | 31
5 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 1 | p | 2 | -200% | 3
6 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 31 | p | 1 | -3% | 32
7 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
8 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
9 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 1 | p | 3 | -300% | 4
10 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 1 | q | -1 | (-100%) | 0
11 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 27 | q | -1 | (-4%) | 26
12 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 21 | q | -2 | (-10%) | 19
13 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 8 | q | -2 | (-25%) | 6
14 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 4 | q | -2 | (-50%) | 2
15 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 4 | q | -2 | (-50%) | 2
16 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 3 | q | -1 | (-33%) | 2
17 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 12 | p | 1 | -8% | 13
18 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 12 | p | 1 | -8% | 13
19 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 12 | p | 1 | -8% | 13
20 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 15 | p | 3 | -20% | 18
21 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2 | q | -1 | (-50%) | 1
22 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
23 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 57 | p | 3 | -5% | 60
24 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 3 | q | -1 | (-33%) | 2
25 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2 | p | 1 | -50% | 3
26 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 12 | p | 1 | -8% | 13
27 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 4 | p | 1 | -25% | 5
28 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 1 | p | 1 | -100% | 2
29 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 49 | q | -38 | (-78%) | 11
30 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 5 | q | -3 | (-60%) | 2
31 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 40 | p | 7 | -18% | 47

## Actual-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%) | Actual Duration - 29 (21%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 27 | p | 4 | -15% | 31
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 27 | p | 4 | -15% | 31
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 0 | p | 1 |  | 1
4 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 0 | p | 3 |  | 3
5 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 0 | p | 13 |  | 13
6 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 0 | p | 2 |  | 2
7 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 0 | p | 12 |  | 12
8 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 0 | p | 4 |  | 4
9 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
10 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 4 |  | 4
11 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 0 | p | 8 |  | 8
12 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
13 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
14 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 0 | p | 5 |  | 5
15 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 0 | p | 2 |  | 2
16 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2
17 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
18 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
19 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
20 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
21 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
22 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
23 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
24 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 5 | p | 5 | -100% | 10
25 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 5 | p | 5 | -100% | 10
26 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 6 | p | 5 | -83% | 11
27 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 9 | p | 9 | -100% | 18
28 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 18 | p | 1 | -6% | 19
29 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 36 | q | -28 | (-78%) | 8

## Remaining-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%) | Remaining Duration - 47 (33%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 8 | q | -1 | (-12%) | 7
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 4 | q | -1 | (-25%) | 3
3 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 2 | q | -2 | (-100%) | 0
4 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 2 | q | -2 | (-100%) | 0
5 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 1 | q | -1 | (-100%) | 0
6 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 1 | q | -1 | (-100%) | 0
7 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 31 | q | -12 | (-39%) | 19
8 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 2 | q | -2 | (-100%) | 0
9 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
10 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
11 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 31 | q | -12 | (-39%) | 19
12 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 4 | q | -4 | (-100%) | 0
13 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
14 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
15 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 1 | q | -1 | (-100%) | 0
16 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 27 | q | -8 | (-30%) | 19
17 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 21 | q | -2 | (-10%) | 19
18 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 8 | q | -2 | (-25%) | 6
19 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 4 | q | -2 | (-50%) | 2
20 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
21 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
22 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 5 | q | -5 | (-100%) | 0
23 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 4 | q | -4 | (-100%) | 0
24 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2 | q | -2 | (-100%) | 0
25 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
26 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
27 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
28 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
29 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
30 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
31 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
32 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 3 | q | -1 | (-33%) | 2
33 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 7 | q | -4 | (-57%) | 3
34 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 7 | q | -4 | (-57%) | 3
35 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 6 | q | -4 | (-67%) | 2
36 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 6 | q | -6 | (-100%) | 0
37 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2 | q | -1 | (-50%) | 1
38 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
39 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 39 | p | 2 | -5% | 41
40 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 3 | q | -1 | (-33%) | 2
41 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2 | p | 1 | -50% | 3
42 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 12 | p | 1 | -8% | 13
43 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 4 | p | 1 | -25% | 5
44 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 1 | p | 1 | -100% | 2
45 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 13 | q | -10 | (-77%) | 3
46 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 5 | q | -3 | (-60%) | 2
47 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 40 | p | 7 | -18% | 47

## Total-Float
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%) | Total Float - 109 (77%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 0 | q | -1 |  | -1
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 0 | q | -1 |  | -1
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 0 | q | -3 |  | -3
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 0 | q | -1 |  | -1
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
15 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 3 | q | -3 | (-100%) | 0
16 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 3 | q | -3 | (-100%) | 0
17 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 2 | q | -2 | (-100%) | 0
18 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 3 | q | -3 | (-100%) | 0
19 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 3 | q | -3 | (-100%) | 0
20 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 0 | q | -1 |  | -1
21 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 0 | p | 26 |  | 26
22 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 0 | q | -2 |  | -2
23 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 3 | q | -3 | (-100%) | 0
24 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 0 | q | -2 |  | -2
25 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 0 | q | -2 |  | -2
26 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 0 | q | -2 |  | -2
27 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
28 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
29 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
30 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
31 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
32 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 0 | q | -2 |  | -2
33 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 0 | q | -2 |  | -2
34 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
35 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
36 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
37 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
38 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
39 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
40 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
41 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
42 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
43 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
44 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
45 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
46 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 0 | q | -2 |  | -2
47 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
48 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
49 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
50 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 37 | p | 7 | -19% | 44
51 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 37 | p | 7 | -19% | 44
52 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 37 | p | 7 | -19% | 44
53 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 37 | p | 7 | -19% | 44
54 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 54 | p | 2 | -4% | 56
55 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
56 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
57 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
58 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 11 | p | 1 | -9% | 12
59 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 11 | p | 1 | -9% | 12
60 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
61 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 11 | p | 1 | -9% | 12
62 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 13 | q | -1 | (-8%) | 12
63 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 11 | p | 1 | -9% | 12
64 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 14 | q | -1 | (-7%) | 13
65 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 38 | p | 6 | -16% | 44
66 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 38 | p | 6 | -16% | 44
67 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 39 | p | 5 | -13% | 44
68 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 50 | p | 4 | -8% | 54
69 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 0 | q | -2 |  | -2
70 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 0 | q | -1 |  | -1
71 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
72 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 0 | q | -1 |  | -1
73 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
74 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
75 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
76 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
77 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
78 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
79 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 0 | q | -2 |  | -2
80 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 0 | q | -2 |  | -2
81 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
82 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
83 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 0 | q | -1 |  | -1
84 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
85 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
86 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
87 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
88 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
89 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 0 | q | -2 |  | -2
90 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 0 | q | -1 |  | -1
91 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 14 | q | -1 | (-7%) | 13
92 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 22 | p | 40 | -182% | 62
93 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 22 | p | 40 | -182% | 62
94 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 22 | p | 40 | -182% | 62
95 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 22 | p | 40 | -182% | 62
96 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 53 | q | -27 | (-51%) | 26
97 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 53 | q | -27 | (-51%) | 26
98 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 53 | q | -27 | (-51%) | 26
99 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 54 | q | -28 | (-52%) | 26
100 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 54 | q | -28 | (-52%) | 26
101 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 8 | q | -1 | (-12%) | 7
102 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 0 | q | -1 |  | -1
103 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
104 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
105 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
106 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 10 | q | -2 | (-20%) | 8
107 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 38 | p | 6 | -16% | 44
108 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1
109 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 0 | q | -1 |  | -1

## Free-Float
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%) | Free Float - 23 (16%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 3 | q | -3 | (-100%) | 0
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 3 | q | -3 | (-100%) | 0
3 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 0 | p | 26 |  | 26
4 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 3 | q | -3 | (-100%) | 0
5 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 37 | p | 7 | -19% | 44
6 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 54 | p | 2 | -4% | 56
7 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
8 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
9 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
10 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 11 | p | 1 | -9% | 12
11 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 11 | p | 1 | -9% | 12
12 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2 | q | -1 | (-50%) | 1
13 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 14 | q | -1 | (-7%) | 13
14 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 38 | p | 6 | -16% | 44
15 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 50 | p | 4 | -8% | 54
16 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 14 | q | -1 | (-7%) | 13
17 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 22 | p | 40 | -182% | 62
18 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 22 | p | 40 | -182% | 62
19 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 53 | q | -27 | (-51%) | 26
20 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 54 | q | -28 | (-52%) | 26
21 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 8 | q | -1 | (-12%) | 7
22 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 10 | q | -2 | (-20%) | 8
23 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 38 | p | 6 | -16% | 44

## Calendar
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%) | Start - 124 (88%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-26 08:00 | p | 3 |  | 2026-10-29 08:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-26 20:00 | p | 2 |  | 2026-10-29 17:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-10-29 21:00 | p | 3 |  | 2026-11-02 08:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-10-30 13:00 | p | 3 |  | 2026-11-02 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-10-30 21:00 | p | 3 |  | 2026-11-03 08:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-10-30 13:00 | p | 3 |  | 2026-11-02 17:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-02 13:00 | p | 1 |  | 2026-11-03 17:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-02 21:00 | p | 1 |  | 2026-11-04 08:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-03 12:00 | p | 1 |  | 2026-11-04 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
15 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
16 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 08:00
17 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
18 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 1 |  | 2026-08-19 08:00
19 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 2026-08-18 08:00 | p | 1 |  | 2026-08-19 08:00
20 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-18 08:00 | p | 1 |  | 2026-08-19 08:00
21 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-19 08:00 | p | 0 |  | 2026-08-19 13:00
22 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-19 13:00 | p | 0 |  | 2026-08-20 08:00
23 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
24 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
25 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-20 20:00 | p | 4 |  | 2026-08-25 17:00
26 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-20 12:00 | q | 0 |  | 2026-08-20 08:00
27 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
28 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
29 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
30 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-08-27 08:00 | p | 6 |  | 2026-09-02 08:00
31 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-14 08:00 | p | 4 |  | 2026-09-18 08:00
32 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-14 08:00 | p | 4 |  | 2026-09-18 08:00
33 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-17 08:00 | p | 5 |  | 2026-09-22 17:00
34 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-22 15:00 | p | 2 |  | 2026-09-24 16:12
35 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-15 08:00 | p | 6 |  | 2026-09-21 08:00
36 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:00 | p | 6 |  | 2026-09-22 08:00
37 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-08-27 08:00 | p | 6 |  | 2026-09-02 08:00
38 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-27 08:00 | p | 6 |  | 2026-09-02 08:00
39 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-28 08:00 | p | 6 |  | 2026-09-03 08:00
40 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-08-31 08:00 | p | 4 |  | 2026-09-04 08:00
41 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-08-31 08:00 | p | 4 |  | 2026-09-04 08:00
42 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-07 08:00 | p | 4 |  | 2026-09-11 08:00
43 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-10 08:00 | p | 6 |  | 2026-09-16 08:00
44 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-11 08:00 | p | 6 |  | 2026-09-17 08:00
45 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-08 08:00 | p | 6 |  | 2026-09-14 08:00
46 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-09 08:00 | p | 6 |  | 2026-09-15 08:00
47 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
48 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
49 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-23 15:00 | p | 2 |  | 2026-09-25 16:12
50 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
51 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
52 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
53 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
54 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-22 04:00 | p | 5 |  | 2026-08-27 04:00
55 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-24 08:00 | p | 3 |  | 2026-08-27 13:00
56 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-24 17:00 | p | 3 |  | 2026-08-28 12:00
57 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 2026-08-26 01:00 | p | 3 |  | 2026-08-29 12:00
58 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 2026-08-25 09:00 | p | 3 |  | 2026-08-29 04:00
59 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
60 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 2026-08-25 01:00 | p | 3 |  | 2026-08-28 20:00
61 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 2026-08-26 09:00 | p | 3 |  | 2026-08-29 20:00
62 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
63 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-25 15:00 | p | 4 |  | 2026-09-29 16:12
64 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
65 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-28 15:00 | p | 2 |  | 2026-09-30 16:12
66 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-18 13:00 | p | 0 |  | 2026-08-19 08:00
67 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-19 16:59 | p | 0 |  | 2026-08-20 08:00
68 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-18 13:00 | p | 0 |  | 2026-08-19 08:00
69 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
70 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
71 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
72 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-20 08:00 | p | 1 |  | 2026-08-21 08:00
73 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
74 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
75 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-19 08:00 | p | 1 |  | 2026-08-20 08:00
76 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-18 17:00 | p | 1 |  | 2026-08-19 17:00
77 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
78 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
79 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
80 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 2 |  | 2026-08-19 08:00
81 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-24 13:00 | q | -3 |  | 2026-08-21 08:00
82 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-24 13:00 | q | -3 |  | 2026-08-21 08:00
83 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-25 13:00 | q | -3 |  | 2026-08-21 17:00
84 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
85 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
86 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
87 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
88 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-07 09:00 | p | 4 |  | 2026-10-12 08:00
89 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-06 01:00 | p | 3 |  | 2026-10-09 16:12
90 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-08 20:15 | p | 4 |  | 2026-10-12 22:15
91 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-09 08:00 | p | 5 |  | 2026-10-14 08:00
92 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-14 08:00 | p | 5 |  | 2026-10-19 08:00
93 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
94 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-15 08:00 | p | 5 |  | 2026-10-20 08:00
95 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
96 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-02 15:00 | p | 4 |  | 2026-10-06 16:12
97 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-03 23:00 | p | 4 |  | 2026-10-08 00:12
98 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-03 07:00 | p | 4 |  | 2026-10-07 08:12
99 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-05 08:00 | p | 3 |  | 2026-10-08 08:12
100 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-02 15:00 | p | 4 |  | 2026-10-06 16:12
101 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-02 23:00 | p | 4 |  | 2026-10-07 00:12
102 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-03 15:00 | p | 4 |  | 2026-10-07 16:12
103 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-09-30 15:00 | p | 2 |  | 2026-10-02 16:12
104 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
105 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-01 15:00 | p | 4 |  | 2026-10-05 16:12
106 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
107 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
108 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-20 17:00 | q | -14 |  | 2026-08-06 17:00
109 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-08-21 13:00 | q | -14 |  | 2026-08-07 08:00
110 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
111 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 2026-08-17 08:00 | p | 3 |  | 2026-08-20 13:00
112 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-17 08:00 | p | 3 |  | 2026-08-20 13:00
113 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-18 08:00 | p | 5 |  | 2026-08-24 06:00
114 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-21 08:00 | p | 3 |  | 2026-08-24 15:00
115 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
116 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 2026-08-28 13:00 | q | -3 |  | 2026-08-25 08:00
117 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-16 08:00 | p | 5 |  | 2026-10-21 08:00
118 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-19 08:00 | p | 3 |  | 2026-10-22 08:00
119 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-16 08:00 | p | 5 |  | 2026-10-21 08:00
120 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-20 08:00 | p | 3 |  | 2026-10-23 08:00
121 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
122 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-28 13:00 | q | -3 |  | 2026-08-25 08:00
123 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-23 08:00 | p | 5 |  | 2026-10-28 08:00
124 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00

## Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%) | Finish - 130 (92%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-26 17:00 | p | 3 |  | 2026-10-29 17:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-26 08:00 | p | 3 |  | 2026-10-29 08:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-29 11:00 | p | 3 |  | 2026-11-02 08:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-11-02 12:00 | p | 1 |  | 2026-11-03 17:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-10-30 21:00 | p | 3 |  | 2026-11-03 08:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-02 21:00 | p | 1 |  | 2026-11-04 08:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-03 12:00 | p | 1 |  | 2026-11-04 17:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
15 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
16 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
17 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
18 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
19 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
20 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
21 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-18 17:00 | p | 0 |  | 2026-08-19 12:00
22 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-19 12:00 | p | 0 |  | 2026-08-19 17:00
23 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
24 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
25 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
26 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-20 20:00 | p | 4 |  | 2026-08-25 17:00
27 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 2026-08-18 01:00 | p | 1 |  | 2026-08-19 21:00
28 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
29 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
30 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
31 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-23 15:00 | p | 2 |  | 2026-09-25 16:12
32 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-14 17:00 | p | 4 |  | 2026-09-18 17:00
33 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-22 15:00 | p | 2 |  | 2026-09-24 16:12
34 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-23 15:00 | p | 2 |  | 2026-09-25 16:12
35 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-15 17:00 | p | 6 |  | 2026-09-21 17:00
36 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-16 17:00 | p | 6 |  | 2026-09-22 17:00
37 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
38 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-27 17:00 | p | 6 |  | 2026-09-02 17:00
39 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-28 17:00 | p | 6 |  | 2026-09-03 17:00
40 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
41 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-04 17:00 | p | 6 |  | 2026-09-10 17:00
42 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-07 17:00 | p | 4 |  | 2026-09-11 17:00
43 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | p | 6 |  | 2026-09-16 17:00
44 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
45 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-08 17:00 | p | 6 |  | 2026-09-14 17:00
46 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-09 17:00 | p | 6 |  | 2026-09-15 17:00
47 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
48 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
49 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
50 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
51 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
52 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
53 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-22 04:00 | p | 5 |  | 2026-08-27 04:00
54 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-22 12:00 | p | 5 |  | 2026-08-27 12:00
55 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-24 17:00 | p | 3 |  | 2026-08-28 12:00
56 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-25 01:00 | p | 3 |  | 2026-08-28 20:00
57 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 2026-08-26 09:00 | p | 3 |  | 2026-08-29 20:00
58 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 2026-08-25 17:00 | p | 3 |  | 2026-08-29 12:00
59 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
60 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 2026-08-25 09:00 | p | 3 |  | 2026-08-29 04:00
61 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
62 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
63 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-28 15:00 | p | 2 |  | 2026-09-30 16:12
64 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-25 15:00 | p | 4 |  | 2026-09-29 16:12
65 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
66 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
67 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
68 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-19 12:00 | p | 0 |  | 2026-08-19 17:00
69 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
70 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
71 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
72 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
73 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
74 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
75 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
76 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
77 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-20 08:00 | p | 1 |  | 2026-08-21 08:00
78 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
79 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
80 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-19 08:00 | p | 1 |  | 2026-08-20 08:00
81 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-18 08:00 | p | 2 |  | 2026-08-20 08:00
82 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
83 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
84 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 2026-08-17 17:00 | p | 1 |  | 2026-08-19 08:00
85 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
86 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
87 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-25 12:00 | q | -3 |  | 2026-08-21 17:00
88 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
89 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
90 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
91 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
92 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
93 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-08 09:00 | p | 4 |  | 2026-10-12 17:00
94 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-07 09:00 | p | 3 |  | 2026-10-11 00:12
95 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-09 04:15 | p | 4 |  | 2026-10-14 00:15
96 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-13 17:00 | p | 3 |  | 2026-10-16 17:00
97 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-14 17:00 | p | 5 |  | 2026-10-19 17:00
98 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-06 01:00 | p | 3 |  | 2026-10-09 16:12
99 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
100 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
101 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
102 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-04 07:00 | p | 4 |  | 2026-10-08 08:12
103 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-03 15:00 | p | 4 |  | 2026-10-07 16:12
104 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
105 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-02 23:00 | p | 4 |  | 2026-10-07 00:12
106 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-03 07:00 | p | 4 |  | 2026-10-07 08:12
107 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-03 23:00 | p | 4 |  | 2026-10-08 00:12
108 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-01 15:00 | p | 4 |  | 2026-10-05 16:12
109 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-09-30 15:00 | p | 2 |  | 2026-10-02 16:12
110 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-02 15:00 | p | 4 |  | 2026-10-06 16:12
111 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
112 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
113 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
114 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-21 08:00 | q | -14 |  | 2026-08-07 08:00
115 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
116 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
117 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
118 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 3 |  | 2026-08-21 12:00
119 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-18 17:00 | p | 5 |  | 2026-08-24 15:00
120 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
121 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
122 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
123 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
124 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-19 17:00 | p | 3 |  | 2026-10-22 17:00
125 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-16 17:00 | p | 5 |  | 2026-10-21 17:00
126 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
127 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
128 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-31 12:00 | q | -5 |  | 2026-08-25 17:00
129 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
130 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00

## Actual-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%) | Actual Start - 32 (23%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | O | p |  |  | 2026-08-12 08:00
2 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-18 08:00
4 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 08:00
5 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 08:00
6 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 08:00
7 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 13:00
8 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 08:00
9 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 12:00
10 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 17:00
11 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 17:00
12 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-25 17:00
13 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 08:00
14 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
15 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
16 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-08-26 12:00
17 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-02 08:00
18 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-03 08:00
19 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-04 08:00
20 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-26 12:00
21 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
22 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 04:00
23 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 13:00
24 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 12:00
25 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 12:00
26 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 04:00
27 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-30 04:00
28 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 20:00
29 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 20:00
30 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
31 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
32 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 08:00

## Actual-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%) | Actual Finish - 32 (23%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | O | p |  |  | 2026-08-19 17:00
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | O | p |  |  | 2026-08-19 17:00
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | O | p |  |  | 2026-08-12 17:00
4 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
5 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
6 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-20 12:00
7 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 12:00
8 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
9 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 12:00
10 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 12:00
11 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-26 12:00
12 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
13 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-25 17:00
14 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 21:00
15 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
16 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-02 17:00
17 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-03 17:00
18 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-10 17:00
19 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-30 04:00
20 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 04:00
21 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 12:00
22 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 12:00
23 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 20:00
24 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 20:00
25 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 12:00
26 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-30 04:00
27 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 04:00
28 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-30 04:00
29 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
30 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
31 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
32 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 08:00

## Baseline-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Baseline-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Early-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%) | Early Start - 124 (88%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-26 08:00 | p | 3 |  | 2026-10-29 08:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-26 20:00 | p | 2 |  | 2026-10-29 17:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-10-29 21:00 | p | 3 |  | 2026-11-02 08:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-10-30 13:00 | p | 3 |  | 2026-11-02 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-10-30 21:00 | p | 3 |  | 2026-11-03 08:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-10-30 13:00 | p | 3 |  | 2026-11-02 17:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-02 13:00 | p | 1 |  | 2026-11-03 17:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-02 21:00 | p | 1 |  | 2026-11-04 08:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-03 12:00 | p | 1 |  | 2026-11-04 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
15 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
16 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 08:00
17 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
18 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 1 |  | 2026-08-19 08:00
19 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 2026-08-18 08:00 | p | 1 |  | 2026-08-19 08:00
20 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-18 08:00 | p | 1 |  | 2026-08-19 08:00
21 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-19 08:00 | p | 0 |  | 2026-08-19 13:00
22 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-19 13:00 | p | 0 |  | 2026-08-20 08:00
23 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
24 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
25 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-20 20:00 | p | 4 |  | 2026-08-25 17:00
26 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-20 12:00 | q | 0 |  | 2026-08-20 08:00
27 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
28 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
29 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
30 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-08-27 08:00 | p | 6 |  | 2026-09-02 08:00
31 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-14 08:00 | p | 4 |  | 2026-09-18 08:00
32 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-14 08:00 | p | 4 |  | 2026-09-18 08:00
33 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-17 08:00 | p | 5 |  | 2026-09-22 17:00
34 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-22 15:00 | p | 2 |  | 2026-09-24 16:12
35 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-15 08:00 | p | 6 |  | 2026-09-21 08:00
36 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:00 | p | 6 |  | 2026-09-22 08:00
37 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-08-27 08:00 | p | 6 |  | 2026-09-02 08:00
38 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-27 08:00 | p | 6 |  | 2026-09-02 08:00
39 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-28 08:00 | p | 6 |  | 2026-09-03 08:00
40 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-08-31 08:00 | p | 4 |  | 2026-09-04 08:00
41 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-08-31 08:00 | p | 4 |  | 2026-09-04 08:00
42 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-07 08:00 | p | 4 |  | 2026-09-11 08:00
43 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-10 08:00 | p | 6 |  | 2026-09-16 08:00
44 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-11 08:00 | p | 6 |  | 2026-09-17 08:00
45 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-08 08:00 | p | 6 |  | 2026-09-14 08:00
46 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-09 08:00 | p | 6 |  | 2026-09-15 08:00
47 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
48 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
49 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-23 15:00 | p | 2 |  | 2026-09-25 16:12
50 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
51 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
52 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
53 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
54 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-22 04:00 | p | 5 |  | 2026-08-27 04:00
55 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-24 08:00 | p | 3 |  | 2026-08-27 13:00
56 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-24 17:00 | p | 3 |  | 2026-08-28 12:00
57 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 2026-08-26 01:00 | p | 3 |  | 2026-08-29 12:00
58 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 2026-08-25 09:00 | p | 3 |  | 2026-08-29 04:00
59 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
60 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 2026-08-25 01:00 | p | 3 |  | 2026-08-28 20:00
61 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 2026-08-26 09:00 | p | 3 |  | 2026-08-29 20:00
62 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
63 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-25 15:00 | p | 4 |  | 2026-09-29 16:12
64 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
65 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-28 15:00 | p | 2 |  | 2026-09-30 16:12
66 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-18 13:00 | p | 0 |  | 2026-08-19 08:00
67 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-19 16:59 | p | 0 |  | 2026-08-20 08:00
68 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-18 13:00 | p | 0 |  | 2026-08-19 08:00
69 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
70 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
71 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
72 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-20 08:00 | p | 1 |  | 2026-08-21 08:00
73 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
74 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
75 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-19 08:00 | p | 1 |  | 2026-08-20 08:00
76 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-18 17:00 | p | 1 |  | 2026-08-19 17:00
77 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
78 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
79 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
80 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 2 |  | 2026-08-19 08:00
81 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-24 13:00 | q | -3 |  | 2026-08-21 08:00
82 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-24 13:00 | q | -3 |  | 2026-08-21 08:00
83 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-25 13:00 | q | -3 |  | 2026-08-21 17:00
84 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
85 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
86 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
87 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
88 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-07 09:00 | p | 4 |  | 2026-10-12 08:00
89 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-06 01:00 | p | 3 |  | 2026-10-09 16:12
90 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-08 20:15 | p | 4 |  | 2026-10-12 22:15
91 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-09 08:00 | p | 5 |  | 2026-10-14 08:00
92 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-14 08:00 | p | 5 |  | 2026-10-19 08:00
93 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
94 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-15 08:00 | p | 5 |  | 2026-10-20 08:00
95 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
96 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-02 15:00 | p | 4 |  | 2026-10-06 16:12
97 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-03 23:00 | p | 4 |  | 2026-10-08 00:12
98 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-03 07:00 | p | 4 |  | 2026-10-07 08:12
99 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-05 08:00 | p | 3 |  | 2026-10-08 08:12
100 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-02 15:00 | p | 4 |  | 2026-10-06 16:12
101 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-02 23:00 | p | 4 |  | 2026-10-07 00:12
102 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-03 15:00 | p | 4 |  | 2026-10-07 16:12
103 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-09-30 15:00 | p | 2 |  | 2026-10-02 16:12
104 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
105 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-01 15:00 | p | 4 |  | 2026-10-05 16:12
106 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
107 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
108 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-20 17:00 | q | -14 |  | 2026-08-06 17:00
109 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-08-21 13:00 | q | -14 |  | 2026-08-07 08:00
110 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
111 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 2026-08-17 08:00 | p | 3 |  | 2026-08-20 13:00
112 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-17 08:00 | p | 3 |  | 2026-08-20 13:00
113 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-18 08:00 | p | 5 |  | 2026-08-24 06:00
114 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-21 08:00 | p | 3 |  | 2026-08-24 15:00
115 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
116 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 2026-08-28 13:00 | q | -3 |  | 2026-08-25 08:00
117 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-16 08:00 | p | 5 |  | 2026-10-21 08:00
118 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-19 08:00 | p | 3 |  | 2026-10-22 08:00
119 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-16 08:00 | p | 5 |  | 2026-10-21 08:00
120 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-20 08:00 | p | 3 |  | 2026-10-23 08:00
121 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
122 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-28 13:00 | q | -3 |  | 2026-08-25 08:00
123 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-23 08:00 | p | 5 |  | 2026-10-28 08:00
124 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00

## Early-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%) | Early Finish - 130 (92%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-26 17:00 | p | 3 |  | 2026-10-29 17:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-26 08:00 | p | 3 |  | 2026-10-29 08:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-29 11:00 | p | 3 |  | 2026-11-02 08:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-10-30 12:00 | p | 3 |  | 2026-11-02 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-11-02 12:00 | p | 1 |  | 2026-11-03 17:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-10-30 21:00 | p | 3 |  | 2026-11-03 08:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-02 21:00 | p | 1 |  | 2026-11-04 08:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-03 12:00 | p | 1 |  | 2026-11-04 17:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
15 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
16 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
17 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
18 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 2026-08-17 17:00 | p | 2 |  | 2026-08-19 17:00
19 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
20 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
21 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-18 17:00 | p | 0 |  | 2026-08-19 12:00
22 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-19 12:00 | p | 0 |  | 2026-08-19 17:00
23 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
24 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
25 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
26 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-20 20:00 | p | 4 |  | 2026-08-25 17:00
27 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 2026-08-18 01:00 | p | 1 |  | 2026-08-19 21:00
28 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-21 12:00 | p | 5 |  | 2026-08-26 12:00
29 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
30 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
31 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-23 15:00 | p | 2 |  | 2026-09-25 16:12
32 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-14 17:00 | p | 4 |  | 2026-09-18 17:00
33 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-22 15:00 | p | 2 |  | 2026-09-24 16:12
34 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-23 15:00 | p | 2 |  | 2026-09-25 16:12
35 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-15 17:00 | p | 6 |  | 2026-09-21 17:00
36 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-16 17:00 | p | 6 |  | 2026-09-22 17:00
37 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
38 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-27 17:00 | p | 6 |  | 2026-09-02 17:00
39 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-28 17:00 | p | 6 |  | 2026-09-03 17:00
40 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
41 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-04 17:00 | p | 6 |  | 2026-09-10 17:00
42 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-07 17:00 | p | 4 |  | 2026-09-11 17:00
43 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | p | 6 |  | 2026-09-16 17:00
44 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
45 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-08 17:00 | p | 6 |  | 2026-09-14 17:00
46 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-09 17:00 | p | 6 |  | 2026-09-15 17:00
47 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
48 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | p | 6 |  | 2026-09-17 17:00
49 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
50 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-24 15:00 | p | 4 |  | 2026-09-28 16:12
51 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
52 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
53 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-22 04:00 | p | 5 |  | 2026-08-27 04:00
54 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-22 12:00 | p | 5 |  | 2026-08-27 12:00
55 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-24 17:00 | p | 3 |  | 2026-08-28 12:00
56 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-25 01:00 | p | 3 |  | 2026-08-28 20:00
57 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 2026-08-26 09:00 | p | 3 |  | 2026-08-29 20:00
58 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 2026-08-25 17:00 | p | 3 |  | 2026-08-29 12:00
59 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
60 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 2026-08-25 09:00 | p | 3 |  | 2026-08-29 04:00
61 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 2026-08-26 17:00 | p | 3 |  | 2026-08-30 04:00
62 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
63 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-28 15:00 | p | 2 |  | 2026-09-30 16:12
64 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-25 15:00 | p | 4 |  | 2026-09-29 16:12
65 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-29 15:00 | p | 2 |  | 2026-10-01 16:12
66 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
67 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
68 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-19 12:00 | p | 0 |  | 2026-08-19 17:00
69 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
70 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-21 11:59 | q | 0 |  | 2026-08-20 17:00
71 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
72 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
73 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
74 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
75 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
76 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 1 |  | 2026-08-22 05:49
77 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-20 08:00 | p | 1 |  | 2026-08-21 08:00
78 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
79 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
80 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-19 08:00 | p | 1 |  | 2026-08-20 08:00
81 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-18 08:00 | p | 2 |  | 2026-08-20 08:00
82 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-19 17:00 | p | 1 |  | 2026-08-20 17:00
83 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 08:00 | p | 1 |  | 2026-08-18 17:00
84 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 2026-08-17 17:00 | p | 1 |  | 2026-08-19 08:00
85 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
86 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
87 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-25 12:00 | q | -3 |  | 2026-08-21 17:00
88 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
89 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-27 11:59 | q | -2 |  | 2026-08-24 17:00
90 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
91 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
92 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
93 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-08 09:00 | p | 4 |  | 2026-10-12 17:00
94 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-07 09:00 | p | 3 |  | 2026-10-11 00:12
95 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-09 04:15 | p | 4 |  | 2026-10-14 00:15
96 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-13 17:00 | p | 3 |  | 2026-10-16 17:00
97 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-14 17:00 | p | 5 |  | 2026-10-19 17:00
98 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-06 01:00 | p | 3 |  | 2026-10-09 16:12
99 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
100 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
101 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
102 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-04 07:00 | p | 4 |  | 2026-10-08 08:12
103 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-03 15:00 | p | 4 |  | 2026-10-07 16:12
104 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
105 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-02 23:00 | p | 4 |  | 2026-10-07 00:12
106 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-03 07:00 | p | 4 |  | 2026-10-07 08:12
107 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-03 23:00 | p | 4 |  | 2026-10-08 00:12
108 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-01 15:00 | p | 4 |  | 2026-10-05 16:12
109 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-09-30 15:00 | p | 2 |  | 2026-10-02 16:12
110 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-02 15:00 | p | 4 |  | 2026-10-06 16:12
111 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 3 |  | 2026-10-09 08:12
112 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-15 17:00 | p | 5 |  | 2026-10-20 17:00
113 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
114 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-21 08:00 | q | -14 |  | 2026-08-07 08:00
115 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
116 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-10-06 10:00 | q | -54 |  | 2026-08-12 17:00
117 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
118 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-17 17:00 | p | 3 |  | 2026-08-21 12:00
119 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-18 17:00 | p | 5 |  | 2026-08-24 15:00
120 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
121 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 3 |  | 2026-08-24 23:00
122 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
123 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
124 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-19 17:00 | p | 3 |  | 2026-10-22 17:00
125 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-16 17:00 | p | 5 |  | 2026-10-21 17:00
126 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
127 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-22 17:00 | p | 5 |  | 2026-10-27 17:00
128 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-31 12:00 | q | -5 |  | 2026-08-25 17:00
129 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00
130 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 5 |  | 2026-10-28 17:00

## Late-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%) | Late Start - 111 (79%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 4 |  | 2026-10-27 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-23 17:00 | p | 4 |  | 2026-10-27 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-26 08:00 | p | 2 |  | 2026-10-28 08:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 4 |  | 2026-10-27 17:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-26 20:00 | p | 1 |  | 2026-10-28 17:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-10-29 21:00 | p | 0 |  | 2026-10-30 08:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-10-30 13:00 | p | 0 |  | 2026-10-30 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-10-30 13:00 | p | 0 |  | 2026-10-30 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-10-30 21:00 | p | 2 |  | 2026-11-02 08:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-10-30 13:00 | p | 0 |  | 2026-10-30 17:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-02 13:00 | p | 0 |  | 2026-11-02 17:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-02 21:00 | p | 0 |  | 2026-11-03 08:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-03 12:00 | p | 0 |  | 2026-11-03 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 0 |  | 2026-11-05 17:00
15 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 2026-08-14 14:30 | q | -2 |  | 2026-08-12 08:00
16 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 2026-08-21 05:00 | q | -1 |  | 2026-08-19 17:00
17 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 2026-08-20 15:00 | q | -2 |  | 2026-08-18 08:00
18 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 0 |  | 2026-11-05 17:00
19 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 2026-08-18 13:00 | p | 0 |  | 2026-08-19 08:00
20 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 2026-08-18 13:00 | p | 0 |  | 2026-08-19 08:00
21 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-18 13:00 | p | 0 |  | 2026-08-19 08:00
22 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-21 05:00 | q | 0 |  | 2026-08-20 12:00
23 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 2026-08-21 05:00 | q | -1 |  | 2026-08-19 17:00
24 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 2026-08-21 05:00 | q | -1 |  | 2026-08-19 17:00
25 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-21 13:00 | p | 4 |  | 2026-08-25 17:00
26 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-21 05:00 | q | 0 |  | 2026-08-20 08:00
27 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 2026-08-21 05:00 | q | -1 |  | 2026-08-19 17:00
28 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-23 10:00 | p | 3 |  | 2026-08-26 12:00
29 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-08-23 10:00 | p | 3 |  | 2026-08-26 12:00
30 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-08-27 10:00 | p | 3 |  | 2026-08-31 08:48
31 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
32 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
33 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-17 10:00 | p | 3 |  | 2026-09-21 08:48
34 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-15 10:00 | p | 1 |  | 2026-09-17 08:48
35 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-16 10:00 | p | 1 |  | 2026-09-18 08:48
36 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-08-27 10:00 | p | 3 |  | 2026-08-31 08:48
37 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-27 10:00 | p | 5 |  | 2026-09-02 08:00
38 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-28 10:00 | p | 5 |  | 2026-09-03 08:00
39 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-08-31 10:00 | p | 1 |  | 2026-09-02 08:48
40 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-08-31 10:00 | p | 3 |  | 2026-09-04 08:00
41 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-07 10:00 | p | 1 |  | 2026-09-09 08:48
42 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-10 10:00 | p | 3 |  | 2026-09-14 08:48
43 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-11 10:00 | p | 3 |  | 2026-09-15 08:48
44 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-08 10:00 | p | 1 |  | 2026-09-10 08:48
45 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-09 10:00 | p | 1 |  | 2026-09-11 08:48
46 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
47 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
48 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 2026-08-23 10:00 | p | 3 |  | 2026-08-26 12:00
49 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-23 10:00 | p | 3 |  | 2026-08-26 12:00
50 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-24 02:00 | p | 3 |  | 2026-08-27 04:00
51 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-24 10:00 | p | 3 |  | 2026-08-27 13:00
52 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-25 10:00 | p | 3 |  | 2026-08-28 12:00
53 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 2026-08-26 18:00 | p | 2 |  | 2026-08-29 12:00
54 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 2026-08-26 02:00 | p | 3 |  | 2026-08-29 04:00
55 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 2026-08-27 10:00 | p | 2 |  | 2026-08-30 04:00
56 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 2026-08-25 18:00 | p | 3 |  | 2026-08-28 20:00
57 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 2026-08-27 02:00 | p | 2 |  | 2026-08-29 20:00
58 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-10-08 09:01 | p | 11 |  | 2026-10-20 08:00
59 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-10-09 13:00 | p | 11 |  | 2026-10-21 08:00
60 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-10-08 09:01 | p | 11 |  | 2026-10-20 08:00
61 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-10-13 06:59 | p | 9 |  | 2026-10-22 08:00
62 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
63 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 2026-08-17 13:00 | p | 1 |  | 2026-08-18 17:00
64 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-09-04 19:00 | p | 3 |  | 2026-09-08 10:59
65 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-09-04 10:00 | p | 3 |  | 2026-09-07 19:59
66 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-09-03 19:00 | p | 3 |  | 2026-09-07 10:59
67 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-09-03 19:00 | p | 3 |  | 2026-09-07 10:59
68 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-09-03 19:00 | p | 3 |  | 2026-09-07 10:59
69 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-09-03 19:00 | p | 3 |  | 2026-09-07 10:59
70 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-09-04 10:00 | p | 3 |  | 2026-09-07 19:59
71 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 13:00 | p | 1 |  | 2026-08-18 17:00
72 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 2026-08-17 13:00 | p | 1 |  | 2026-08-19 08:00
73 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-10-16 08:00 | p | 6 |  | 2026-10-22 08:00
74 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-10-16 08:00 | p | 6 |  | 2026-10-22 08:00
75 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-10-19 08:01 | p | 3 |  | 2026-10-23 08:00
76 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
77 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-05 21:00 | p | 1 |  | 2026-10-07 16:00
78 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-16 08:00 | p | 4 |  | 2026-10-20 08:00
79 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-07 13:00 | p | 1 |  | 2026-10-09 08:00
80 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-06 05:00 | p | 1 |  | 2026-10-08
81 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-09 | p | 3 |  | 2026-10-12 06:00
82 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-09 08:00 | p | 4 |  | 2026-10-13 08:00
83 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-14 08:00 | p | 2 |  | 2026-10-16 08:00
84 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-05 21:00 | p | 1 |  | 2026-10-07 16:00
85 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-15 08:00 | p | 4 |  | 2026-10-19 08:00
86 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-03 16:00 | p | 1 |  | 2026-10-05
87 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 | p | 1 |  | 2026-10-06 08:00
88 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-04 08:00 | p | 1 |  | 2026-10-05 16:00
89 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-05 08:00 | p | 1 |  | 2026-10-06 16:00
90 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-03 16:00 | p | 1 |  | 2026-10-05
91 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-04 | p | 1 |  | 2026-10-05 08:00
92 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-04 16:00 | p | 1 |  | 2026-10-06
93 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 21:00 | p | 1 |  | 2026-10-07 16:00
94 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
95 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-09-21 19:00 | p | 41 |  | 2026-11-02 17:00
96 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-09-22 15:00 | p | 41 |  | 2026-11-03 08:00
97 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
98 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 2026-10-29 08:00 | q | -31 |  | 2026-09-28 08:00
99 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-10-29 08:00 | q | -31 |  | 2026-09-28 08:00
100 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-10-30 15:00 | q | -31 |  | 2026-09-29 08:00
101 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-11-04 21:00 | q | -36 |  | 2026-09-29 17:00
102 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-11-05 12:00 | q | -36 |  | 2026-09-30 08:00
103 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 2026-10-16 08:00 | p | 4 |  | 2026-10-20 08:00
104 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-16 08:00 | p | 4 |  | 2026-10-20 08:00
105 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-19 08:00 | p | 2 |  | 2026-10-21 08:00
106 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-16 08:00 | p | 4 |  | 2026-10-20 08:00
107 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-20 08:00 | p | 2 |  | 2026-10-22 08:00
108 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
109 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-10-22 08:00 | p | 4 |  | 2026-10-26 08:00
110 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-23 08:00 | p | 4 |  | 2026-10-27 08:00
111 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 4 |  | 2026-10-27 17:00

## Late-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%) | Late Finish - 117 (83%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 37 | Post Launch | Summary | 8 | 8 | 8 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 0 |  | 2026-11-05 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 4 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-30 13:00 | p | 0 |  | 2026-10-30 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-26 17:00 | p | 2 |  | 2026-10-28 17:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-26 08:00 | p | 2 |  | 2026-10-28 08:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-29 11:00 | p | 0 |  | 2026-10-30 08:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-10-30 12:00 | p | 0 |  | 2026-10-30 17:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-10-30 13:00 | p | 0 |  | 2026-10-30 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 0 |  | 2026-11-05 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-11-02 12:00 | p | 0 |  | 2026-11-02 17:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-10-30 21:00 | p | 2 |  | 2026-11-02 08:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-02 21:00 | p | 0 |  | 2026-11-03 08:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-03 12:00 | p | 0 |  | 2026-11-03 17:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 0 |  | 2026-11-05 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 0 |  | 2026-11-05 17:00
15 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 2026-08-21 05:00 | q | -1 |  | 2026-08-19 17:00
16 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 2026-08-21 05:00 | q | -1 |  | 2026-08-19 17:00
17 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 2026-08-14 23:00 | q | -2 |  | 2026-08-12 17:00
18 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 2026-08-21 05:00 | q | -1 |  | 2026-08-19 17:00
19 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 2026-08-20 23:00 | q | -1 |  | 2026-08-19 17:00
20 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-05 12:00 | p | 0 |  | 2026-11-05 17:00
21 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
22 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 2026-08-21 05:00 | q | 0 |  | 2026-08-20 12:00
23 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-20 17:00 | q | 0 |  | 2026-08-20 12:00
24 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-21 05:00 | q | 0 |  | 2026-08-20 12:00
25 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 2026-08-23 10:00 | p | 3 |  | 2026-08-26 12:00
26 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-23 10:00 | p | 3 |  | 2026-08-26 12:00
27 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-21 13:00 | p | 4 |  | 2026-08-25 17:00
28 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 2026-08-21 13:00 | q | -1 |  | 2026-08-19 21:00
29 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-23 10:00 | p | 3 |  | 2026-08-26 12:00
30 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-15 10:00 | p | 1 |  | 2026-09-17 08:48
31 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-22 17:00 | p | 0 |  | 2026-09-23 08:00
32 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-16 10:00 | p | 1 |  | 2026-09-18 08:48
33 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-17 10:00 | p | 3 |  | 2026-09-21 08:48
34 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
35 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-28 10:00 | p | 5 |  | 2026-09-02 17:00
36 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-31 10:00 | p | 3 |  | 2026-09-03 17:00
37 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
38 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-07 10:00 | p | 3 |  | 2026-09-10 17:00
39 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-08 10:00 | p | 1 |  | 2026-09-10 08:48
40 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-11 10:00 | p | 3 |  | 2026-09-15 08:48
41 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
42 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-09 10:00 | p | 1 |  | 2026-09-11 08:48
43 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-10 10:00 | p | 3 |  | 2026-09-14 08:48
44 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
45 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-14 10:00 | p | 1 |  | 2026-09-16 08:48
46 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 2026-08-27 10:00 | p | 2 |  | 2026-08-30 04:00
47 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 2026-08-24 02:00 | p | 3 |  | 2026-08-27 04:00
48 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 2026-08-24 10:00 | p | 3 |  | 2026-08-27 12:00
49 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-25 10:00 | p | 3 |  | 2026-08-28 12:00
50 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-08-25 18:00 | p | 3 |  | 2026-08-28 20:00
51 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 2026-08-27 02:00 | p | 2 |  | 2026-08-29 20:00
52 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 2026-08-26 10:00 | p | 3 |  | 2026-08-29 12:00
53 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 2026-08-27 10:00 | p | 2 |  | 2026-08-30 04:00
54 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 2026-08-26 02:00 | p | 3 |  | 2026-08-29 04:00
55 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 2026-08-27 10:00 | p | 2 |  | 2026-08-30 04:00
56 | 318 | Technology Infrastructure | Summary | 3 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-10-13 06:59 | p | 9 |  | 2026-10-22 08:00
57 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-10-12 17:00 | p | 9 |  | 2026-10-21 17:00
58 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-10-09 09:01 | p | 11 |  | 2026-10-20 17:00
59 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-10-13 06:59 | p | 9 |  | 2026-10-22 08:00
60 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
61 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 2026-09-07 10:00 | p | 1 |  | 2026-09-09 08:48
62 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 2026-09-07 10:00 | p | 1 |  | 2026-09-09 08:48
63 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 2026-09-07 10:00 | p | 1 |  | 2026-09-09 08:48
64 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 2026-08-17 13:00 | p | 1 |  | 2026-08-18 17:00
65 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 12:00 | p | 1 |  | 2026-08-18 17:00
66 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-09-07 10:00 | p | 1 |  | 2026-09-09 08:48
67 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-09-04 19:00 | p | 3 |  | 2026-09-08 10:59
68 | 45 | Design Customer Service Contact Scenarios | Summary | 2 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-09-04 10:00 | p | 3 |  | 2026-09-07 19:59
69 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-09-04 10:00 | p | 3 |  | 2026-09-07 19:59
70 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-09-04 10:00 | p | 3 |  | 2026-09-07 19:59
71 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-09-04 10:00 | p | 3 |  | 2026-09-07 19:59
72 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-09-04 10:00 | p | 3 |  | 2026-09-07 19:59
73 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 2026-08-17 13:00 | p | 1 |  | 2026-08-18 17:00
74 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 2026-08-18 12:00 | p | 0 |  | 2026-08-19 08:00
75 | 373 | Build Customer Service Program | Summary | 39 | 6 | 6 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
76 | 372 | Build Technology Infrastructure | Summary | 3 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
77 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-10-16 17:00 | p | 6 |  | 2026-10-22 17:00
78 | 398 | Test technology infrastructure | Normal | 2 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-10-21 06:59 | p | 5 |  | 2026-10-26 08:00
79 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
80 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
81 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-16 08:00 | p | 4 |  | 2026-10-20 08:00
82 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-16 08:00 | p | 4 |  | 2026-10-20 08:00
83 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-08 12:00 | p | 1 |  | 2026-10-09 17:00
84 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-07 13:00 | p | 1 |  | 2026-10-09 08:00
85 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-09 08:00 | p | 4 |  | 2026-10-13 08:00
86 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-13 17:00 | p | 2 |  | 2026-10-15 17:00
87 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-14 17:00 | p | 2 |  | 2026-10-16 17:00
88 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-06 05:00 | p | 1 |  | 2026-10-08
89 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-15 17:00 | p | 4 |  | 2026-10-19 17:00
90 | 219 | Training Content Development | Summary | 4 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-05 21:00 | p | 1 |  | 2026-10-07 16:00
91 | 221 | Build Training Content | Summary | 1 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-05 17:00 | p | 1 |  | 2026-10-07 16:00
92 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 08:00 | p | 1 |  | 2026-10-06 16:00
93 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-04 16:00 | p | 1 |  | 2026-10-06
94 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-05 17:00 | p | 1 |  | 2026-10-07 16:00
95 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-04 | p | 1 |  | 2026-10-05 08:00
96 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-04 08:00 | p | 1 |  | 2026-10-05 16:00
97 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-05 | p | 1 |  | 2026-10-06 08:00
98 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-05 21:00 | p | 1 |  | 2026-10-07 16:00
99 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
100 | 392 | Customer Service Program Development | Summary | 13 | 6.3 | 6.3 |  | 1 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
101 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-09-22 10:00 | p | 41 |  | 2026-11-03 08:00
102 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
103 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
104 | 383 | Business Performance Planning | Summary | 5 | 5 | 5 |  | 0 | 0 |  | 2026-11-05 12:00 | q | -36 |  | 2026-09-30 08:00
105 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-10-29 17:00 | q | -31 |  | 2026-09-28 17:00
106 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-10-30 23:00 | q | -31 |  | 2026-09-29 17:00
107 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-11-05 12:00 | q | -36 |  | 2026-09-30 08:00
108 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-11-05 12:00 | q | -36 |  | 2026-09-30 08:00
109 | 391 | Program Deployment | Summary | 40 | 7 | 7 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
110 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
111 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-19 17:00 | p | 2 |  | 2026-10-21 17:00
112 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-16 17:00 | p | 4 |  | 2026-10-20 17:00
113 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-22 17:00 | p | 4 |  | 2026-10-26 17:00
114 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-11-05 12:00 | p | 1 |  | 2026-11-06 17:00
115 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-10-22 17:00 | p | 4 |  | 2026-10-26 17:00
116 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 4 |  | 2026-10-27 17:00
117 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-23 17:00 | p | 4 |  | 2026-10-27 17:00

## Expected-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Suspend-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%) | Suspend Date - 36 (26%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | O | p |  |  | 2026-08-12 17:00
2 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
4 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 08:00
5 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 12:00
6 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 12:00
7 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
8 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 12:00
9 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 12:00
10 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 21:00
11 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 21:00
12 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
13 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-25 17:00
14 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 21:00
15 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
16 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-08-27 04:00
17 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-02 17:00
18 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-03 17:00
19 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-10 17:00
20 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-27 04:00
21 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 04:00
22 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 12:00
23 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 12:00
24 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 20:00
25 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 20:00
26 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 12:00
27 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-30 04:00
28 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 04:00
29 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-30 04:00
30 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
31 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
32 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
33 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
34 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
35 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
36 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 08:00

## Resume-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%) | Resume Date - 36 (26%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | O | p |  |  | 2026-08-12 17:00
2 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
4 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 08:00
5 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 12:00
6 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 12:00
7 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 17:00
8 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 12:00
9 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-20 12:00
10 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 21:00
11 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-19 21:00
12 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
13 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-25 17:00
14 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | O | p |  |  | 2026-08-19 21:00
15 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-26 12:00
16 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-08-27 04:00
17 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-02 17:00
18 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-03 17:00
19 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-10 17:00
20 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-08-27 04:00
21 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 04:00
22 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-27 12:00
23 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 12:00
24 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-28 20:00
25 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 20:00
26 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 12:00
27 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-30 04:00
28 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-29 04:00
29 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-30 04:00
30 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
31 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
32 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
33 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
34 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-08-11 17:00 | p | 7 |  | 2026-08-18 17:00
35 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-18 17:00
36 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-08-19 08:00

## Activity-Status
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%) | Activity Status - 35 (25%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | InProgress |  |  |  | Complete
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | InProgress |  |  |  | Complete
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | Planned |  |  |  | Complete
4 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | Planned |  |  |  | Complete
5 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | Planned |  |  |  | Complete
6 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | Planned |  |  |  | InProgress
7 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | Planned |  |  |  | Complete
8 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
9 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
10 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
11 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
12 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | Planned |  |  |  | InProgress
13 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | Planned |  |  |  | Complete
14 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
15 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
16 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | Planned |  |  |  | Complete
17 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
18 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | Planned |  |  |  | InProgress
19 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
20 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
21 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
22 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | Planned |  |  |  | Complete
23 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
24 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
25 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
26 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
27 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
28 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
29 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
30 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
31 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
32 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
33 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | InProgress |  |  |  | Complete
34 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
35 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete

## Percent-Complete
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%) | Percent Complete - 38 (27%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 0.94 | p | 0.06 | -6% | 1
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 0.94 | p | 0.06 | -6% | 1
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 0 | p | 1 |  | 1
4 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 0 | p | 1 |  | 1
5 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 0 | p | 1 |  | 1
6 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 0 | p | 0.4 |  | 0.4
7 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 0 | p | 1 |  | 1
8 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
9 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
10 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
11 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
12 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 0 | p | 0.4 |  | 0.4
13 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 0 | p | 1 |  | 1
14 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
15 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
16 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 0 | p | 1 |  | 1
17 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
18 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 0 | p | 0.29 |  | 0.29
19 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
20 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
21 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
22 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 0 | p | 1 |  | 1
23 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
24 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
25 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
26 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
27 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
28 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
29 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
30 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
31 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
32 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 0.43 | p | 0.34 | -79% | 0.77
33 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 0.45 | p | 0.32 | -71% | 0.77
34 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 0.53 | p | 0.35 | -66% | 0.88
35 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
36 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 0.6 | p | 0.4 | -67% | 1
37 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
38 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1

## Physical---Complete
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%) | Physical % Complete - 26 (18%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 0 | p | 1 |  | 1
2 | 147 | Product Review COMPLETE | Milestone | 0 | 2.1.6 | 2.1.6 |  | 0 | 4.88 | Path 02 | 0 | p | 1 |  | 1
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 0 | p | 1 |  | 1
4 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
5 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
6 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
7 | 149 | Resource Planning COMPLETE | Milestone | 0 | 4.1.4 | 4.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
8 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
9 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
10 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 0 | p | 1 |  | 1
11 | 216 | Training Needs Assessment COMPLETE | Milestone | 0 | 4.2.1.4 | 4.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
12 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
13 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
14 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
15 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
16 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
17 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
18 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
19 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
20 | 300 | Content Development Planning COMPLETE | Milestone | 0 | 4.2.2.1.9 | 4.2.2.1.9 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
21 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
22 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
23 | 184 | Customer Service Level Design COMPLETE | Milestone | 0 | 3.1.2.4 | 3.1.2.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
24 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
25 | 148 | Design of Support Services COMPLETE | Milestone | 0 | 3.1.3 | 3.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
26 | 323 | Service Planning & Design COMPLETE | Normal | 1 | 3.2 | 3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1

## Critical
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%) | Critical - 35 (25%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | O |  |  |  | P
2 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | O |  |  |  | P
3 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | O |  |  |  | P
4 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | O |  |  |  | P
5 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
6 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
7 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
8 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
9 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
10 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | O |  |  |  | P
11 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
12 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
13 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | O |  |  |  | P
14 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
15 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
16 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
17 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
18 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
19 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
20 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
21 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
22 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
23 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
24 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
25 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
26 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
27 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | O |  |  |  | P
28 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
29 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
30 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
31 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | O |  |  |  | P
32 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
33 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
34 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
35 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P

## Longest-Path
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%) | Longest Path - 35 (25%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | O |  |  |  | P
2 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | O |  |  |  | P
3 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | O |  |  |  | P
4 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | O |  |  |  | P
5 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
6 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
7 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
8 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
9 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
10 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | O |  |  |  | P
11 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
12 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
13 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | O |  |  |  | P
14 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
15 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
16 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
17 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
18 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
19 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
20 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
21 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
22 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
23 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
24 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
25 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
26 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
27 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | O |  |  |  | P
28 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
29 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
30 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
31 | 375 | Training/Readiness Development | Summary | 12 | 6.1 | 6.1 |  | 0 | 0 |  | O |  |  |  | P
32 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
33 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
34 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | O |  |  |  | P
35 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | O |  |  |  | P

## Primary-Constraint
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%) | Primary Constraint - 1 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter

## Secondary-Constraint
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Primary-Constraint-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%) | Primary Constraint Date - 1 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-02 08:00

## Secondary-Constraint-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Baseline-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Actual-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%) | Actual Work - 31 (22%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 232 | p | 32 | -14% | 264
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 232 | p | 32 | -14% | 264
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 0 | p | 8 |  | 8
4 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 0 | p | 24 |  | 24
5 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 0 | p | 162 |  | 162
6 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 0 | p | 12 |  | 12
7 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 4 |  | 4
8 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 4 |  | 4
9 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 4 |  | 4
10 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 0 | p | 150 |  | 150
11 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 0 | p | 86 |  | 86
12 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
13 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 74 |  | 74
14 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 0 | p | 4 |  | 4
15 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 0 | p | 64 |  | 64
16 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
17 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
18 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 0 | p | 55 |  | 55
19 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 0 | p | 64 |  | 64
20 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
21 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
22 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
23 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
24 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
25 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
26 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
27 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
28 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 72 | p | 72 | -100% | 144
29 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 72 | p | 72 | -100% | 144
30 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 72 | p | 72 | -100% | 144
31 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 72 | p | 72 | -100% | 144

## Remaining-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%) | Remaining Work - 34 (24%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 16 | q | -16 | (-100%) | 0
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 16 | q | -16 | (-100%) | 0
3 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 8 | q | -8 | (-100%) | 0
4 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 8 | q | -8 | (-100%) | 0
5 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 333 | q | -128 | (-38%) | 205
6 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 20 | q | -20 | (-100%) | 0
7 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
8 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 4 | q | -4 | (-100%) | 0
9 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
10 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 297 | q | -108 | (-36%) | 189
11 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 24 | q | -24 | (-100%) | 0
12 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
13 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
14 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 8 | q | -8 | (-100%) | 0
15 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 273 | q | -84 | (-31%) | 189
16 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 185 | q | -20 | (-11%) | 165
17 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 64 | q | -20 | (-31%) | 44
18 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 40 | q | -20 | (-50%) | 20
19 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
20 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
21 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 55 | q | -55 | (-100%) | 0
22 | 299 | Content Development Planning | Summary | 4 | 4.2.2.1 | 4.2.2.1 |  | 0 | 0 |  | 64 | q | -64 | (-100%) | 0
23 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
24 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
25 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
26 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
27 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
28 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
29 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
30 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
31 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 88 | q | -48 | (-55%) | 40
32 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 88 | q | -48 | (-55%) | 40
33 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 64 | q | -48 | (-75%) | 16
34 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 48 | q | -48 | (-100%) | 0

## Total-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%) | Total Work - 19 (13%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 91 | Initial Assessment | Summary | 2 | 2 | 2 |  | 2 | 0 |  | 248 | p | 16 | -6% | 264
2 | 92 | Perform Product Review | Summary | 2 | 2.1 | 2.1 |  | 2 | 0 |  | 248 | p | 16 | -6% | 264
3 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 8 | p | 16 | -200% | 24
4 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 333 | p | 34 | -10% | 367
5 | 100 | Resources Requirements | Summary | 2 | 4.1 | 4.1 |  | 0 | 0 |  | 20 | q | -8 | (-40%) | 12
6 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 8 | q | -4 | (-50%) | 4
7 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 8 | q | -4 | (-50%) | 4
8 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 297 | p | 42 | -14% | 339
9 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 24 | p | 62 | -258% | 86
10 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 8 | p | 66 | -825% | 74
11 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 8 | q | -4 | (-50%) | 4
12 | 235 | Training Planning | Summary | 27 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 273 | q | -20 | (-7%) | 253
13 | 237 | Training Delivery Planning | Summary | 21 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 185 | q | -20 | (-11%) | 165
14 | 283 | Training Delivery Logistics | Summary | 8 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 64 | q | -20 | (-31%) | 44
15 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 40 | q | -20 | (-50%) | 20
16 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 160 | p | 24 | -15% | 184
17 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 160 | p | 24 | -15% | 184
18 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 136 | p | 24 | -18% | 160
19 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 120 | p | 24 | -20% | 144

## Baseline-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Budget-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Actual-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%) | Actual Cost - 20 (14%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 0 | p | 400 |  | 400
2 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 0 | p | 1200 |  | 1200
3 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
4 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
5 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
6 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1200 |  | 1200
7 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 10863 |  | 10863
8 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 0 | p | 400 |  | 400
9 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600
10 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600
11 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 0 | p | 12500 |  | 12500
12 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
13 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
14 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600
15 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
16 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
17 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
18 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
19 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 0 | p | 800 |  | 800
20 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 3600 | p | 3600 | -100% | 7200

## Remaining-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%) | Remaining Cost - 22 (16%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 94 | Determine solutions for product points | Normal | 1 | 2.1.4 | 2.1.4 |  | 0 | 6.88 | Path 02 | 400 | q | -400 | (-100%) | 0
2 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 400 | q | -400 | (-100%) | 0
3 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
4 | 99 | Estimate resource requirements | Normal | 0 | 4.1.2 | 4.1.2 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
5 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
6 | 200 | Determine product-specific training needs | Normal | 1 | 4.2.1.3 | 4.2.1.3 |  | 0 | 1.88 | Path 02 | 1200 | q | -1200 | (-100%) | 0
7 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 800 | p | 1150 | -144% | 1950
8 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 800 | p | 200 | -25% | 1000
9 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 9000 | q | -3474 | (-39%) | 5526
10 | 199 | Identify internal resources that can serve as potential trainers | Normal | 1 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
11 | 268 | Determine whether additional trainers will be needed | Normal | 1 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
12 | 290 | Review expertise of potential vendors | Normal | 5 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 12500 | q | -12500 | (-100%) | 0
13 | 241 | Determine methods for delivering training | Normal | 2 | 4.2.2.1.1 | 4.2.2.1.1 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
14 | 249 | Determine form factor for training content | Normal | 1 | 4.2.2.1.2 | 4.2.2.1.2 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
15 | 251 | Identify internal resources that can review training materials | Normal | 1 | 4.2.2.1.3 | 4.2.2.1.3 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
16 | 254 | Determine training course topics | Normal | 1 | 4.2.2.1.4 | 4.2.2.1.4 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
17 | 255 | Draft description of training program/courses | Normal | 1 | 4.2.2.1.7 | 4.2.2.1.7 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
18 | 282 | Design student materials | Normal | 1 | 4.2.2.1.6 | 4.2.2.1.6 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
19 | 301 | Determine number of training courses | Normal | 1 | 4.2.2.1.5 | 4.2.2.1.5 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
20 | 303 | Draft content development budget | Normal | 1 | 4.2.2.1.8 | 4.2.2.1.8 |  | 0 | 1.88 | Path 02 | 800 | q | -800 | (-100%) | 0
21 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 2400 | q | -2400 | (-100%) | 0
22 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 400 | q | -80 | (-20%) | 320

## Total-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%) | Total Cost - 8 (6%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 400 | p | 800 | -200% | 1200
2 | 98 | Estimate demand for customer support (all options) | Normal | 1 | 4.1.1 | 4.1.1 |  | 0 | 1.88 | Path 02 | 1600 | q | -800 | (-50%) | 800
3 | 131 | Estimate effort to hire new resources | Normal | 1 | 4.1.3 | 4.1.3 |  | 0 | 1.88 | Path 02 | 1600 | q | -800 | (-50%) | 800
4 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 800 | p | 12013 | -1502% | 12813
5 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 800 | p | 600 | -75% | 1400
6 | 267 | Develop training delivery budget | Normal | 4 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 9000 | q | -3474 | (-39%) | 5526
7 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 6000 | p | 1200 | -20% | 7200
8 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 400 | q | -80 | (-20%) | 320

## WBS-Code
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Existence--
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Use-Cost-Uncertainty
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Cost-Uncertainty-Distribution
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Max-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Most-Likely-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Min-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Upper---Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Lower---Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Mean-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Std-Deviation-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Use-Duration-Uncertainty
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Duration-Uncertainty-Distribut
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Max-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Most-Likely-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Min-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Upper---Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Lower---Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Mean-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Std-Deviation-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Budget
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 0 | p | 2 |  | 2
2 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 0 | p | 1 |  | 1
3 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
4 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 0 | p | 2 |  | 2
5 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2
6 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 0 | p | 2 |  | 2
7 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 0 | p | 1 |  | 1
8 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 0 | p | 1 |  | 1
9 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
10 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2

## Task-Budget
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2
1 | 157 | Document product review results | Normal | 1 | 2.1.5 | 2.1.5 |  | 0 | 4.88 | Path 02 | 0 | p | 2 |  | 2
2 | 315 | Service Delivery Infrastructure Planning | Summary | 31 | 4 | 4 |  | 0 | 0 |  | 0 | p | 1 |  | 1
3 | 129 | Training & Readiness | Summary | 31 | 4.2 | 4.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
4 | 212 | Training Needs Assessment | Summary | 4 | 4.2.1 | 4.2.1 |  | 0 | 0 |  | 0 | p | 2 |  | 2
5 | 210 | Review anticipated skill sets of support resources | Normal | 1 | 4.2.1.2 | 4.2.1.2 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2
6 | 211 | Review output of product review phase | Normal | 1 | 4.2.1.1 | 4.2.1.1 |  | 0 | 4.88 | Path 02 | 0 | p | 2 |  | 2
7 | 322 | Service Planning | Summary | 7 | 3 | 3 |  | 0 | 0 |  | 0 | p | 1 |  | 1
8 | 125 | Design Support Services | Summary | 7 | 3.1 | 3.1 |  | 0 | 0 |  | 0 | p | 1 |  | 1
9 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 6 | 3.1.2 | 3.1.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
10 | 187 | Determine required skill sets for various support options | Normal | 6 | 3.1.2.3 | 3.1.2.3 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2

## Driving-Slack
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2

## Trace-Log-Field
Acumen Fuse® Forensic Analysis Report
Hard_File_update vs update2_Fuse
Hard_File_updated - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2