## Projects
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects
Name | Start | Start | Finish | Finish | Time Now | Time Now | Baseline Start | Baseline Start | Baseline Finish | Baseline Finish | Activities | Activities | Budget Duration | Budget Duration | Actual Duration | Actual Duration | Remaining Duration | Remaining Duration | Total Duration | Total Duration | Budget Cost | Budget Cost | Actual Cost | Actual Cost | Remaining Cost | Remaining Cost | Total Cost | Total Cost
Hard_File_updated2 |  | 2026-07-08 08:00 |  | 2026-11-06 17:00 |  | 2026-09-10 17:00 |  | 2026-07-08 08:00 |  | 2026-11-05 12:00 |  | 141 |  | 120.1667 |  | 47 |  | 41 |  | 88 |  | 133400 |  | 63763 |  | 83096 |  | 146859
Hard_File_updated3 | = | 2026-07-08 08:00 | p | 2026-12-12 17:00 | p | 2026-10-12 17:00 | = | 2026-07-08 08:00 | = | 2026-11-05 12:00 | = | 141 | = | 120.1667 | p | 69 | p | 44 | p | 113 | = | 133400 | p | 67703 | p | 124304 | p | 192007

## Activities
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3

## Relationships
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%) | Relationships - 3 (3%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Hard_File_updated2 | Hard_File_updated3
267 | Develop training delivery budget | True | 278 | Training Delivery Logistics COMPLETE | True | FinishToStart (0) | O
298 | Trainer Needs Assessment COMPLETE | False | 278 | Training Delivery Logistics COMPLETE | True | O | FinishToStart (0)
267 | Develop training delivery budget | True | 270 | Create communications plan | True | O | FinishToStart (0)

## Leads-Lags
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%) | Leads/Lags - 3 (3%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Hard_File_updated2 Relationship Type | Hard_File_updated3 Relationship Type | Hard_File_updated2 Lead/Lag | Hard_File_updated3 Lead/Lag
267 | Develop training delivery budget | True | 278 | Training Delivery Logistics COMPLETE | True | FinishToStart | O | 0 | O
298 | Trainer Needs Assessment COMPLETE | False | 278 | Training Delivery Logistics COMPLETE | True | O | FinishToStart | O | 0
267 | Develop training delivery budget | True | 270 | Create communications plan | True | O | FinishToStart | O | 0

## Resources
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%) | Resources - 17 (17%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Resource | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
2 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
3 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
4 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | Trainer | 2 | q | 0
5 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
6 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
7 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | q | 0
8 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | p | 30
9 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | Customer Service Lead | 8 | p | 24
10 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | Customer Service Team | 8 | p | 70.4
11 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | Customer Service Team | 8 | p | 40
12 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 6 | 4.2.2.2.3 | 4.2.2.2.3 |  | 2 | 1.88 | Path 02 | AI Token Time | O |  | 1
13 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 6 | 4.2.2.2.3 | 4.2.2.2.3 |  | 2 | 1.88 | Path 02 | Cleaning | O |  | 0.15
14 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 6 | 4.2.2.2.3 | 4.2.2.2.3 |  | 2 | 1.88 | Path 02 | Customer Service Team | O |  | 30
15 | 385 | Determine success metrics | Normal | 12 | 5.2 | 5.2 |  | 2 | 0 |  | AI Token Time | O |  | 1
16 | 385 | Determine success metrics | Normal | 12 | 5.2 | 5.2 |  | 2 | 0 |  | Cleaning | O |  | 2.5
17 | 385 | Determine success metrics | Normal | 12 | 5.2 | 5.2 |  | 2 | 0 |  | Logistics | O |  | 17.6

## Calendars
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars
Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 |  |  | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar
Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 |  |  | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 24 Hours
Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 |  |  | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: 16 Hour Work Days
Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 |  |  | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Standard+Sat.
Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 |  |  | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ASIT_REFERENCE
Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 |  |  | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: SSI 24 Hour
Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 | Hard_File_updated2 |  |  | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00

## Calendar Exceptions
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Calendar: Standard
Hard_File_updated2 | Hard_File_updated3
Calendar: Used for Microsoft Project 98 Baseline Calendar
Hard_File_updated2 | Hard_File_updated3
Calendar: 24 Hours
Hard_File_updated2 | Hard_File_updated3
Calendar: 16 Hour Work Days
Hard_File_updated2 | Hard_File_updated3
2011-05-30 | 2011-05-30
2012-05-28 | 2012-05-28
2013-05-27 | 2013-05-27
2014-05-26 | 2014-05-26
2015-05-25 | 2015-05-25
2016-05-30 | 2016-05-30
2017-05-29 | 2017-05-29
2018-05-28 | 2018-05-28
2019-05-27 | 2019-05-27
2011-07-04 | 2011-07-04
2012-07-04 | 2012-07-04
2013-07-04 | 2013-07-04
2014-07-04 | 2014-07-04
2015-07-04 | 2015-07-04
2016-07-04 | 2016-07-04
2017-07-04 | 2017-07-04
2018-07-04 | 2018-07-04
2019-07-04 | 2019-07-04
2011-09-05 | 2011-09-05
2012-09-03 | 2012-09-03
2013-09-02 | 2013-09-02
2014-09-01 | 2014-09-01
2015-09-07 | 2015-09-07
2016-09-05 | 2016-09-05
2017-09-04 | 2017-09-04
2018-09-03 | 2018-09-03
2019-09-02 | 2019-09-02
2011-11-24 | 2011-11-24
2012-11-22 | 2012-11-22
2013-11-21 | 2013-11-21
2014-11-27 | 2014-11-27
2015-11-26 | 2015-11-26
2016-11-24 | 2016-11-24
2017-11-23 | 2017-11-23
2018-11-22 | 2018-11-22
2011-12-25 | 2011-12-25
2012-12-25 | 2012-12-25
2013-12-25 | 2013-12-25
2014-12-25 | 2014-12-25
2015-12-25 | 2015-12-25
2016-12-25 | 2016-12-25
2017-12-25 | 2017-12-25
2018-12-25 | 2018-12-25
2019-12-25 | 2019-12-25
2020-12-25 | 2020-12-25
2021-12-25 | 2021-12-25
2022-12-25 | 2022-12-25
2023-12-25 | 2023-12-25
2024-12-25 | 2024-12-25
2025-12-25 | 2025-12-25
2015-11-27 | 2015-11-27
2016-11-25 | 2016-11-25
2017-11-24 | 2017-11-24
2018-11-23 | 2018-11-23
2019-11-22 | 2019-11-22
2017-01-01 | 2017-01-01
2018-01-01 | 2018-01-01
2018-03-30 | 2018-03-30
2018-08-26 | 2018-08-26
2018-12-24 | 2018-12-24
2018-12-31 | 2018-12-31
2019-01-01 | 2019-01-01
2019-11-29 | 2019-11-29
2019-12-24 | 2019-12-24
2020-01-01 | 2020-01-01
2020-01-20 | 2020-01-20
2020-05-25 | 2020-05-25
2020-07-06 | 2020-07-06
2020-09-07 | 2020-09-07
2020-11-26 | 2020-11-26
2021-01-18 | 2021-01-18
2021-05-31 | 2021-05-31
2021-07-05 | 2021-07-05
2021-09-06 | 2021-09-06
2021-11-25 | 2021-11-25
2021-12-24 | 2021-12-24
2021-12-31 | 2021-12-31
2022-01-17 | 2022-01-17
2022-05-30 | 2022-05-30
2022-07-04 | 2022-07-04
2022-09-05 | 2022-09-05
2022-11-24 | 2022-11-24
2022-12-26 | 2022-12-26
2023-01-02 | 2023-01-02
2023-01-16 | 2023-01-16
2023-05-29 | 2023-05-29
2023-07-04 | 2023-07-04
2023-09-04 | 2023-09-04
2023-11-23 | 2023-11-23
2024-01-01 | 2024-01-01
2024-01-15 | 2024-01-15
2024-05-27 | 2024-05-27
2024-07-04 | 2024-07-04
2024-09-02 | 2024-09-02
2024-11-28 | 2024-11-28
2025-01-01 | 2025-01-01
2025-01-20 | 2025-01-20
Calendar: Standard+Sat.
Hard_File_updated2 | Hard_File_updated3
Calendar: ASIT_REFERENCE
Hard_File_updated2 | Hard_File_updated3
Calendar: SSI 24 Hour
Hard_File_updated2 | Hard_File_updated3

## ID
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Description
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Activity-Type
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Baseline-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Original-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%) | Original Duration - 24 (17%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 37 | Post Launch | Summary | 7 | 8 | 8 |  | 0 | 0 |  | 7 | q | -1 | (-14%) | 6
2 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 4 | q | -1 | (-25%) | 3
3 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 32 | p | 23 | -72% | 55
4 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 31 | p | 23 | -74% | 54
5 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 26 | p | 24 | -92% | 50
6 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 19 | p | 26 | -137% | 45
7 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 6 | p | 22 | -367% | 28
8 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 12 | q | -3 | (-25%) | 9
9 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 10 | q | -3 | (-30%) | 7
10 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 5 | q | -3 | (-60%) | 2
11 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 1 | p | 5 | -500% | 6
12 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 3 | p | 2 | -67% | 5
13 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 1 | p | 2 | -200% | 3
14 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 13 | p | 38 | -292% | 51
15 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 13 | p | 38 | -292% | 51
16 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 13 | p | 38 | -292% | 51
17 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 1 | q | -1 | (-100%) | 0
18 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 60 | p | 26 | -43% | 86
19 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 3 | q | -1 | (-33%) | 2
20 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 11 | p | 60 | -545% | 71
21 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2 | p | 17 | -850% | 19
22 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 1 | p | 11 | -1100% | 12
23 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 1 | p | 4 | -400% | 5
24 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 47 | q | -13 | (-28%) | 34

## Actual-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%) | Actual Duration - 19 (13%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 13 | p | 20 | -154% | 33
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 12 | p | 21 | -175% | 33
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 8 | p | 19 | -238% | 27
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 0 | p | 22 |  | 22
5 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 0 | p | 5 |  | 5
6 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
7 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 0 | p | 9 |  | 9
8 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 0 | p | 7 |  | 7
9 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 5 | q | -3 | (-60%) | 2
10 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
11 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
12 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
13 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
14 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
15 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 10 | p | 29 | -290% | 39
16 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 10 | p | 29 | -290% | 39
17 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 11 | p | 34 | -309% | 45
18 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 19 | p | 9 | -47% | 28
19 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 8 | p | 44 | -550% | 52

## Remaining-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%) | Remaining Duration - 29 (21%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 37 | Post Launch | Summary | 7 | 8 | 8 |  | 0 | 0 |  | 7 | q | -1 | (-14%) | 6
2 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 4 | q | -1 | (-25%) | 3
3 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 19 | p | 3 | -16% | 22
4 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 19 | p | 2 | -11% | 21
5 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 19 | p | 4 | -21% | 23
6 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 19 | p | 4 | -21% | 23
7 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 6 | p | 18 | -300% | 24
8 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
9 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 12 | q | -12 | (-100%) | 0
10 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 10 | q | -10 | (-100%) | 0
11 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
12 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
13 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
14 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
15 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 1 | q | -1 | (-100%) | 0
16 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 1 | p | 5 | -500% | 6
17 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 3 | p | 2 | -67% | 5
18 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 1 | p | 2 | -200% | 3
19 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 3 | p | 9 | -300% | 12
20 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 3 | p | 9 | -300% | 12
21 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 2 | p | 4 | -200% | 6
22 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 1 | q | -1 | (-100%) | 0
23 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 41 | p | 17 | -41% | 58
24 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 3 | q | -1 | (-33%) | 2
25 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 3 | p | 16 | -533% | 19
26 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2 | p | 17 | -850% | 19
27 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 1 | p | 11 | -1100% | 12
28 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 1 | p | 4 | -400% | 5
29 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 47 | q | -13 | (-28%) | 34

## Total-Float
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%) | Total Float - 102 (72%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 37 | Post Launch | Summary | 7 | 8 | 8 |  | 0 | 0 |  | -1 | q | -26 | -2600% | -27
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 3 | 8.1 | 8.1 |  | 0 | 0 |  | -1 | q | -26 | -2600% | -27
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | -3 | q | -36 | -1200% | -39
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | -1 | q | -26 | -2600% | -27
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | -1 | q | -26 | -2600% | -27
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | -1 | q | -26 | -2600% | -27
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | -1 | q | -26 | -2600% | -27
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | -1 | q | -26 | -2600% | -27
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | -1 | q | -26 | -2600% | -27
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | -1 | q | -26 | -2600% | -27
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | -1 | q | -36 | -3600% | -37
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | -1 | q | -25 | -2500% | -26
15 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | -1 | q | -25 | -2500% | -26
16 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 26 | p | 2 | -8% | 28
17 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | -2 | q | -14 | -700% | -16
18 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | -2 | q | -14 | -700% | -16
19 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | -2 | q | -14 | -700% | -16
20 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | -2 | q | -14 | -700% | -16
21 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
22 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | -2 | q | -14 | -700% | -16
23 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
24 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
25 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
26 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | -2 | p | 2 | (-100%) | 0
27 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | -2 | p | 2 | (-100%) | 0
28 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
29 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
30 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
31 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
32 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
33 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
34 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | -2 | p | 2 | (-100%) | 0
35 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
36 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
37 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
38 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | -2 | q | -16 | -800% | -18
39 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
40 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
41 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | -2 | q | -16 | -800% | -18
42 | 318 | Technology Infrastructure | Summary | 2 | 4.3 | 4.3 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
43 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
44 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
45 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
46 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 56 | q | -14 | (-25%) | 42
47 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 12 | p | 30 | -250% | 42
48 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 12 | p | 30 | -250% | 42
49 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 12 | p | 30 | -250% | 42
50 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 12 | p | 30 | -250% | 42
51 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 12 | p | 30 | -250% | 42
52 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 12 | p | 30 | -250% | 42
53 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 12 | p | 30 | -250% | 42
54 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 12 | p | 30 | -250% | 42
55 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 12 | p | 30 | -250% | 42
56 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 12 | p | 31 | -258% | 43
57 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 13 | q | -1 | (-8%) | 12
58 | 372 | Build Technology Infrastructure | Summary | 2 | 6.2 | 6.2 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
59 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
60 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
61 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 54 | q | -14 | (-26%) | 40
62 | 375 | Training/Readiness Development | Summary | 13 | 6.1 | 6.1 |  | 0 | 0 |  | -2 | q | -23 | -1150% | -25
63 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | -1 | q | -26 | -2600% | -27
64 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
65 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | -1 | q | -26 | -2600% | -27
66 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | -2 | q | -25 | -1250% | -27
67 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
68 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
69 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
70 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | -2 | q | -24 | -1200% | -26
71 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
72 | 219 | Training Content Development | Summary | 5 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | -2 | q | -23 | -1150% | -25
73 | 221 | Build Training Content | Summary | 2 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | -2 | q | -23 | -1150% | -25
74 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
75 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
76 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | -1 | q | -24 | -2400% | -25
77 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
78 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
79 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
80 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
81 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
82 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | -2 | q | -23 | -1150% | -25
83 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | -1 | q | -24 | -2400% | -25
84 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 13 | q | -1 | (-8%) | 12
85 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 62 | q | -35 | (-56%) | 27
86 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 62 | q | -35 | (-56%) | 27
87 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 62 | q | -35 | (-56%) | 27
88 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 62 | q | -35 | (-56%) | 27
89 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 26 | q | -52 | (-200%) | -26
90 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 26 | q | -52 | (-200%) | -26
91 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 26 | q | -52 | (-200%) | -26
92 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 26 | q | -52 | (-200%) | -26
93 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 26 | q | -51 | (-196%) | -25
94 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 7 | q | -6 | (-86%) | 1
95 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | -1 | q | -26 | -2600% | -27
96 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
97 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
98 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
99 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 8 | q | -1 | (-12%) | 7
100 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
101 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27
102 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | -1 | q | -26 | -2600% | -27

## Free-Float
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%) | Free Float - 21 (15%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 26 | p | 2 | -8% | 28
2 | 318 | Technology Infrastructure | Summary | 2 | 4.3 | 4.3 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
3 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 56 | q | -14 | (-25%) | 42
4 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 12 | p | 30 | -250% | 42
5 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 12 | p | 30 | -250% | 42
6 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 12 | p | 30 | -250% | 42
7 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 12 | p | 30 | -250% | 42
8 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 12 | p | 30 | -250% | 42
9 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 1 | q | -1 | (-100%) | 0
10 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 1 | q | -1 | (-100%) | 0
11 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 13 | q | -1 | (-8%) | 12
12 | 372 | Build Technology Infrastructure | Summary | 2 | 6.2 | 6.2 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5
13 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 54 | q | -14 | (-26%) | 40
14 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 13 | q | -1 | (-8%) | 12
15 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 62 | q | -35 | (-56%) | 27
16 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 62 | q | -35 | (-56%) | 27
17 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 26 | q | -26 | (-100%) | 0
18 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 26 | q | -26 | (-100%) | 0
19 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 7 | q | -6 | (-86%) | 1
20 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 8 | q | -1 | (-12%) | 7
21 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 44 | q | -39 | (-89%) | 5

## Calendar
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%) | Start - 91 (65%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 37 | Post Launch | Summary | 7 | 8 | 8 |  | 0 | 0 |  | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 3 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-29 08:00 | p | 36 |  | 2026-12-04 08:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-29 17:00 | p | 36 |  | 2026-12-04 17:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-11-02 08:00 | p | 36 |  | 2026-12-08 08:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-11-03 08:00 | p | 36 |  | 2026-12-09 08:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-03 17:00 | p | 36 |  | 2026-12-09 17:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-04 08:00 | p | 36 |  | 2026-12-10 08:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-04 17:00 | p | 36 |  | 2026-12-10 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
15 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
16 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-18 08:00 | p | 7 |  | 2026-09-25 08:00
17 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-18 08:00 | p | 7 |  | 2026-09-25 08:00
18 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-22 17:00 | p | 40 |  | 2026-11-02 13:00
19 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-24 16:12 | p | 18 |  | 2026-10-13 08:00
20 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-21 08:00 | p | 22 |  | 2026-10-13 08:00
21 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-22 08:00 | p | 22 |  | 2026-10-14 08:00
22 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-11 08:00 | q | -3 |  | 2026-09-08 08:00
23 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:00 | q | -5 |  | 2026-09-11 08:00
24 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-17 08:00 | q | -3 |  | 2026-09-14 08:00
25 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-14 08:00 | q | -5 |  | 2026-09-09 08:00
26 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-15 08:00 | q | -5 |  | 2026-09-10 08:00
27 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
28 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
29 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-25 16:12 | p | 18 |  | 2026-10-13 17:00
30 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 12:00
31 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
32 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 13:00
33 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-29 16:12 | p | 22 |  | 2026-10-22 13:00
34 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 13:00
35 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-30 16:12 | p | 26 |  | 2026-10-27 13:00
36 | 318 | Technology Infrastructure | Summary | 2 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-19 08:00 | p | 55 |  | 2026-10-13 08:00
37 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-20 08:00 | p | 55 |  | 2026-10-14 08:00
38 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-19 08:00 | p | 55 |  | 2026-10-13 08:00
39 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
40 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
41 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-21 08:00 | p | 53 |  | 2026-10-13 17:00
42 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
43 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-19 17:00 | p | 54 |  | 2026-10-12 17:00
44 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-20 08:00 | p | 53 |  | 2026-10-12 17:00
45 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-19 17:00 | p | 54 |  | 2026-10-12 17:00
46 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-19 17:00 | p | 54 |  | 2026-10-12 17:00
47 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
48 | 372 | Build Technology Infrastructure | Summary | 2 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-21 08:00 | p | 55 |  | 2026-10-15 08:00
49 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-21 08:00 | p | 55 |  | 2026-10-15 08:00
50 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 55 |  | 2026-10-15 17:00
51 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
52 | 375 | Training/Readiness Development | Summary | 13 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 38 |  | 2026-11-09 08:00
53 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
54 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
55 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-12 08:00 | p | 37 |  | 2026-11-18 08:00
56 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-09 16:12 | p | 38 |  | 2026-11-16 17:00
57 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-12 22:15 | p | 36 |  | 2026-11-18 17:00
58 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-14 08:00 | p | 36 |  | 2026-11-19 08:00
59 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-19 08:00 | p | 36 |  | 2026-11-24 08:00
60 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
61 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-20 08:00 | p | 36 |  | 2026-11-25 08:00
62 | 219 | Training Content Development | Summary | 5 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 38 |  | 2026-11-09 08:00
63 | 221 | Build Training Content | Summary | 2 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-06 16:12 | p | 36 |  | 2026-11-11 17:00
64 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-08 00:12 | p | 36 |  | 2026-11-13 01:00
65 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-07 08:12 | p | 36 |  | 2026-11-12 09:00
66 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-08 08:12 | p | 36 |  | 2026-11-13 09:00
67 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-06 16:12 | p | 36 |  | 2026-11-11 17:00
68 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-07 00:12 | p | 36 |  | 2026-11-12 01:00
69 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:12 | p | 36 |  | 2026-11-12 17:00
70 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-02 16:12 | p | 38 |  | 2026-11-10 08:00
71 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 38 |  | 2026-11-09 08:00
72 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-05 16:12 | p | 36 |  | 2026-11-11 08:00
73 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
74 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
75 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-06 17:00 | p | 67 |  | 2026-10-12 17:00
76 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-08-07 08:00 | p | 73 |  | 2026-10-19 15:00
77 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
78 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2026-08-20 13:00 | p | 53 |  | 2026-10-13 08:00
79 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-20 13:00 | p | 53 |  | 2026-10-13 08:00
80 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-24 06:00 | p | 50 |  | 2026-10-13 17:00
81 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-24 15:00 | p | 71 |  | 2026-11-04 14:24
82 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
83 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 2026-08-25 08:00 | p | 55 |  | 2026-10-19 08:00
84 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-21 08:00 | p | 36 |  | 2026-11-26 08:00
85 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-22 08:00 | p | 36 |  | 2026-11-27 08:00
86 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-21 08:00 | p | 36 |  | 2026-11-26 08:00
87 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-23 08:00 | p | 38 |  | 2026-11-30 08:00
88 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
89 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-25 08:00 | p | 55 |  | 2026-10-19 08:00
90 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-28 08:00 | p | 36 |  | 2026-12-03 08:00
91 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00

## Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%) | Finish - 103 (73%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 37 | Post Launch | Summary | 7 | 8 | 8 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 3 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-29 17:00 | p | 36 |  | 2026-12-04 17:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-29 08:00 | p | 36 |  | 2026-12-04 08:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-11-02 08:00 | p | 36 |  | 2026-12-08 08:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-11-03 17:00 | p | 36 |  | 2026-12-09 17:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-11-03 08:00 | p | 36 |  | 2026-12-09 08:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-04 08:00 | p | 36 |  | 2026-12-10 08:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-04 17:00 | p | 36 |  | 2026-12-10 17:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
15 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
16 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 2026-10-01 16:12 | p | 33 |  | 2026-11-04 11:12
17 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 2026-10-01 16:12 | p | 33 |  | 2026-11-04 11:12
18 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 33 |  | 2026-11-04 11:12
19 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-09-28 16:12 | p | 36 |  | 2026-11-04 11:12
20 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-25 16:12 | p | 39 |  | 2026-11-04 11:12
21 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-18 17:00 | p | 7 |  | 2026-09-25 17:00
22 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-24 16:12 | p | 40 |  | 2026-11-04 11:12
23 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-25 16:12 | p | 18 |  | 2026-10-13 17:00
24 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-21 17:00 | p | 22 |  | 2026-10-13 17:00
25 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-22 17:00 | p | 22 |  | 2026-10-14 17:00
26 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
27 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
28 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | q | -3 |  | 2026-09-07 17:00
29 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | q | -3 |  | 2026-09-08 17:00
30 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-16 17:00 | q | -5 |  | 2026-09-11 17:00
31 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
32 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-14 17:00 | q | -5 |  | 2026-09-09 17:00
33 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-15 17:00 | q | -5 |  | 2026-09-10 17:00
34 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
35 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
36 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 12:00
37 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 12:00
38 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
39 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
40 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-30 16:12 | p | 26 |  | 2026-10-27 12:00
41 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-29 16:12 | p | 22 |  | 2026-10-22 12:00
42 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
43 | 318 | Technology Infrastructure | Summary | 2 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
44 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
45 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-19 17:00 | p | 55 |  | 2026-10-13 17:00
46 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
47 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
48 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
49 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
50 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
51 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
52 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-21 08:00 | p | 53 |  | 2026-10-13 17:00
53 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
54 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
55 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-20 08:00 | p | 54 |  | 2026-10-13 08:00
56 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-20 08:00 | p | 54 |  | 2026-10-13 08:00
57 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
58 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
59 | 372 | Build Technology Infrastructure | Summary | 2 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
60 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 55 |  | 2026-10-15 17:00
61 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
62 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
63 | 375 | Training/Readiness Development | Summary | 13 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
64 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
65 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
66 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-12 17:00 | p | 37 |  | 2026-11-18 17:00
67 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-11 00:12 | p | 38 |  | 2026-11-18 01:00
68 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-14 00:15 | p | 36 |  | 2026-11-19 01:00
69 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-16 17:00 | p | 38 |  | 2026-11-23 17:00
70 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-19 17:00 | p | 36 |  | 2026-11-24 17:00
71 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-09 16:12 | p | 38 |  | 2026-11-16 17:00
72 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
73 | 219 | Training Content Development | Summary | 5 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
74 | 221 | Build Training Content | Summary | 2 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
75 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-08 08:12 | p | 36 |  | 2026-11-13 09:00
76 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:12 | p | 36 |  | 2026-11-12 17:00
77 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
78 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-07 00:12 | p | 36 |  | 2026-11-12 01:00
79 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-07 08:12 | p | 36 |  | 2026-11-12 09:00
80 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-08 00:12 | p | 36 |  | 2026-11-13 01:00
81 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-05 16:12 | p | 36 |  | 2026-11-10 17:00
82 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-10-02 16:12 | p | 38 |  | 2026-11-09 17:00
83 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-06 16:12 | p | 36 |  | 2026-11-11 17:00
84 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
85 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
86 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
87 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-07 08:00 | p | 67 |  | 2026-10-13 08:00
88 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
89 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
90 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
91 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 53 |  | 2026-10-13 17:00
92 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-24 15:00 | p | 71 |  | 2026-11-04 14:24
93 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
94 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
95 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
96 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
97 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-22 17:00 | p | 36 |  | 2026-11-27 17:00
98 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-21 17:00 | p | 36 |  | 2026-11-26 17:00
99 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
100 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
101 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-25 17:00 | p | 55 |  | 2026-10-19 17:00
102 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
103 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00

## Actual-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%) | Actual Start - 12 (9%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-09-02 08:00
2 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-09-25 08:00
3 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-25 08:00
4 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-09-02 08:00
5 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | O | p |  |  | 2026-09-04 08:00
6 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-08 08:00
7 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-11 08:00
8 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 08:00
9 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-09 08:00
10 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-10 08:00
11 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00
12 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00

## Actual-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%) | Actual Finish - 11 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-25 17:00
2 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-09-14 17:00
3 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | O | p |  |  | 2026-09-14 17:00
4 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | q | -3 |  | 2026-09-07 17:00
5 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-08 17:00
6 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-11 17:00
7 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00
8 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-09 17:00
9 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-10 17:00
10 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00
11 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00

## Baseline-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Baseline-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%) | Baseline Finish - 2 (1%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-04 17:00 | p | 3 |  | 2026-09-07 17:00
2 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-07 17:00 | p | 1 |  | 2026-09-08 17:00

## Early-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%) | Early Start - 91 (65%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 37 | Post Launch | Summary | 7 | 8 | 8 |  | 0 | 0 |  | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 3 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-29 08:00 | p | 36 |  | 2026-12-04 08:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-10-29 17:00 | p | 36 |  | 2026-12-04 17:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-11-02 08:00 | p | 36 |  | 2026-12-08 08:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-11-03 08:00 | p | 36 |  | 2026-12-09 08:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-03 17:00 | p | 36 |  | 2026-12-09 17:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-04 08:00 | p | 36 |  | 2026-12-10 08:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-04 17:00 | p | 36 |  | 2026-12-10 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
15 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
16 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-18 08:00 | p | 7 |  | 2026-09-25 08:00
17 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-18 08:00 | p | 7 |  | 2026-09-25 08:00
18 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-22 17:00 | p | 40 |  | 2026-11-02 13:00
19 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-24 16:12 | p | 18 |  | 2026-10-13 08:00
20 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-21 08:00 | p | 22 |  | 2026-10-13 08:00
21 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-22 08:00 | p | 22 |  | 2026-10-14 08:00
22 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-11 08:00 | q | -3 |  | 2026-09-08 08:00
23 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:00 | q | -5 |  | 2026-09-11 08:00
24 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-17 08:00 | q | -3 |  | 2026-09-14 08:00
25 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-14 08:00 | q | -5 |  | 2026-09-09 08:00
26 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-15 08:00 | q | -5 |  | 2026-09-10 08:00
27 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
28 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
29 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-25 16:12 | p | 18 |  | 2026-10-13 17:00
30 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 12:00
31 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
32 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 13:00
33 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-29 16:12 | p | 22 |  | 2026-10-22 13:00
34 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 13:00
35 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-30 16:12 | p | 26 |  | 2026-10-27 13:00
36 | 318 | Technology Infrastructure | Summary | 2 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-19 08:00 | p | 55 |  | 2026-10-13 08:00
37 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-20 08:00 | p | 55 |  | 2026-10-14 08:00
38 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-19 08:00 | p | 55 |  | 2026-10-13 08:00
39 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
40 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
41 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-21 08:00 | p | 53 |  | 2026-10-13 17:00
42 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
43 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-19 17:00 | p | 54 |  | 2026-10-12 17:00
44 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-20 08:00 | p | 53 |  | 2026-10-12 17:00
45 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-19 17:00 | p | 54 |  | 2026-10-12 17:00
46 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-19 17:00 | p | 54 |  | 2026-10-12 17:00
47 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
48 | 372 | Build Technology Infrastructure | Summary | 2 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-21 08:00 | p | 55 |  | 2026-10-15 08:00
49 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-21 08:00 | p | 55 |  | 2026-10-15 08:00
50 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 55 |  | 2026-10-15 17:00
51 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
52 | 375 | Training/Readiness Development | Summary | 13 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 38 |  | 2026-11-09 08:00
53 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
54 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
55 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-12 08:00 | p | 37 |  | 2026-11-18 08:00
56 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-09 16:12 | p | 38 |  | 2026-11-16 17:00
57 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-12 22:15 | p | 36 |  | 2026-11-18 17:00
58 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-14 08:00 | p | 36 |  | 2026-11-19 08:00
59 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-19 08:00 | p | 36 |  | 2026-11-24 08:00
60 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
61 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-20 08:00 | p | 36 |  | 2026-11-25 08:00
62 | 219 | Training Content Development | Summary | 5 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 38 |  | 2026-11-09 08:00
63 | 221 | Build Training Content | Summary | 2 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-06 16:12 | p | 36 |  | 2026-11-11 17:00
64 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-08 00:12 | p | 36 |  | 2026-11-13 01:00
65 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-07 08:12 | p | 36 |  | 2026-11-12 09:00
66 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-08 08:12 | p | 36 |  | 2026-11-13 09:00
67 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-06 16:12 | p | 36 |  | 2026-11-11 17:00
68 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-07 00:12 | p | 36 |  | 2026-11-12 01:00
69 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:12 | p | 36 |  | 2026-11-12 17:00
70 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-02 16:12 | p | 38 |  | 2026-11-10 08:00
71 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 38 |  | 2026-11-09 08:00
72 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-05 16:12 | p | 36 |  | 2026-11-11 08:00
73 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
74 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
75 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-06 17:00 | p | 67 |  | 2026-10-12 17:00
76 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-08-07 08:00 | p | 73 |  | 2026-10-19 15:00
77 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
78 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2026-08-20 13:00 | p | 53 |  | 2026-10-13 08:00
79 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-20 13:00 | p | 53 |  | 2026-10-13 08:00
80 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-24 06:00 | p | 50 |  | 2026-10-13 17:00
81 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-24 15:00 | p | 71 |  | 2026-11-04 14:24
82 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
83 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 2026-08-25 08:00 | p | 55 |  | 2026-10-19 08:00
84 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-21 08:00 | p | 36 |  | 2026-11-26 08:00
85 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-22 08:00 | p | 36 |  | 2026-11-27 08:00
86 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-21 08:00 | p | 36 |  | 2026-11-26 08:00
87 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-23 08:00 | p | 38 |  | 2026-11-30 08:00
88 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
89 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-25 08:00 | p | 55 |  | 2026-10-19 08:00
90 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-28 08:00 | p | 36 |  | 2026-12-03 08:00
91 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00

## Early-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%) | Early Finish - 103 (73%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 37 | Post Launch | Summary | 7 | 8 | 8 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
2 | 142 | Engage in Post Launch Preparation Activities | Summary | 3 | 8.1 | 8.1 |  | 0 | 0 |  | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
3 | 7 | Create method for tracking common problems and solutions | Normal | 1 | 8.1.2 | 8.1.2 |  | 0 | 1 | Path 02 | 2026-10-29 17:00 | p | 36 |  | 2026-12-04 17:00
4 | 13 | Determine success metrics | Normal | 1 | 8.1.1 | 8.1.1 |  | 0 | 1 | Path 02 | 2026-10-29 08:00 | p | 36 |  | 2026-12-04 08:00
5 | 14 | Create method to track support issues vs. product aspects | Normal | 1 | 8.1.3 | 8.1.3 |  | 0 | 0.63 | Path 02 | 2026-11-02 08:00 | p | 36 |  | 2026-12-08 08:00
6 | 141 | Create method for distributing common solutions to all support resources | Normal | 1 | 8.1.4 | 8.1.4 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
7 | 156 | Post Launch Preparation COMPLETE | Milestone | 0 | 8.1.5 | 8.1.5 |  | 0 | 0 | Path 01 | 2026-11-02 17:00 | p | 36 |  | 2026-12-08 17:00
8 | 143 | Monitoring | Summary | 4 | 8.2 | 8.2 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
9 | 9 | Aggregate best practices (solutions) - distribute to support services | Normal | 1 | 8.2.2 | 8.2.2 |  | 0 | 0 | Path 01 | 2026-11-03 17:00 | p | 36 |  | 2026-12-09 17:00
10 | 36 | Monitor customer support issues - look for common problems | Normal | 1 | 8.2.1 | 8.2.1 |  | 0 | 0 | Path 01 | 2026-11-03 08:00 | p | 36 |  | 2026-12-09 08:00
11 | 144 | Review support data, determine which product aspects cause the most support incidents | Normal | 1 | 8.2.3 | 8.2.3 |  | 0 | 0 | Path 01 | 2026-11-04 08:00 | p | 36 |  | 2026-12-10 08:00
12 | 145 | Review resource performance, determine which ones are the most effective | Normal | 1 | 8.2.4 | 8.2.4 |  | 0 | 0 | Path 01 | 2026-11-04 17:00 | p | 36 |  | 2026-12-10 17:00
13 | 146 | Revise training materials based on data collected from customer service program | Normal | 2 | 8.2.5 | 8.2.5 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
14 | 411 | Post Launch Activities COMPLETE | Milestone | 0 | 8.3 | 8.3 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
15 | 155 | Customer Service Program Development COMPLETE | Milestone | 0 | 9 | 9 |  | 0 | 0 | Path 01 | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
16 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 2026-10-01 16:12 | p | 33 |  | 2026-11-04 11:12
17 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 2026-10-01 16:12 | p | 33 |  | 2026-11-04 11:12
18 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 33 |  | 2026-11-04 11:12
19 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-09-28 16:12 | p | 36 |  | 2026-11-04 11:12
20 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-25 16:12 | p | 39 |  | 2026-11-04 11:12
21 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-18 17:00 | p | 7 |  | 2026-09-25 17:00
22 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-24 16:12 | p | 40 |  | 2026-11-04 11:12
23 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-25 16:12 | p | 18 |  | 2026-10-13 17:00
24 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-21 17:00 | p | 22 |  | 2026-10-13 17:00
25 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-22 17:00 | p | 22 |  | 2026-10-14 17:00
26 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
27 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
28 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | q | -3 |  | 2026-09-07 17:00
29 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-11 17:00 | q | -3 |  | 2026-09-08 17:00
30 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-16 17:00 | q | -5 |  | 2026-09-11 17:00
31 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
32 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-14 17:00 | q | -5 |  | 2026-09-09 17:00
33 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-15 17:00 | q | -5 |  | 2026-09-10 17:00
34 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
35 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-17 17:00 | q | -3 |  | 2026-09-14 17:00
36 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 12:00
37 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-28 16:12 | p | 22 |  | 2026-10-21 12:00
38 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
39 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
40 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-30 16:12 | p | 26 |  | 2026-10-27 12:00
41 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-29 16:12 | p | 22 |  | 2026-10-22 12:00
42 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-10-01 16:12 | p | 26 |  | 2026-10-28 12:00
43 | 318 | Technology Infrastructure | Summary | 2 | 4.3 | 4.3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
44 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
45 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | 2026-08-19 17:00 | p | 55 |  | 2026-10-13 17:00
46 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
47 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 55 |  | 2026-10-14 17:00
48 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
49 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
50 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
51 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-08-22 05:49 | p | 53 |  | 2026-10-14 14:06
52 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-08-21 08:00 | p | 53 |  | 2026-10-13 17:00
53 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
54 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
55 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-08-20 08:00 | p | 54 |  | 2026-10-13 08:00
56 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-08-20 08:00 | p | 54 |  | 2026-10-13 08:00
57 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-08-20 17:00 | p | 53 |  | 2026-10-13 08:00
58 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
59 | 372 | Build Technology Infrastructure | Summary | 2 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
60 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | 2026-08-21 17:00 | p | 55 |  | 2026-10-15 17:00
61 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
62 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-08-24 17:00 | p | 53 |  | 2026-10-16 17:00
63 | 375 | Training/Readiness Development | Summary | 13 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
64 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
65 | 150 | Training Delivery Engine Development COMPLETE | Milestone | 0 | 6.1.2.8 | 6.1.2.8 |  | 0 | 1 | Path 02 | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
66 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-12 17:00 | p | 37 |  | 2026-11-18 17:00
67 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-11 00:12 | p | 38 |  | 2026-11-18 01:00
68 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-14 00:15 | p | 36 |  | 2026-11-19 01:00
69 | 270 | Create communications plan | Normal | 3 | 6.1.2.5 | 6.1.2.5 |  | 0 | 1 | Path 02 | 2026-10-16 17:00 | p | 38 |  | 2026-11-23 17:00
70 | 272 | Provide new hires with information on training program | Normal | 1 | 6.1.2.6 | 6.1.2.6 |  | 0 | 1 | Path 02 | 2026-10-19 17:00 | p | 36 |  | 2026-11-24 17:00
71 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-09 16:12 | p | 38 |  | 2026-11-16 17:00
72 | 310 | Send out communication to existing support resources regarding new training plan | Normal | 1 | 6.1.2.7 | 6.1.2.7 |  | 0 | 1 | Path 02 | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
73 | 219 | Training Content Development | Summary | 5 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
74 | 221 | Build Training Content | Summary | 2 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
75 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-08 08:12 | p | 36 |  | 2026-11-13 09:00
76 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:12 | p | 36 |  | 2026-11-12 17:00
77 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
78 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-07 00:12 | p | 36 |  | 2026-11-12 01:00
79 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-07 08:12 | p | 36 |  | 2026-11-12 09:00
80 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-08 00:12 | p | 36 |  | 2026-11-13 01:00
81 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-05 16:12 | p | 36 |  | 2026-11-10 17:00
82 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-10-02 16:12 | p | 38 |  | 2026-11-09 17:00
83 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-06 16:12 | p | 36 |  | 2026-11-11 17:00
84 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:12 | p | 38 |  | 2026-11-16 09:00
85 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-10-20 17:00 | p | 36 |  | 2026-11-25 17:00
86 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
87 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-08-07 08:00 | p | 67 |  | 2026-10-13 08:00
88 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
89 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-08-12 17:00 | p | 84 |  | 2026-11-05 09:12
90 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
91 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-08-21 12:00 | p | 53 |  | 2026-10-13 17:00
92 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-08-24 15:00 | p | 71 |  | 2026-11-04 14:24
93 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
94 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-08-24 23:00 | p | 73 |  | 2026-11-06 22:24
95 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
96 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
97 | 34 | Train new resources | Normal | 1 | 7.1.2 | 7.1.2 |  | 0 | 1 | Path 02 | 2026-10-22 17:00 | p | 36 |  | 2026-11-27 17:00
98 | 49 | Hire new resources | Normal | 1 | 7.1.1 | 7.1.1 |  | 0 | 1 | Path 02 | 2026-10-21 17:00 | p | 36 |  | 2026-11-26 17:00
99 | 389 | Certify new resources | Normal | 3 | 7.1.3 | 7.1.3 |  | 0 | 1 | Path 02 | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
100 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-10-27 17:00 | p | 36 |  | 2026-12-02 17:00
101 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | 2026-08-25 17:00 | p | 55 |  | 2026-10-19 17:00
102 | 409 | Deploy new customer service programs | Normal | 1 | 7.3 | 7.3 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00
103 | 410 | Program Deployment COMPLETE | Milestone | 0 | 7.4 | 7.4 |  | 0 | 1 | Path 02 | 2026-10-28 17:00 | p | 36 |  | 2026-12-03 17:00

## Late-Start
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%) | Late Start - 60 (43%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-08-31 08:48 | p | 1 |  | 2026-09-02 08:00
2 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-16 08:48 | p | 0 |  | 2026-09-17 08:00
3 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:48 | p | 8 |  | 2026-09-25 08:00
4 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-21 08:48 | p | 18 |  | 2026-10-09 08:48
5 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-23 08:00 | q | -5 |  | 2026-09-17 11:00
6 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-17 08:48 | q | 0 |  | 2026-09-17 08:00
7 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-18 08:48 | q | 0 |  | 2026-09-18 08:00
8 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-08-31 08:48 | p | 1 |  | 2026-09-02 08:00
9 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-09-02 08:48 | p | 1 |  | 2026-09-04 08:00
10 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-09 08:48 | q | -1 |  | 2026-09-08 08:00
11 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-14 08:48 | q | -3 |  | 2026-09-11 08:00
12 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-15 08:48 | q | -1 |  | 2026-09-14 08:00
13 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-10 08:48 | q | -1 |  | 2026-09-09 08:00
14 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-11 08:48 | q | -1 |  | 2026-09-10 08:00
15 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:48 | q | -1 |  | 2026-09-14 17:00
16 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:48 | q | -1 |  | 2026-09-14 17:00
17 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-24 08:00 | q | -5 |  | 2026-09-18 11:00
18 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-25 08:00 | p | 0 |  | 2026-09-25 16:00
19 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
20 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-25 08:00 | p | 0 |  | 2026-09-25 16:00
21 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-28 08:00 | p | 0 |  | 2026-09-28 16:00
22 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-25 08:00 | p | 0 |  | 2026-09-25 16:00
23 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-29 08:00 | p | 2 |  | 2026-10-01 16:00
24 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
25 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-09-08 10:59 | p | 93 |  | 2026-12-11 10:54
26 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-09-07 19:59 | p | 93 |  | 2026-12-10 19:54
27 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-09-07 10:59 | p | 93 |  | 2026-12-10 10:54
28 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-09-07 10:59 | p | 93 |  | 2026-12-10 10:54
29 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-09-07 10:59 | p | 93 |  | 2026-12-10 10:54
30 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-09-07 10:59 | p | 93 |  | 2026-12-10 10:54
31 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-09-07 19:59 | p | 93 |  | 2026-12-10 19:54
32 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
33 | 375 | Training/Readiness Development | Summary | 13 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
34 | 175 | Develop Training Delivery Engine | Summary | 8 | 6.1.2 | 6.1.2 |  | 0 | 0 |  | 2026-10-07 16:00 | p | 3 |  | 2026-10-10 16:00
35 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:00 | p | 3 |  | 2026-10-12 08:00
36 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-08 | p | 3 |  | 2026-10-11
37 | 269 | Prepare training venues | Normal | 1 | 6.1.2.4 | 6.1.2.4 |  | 0 | 1 | Path 02 | 2026-10-12 06:00 | p | 0 |  | 2026-10-13
38 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:00 | p | 3 |  | 2026-10-10 16:00
39 | 219 | Training Content Development | Summary | 5 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
40 | 221 | Build Training Content | Summary | 2 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-05 | p | 2 |  | 2026-10-07 16:00
41 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-06 08:00 | p | 2 |  | 2026-10-09
42 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-05 16:00 | p | 2 |  | 2026-10-08 08:00
43 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-06 16:00 | p | 2 |  | 2026-10-09 08:00
44 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-05 | p | 2 |  | 2026-10-07 16:00
45 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-05 08:00 | p | 2 |  | 2026-10-08
46 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-06 | p | 2 |  | 2026-10-08 16:00
47 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-01 08:00 | p | 4 |  | 2026-10-05 16:00
48 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
49 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-02 08:00 | p | 4 |  | 2026-10-06 16:00
50 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:00 | p | 3 |  | 2026-10-10 16:00
51 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
52 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-11-02 17:00 | p | 15 |  | 2026-11-18 15:48
53 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-11-03 08:00 | p | 22 |  | 2026-11-25 13:48
54 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
55 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2026-09-28 08:00 | q | -20 |  | 2026-09-07 10:36
56 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-09-28 08:00 | q | -20 |  | 2026-09-07 10:36
57 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-09-29 08:00 | q | -20 |  | 2026-09-08 10:36
58 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-09-29 17:00 | p | 0 |  | 2026-09-30 07:00
59 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
60 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00

## Late-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%) | Late Finish - 70 (50%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 2026-09-30 08:00 | p | 13 |  | 2026-10-13 08:00
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 2026-09-30 08:00 | p | 13 |  | 2026-10-13 08:00
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 2026-09-25 08:00 | p | 18 |  | 2026-10-13 08:00
5 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 2026-09-23 17:00 | p | 19 |  | 2026-10-13 08:00
6 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 2026-09-17 08:48 | p | 8 |  | 2026-09-25 17:00
7 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-23 08:00 | p | 20 |  | 2026-10-13 08:00
8 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | 2026-09-23 17:00 | q | -5 |  | 2026-09-18 11:00
9 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | 2026-09-18 08:48 | q | 0 |  | 2026-09-17 17:00
10 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-21 08:48 | q | -2 |  | 2026-09-18 17:00
11 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 2026-09-16 08:48 | q | -1 |  | 2026-09-14 17:00
12 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 2026-09-16 08:48 | q | -1 |  | 2026-09-14 17:00
13 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | q | -3 |  | 2026-09-07 17:00
14 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-10 08:48 | q | -1 |  | 2026-09-08 17:00
15 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 2026-09-15 08:48 | q | -3 |  | 2026-09-11 17:00
16 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:48 | q | -1 |  | 2026-09-14 17:00
17 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-11 08:48 | q | -1 |  | 2026-09-09 17:00
18 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 2026-09-14 08:48 | q | -3 |  | 2026-09-10 17:00
19 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:48 | q | -1 |  | 2026-09-14 17:00
20 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 2026-09-16 08:48 | q | -1 |  | 2026-09-14 17:00
21 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 2026-09-24 17:00 | p | 0 |  | 2026-09-25 16:00
22 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-25 08:00 | p | 0 |  | 2026-09-25 16:00
23 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
24 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 2026-09-29 17:00 | p | 2 |  | 2026-10-02 16:00
25 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 2026-09-28 17:00 | p | 2 |  | 2026-10-01 16:00
26 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-25 17:00 | p | 2 |  | 2026-09-28 16:00
27 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | 2026-09-29 17:00 | p | 2 |  | 2026-10-02 16:00
28 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
29 | 322 | Service Planning | Summary | 3 | 3 | 3 |  | 1 | 0 |  | 2026-09-09 08:48 | p | 94 |  | 2026-12-12 17:00
30 | 125 | Design Support Services | Summary | 3 | 3.1 | 3.1 |  | 1 | 0 |  | 2026-09-09 08:48 | p | 94 |  | 2026-12-12 17:00
31 | 4 | Develop Levels of Customer Service (Free and Paid) | Summary | 2 | 3.1.2 | 3.1.2 |  | 1 | 0 |  | 2026-09-09 08:48 | p | 94 |  | 2026-12-12 17:00
32 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | 2026-09-09 08:48 | p | 94 |  | 2026-12-12 17:00
33 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-09-08 10:59 | p | 93 |  | 2026-12-11 10:54
34 | 45 | Design Customer Service Contact Scenarios | Summary | 1 | 3.1.1 | 3.1.1 |  | 0 | 0 |  | 2026-09-07 19:59 | p | 93 |  | 2026-12-10 19:54
35 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | 2026-09-07 19:59 | p | 93 |  | 2026-12-10 19:54
36 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | 2026-09-07 19:59 | p | 93 |  | 2026-12-10 19:54
37 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | 2026-09-07 19:59 | p | 93 |  | 2026-12-10 19:54
38 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | 2026-09-07 19:59 | p | 93 |  | 2026-12-10 19:54
39 | 373 | Build Customer Service Program | Summary | 41 | 6 | 6 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
40 | 372 | Build Technology Infrastructure | Summary | 2 | 6.2 | 6.2 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
41 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
42 | 375 | Training/Readiness Development | Summary | 13 | 6.1 | 6.1 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
43 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | 2026-10-09 17:00 | p | 3 |  | 2026-10-12 17:00
44 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | 2026-10-09 08:00 | p | 3 |  | 2026-10-12 08:00
45 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | 2026-10-08 | p | 3 |  | 2026-10-11
46 | 219 | Training Content Development | Summary | 5 | 6.1.1 | 6.1.1 |  | 0 | 0 |  | 2026-10-07 16:00 | p | 3 |  | 2026-10-10 16:00
47 | 221 | Build Training Content | Summary | 2 | 6.1.1.4 | 6.1.1.4 |  | 0 | 0 |  | 2026-10-07 16:00 | p | 2 |  | 2026-10-09 17:00
48 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | 2026-10-06 16:00 | p | 2 |  | 2026-10-09 08:00
49 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | 2026-10-06 | p | 2 |  | 2026-10-08 16:00
50 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:00 | p | 2 |  | 2026-10-09 17:00
51 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | 2026-10-05 08:00 | p | 2 |  | 2026-10-08
52 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | 2026-10-05 16:00 | p | 2 |  | 2026-10-08 08:00
53 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | 2026-10-06 08:00 | p | 2 |  | 2026-10-09
54 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | 2026-10-01 17:00 | p | 4 |  | 2026-10-06 16:00
55 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | 2026-09-30 17:00 | p | 4 |  | 2026-10-05 16:00
56 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | 2026-10-02 17:00 | p | 4 |  | 2026-10-07 16:00
57 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | 2026-10-07 16:00 | p | 3 |  | 2026-10-10 16:00
58 | 406 | Training/Readiness Development COMPLETE | Milestone | 0 | 6.1.3 | 6.1.3 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
59 | 392 | Customer Service Program Development | Summary | 3 | 6.3 | 6.3 |  | 1 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
60 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | 2026-11-03 08:00 | p | 15 |  | 2026-11-19 06:48
61 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 35 |  | 2026-12-11 17:00
62 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
63 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
64 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | 2026-09-28 17:00 | q | -20 |  | 2026-09-08 10:36
65 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 2026-09-29 17:00 | p | 0 |  | 2026-09-30 07:00
66 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
67 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | 2026-09-30 08:00 | p | 2 |  | 2026-10-02 16:00
68 | 391 | Program Deployment | Summary | 47 | 7 | 7 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
69 | 393 | Resource Readiness | Summary | 5 | 7.1 | 7.1 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00
70 | 407 | Resource Readiness Training COMPLETE | Milestone | 0 | 7.1.4 | 7.1.4 |  | 0 | 0 |  | 2026-11-06 17:00 | p | 36 |  | 2026-12-12 17:00

## Expected-Finish
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Suspend-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%) | Suspend Date - 14 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 2026-08-19 08:00 | p | 0 |  | 2026-08-19 12:00
2 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-09-02 17:00
3 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-09-25 17:00
4 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-25 17:00
5 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-09-02 17:00
6 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | O | p |  |  | 2026-09-07 17:00
7 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | q | -3 |  | 2026-09-07 17:00
8 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-08 17:00
9 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-11 17:00
10 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00
11 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-09 17:00
12 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-10 17:00
13 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00
14 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00

## Resume-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%) | Resume Date - 14 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 2026-08-19 08:00 | p | 0 |  | 2026-08-19 12:00
2 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-09-02 17:00
3 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-09-25 17:00
4 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-25 17:00
5 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-09-02 17:00
6 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | O | p |  |  | 2026-09-07 17:00
7 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 2026-09-10 17:00 | q | -3 |  | 2026-09-07 17:00
8 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-08 17:00
9 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-11 17:00
10 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00
11 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-09 17:00
12 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-10 17:00
13 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00
14 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-14 17:00

## Activity-Status
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%) | Activity Status - 12 (9%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | Planned |  |  |  | InProgress
2 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | Planned |  |  |  | InProgress
3 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
4 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | Planned |  |  |  | Complete
5 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | Planned |  |  |  | Complete
6 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
7 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
8 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
9 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
10 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
11 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete
12 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | Planned |  |  |  | Complete

## Percent-Complete
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%) | Percent Complete - 15 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 0.4 | p | 0.2 | -50% | 0.6
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 0.4 | p | 0.21 | -52% | 0.61
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 0.29 | p | 0.26 | -90% | 0.55
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 0 | p | 0.48 |  | 0.48
5 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 0 | p | 0.17 |  | 0.17
6 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
7 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 0 | p | 1 |  | 1
8 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 0 | p | 1 |  | 1
9 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
10 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
11 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
12 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
13 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
14 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
15 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1

## Physical---Complete
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%) | Physical % Complete - 8 (6%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
2 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
3 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
4 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
5 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
6 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
7 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1
8 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1 |  | 1

## Critical
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%) | Critical - 18 (13%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
2 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | P |  |  |  | O
3 | 199 | Identify internal resources that can serve as potential trainers | Normal | 0 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
4 | 268 | Determine whether additional trainers will be needed | Normal | 0 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
5 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | P |  |  |  | O
6 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
7 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
8 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
9 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
10 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
11 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
12 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
13 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
14 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | O |  |  |  | P
15 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | O |  |  |  | P
16 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | O |  |  |  | P
17 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | O |  |  |  | P
18 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | O |  |  |  | P

## Longest-Path
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%) | Longest Path - 18 (13%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
2 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | P |  |  |  | O
3 | 199 | Identify internal resources that can serve as potential trainers | Normal | 0 | 4.2.2.2.1.1 | 4.2.2.2.1.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
4 | 268 | Determine whether additional trainers will be needed | Normal | 0 | 4.2.2.2.1.2 | 4.2.2.2.1.2 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
5 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | P |  |  |  | O
6 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
7 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
8 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
9 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
10 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
11 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
12 | 297 | Outsourcing Review COMPLETE | Milestone | 0 | 4.2.2.2.1.3.7 | 4.2.2.2.1.3.7 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
13 | 298 | Trainer Needs Assessment COMPLETE | Milestone | 0 | 4.2.2.2.1.4 | 4.2.2.2.1.4 |  | 0 | 1.88 | Path 02 | P |  |  |  | O
14 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | O |  |  |  | P
15 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | O |  |  |  | P
16 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | O |  |  |  | P
17 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | O |  |  |  | P
18 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | O |  |  |  | P

## Primary-Constraint
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%) | Primary Constraint - 44 (31%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
2 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
3 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
4 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
5 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
6 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
7 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
8 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
9 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
10 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
11 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
12 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
13 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
14 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
15 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
16 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | None |  |  |  | StartOnOrAfter
17 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | None |  |  |  | StartOnOrAfter
18 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | None |  |  |  | StartOnOrAfter
19 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | None |  |  |  | StartOnOrAfter
20 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | None |  |  |  | StartOnOrAfter
21 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
22 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
23 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
24 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
25 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
26 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
27 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
28 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
29 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
30 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
31 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
32 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
33 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
34 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
35 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
36 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | None |  |  |  | StartOnOrAfter
37 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
38 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
39 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
40 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
41 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
42 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
43 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter
44 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | None |  |  |  | StartOnOrAfter

## Secondary-Constraint
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Primary-Constraint-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%) | Primary Constraint Date - 45 (32%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-09-23 08:00
2 | 267 | Develop training delivery budget | Normal | 2 | 4.2.2.2.2.4 | 4.2.2.2.2.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
3 | 278 | Training Delivery Logistics COMPLETE | Normal | 1 | 4.2.2.2.2.5 | 4.2.2.2.2.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
4 | 281 | Determine training delivery locations | Normal | 1 | 4.2.2.2.2.2 | 4.2.2.2.2.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
5 | 289 | Review outsourcing options - event logistics | Normal | 1 | 4.2.2.2.2.3 | 4.2.2.2.2.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
6 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
7 | 305 | Training Delivery Planning Complete | Milestone | 0 | 4.2.2.2.4 | 4.2.2.2.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
8 | 256 | Training Planning COMPLETE | Milestone | 0 | 4.2.2.4 | 4.2.2.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
9 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
10 | 276 | Draft Overall Budget | Normal | 1 | 4.2.2.3.1 | 4.2.2.3.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
11 | 307 | Acquire executive sign-off on training plans | Normal | 1 | 4.2.2.3.3 | 4.2.2.3.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
12 | 321 | Determine technology budget | Normal | 1 | 4.3.2 | 4.3.2 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
13 | 379 | Build technology infrastructure plan (separate project plan required) | Normal | 1 | 4.3.1 | 4.3.1 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
14 | 381 | Technology infrastructure planning COMPLETE | Milestone | 0 | 4.3.3 | 4.3.3 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
15 | 388 | Service Delivery Planning COMPLETE | Milestone | 0 | 4.4 | 4.4 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
16 | 188 | Identify service delivery options | Normal | 1 | 3.1.2.2 | 3.1.2.2 |  | 0 | 12.88 | Path 03 | O | p |  |  | 2026-10-12 17:00
17 | 189 | Identify types of problems to be solved | Normal | 1 | 3.1.2.1 | 3.1.2.1 |  | 0 | 12.88 | Path 03 | 2026-07-31 08:00 | p | 73 |  | 2026-10-12 17:00
18 | 178 | On-site support | Normal | 1 | 3.1.1.3 | 3.1.1.3 |  | 0 | 12.88 | Path 03 | O | p |  |  | 2026-10-12 17:00
19 | 179 | Phone support | Normal | 1 | 3.1.1.2 | 3.1.1.2 |  | 0 | 13.88 | Path 03 | O | p |  |  | 2026-10-12 17:00
20 | 180 | Online support | Normal | 1 | 3.1.1.1 | 3.1.1.1 |  | 0 | 14.88 | Path 03 | O | p |  |  | 2026-10-12 17:00
21 | 181 | Design of customer service contact scenarios COMPLETE | Milestone | 0 | 3.1.1.4 | 3.1.1.4 |  | 0 | 12.88 | Path 03 | O | p |  |  | 2026-10-12 17:00
22 | 396 | Design and develop technology solution (separate schedule required) | Normal | 1 | 6.2.1 | 6.2.1 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
23 | 398 | Test technology infrastructure | Normal | 3 | 6.2.2 | 6.2.2 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
24 | 405 | Technology Infrastructure Development COMPLETE | Milestone | 0 | 6.2.3 | 6.2.3 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
25 | 262 | Train additional trainers | Normal | 1 | 6.1.2.3 | 6.1.2.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
26 | 264 | Create proficiency exams | Normal | 4 | 6.1.2.2 | 6.1.2.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
27 | 274 | Create additional "train the trainer" learning materials | Normal | 1 | 6.1.2.1 | 6.1.2.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
28 | 140 | Create "cheat sheets" and additional learning resources for customer support | Normal | 1 | 6.1.1.4.5 | 6.1.1.4.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
29 | 228 | Perform SME review of training content | Normal | 1 | 6.1.1.4.3 | 6.1.1.4.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
30 | 229 | Acquire final content approval | Normal | 1 | 6.1.1.4.6 | 6.1.1.4.6 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
31 | 244 | Review existing intellectual property | Normal | 1 | 6.1.1.4.1 | 6.1.1.4.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
32 | 257 | Develop beta content | Normal | 1 | 6.1.1.4.2 | 6.1.1.4.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
33 | 258 | Revise and update content | Normal | 1 | 6.1.1.4.4 | 6.1.1.4.4 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
34 | 222 | Define roles and responsibilities | Normal | 1 | 6.1.1.2 | 6.1.1.2 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
35 | 223 | Assemble content development team | Normal | 1 | 6.1.1.1 | 6.1.1.1 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
36 | 253 | Create content development schedule | Normal | 1 | 6.1.1.3 | 6.1.1.3 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
37 | 260 | Content Development COMPLETE | Milestone | 0 | 6.1.1.5 | 6.1.1.5 |  | 0 | 1.88 | Path 02 | O | p |  |  | 2026-10-12 17:00
38 | 402 | Revise programs and related processes | Normal | 1 | 6.3.4 | 6.3.4 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
39 | 403 | Acquire executive sign-off | Normal | 4 | 6.3.5 | 6.3.5 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
40 | 404 | Customer Service Program Development COMPLETE | Milestone | 0 | 6.3.6 | 6.3.6 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
41 | 384 | Determine business objectives of support services | Normal | 1 | 5.1 | 5.1 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
42 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
43 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
44 | 387 | Business Performance Planning COMPLETE | Milestone | 0 | 5.4 | 5.4 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00
45 | 408 | Deploy technology infrastructure | Normal | 1 | 7.2 | 7.2 |  | 0 | 0 |  | O | p |  |  | 2026-10-12 17:00

## Secondary-Constraint-Date
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%) | Secondary Constraint Date - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Baseline-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Actual-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%) | Actual Work - 14 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 162 | p | 97 | -60% | 259
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 150 | p | 97 | -65% | 247
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 64 | p | 97 | -152% | 161
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 0 | p | 97 |  | 97
5 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 0 | p | 8 |  | 8
6 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
7 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 0 | p | 89 |  | 89
8 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 0 | p | 73 |  | 73
9 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 55 | q | -24 | (-44%) | 31
10 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
11 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 0 | p | 10 |  | 10
12 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
13 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8
14 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 0 | p | 8 |  | 8

## Remaining-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%) | Remaining Work - 19 (13%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 205 | q | -53 | (-26%) | 152
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 189 | q | -53 | (-28%) | 136
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 189 | q | -53 | (-28%) | 136
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 165 | q | -69 | (-42%) | 96
5 | 283 | Training Delivery Logistics | Summary | 6 | 4.2.2.2.2 | 4.2.2.2.2 |  | 0 | 0 |  | 44 | q | -8 | (-18%) | 36
6 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
7 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 113 | q | -113 | (-100%) | 0
8 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 97 | q | -97 | (-100%) | 0
9 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
10 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 10 | q | -10 | (-100%) | 0
11 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
12 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
13 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 8 | q | -8 | (-100%) | 0
14 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 8 | p | 52 | -650% | 60
15 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 24 | p | 16 | -67% | 40
16 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 8 | p | 16 | -200% | 24
17 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 24 | p | 112 | -467% | 136
18 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 8 | p | 80 | -1000% | 88
19 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 8 | p | 32 | -400% | 40

## Total-Work
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%) | Total Work - 13 (9%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 367 | p | 44 | -12% | 411
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 339 | p | 44 | -13% | 383
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 253 | p | 44 | -17% | 297
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 165 | p | 28 | -17% | 193
5 | 293 | Assess Trainer Needs & Options | Summary | 12 | 4.2.2.2.1 | 4.2.2.2.1 |  | 0 | 0 |  | 113 | q | -24 | (-21%) | 89
6 | 285 | Review Outsourcing Options - Training Delivery | Summary | 10 | 4.2.2.2.1.3 | 4.2.2.2.1.3 |  | 0 | 0 |  | 97 | q | -24 | (-25%) | 73
7 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 55 | q | -24 | (-44%) | 31
8 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 8 | p | 52 | -650% | 60
9 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 24 | p | 16 | -67% | 40
10 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 8 | p | 16 | -200% | 24
11 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 24 | p | 112 | -467% | 136
12 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 8 | p | 80 | -1000% | 88
13 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 8 | p | 32 | -400% | 40

## Baseline-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Budget-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Actual-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%) | Actual Cost - 7 (5%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600
2 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 12500 | q | -5700 | (-46%) | 6800
3 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600
4 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 0 | p | 1640 |  | 1640
5 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600
6 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600
7 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 0 | p | 1600 |  | 1600

## Remaining-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%) | Remaining Cost - 11 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 0 | q | 0 |  | 0
2 | 261 | Create training delivery schedule | Normal | 1 | 4.2.2.2.2.1 | 4.2.2.2.2.1 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
3 | 291 | Review cost | Normal | 1 | 4.2.2.2.1.3.2 | 4.2.2.2.1.3.2 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
4 | 292 | Determine time required to ready external trainers | Normal | 1 | 4.2.2.2.1.3.5 | 4.2.2.2.1.3.5 |  | 0 | 1.88 | Path 02 | 1640 | q | -1640 | (-100%) | 0
5 | 294 | Make outsourcing decision | Normal | 1 | 4.2.2.2.1.3.6 | 4.2.2.2.1.3.6 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
6 | 295 | Review service levels | Normal | 1 | 4.2.2.2.1.3.3 | 4.2.2.2.1.3.3 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
7 | 296 | Review customer references | Normal | 1 | 4.2.2.2.1.3.4 | 4.2.2.2.1.3.4 |  | 0 | 1.88 | Path 02 | 1600 | q | -1600 | (-100%) | 0
8 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 1600 | p | 12400 | -775% | 14000
9 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 1600 | p | 3200 | -200% | 4800
10 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 400 | p | 33648 | -8412% | 34048
11 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 400 | p | 1600 | -400% | 2000

## Total-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%) | Total Cost - 6 (4%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 0 | q | 0 |  | 0
2 | 290 | Review expertise of potential vendors | Normal | 0 | 4.2.2.2.1.3.1 | 4.2.2.2.1.3.1 |  | 0 | 1.88 | Path 02 | 12500 | q | -5700 | (-46%) | 6800
3 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 1600 | p | 12400 | -775% | 14000
4 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 1600 | p | 3200 | -200% | 4800
5 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 400 | p | 33648 | -8412% | 34048
6 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 400 | p | 1600 | -400% | 2000

## WBS-Code
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Existence--
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%) | Existence % - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Use-Cost-Uncertainty
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%) | Use Cost Uncertainty - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Cost-Uncertainty-Distribution
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%) | Cost Uncertainty Distribution - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Max-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%) | Max Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Most-Likely-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%) | Most Likely Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Min-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%) | Min Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Upper---Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%) | Upper % Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Lower---Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%) | Lower % Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Mean-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%) | Mean Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Std-Deviation-Cost
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%) | Std Deviation Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Use-Duration-Uncertainty
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%) | Use Duration Uncertainty - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Duration-Uncertainty-Distribut
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%) | Duration Uncertainty Distribution - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Max-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%) | Max Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Most-Likely-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%) | Most Likely Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Min-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%) | Min Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Upper---Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%) | Upper % Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Lower---Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%) | Lower % Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Mean-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%) | Mean Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Std-Deviation-Duration
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%) | Std Deviation Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Budget
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%) | Budget - 10 (7%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 1 | p | 1 | -100% | 2
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 1 | p | 1 | -100% | 2
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
5 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2
6 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 0 | p | 2 |  | 2
7 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2
8 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 0 | p | 2 |  | 2
9 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 0 | p | 2 |  | 2
10 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 0 | p | 2 |  | 2

## Task-Budget
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%) | Task Budget - 10 (7%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3
1 | 315 | Service Delivery Infrastructure Planning | Summary | 19 | 4 | 4 |  | 1 | 0 |  | 1 | p | 1 | -100% | 2
2 | 129 | Training & Readiness | Summary | 19 | 4.2 | 4.2 |  | 1 | 0 |  | 1 | p | 1 | -100% | 2
3 | 235 | Training Planning | Summary | 19 | 4.2.2 | 4.2.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
4 | 237 | Training Delivery Planning | Summary | 19 | 4.2.2.2 | 4.2.2.2 |  | 0 | 0 |  | 0 | p | 1 |  | 1
5 | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Normal | 1 | 4.2.2.2.3 | 4.2.2.2.3 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2
6 | 306 | Finalize Training Planning | Summary | 3 | 4.2.2.3 | 4.2.2.3 |  | 0 | 0 |  | 0 | p | 2 |  | 2
7 | 275 | Acquire executive sign-off on budget | Normal | 1 | 4.2.2.3.2 | 4.2.2.3.2 |  | 0 | 1.88 | Path 02 | 0 | p | 2 |  | 2
8 | 383 | Business Performance Planning | Summary | 2 | 5 | 5 |  | 0 | 0 |  | 0 | p | 2 |  | 2
9 | 385 | Determine success metrics | Normal | 1 | 5.2 | 5.2 |  | 0 | 0 |  | 0 | p | 2 |  | 2
10 | 386 | Determine cost efficiency standards | Normal | 1 | 5.3 | 5.3 |  | 0 | 0 |  | 0 | p | 2 |  | 2

## Driving-Slack
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%) | Driving Slack - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3

## Trace-Log-Field
Acumen Fuse® Forensic Analysis Report
Hard_File_update2 vs update3_Fuse
Hard_File_updated2 - 141 Activities
Compared to: 1 Snapshot
Created on: 7/9/2026
Created by: dpolitte
Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%) | Trace Log Field - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Task Budget | Driving Slack | Trace Log Field | Hard_File_updated2 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3 | Hard_File_updated3