## Ribbon View
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
[404 empty] | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% of Rem Project Duration | High Float 44d | Zero Days Float | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | New To-Go Tasks in Status Period | New Completed Tasks in Status Period | New Critical Tasks in Status Period | Riding Data Date | Deadlines | Missed Activities | High Float 10% | Negative Float | Max Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Milestone-to-Task Ratio (To-Go) | Float Ratio™ | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | Near CP - Float Ratio™ | CP Logic Density™ | Critical Tasks Created in Status Period | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | SV(t) | SPI(t) | Missing Predecessors | Missing Successors | Activities with Lags | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | Logic Density™ | Merge Hotspot | Diverge Hotspot | Logic Hotspot™ | Summary Links | Open Start | Open Finish | Open Ends with Constraints | Open Ends w/o Constraints | Open Ends | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score | time axis 2012-08-01 to 2029-04-01
Ribbons | Project5_FX04_TamperDuration | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 53 | 56 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 43 | 0 | 306 | 99 | 0 | 99 | 2 | N/A | 25.63 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.2 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 43 | 56 | 4 | 0 | 306 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 0
Ribbons | Project5_FX04_TamperDuration | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 54% | 57% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 43% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 43% | 57% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 57% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | Project5_FX05_TamperLogicDrop | [402 empty] | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 57 | 58 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 47 | 0 | 472 | 99 | 0 | 99 | 2 | N/A | 36.91 | 1 | 0 | 1 | 0 | N/A | 0 | 1 | 1 | 0 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 47 | 58 | 1 | 0 | 472 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 2 | 8 | 2 | 0 | 0 | 1 | 124 | 2.78 | 10 | 13 | 1 | 0 | 0 | 0 | 1 | 9 | 10 | 8 | 0 | 1 | 0 | 0 | 1 | 58 | 0 | 0 | 8 | 0 | 0 | 37 | x | 1 | 0.59 | 0
Ribbons | Project5_FX05_TamperLogicDrop | [402 empty] | 0% | 0% | 8% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 8% | 1% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 58% | 59% | 1% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 90% | 47% | 0% |  | 79% | 0% | 100% | 2% |  |  | 1% | 0% | 100% | 0% |  | 0% | 1% | 1% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 47% | 59% | 1% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 8% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 8% | 1% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 2% | 6% | 2% | 0% | 0% | 1% | 98% |  | 8% | 10% | 1% | 0% | 0% | 0% | 1% | 6% | 8% | 8% | 0% | 1% | 0% | 0% | 1% | 59% | 0% | 0% | 8% | 0% | 0% | 80%
Ribbons | Project5_FX06_TamperBaselineShift | [402 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 53 | 56 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 43 | 0 | 306 | 99 | 0 | 99 | 2 | N/A | 25.63 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.2 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 43 | 56 | 4 | 0 | 306 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 37 | x | 1 | 0.59 | 0
Ribbons | Project5_FX06_TamperBaselineShift | [402 empty] | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 54% | 57% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 43% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 43% | 57% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 57% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | TP4_DataCenter_v3_FX01_MilestoneLate | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v3_FX01_MilestoneLate | [402 empty] | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%
Ribbons | TP4_DataCenter_v3_FX02_EarlyFinish | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -113 | 0.78 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 2 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v3_FX02_EarlyFinish | [402 empty] | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 23% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 29% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 29%
Ribbons | TP4_DataCenter_v3_FX03_DurationCut | [402 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v3_FX03_DurationCut | [402 empty] | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%
Phase Analyzer | Status Date | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: 2026-03-31; 2026-02-01: 2026-03-31; 2026-03-01: 2026-03-31; 2026-04-01: 2026-08-27; 2026-05-01: 2026-08-27; 2026-06-01: 2026-08-27; 2026-07-01: 2026-08-27; 2026-08-01: 2026-08-27; 2026-09-01: 2026-08-27; 2026-10-01: 2026-08-27; 2026-11-01: 2026-08-27; 2026-12-01: 2026-08-27; 2027-01-01: 2026-08-27; 2027-02-01: 2026-08-27; 2027-03-01: 2026-08-27; 2027-04-01: 2026-08-27; 2027-05-01: 2026-08-27; 2027-06-01: 2026-08-27; 2027-07-01: 2026-08-27; 2027-08-01: 2026-08-27; 2027-09-01: 2026-08-27; 2027-10-01: 2026-08-27; 2027-11-01: 2026-08-27; 2027-12-01: 2026-08-27; 2028-01-01: 2026-08-27; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | WBS | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: 1; 2026-02-01: 3; 2026-03-01: 4; 2026-04-01: 1; 2026-05-01: 1; 2026-06-01: 2; 2026-07-01: 4; 2026-08-01: 5; 2026-09-01: 5; 2026-10-01: 5; 2026-11-01: 5; 2026-12-01: 5; 2027-01-01: 6; 2027-02-01: 7; 2027-03-01: 7; 2027-04-01: 7; 2027-05-01: 9; 2027-06-01: 9; 2027-07-01: 16; 2027-08-01: 16; 2027-09-01: 16; 2027-10-01: 16; 2027-11-01: 16; 2027-12-01: 16; 2028-01-01: 16; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | New Activity - Created (Snapshot) | 2012-08-01: 0; 2012-09-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 0; 2013-10-01: 0; 2013-11-01: 0; 2013-12-01: 0; 2014-01-01: 0; 2014-02-01: 0; 2014-03-01: 0; 2014-04-01: 0; 2014-05-01: 0; 2014-06-01: 0; 2014-07-01: 0; 2014-08-01: 0; 2014-09-01: 0; 2014-10-01: 0; 2014-11-01: 0; 2014-12-01: 0; 2015-01-01: 0; 2015-02-01: 0; 2015-03-01: 0; 2015-04-01: 0; 2015-05-01: 0; 2015-06-01: 0; 2015-07-01: 0; 2015-08-01: 0; 2015-09-01: 0; 2015-10-01: 0; 2015-11-01: 0; 2015-12-01: 0; 2016-01-01: 0; 2016-02-01: 0; 2016-03-01: 0; 2016-04-01: 0; 2016-05-01: 0; 2016-06-01: 0; 2016-07-01: 0; 2016-08-01: 0; 2016-09-01: 0; 2016-10-01: 0; 2016-11-01: 0; 2016-12-01: 0; 2017-01-01: 0; 2017-02-01: 0; 2017-03-01: 0; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: 0; 2018-04-01: 0; 2018-05-01: 0; 2018-06-01: 0; 2018-07-01: 0; 2018-08-01: 0; 2018-09-01: 0; 2018-10-01: 0; 2018-11-01: 0; 2018-12-01: 0; 2019-01-01: 0; 2019-02-01: 0; 2019-03-01: 0; 2019-04-01: 0; 2019-05-01: 0; 2019-06-01: 0; 2019-07-01: 0; 2019-08-01: 0; 2019-09-01: 0; 2019-10-01: 0; 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0; 2023-12-01: 0; 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0; 2024-05-01: 0; 2024-06-01: 0; 2024-07-01: 0; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0; 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0; 2027-06-01: 0; 2027-07-01: 0; 2027-08-01: 0; 2027-09-01: 0; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0; 2028-08-01: 0; 2028-09-01: 0; 2028-10-01: 0; 2028-11-01: 0; 2028-12-01: 0; 2029-01-01: 0; 2029-02-01: 0; 2029-03-01: 0; 2029-04-01: 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 2012-08-01: 0; 2012-09-01: 0; 2012-10-01: 0; 2012-11-01: 0; 2012-12-01: 0; 2013-01-01: 0; 2013-02-01: 0; 2013-03-01: 0; 2013-04-01: 0; 2013-05-01: 0; 2013-06-01: 0; 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 0; 2013-10-01: 0; 2013-11-01: 0; 2013-12-01: 0; 2014-01-01: 0; 2014-02-01: 0; 2014-03-01: 0; 2014-04-01: 0; 2014-05-01: 0; 2014-06-01: 0; 2014-07-01: 0; 2014-08-01: 0; 2014-09-01: 0; 2014-10-01: 0; 2014-11-01: 0; 2014-12-01: 0; 2015-01-01: 0; 2015-02-01: 0; 2015-03-01: 0; 2015-04-01: 0; 2015-05-01: 0; 2015-06-01: 0; 2015-07-01: 0; 2015-08-01: 0; 2015-09-01: 0; 2015-10-01: 0; 2015-11-01: 0; 2015-12-01: 0; 2016-01-01: 0; 2016-02-01: 0; 2016-03-01: 0; 2016-04-01: 0; 2016-05-01: 0; 2016-06-01: 0; 2016-07-01: 0; 2016-08-01: 0; 2016-09-01: 0; 2016-10-01: 0; 2016-11-01: 0; 2016-12-01: 0; 2017-01-01: 0; 2017-02-01: 0; 2017-03-01: 0; 2017-04-01: 0; 2017-05-01: 0; 2017-06-01: 0; 2017-07-01: 0; 2017-08-01: 0; 2017-09-01: 0; 2017-10-01: 0; 2017-11-01: 0; 2017-12-01: 0; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: 0; 2018-04-01: 0; 2018-05-01: 0; 2018-06-01: 0; 2018-07-01: 0; 2018-08-01: 0; 2018-09-01: 0; 2018-10-01: 0; 2018-11-01: 0; 2018-12-01: 0; 2019-01-01: 0; 2019-02-01: 0; 2019-03-01: 0; 2019-04-01: 0; 2019-05-01: 0; 2019-06-01: 0; 2019-07-01: 0; 2019-08-01: 0; 2019-09-01: 0; 2019-10-01: 0; 2019-11-01: 0; 2019-12-01: 0; 2020-01-01: 0; 2020-02-01: 0; 2020-03-01: 0; 2020-04-01: 0; 2020-05-01: 0; 2020-06-01: 0; 2020-07-01: 0; 2020-08-01: 0; 2020-09-01: 0; 2020-10-01: 0; 2020-11-01: 0; 2020-12-01: 0; 2021-01-01: 0; 2021-02-01: 0; 2021-03-01: 0; 2021-04-01: 0; 2021-05-01: 0; 2021-06-01: 0; 2021-07-01: 0; 2021-08-01: 0; 2021-09-01: 0; 2021-10-01: 0; 2021-11-01: 0; 2021-12-01: 0; 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0; 2022-12-01: 0; 2023-01-01: 0; 2023-02-01: 0; 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0; 2023-12-01: 0; 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0; 2024-05-01: 0; 2024-06-01: 0; 2024-07-01: 0; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 0; 2026-08-01: 0; 2026-09-01: 0; 2026-10-01: 0; 2026-11-01: 0; 2026-12-01: 0; 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0; 2027-06-01: 0; 2027-07-01: 0; 2027-08-01: 0; 2027-09-01: 0; 2027-10-01: 0; 2027-11-01: 0; 2027-12-01: 0; 2028-01-01: 0; 2028-02-01: 0; 2028-03-01: 0; 2028-04-01: 0; 2028-05-01: 0; 2028-06-01: 0; 2028-07-01: 0; 2028-08-01: 0; 2028-09-01: 0; 2028-10-01: 0; 2028-11-01: 0; 2028-12-01: 0; 2029-01-01: 0; 2029-02-01: 0; 2029-03-01: 0; 2029-04-01: 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: N/A; 2026-02-01: N/A; 2026-03-01: N/A; 2026-04-01: N/A; 2026-05-01: N/A; 2026-06-01: N/A; 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A; 2027-01-01: N/A; 2027-02-01: N/A; 2027-03-01: N/A; 2027-04-01: N/A; 2027-05-01: N/A; 2027-06-01: N/A; 2027-07-01: N/A; 2027-08-01: N/A; 2027-09-01: N/A; 2027-10-01: N/A; 2027-11-01: N/A; 2027-12-01: N/A; 2028-01-01: N/A; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | Specific Task Start | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: N/A; 2026-02-01: N/A; 2026-03-01: N/A; 2026-04-01: N/A; 2026-05-01: N/A; 2026-06-01: N/A; 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A; 2027-01-01: N/A; 2027-02-01: N/A; 2027-03-01: N/A; 2027-04-01: N/A; 2027-05-01: N/A; 2027-06-01: N/A; 2027-07-01: N/A; 2027-08-01: N/A; 2027-09-01: 2027-09-10; 2027-10-01: 2027-09-10; 2027-11-01: N/A; 2027-12-01: N/A; 2028-01-01: N/A; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | Specific Task Finish | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: N/A; 2026-02-01: N/A; 2026-03-01: N/A; 2026-04-01: N/A; 2026-05-01: N/A; 2026-06-01: N/A; 2026-07-01: N/A; 2026-08-01: N/A; 2026-09-01: N/A; 2026-10-01: N/A; 2026-11-01: N/A; 2026-12-01: N/A; 2027-01-01: N/A; 2027-02-01: N/A; 2027-03-01: N/A; 2027-04-01: N/A; 2027-05-01: N/A; 2027-06-01: N/A; 2027-07-01: N/A; 2027-08-01: N/A; 2027-09-01: N/A; 2027-10-01: 2027-10-07; 2027-11-01: N/A; 2027-12-01: N/A; 2028-01-01: N/A; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A
Phase Analyzer | Score | 2012-08-01: N/A; 2012-09-01: N/A; 2012-10-01: N/A; 2012-11-01: N/A; 2012-12-01: N/A; 2013-01-01: N/A; 2013-02-01: N/A; 2013-03-01: N/A; 2013-04-01: N/A; 2013-05-01: N/A; 2013-06-01: N/A; 2013-07-01: N/A; 2013-08-01: N/A; 2013-09-01: N/A; 2013-10-01: N/A; 2013-11-01: N/A; 2013-12-01: N/A; 2014-01-01: N/A; 2014-02-01: N/A; 2014-03-01: N/A; 2014-04-01: N/A; 2014-05-01: N/A; 2014-06-01: N/A; 2014-07-01: N/A; 2014-08-01: N/A; 2014-09-01: N/A; 2014-10-01: N/A; 2014-11-01: N/A; 2014-12-01: N/A; 2015-01-01: N/A; 2015-02-01: N/A; 2015-03-01: N/A; 2015-04-01: N/A; 2015-05-01: N/A; 2015-06-01: N/A; 2015-07-01: N/A; 2015-08-01: N/A; 2015-09-01: N/A; 2015-10-01: N/A; 2015-11-01: N/A; 2015-12-01: N/A; 2016-01-01: N/A; 2016-02-01: N/A; 2016-03-01: N/A; 2016-04-01: N/A; 2016-05-01: N/A; 2016-06-01: N/A; 2016-07-01: N/A; 2016-08-01: N/A; 2016-09-01: N/A; 2016-10-01: N/A; 2016-11-01: N/A; 2016-12-01: N/A; 2017-01-01: N/A; 2017-02-01: N/A; 2017-03-01: N/A; 2017-04-01: N/A; 2017-05-01: N/A; 2017-06-01: N/A; 2017-07-01: N/A; 2017-08-01: N/A; 2017-09-01: N/A; 2017-10-01: N/A; 2017-11-01: N/A; 2017-12-01: N/A; 2018-01-01: N/A; 2018-02-01: N/A; 2018-03-01: N/A; 2018-04-01: N/A; 2018-05-01: N/A; 2018-06-01: N/A; 2018-07-01: N/A; 2018-08-01: N/A; 2018-09-01: N/A; 2018-10-01: N/A; 2018-11-01: N/A; 2018-12-01: N/A; 2019-01-01: N/A; 2019-02-01: N/A; 2019-03-01: N/A; 2019-04-01: N/A; 2019-05-01: N/A; 2019-06-01: N/A; 2019-07-01: N/A; 2019-08-01: N/A; 2019-09-01: N/A; 2019-10-01: N/A; 2019-11-01: N/A; 2019-12-01: N/A; 2020-01-01: N/A; 2020-02-01: N/A; 2020-03-01: N/A; 2020-04-01: N/A; 2020-05-01: N/A; 2020-06-01: N/A; 2020-07-01: N/A; 2020-08-01: N/A; 2020-09-01: N/A; 2020-10-01: N/A; 2020-11-01: N/A; 2020-12-01: N/A; 2021-01-01: N/A; 2021-02-01: N/A; 2021-03-01: N/A; 2021-04-01: N/A; 2021-05-01: N/A; 2021-06-01: N/A; 2021-07-01: N/A; 2021-08-01: N/A; 2021-09-01: N/A; 2021-10-01: N/A; 2021-11-01: N/A; 2021-12-01: N/A; 2022-01-01: N/A; 2022-02-01: N/A; 2022-03-01: N/A; 2022-04-01: N/A; 2022-05-01: N/A; 2022-06-01: N/A; 2022-07-01: N/A; 2022-08-01: N/A; 2022-09-01: N/A; 2022-10-01: N/A; 2022-11-01: N/A; 2022-12-01: N/A; 2023-01-01: N/A; 2023-02-01: N/A; 2023-03-01: N/A; 2023-04-01: N/A; 2023-05-01: N/A; 2023-06-01: N/A; 2023-07-01: N/A; 2023-08-01: N/A; 2023-09-01: N/A; 2023-10-01: N/A; 2023-11-01: N/A; 2023-12-01: N/A; 2024-01-01: N/A; 2024-02-01: N/A; 2024-03-01: N/A; 2024-04-01: N/A; 2024-05-01: N/A; 2024-06-01: N/A; 2024-07-01: N/A; 2024-08-01: N/A; 2024-09-01: N/A; 2024-10-01: N/A; 2024-11-01: N/A; 2024-12-01: N/A; 2025-01-01: N/A; 2025-02-01: N/A; 2025-03-01: N/A; 2025-04-01: N/A; 2025-05-01: N/A; 2025-06-01: N/A; 2025-07-01: N/A; 2025-08-01: N/A; 2025-09-01: N/A; 2025-10-01: N/A; 2025-11-01: N/A; 2025-12-01: N/A; 2026-01-01: 100; 2026-02-01: 100; 2026-03-01: 100; 2026-04-01: 100; 2026-05-01: 100; 2026-06-01: 100; 2026-07-01: 100; 2026-08-01: 100; 2026-09-01: 100; 2026-10-01: 100; 2026-11-01: 100; 2026-12-01: 100; 2027-01-01: 100; 2027-02-01: 100; 2027-03-01: 100; 2027-04-01: 100; 2027-05-01: 100; 2027-06-01: 100; 2027-07-01: 100; 2027-08-01: 100; 2027-09-01: 100; 2027-10-01: 100; 2027-11-01: 100; 2027-12-01: 100; 2028-01-01: 100; 2028-02-01: N/A; 2028-03-01: N/A; 2028-04-01: N/A; 2028-05-01: N/A; 2028-06-01: N/A; 2028-07-01: N/A; 2028-08-01: N/A; 2028-09-01: N/A; 2028-10-01: N/A; 2028-11-01: N/A; 2028-12-01: N/A; 2029-01-01: N/A; 2029-02-01: N/A; 2029-03-01: N/A; 2029-04-01: N/A

## Ribbon Analysis
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% of Rem Project Duration | High Float 44d | Zero Days Float | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | New To-Go Tasks in Status Period | New Completed Tasks in Status Period | New Critical Tasks in Status Period | Riding Data Date | Deadlines | Missed Activities | High Float 10% | Negative Float | Max Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Milestone-to-Task Ratio (To-Go) | Float Ratio™ | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | Near CP - Float Ratio™ | CP Logic Density™ | Critical Tasks Created in Status Period | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | SV(t) | SPI(t) | Missing Predecessors | Missing Successors | Activities with Lags | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | Logic Density™ | Merge Hotspot | Diverge Hotspot | Logic Hotspot™ | Summary Links | Open Start | Open Finish | Open Ends with Constraints | Open Ends w/o Constraints | Open Ends | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score
Ribbons | Project5_FX04_TamperDuration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 53 | 56 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 43 | 0 | 306 | 99 | 0 | 99 | 2 | N/A | 25.63 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.2 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 43 | 56 | 4 | 0 | 306 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 37 | ✓ | 1 | 0.59 | 0
Ribbons | Project5_FX05_TamperLogicDrop | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 57 | 58 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 47 | 0 | 472 | 99 | 0 | 99 | 2 | N/A | 36.91 | 1 | 0 | 1 | 0 | N/A | 0 | 1 | 1 | 0 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 47 | 58 | 1 | 0 | 472 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 2 | 8 | 2 | 0 | 0 | 1 | 124 | 2.78 | 10 | 13 | 1 | 0 | 0 | 0 | 1 | 9 | 10 | 8 | 0 | 1 | 0 | 0 | 1 | 58 | 0 | 0 | 8 | 0 | 0 | 37 | x | 1 | 0.59 | 0
Ribbons | Project5_FX06_TamperBaselineShift | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | 53 | 56 | 4 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 43 | 0 | 306 | 99 | 0 | 99 | 2 | N/A | 25.63 | 4 | 0 | 4 | 0 | N/A | 0 | 4 | 5 | 0.2 | 3 | 0 | N/A | N/A | N/A | 0 | 0 | 0.59 | 46 | 27 | 19 | 2026-08-27 | 0.59 | 46 | 27 | 19 | 0.59 | 27 | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-08-27 | 43 | 56 | 4 | 0 | 306 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2026-08-27 | -902 | 0.91 | 1 | 6 | 2 | 0 | 0 | 1 | 125 | 2.81 | 10 | 13 | 1 | 0 | 0 | 0 | 0 | 7 | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 56 | 0 | 0 | 0 | 0 | 0 | 37 | x | 1 | 0.59 | 0
Ribbons | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -113 | 0.78 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 2 | ✓ | 1 | 0.71 | 0
Ribbons | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 30 | 9 | 1 | 8 | 2 | 1:08 | 0.34 | 7 | 1 | 6 | 1 | 1:06 | 0 | 7 | 7 | 0 | 2.86 | 0 | N/A | N/A | N/A | 0 | 0 | 0.71 | 7 | 5 | 2 | 2026-03-31 | 0.71 | 7 | 5 | 2 | 0.71 | 5 | N/A | 2026-03-31 | 1 | 1 | 1 | 0 | 1 | 1 | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 1 | 0 | 7 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | N/A | 0 | N/A | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 2026-03-31 | -123 | 0.67 | 1 | 1 | 0 | 0 | 0 | 0 | 14 | 2.67 | 1 | 1 | 0 | N/A | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 3 | ✓ | 1 | 0.71 | 0
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% of Rem Project Duration | High Float 44d | Zero Days Float | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | New To-Go Tasks in Status Period | New Completed Tasks in Status Period | New Critical Tasks in Status Period | Riding Data Date | Deadlines | Missed Activities | High Float 10% | Negative Float | Max Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Milestone-to-Task Ratio (To-Go) | Float Ratio™ | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | Near CP - Float Ratio™ | CP Logic Density™ | Critical Tasks Created in Status Period | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Status Date | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Status Date | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | New Activity - Created | New Activity - Already Finished | New Activity - Finished in Status Period | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Max Float | Newly Created Activity & Critical - Created (Snapshot) | Number of Leads | Number of Lags | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Total New Completed Tasks & Milestones in Status Period | Total New Tasks & Milestones in Status Period | Riding Data Date | Deadlines | Missed Activities | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | SF Relations | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Missing Baseline Starts | Missing Baseline Finishes | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | SV(t) | SPI(t) | Missing Predecessors | Missing Successors | Activities with Lags | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | Logic Density™ | Merge Hotspot | Diverge Hotspot | Logic Hotspot™ | Summary Links | Open Start | Open Finish | Open Ends with Constraints | Open Ends w/o Constraints | Open Ends | 1. Logic | 2. Leads | 3. Lags | 4. SS/FF Relations | 4. SF Relations | 5. Hard Constraint | 6. High Float | 7. Negative Float | 8. High Duration | 9. Invalid Forecast Dates | 9. Invalid Actual Dates | 10. Resources | 11. Missed Activities | 12. Critical Path Test | 13. CPLI | 14. BEI | Score
Ribbons | Project5_FX04_TamperDuration | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 54% | 57% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 43% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 43% | 57% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 57% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | Project5_FX05_TamperLogicDrop | 0% | 0% | 8% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 8% | 1% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 58% | 59% | 1% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 90% | 47% | 0% |  | 79% | 0% | 100% | 2% |  |  | 1% | 0% | 100% | 0% |  | 0% | 1% | 1% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 47% | 59% | 1% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 8% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 8% | 1% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 2% | 6% | 2% | 0% | 0% | 1% | 98% |  | 8% | 10% | 1% | 0% | 0% | 0% | 1% | 6% | 8% | 8% | 0% | 1% | 0% | 0% | 1% | 59% | 0% | 0% | 8% | 0% | 0% | 80%
Ribbons | Project5_FX06_TamperBaselineShift | 0% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  | 54% | 57% | 4% | 0% | 1% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 93% | 43% | 0% |  | 79% | 0% | 100% | 2% |  |  | 4% | 0% | 100% | 0% |  | 0% | 4% | 5% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 59% | 41% |  |  |  | 59% | 41% |  | 59% |  |  |  |  | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 43% | 57% | 4% | 0% |  |  | 0% | 2% | 1% | 0% | 1% | 0% | 0% | 0% |  |  | 0% | 0% | 80% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | 0% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 0% | 0% |  |  |  | 1% | 5% | 2% | 0% | 0% | 1% | 99% |  | 8% | 10% | 1% | 0% | 0% | 0% | 0% | 5% | 6% | 5% | 0% | 1% | 0% | 0% | 1% | 57% | 0% | 0% | 0% | 0% | 0% | 80%
Ribbons | TP4_DataCenter_v3_FX01_MilestoneLate | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%
Ribbons | TP4_DataCenter_v3_FX02_EarlyFinish | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 23% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 29% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 29%
Ribbons | TP4_DataCenter_v3_FX03_DurationCut | 0% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 22% | 0% | 78% | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 31% | 11% | 0% |  | 60% | 11% | 89% | 22% |  |  | 78% | 14% | 86% | 14% |  | 0% | 78% | 78% |  |  | 0% |  | N/A | N/A | 0% | 0% |  |  | 71% | 29% |  |  |  | 71% | 29% |  | 71% |  |  |  |  | 100% | 0% |  | 100% |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A | N/A |  | N/A |  |  |  |  | N/A | N/A |  | N/A | [7 empty] | N/A | N/A |  | N/A |  |  | 11% | 0% | 78% | 0% |  |  | 0% | 0% | 0% | 0% | 14% | ( N/A ) | 0% | ( N/A ) |  |  | 0% | 0% | 43% | 0% | 44% | 0% | 0% | 0% | 0% | 0% | 0% | 11% | 0% | 11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 7% | 7% | 0% | 0% | 0% | 0% | 93% |  | 7% | 7% | 0% | N/A | 0% | 0% | 0% | 7% | 13% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 100% | 43%

## Project5_FX04_TamperDurati1
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View | Project5_FX04_TamperDuration: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | 0 | 220 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | 0 | 128 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 20 | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | 0 | 37 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | 0 | 47 | Planned
FALSE |  | TRUE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | 0 | 0 | Planned
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 20 | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | TRUE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Hard Constraints
Number of activities with hard or two-way constraints.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
High Float 10% of Rem Project Duration
Number of activities that have a total float value higher than 10% of the remaining duration of the project. This number should not exceed 20%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 368 | 306 |  | -1 |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE | FALSE | 368 | 306 |  | -1 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE | FALSE | 368 | 66 |  | -1 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 149 |  | -1 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 99 |  | -1 |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 64 |  | -1 |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 128 |  | -1 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 90 |  | -1 |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE | FALSE | 368 | 73 |  | -1 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 10%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 368 | 306 |  | -1 |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE | FALSE | 368 | 306 |  | -1 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE | FALSE | 368 | 66 |  | -1 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE | FALSE | 368 | 45 |  | -1 |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 149 |  | -1 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 99 |  | -1 |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 64 |  | -1 |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 128 |  | -1 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 90 |  | -1 |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE | FALSE | 368 | 73 |  | -1 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE | FALSE | 368 | 45 |  | -1 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 47 |  | -1 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
Zero Days Float
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | TRUE | 0 |  | -1 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
Hidden Duration (Planned)
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of their original durations.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links (>2) that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline finish dates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 29
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 57 | Pour 2nd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 29
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 29
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 62 | Pour 3rd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 29
FALSE |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 29
FALSE |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE |  | 65 | Form roof slab including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 67 | Pour roof slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 29
FALSE |  | 68 | Cure roof slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 29
FALSE |  | 69 | Strip forms from roof slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 29
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_FX04_TamperDuration | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 29
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 29
FALSE |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 29
FALSE |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 29
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 96 | Install interior doors and hardware | Project5_FX04_TamperDuration | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 34
FALSE |  | 99 | Install millwork and wood trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 107 | Install hardware and accessories | Project5_FX04_TamperDuration | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 29
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 42
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 42
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 138 | Complete elevator inspection and certification | Project5_FX04_TamperDuration | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 140 | Perform local building agency inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 29
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 1
FALSE |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
Tasks & Milestones (To Go)
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 306 | 93 |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 29 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 306 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 66 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 67 | Pour roof slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 68 | Cure roof slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 69 | Strip forms from roof slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 64 | 0 |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 128 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 96 | Install interior doors and hardware | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX04_TamperDuration | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 47 | 0 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Normal Tasks (To-Go)
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 306 | 93 |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 29 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 306 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 66 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 67 | Pour roof slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 68 | Cure roof slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 69 | Strip forms from roof slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 64 | 0 |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 128 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 96 | Install interior doors and hardware | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX04_TamperDuration | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 47 | 0 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Normal Tasks (To-Go, In Progress)
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 306 | 93 |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 29 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 306 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 66 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 67 | Pour roof slab | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 68 | Cure roof slab | Project5_FX04_TamperDuration | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 69 | Strip forms from roof slab | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 64 | 0 |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 128 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 96 | Install interior doors and hardware | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX04_TamperDuration | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 47 | 0 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX04_TamperDuration | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 306 |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE |  | FALSE | 29 |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36
FALSE |  | FALSE | 306 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | FALSE | 66 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 57 | Pour 2nd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 60 | Form 3rd floor including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 62 | Pour 3rd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 65 | Form roof slab including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 149 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 67 | Pour roof slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 68 | Cure roof slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 69 | Strip forms from roof slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 78 | Install exterior sheathing and metal studs | Project5_FX04_TamperDuration | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | FALSE | 99 |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | FALSE | 64 |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 128 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 90 |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 34 |  | 96 | Install interior doors and hardware | Project5_FX04_TamperDuration | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 99 | Install millwork and wood trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | FALSE | 73 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | FALSE | 37 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 107 | Install hardware and accessories | Project5_FX04_TamperDuration | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | FALSE | 47 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 138 | Complete elevator inspection and certification | Project5_FX04_TamperDuration | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 140 | Perform local building agency inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 141 | Perform Fire Marshal's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 306 |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE |  | FALSE | 29 |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36
FALSE |  | FALSE | 306 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | FALSE | 66 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 57 | Pour 2nd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 60 | Form 3rd floor including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 62 | Pour 3rd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 65 | Form roof slab including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 149 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 67 | Pour roof slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 68 | Cure roof slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 69 | Strip forms from roof slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 78 | Install exterior sheathing and metal studs | Project5_FX04_TamperDuration | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | FALSE | 99 |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | FALSE | 64 |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 128 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 90 |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 34 |  | 96 | Install interior doors and hardware | Project5_FX04_TamperDuration | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 99 | Install millwork and wood trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | FALSE | 73 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | FALSE | 37 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 107 | Install hardware and accessories | Project5_FX04_TamperDuration | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | FALSE | 47 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 138 | Complete elevator inspection and certification | Project5_FX04_TamperDuration | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 140 | Perform local building agency inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 141 | Perform Fire Marshal's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Critical Path (Tasks & Milestones)
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Critical Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Critical Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Planned | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Near-Critical (<10 Days Float)
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Near CP - Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX04_TamperDuration | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX04_TamperDuration | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Complete Tasks
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX04_TamperDuration | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX04_TamperDuration | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX04_TamperDuration | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX04_TamperDuration | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX04_TamperDuration | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX04_TamperDuration | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX04_TamperDuration | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX04_TamperDuration | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE | FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
Hidden Duration (Planned)
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE | None | TRUE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE | None | TRUE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Hard Constraints
Number of activities with hard or two-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Activities with Lags
Number of activities that have lag in their predecessors. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FF Predecessors
Number of activities with Finish-to-Finish (FF) logic links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Obtain building permits | Project5_FX04_TamperDuration | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX04_TamperDuration | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 29
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 57 | Pour 2nd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 29
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 29
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 62 | Pour 3rd floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 29
FALSE |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 29
FALSE |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE |  | 65 | Form roof slab including all floor openings | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 67 | Pour roof slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 29
FALSE |  | 68 | Cure roof slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 29
FALSE |  | 69 | Strip forms from roof slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 29
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_FX04_TamperDuration | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 29
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 29
FALSE |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 29
FALSE |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 29
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 96 | Install interior doors and hardware | Project5_FX04_TamperDuration | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 34
FALSE |  | 99 | Install millwork and wood trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 107 | Install hardware and accessories | Project5_FX04_TamperDuration | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 29
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 42
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 42
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 138 | Complete elevator inspection and certification | Project5_FX04_TamperDuration | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 140 | Perform local building agency inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 29
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX04_TamperDuration | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX04_TamperDuration | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 1
FALSE |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Merge Hotspot
Number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX04_TamperDuration | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 29
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Diverge Hotspot
Number of activities with a high number of successor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 29
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 29
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX04_TamperDuration | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 29
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX04_TamperDuration | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 29
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX04_TamperDuration | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 29
FALSE |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX04_TamperDuration | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
Open Ends w/o Constraints
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Open Ends
Number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX04_TamperDuration | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
1. Logic
Number of activities that are missing a predecessor, a successor or both. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX04_TamperDuration | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX04_TamperDuration | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
3. Lags
Number of lags in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
5. Hard Constraint
Number of activities with hard or two-way constraints. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX04_TamperDuration | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX04_TamperDuration | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX04_TamperDuration | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX04_TamperDuration | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX04_TamperDuration | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 70 | Form 1st floor | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX04_TamperDuration | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 74 | Pour 1st floor slab | Project5_FX04_TamperDuration | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 75 | Cure 1st floor slab | Project5_FX04_TamperDuration | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX04_TamperDuration | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX04_TamperDuration | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 86 | Clean toilet room tile | Project5_FX04_TamperDuration | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX04_TamperDuration | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 97 | Install store front doors and hardware | Project5_FX04_TamperDuration | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX04_TamperDuration | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX04_TamperDuration | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX04_TamperDuration | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX04_TamperDuration | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX04_TamperDuration | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX04_TamperDuration | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 130 | Install duct in building chase | Project5_FX04_TamperDuration | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX04_TamperDuration | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX04_TamperDuration | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX04_TamperDuration | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX04_TamperDuration | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 103 | Install ceiling grid | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX04_TamperDuration | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX04_TamperDuration | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 136 | Substantial completion date | Project5_FX04_TamperDuration | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX04_TamperDuration | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX04_TamperDuration | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX04_TamperDuration | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX04_TamperDuration | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX04_TamperDuration | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX04_TamperDuration | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX04_TamperDuration | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX04_TamperDuration | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX04_TamperDuration | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX04_TamperDuration | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX04_TamperDuration | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX04_TamperDuration | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX04_TamperDuration | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX04_TamperDuration | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX04_TamperDuration | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX04_TamperDuration | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX04_TamperDuration | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX04_TamperDuration | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX04_TamperDuration | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX04_TamperDuration | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX04_TamperDuration | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX04_TamperDuration | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX04_TamperDuration | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX04_TamperDuration | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX04_TamperDuration | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX04_TamperDuration | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX04_TamperDuration | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX04_TamperDuration | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX04_TamperDuration | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX04_TamperDuration | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX04_TamperDuration | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX04_TamperDuration | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29

## Project5_FX05_TamperLogicD2
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View | Project5_FX05_TamperLogicDrop: Detailed View
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Created | Actual Start | Actual Finish | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  |  |  |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | 0 | 471 | Planned
FALSE |  |  |  |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | 0 | 471 | Planned
FALSE |  |  |  |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | 0 | 472 | Planned
FALSE |  |  |  |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | 0 | 471 | Planned
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | FALSE | None | 0 | 2 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | 0 | 471 | Planned
FALSE |  | FALSE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | 0 | 471 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | 0 | 207 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | 0 | 115 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 20 | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | 0 | 24 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | 0 | 34 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | 0 | 29 | Planned
FALSE |  | TRUE | MandatoryStart | 3 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | 0 | 0 | Planned
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | FALSE | None | 0 | 2 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | FALSE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 20 | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE |  | FALSE | None | 1 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | TRUE | MandatoryStart | 3 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Hard Constraints
Number of activities with hard or two-way constraints.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
High Float 10% of Rem Project Duration
Number of activities that have a total float value higher than 10% of the remaining duration of the project. This number should not exceed 20%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 355 | 471 |  | -1 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE | FALSE | 355 | 471 |  | -1 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 472 |  | -1 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE | FALSE | 355 | 471 |  | -1 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
FALSE | FALSE | 355 | 293 |  | -1 |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE | FALSE | 355 | 293 |  | -1 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE | FALSE | 355 | 293 |  | -1 |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE | FALSE | 355 | 293 |  | -1 |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE | FALSE | 355 | 202 |  | -1 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE | FALSE | 355 | 61 |  | -1 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE | FALSE | 355 | 202 |  | -1 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 355 | 207 |  | -1 |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | FALSE | 355 | 202 |  | -1 |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 207 |  | -1 |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 355 | 135 |  | -1 |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 135 |  | -1 |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | FALSE | 355 | 207 |  | -1 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 149 |  | -1 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE | FALSE | 355 | 99 |  | -1 |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE | FALSE | 355 | 115 |  | -1 |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE | FALSE | 355 | 59 |  | -1 |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 115 |  | -1 |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE | FALSE | 355 | 60 |  | -1 |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 70 |  | -1 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE | FALSE | 355 | 70 |  | -1 |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 115 |  | -1 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 90 |  | -1 |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | FALSE | 355 | 60 |  | -1 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 70 |  | -1 |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE | FALSE | 355 | 81 |  | -1 |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE | FALSE | 355 | 60 |  | -1 |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE | FALSE | 355 | 73 |  | -1 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE | FALSE | 355 | 81 |  | -1 |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 10%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 355 | 471 |  | -1 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE | FALSE | 355 | 471 |  | -1 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 472 |  | -1 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE | FALSE | 355 | 471 |  | -1 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
FALSE | FALSE | 355 | 293 |  | -1 |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE | FALSE | 355 | 293 |  | -1 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE | FALSE | 355 | 293 |  | -1 |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE | FALSE | 355 | 293 |  | -1 |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE | FALSE | 355 | 202 |  | -1 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 242 |  | -1 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE | FALSE | 355 | 61 |  | -1 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE | FALSE | 355 | 202 |  | -1 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 355 | 207 |  | -1 |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | FALSE | 355 | 202 |  | -1 |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 207 |  | -1 |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 355 | 135 |  | -1 |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 135 |  | -1 |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | FALSE | 355 | 207 |  | -1 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 149 |  | -1 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE | FALSE | 355 | 134 |  | -1 |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE | FALSE | 355 | 99 |  | -1 |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE | FALSE | 355 | 115 |  | -1 |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE | FALSE | 355 | 59 |  | -1 |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | FALSE | 355 | 115 |  | -1 |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE | FALSE | 355 | 97 |  | -1 |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE | FALSE | 355 | 60 |  | -1 |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 70 |  | -1 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE | FALSE | 355 | 70 |  | -1 |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 115 |  | -1 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 90 |  | -1 |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | FALSE | 355 | 60 |  | -1 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 70 |  | -1 |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE | FALSE | 355 | 81 |  | -1 |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE | FALSE | 355 | 60 |  | -1 |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE | FALSE | 355 | 73 |  | -1 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE | FALSE | 355 | 81 |  | -1 |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 355 | 55 |  | -1 |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE | FALSE | 355 | 45 |  | -1 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
Zero Days Float
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | TRUE | 0 |  | -1 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
Hidden Duration (Planned)
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of their original durations.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links (>2) that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 0 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline finish dates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 24
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 207
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 57 | Pour 2nd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 24
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 24
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 207
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 24
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 24
FALSE |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 62 | Pour 3rd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 24
FALSE |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 24
FALSE |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 40
FALSE |  | 65 | Form roof slab including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 24
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 24
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 67 | Pour roof slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 24
FALSE |  | 68 | Cure roof slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 24
FALSE |  | 69 | Strip forms from roof slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 24
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 24
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 24
FALSE |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 24
FALSE |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 59
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 24
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 96 | Install interior doors and hardware | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 29
FALSE |  | 99 | Install millwork and wood trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 24
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 24
FALSE |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE |  | 107 | Install hardware and accessories | Project5_FX05_TamperLogicDrop | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 29
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 42
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 42
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE |  | 138 | Complete elevator inspection and certification | Project5_FX05_TamperLogicDrop | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 140 | Perform local building agency inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 29
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
FALSE | FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
Tasks & Milestones (To Go)
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 471 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | FALSE | 471 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 472 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | FALSE | 471 | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned
FALSE |  | FALSE | 293 | 93 |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 24 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 293 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 293 | 0 |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 293 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 61 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 40 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 67 | Pour roof slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 68 | Cure roof slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 69 | Strip forms from roof slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 59 | 0 |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 96 | Install interior doors and hardware | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 99 | Install millwork and wood trim | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX05_TamperLogicDrop | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
Normal Tasks (To-Go)
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 471 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | FALSE | 471 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 472 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | FALSE | 471 | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned
FALSE |  | FALSE | 293 | 93 |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 24 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 293 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 293 | 0 |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 293 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 61 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 40 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 67 | Pour roof slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 68 | Cure roof slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 69 | Strip forms from roof slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 59 | 0 |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 96 | Install interior doors and hardware | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 99 | Install millwork and wood trim | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX05_TamperLogicDrop | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
Normal Tasks (To-Go, In Progress)
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 471 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | FALSE | 471 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 472 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | FALSE | 471 | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned
FALSE |  | FALSE | 293 | 93 |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 24 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 293 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 293 | 0 |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 293 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 242 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 61 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 207 | 0 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 40 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 67 | Pour roof slab | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 68 | Cure roof slab | Project5_FX05_TamperLogicDrop | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 69 | Strip forms from roof slab | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 59 | 0 |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 96 | Install interior doors and hardware | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 99 | Install millwork and wood trim | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 24 | 0 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX05_TamperLogicDrop | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX05_TamperLogicDrop | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX05_TamperLogicDrop | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 471 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | FALSE | 471 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 472 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 471 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
FALSE |  | FALSE | 293 |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE |  | FALSE | 24 |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36
FALSE |  | FALSE | 293 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | FALSE | 293 |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | FALSE | 293 |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | FALSE | 61 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 207 |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 57 | Pour 2nd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 207 |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 60 | Form 3rd floor including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 62 | Pour 3rd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | FALSE | 207 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | FALSE | 40 |  | 64 | Strip forms from 3rd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 65 | Form roof slab including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 149 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 67 | Pour roof slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 68 | Cure roof slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 69 | Strip forms from roof slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 78 | Install exterior sheathing and metal studs | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | FALSE | 99 |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | FALSE | 59 |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 90 |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 96 | Install interior doors and hardware | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 99 | Install millwork and wood trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | FALSE | 73 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 107 | Install hardware and accessories | Project5_FX05_TamperLogicDrop | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | FALSE | 34 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 138 | Complete elevator inspection and certification | Project5_FX05_TamperLogicDrop | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 140 | Perform local building agency inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 471 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | FALSE | 471 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 472 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 471 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
FALSE |  | FALSE | 293 |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE |  | FALSE | 24 |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36
FALSE |  | FALSE | 293 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | FALSE | 293 |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | FALSE | 293 |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 242 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | FALSE | 61 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 207 |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 57 | Pour 2nd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 207 |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 60 | Form 3rd floor including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 62 | Pour 3rd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | FALSE | 207 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | FALSE | 40 |  | 64 | Strip forms from 3rd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 65 | Form roof slab including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 149 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 67 | Pour roof slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 68 | Cure roof slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 69 | Strip forms from roof slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 78 | Install exterior sheathing and metal studs | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | FALSE | 99 |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | FALSE | 59 |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 90 |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 96 | Install interior doors and hardware | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 99 | Install millwork and wood trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | FALSE | 73 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | FALSE | 24 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 107 | Install hardware and accessories | Project5_FX05_TamperLogicDrop | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | FALSE | 34 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 138 | Complete elevator inspection and certification | Project5_FX05_TamperLogicDrop | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 140 | Perform local building agency inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Critical Path (Tasks & Milestones)
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
Critical Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned
Critical Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Planned | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Near-Critical (<10 Days Float)
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Near CP - Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX05_TamperLogicDrop | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX05_TamperLogicDrop | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24
BEI - Complete Tasks
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX05_TamperLogicDrop | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX05_TamperLogicDrop | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX05_TamperLogicDrop | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX05_TamperLogicDrop | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX05_TamperLogicDrop | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX05_TamperLogicDrop | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX05_TamperLogicDrop | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX05_TamperLogicDrop | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
FALSE | FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
FALSE | FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE | FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 59
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
Hidden Duration (Planned)
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 0 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Actual Start | Actual Finish | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE |  |  |  | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 471
FALSE |  |  |  | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
FALSE |  |  |  | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 0 | 2 |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE | None | FALSE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE | MandatoryStart | TRUE | 3 | 0 |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 0 | 2 |  | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE | MandatoryStart | TRUE | 3 | 0 |  | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Hard Constraints
Number of activities with hard or two-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Activities with Lags
Number of activities that have lag in their predecessors. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FF Predecessors
Number of activities with Finish-to-Finish (FF) logic links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Obtain building permits | Project5_FX05_TamperLogicDrop | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX05_TamperLogicDrop | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 471
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 24
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 207
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 57 | Pour 2nd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 24
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 24
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 207
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 24
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 24
FALSE |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 62 | Pour 3rd floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 24
FALSE |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 24
FALSE |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 40
FALSE |  | 65 | Form roof slab including all floor openings | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 24
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 24
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 67 | Pour roof slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 24
FALSE |  | 68 | Cure roof slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 24
FALSE |  | 69 | Strip forms from roof slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 24
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 24
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 24
FALSE |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 24
FALSE |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 59
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 24
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 96 | Install interior doors and hardware | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 29
FALSE |  | 99 | Install millwork and wood trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 24
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 24
FALSE |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE |  | 107 | Install hardware and accessories | Project5_FX05_TamperLogicDrop | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 29
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 42
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 42
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE |  | 138 | Complete elevator inspection and certification | Project5_FX05_TamperLogicDrop | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 140 | Perform local building agency inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 29
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Merge Hotspot
Number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX05_TamperLogicDrop | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 24
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 207
FALSE |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Diverge Hotspot
Number of activities with a high number of successor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 24
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 24
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 24
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 24
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX05_TamperLogicDrop | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 24
FALSE |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 24
FALSE |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
Open Ends with Constraints
Activities where missing logic is accounted for through the use of a constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
Open Ends w/o Constraints
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
Open Ends
Number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
1. Logic
Number of activities that are missing a predecessor, a successor or both. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | 106 | Install building carpet | Project5_FX05_TamperLogicDrop | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 24
FALSE |  | 136 | Substantial completion date | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 34
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX05_TamperLogicDrop | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
3. Lags
Number of lags in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
5. Hard Constraint
Number of activities with hard or two-way constraints. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-06-16 | Normal | Planned | 0 | 0
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 471
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX05_TamperLogicDrop | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 207
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 207
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 70 | Form 1st floor | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 74 | Pour 1st floor slab | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 207
FALSE |  | 75 | Cure 1st floor slab | Project5_FX05_TamperLogicDrop | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 86 | Clean toilet room tile | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 97 | Install store front doors and hardware | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 59
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 115
FALSE |  | 130 | Install duct in building chase | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX05_TamperLogicDrop | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX05_TamperLogicDrop | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX05_TamperLogicDrop | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 103 | Install ceiling grid | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX05_TamperLogicDrop | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
9. Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-03-02 | 2026-03-13 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 471
FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX05_TamperLogicDrop | 2 | 2 | 2026-03-16 | 2026-03-17 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 471
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-16 | 2026-03-16 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 472
FALSE |  | 145 | Issue final request for payment | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-03-18 | 2026-03-18 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 471
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX05_TamperLogicDrop | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX05_TamperLogicDrop | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX05_TamperLogicDrop | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX05_TamperLogicDrop | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX05_TamperLogicDrop | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX05_TamperLogicDrop | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX05_TamperLogicDrop | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX05_TamperLogicDrop | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX05_TamperLogicDrop | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX05_TamperLogicDrop | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX05_TamperLogicDrop | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX05_TamperLogicDrop | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 293
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX05_TamperLogicDrop | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 24
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 293
FALSE |  | 37 | Form elevator pit walls | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 293
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 293
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX05_TamperLogicDrop | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 24
FALSE |  | 39 | Pour column piers and foundations | Project5_FX05_TamperLogicDrop | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 24
FALSE |  | 42 | Cure piers and foundations | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 24
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 24
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 24
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX05_TamperLogicDrop | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 242
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 24
FALSE |  | 43 | Strip wall forms | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 242
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX05_TamperLogicDrop | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 242
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX05_TamperLogicDrop | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 242
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 24
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX05_TamperLogicDrop | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 61
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX05_TamperLogicDrop | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 53 | Touch-up paint on steel | Project5_FX05_TamperLogicDrop | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 24

## Project5_FX06_TamperBaseli3
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View | Project5_FX06_TamperBaselineShift: Detailed View
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | 0 | 220 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | 0 | 128 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 20 | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | 0 | 37 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | 0 | 47 | Planned
FALSE |  | TRUE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | 0 | 0 | Planned
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | FALSE | None | 1 | 0 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | FALSE | None | 1 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | FALSE | None | 1 | 0 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 20 | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | FALSE | None | 1 | 0 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | TRUE | None | 2 | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Hard Constraints
Number of activities with hard or two-way constraints.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0 | 0
High Float 10% of Rem Project Duration
Number of activities that have a total float value higher than 10% of the remaining duration of the project. This number should not exceed 20%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 368 | 306 |  | -1 |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE | FALSE | 368 | 306 |  | -1 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE | FALSE | 368 | 66 |  | -1 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 149 |  | -1 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 99 |  | -1 |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 64 |  | -1 |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 128 |  | -1 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 90 |  | -1 |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE | FALSE | 368 | 73 |  | -1 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 10%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 368 | 306 |  | -1 |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE | FALSE | 368 | 306 |  | -1 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 306 |  | -1 |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 255 |  | -1 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE | FALSE | 368 | 66 |  | -1 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 202 |  | -1 |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 135 |  | -1 |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE | FALSE | 368 | 220 |  | -1 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE | FALSE | 368 | 45 |  | -1 |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 149 |  | -1 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE | FALSE | 368 | 134 |  | -1 |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE | FALSE | 368 | 99 |  | -1 |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 64 |  | -1 |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE | FALSE | 368 | 115 |  | -1 |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE | FALSE | 368 | 97 |  | -1 |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 128 |  | -1 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 90 |  | -1 |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 70 |  | -1 |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE | FALSE | 368 | 60 |  | -1 |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE | FALSE | 368 | 73 |  | -1 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 81 |  | -1 |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 55 |  | -1 |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE | FALSE | 368 | 45 |  | -1 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE | FALSE | 368 | 47 |  | -1 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
Zero Days Float
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | TRUE | 0 |  | -1 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
Hidden Duration (Planned)
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of their original durations.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links (>2) that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline finish dates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 29
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 57 | Pour 2nd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 29
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 29
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 62 | Pour 3rd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 29
FALSE |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 29
FALSE |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE |  | 65 | Form roof slab including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 67 | Pour roof slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 29
FALSE |  | 68 | Cure roof slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 29
FALSE |  | 69 | Strip forms from roof slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 29
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 29
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 29
FALSE |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 29
FALSE |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 29
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 96 | Install interior doors and hardware | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 34
FALSE |  | 99 | Install millwork and wood trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 107 | Install hardware and accessories | Project5_FX06_TamperBaselineShift | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 29
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 42
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 42
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 138 | Complete elevator inspection and certification | Project5_FX06_TamperBaselineShift | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 140 | Perform local building agency inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 29
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 1
FALSE |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
Tasks & Milestones (To Go)
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 306 | 93 |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 29 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 306 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 66 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 67 | Pour roof slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 68 | Cure roof slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 69 | Strip forms from roof slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 64 | 0 |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 128 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 96 | Install interior doors and hardware | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX06_TamperBaselineShift | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 47 | 0 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Normal Tasks (To-Go)
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 306 | 93 |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 29 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 306 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 66 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 67 | Pour roof slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 68 | Cure roof slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 69 | Strip forms from roof slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 64 | 0 |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 128 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 96 | Install interior doors and hardware | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX06_TamperBaselineShift | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 47 | 0 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Normal Tasks (To-Go, In Progress)
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 306 | 93 |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | Standard | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress
FALSE |  | FALSE | 29 | 36 |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | Standard | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress
FALSE |  | FALSE | 306 | 0 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned
FALSE |  | FALSE | 306 | 0 |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | Standard | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | Standard | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | Standard | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned
FALSE |  | FALSE | 255 | 0 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 66 | 0 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned
FALSE |  | FALSE | 202 | 0 |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 57 | Pour 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 60 | Form 3rd floor including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 135 | 0 |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 62 | Pour 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned
FALSE |  | FALSE | 220 | 0 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 65 | Form roof slab including all floor openings | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 149 | 0 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 67 | Pour roof slab | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 68 | Cure roof slab | Project5_FX06_TamperBaselineShift | Standard | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 69 | Strip forms from roof slab | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 78 | Install exterior sheathing and metal studs | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned
FALSE |  | FALSE | 134 | 0 |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned
FALSE |  | FALSE | 99 | 0 |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned
FALSE |  | FALSE | 64 | 0 |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned
FALSE |  | FALSE | 115 | 0 |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned
FALSE |  | FALSE | 97 | 0 |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | Standard | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 128 | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 90 | 0 |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 70 | 0 |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned
FALSE |  | FALSE | 34 | 0 |  | 96 | Install interior doors and hardware | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 99 | Install millwork and wood trim | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | Standard | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned
FALSE |  | FALSE | 60 | 0 |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | Standard | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned
FALSE |  | FALSE | 73 | 0 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned
FALSE |  | FALSE | 81 | 0 |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 55 | 0 |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | Standard | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 107 | Install hardware and accessories | Project5_FX06_TamperBaselineShift | Standard | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 45 | 0 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned
FALSE |  | FALSE | 42 | 0 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | Standard | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned
FALSE |  | FALSE | 47 | 0 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 138 | Complete elevator inspection and certification | Project5_FX06_TamperBaselineShift | Standard | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 140 | Perform local building agency inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned
FALSE |  | FALSE | 29 | 0 |  | 141 | Perform Fire Marshal's inspection | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 306 |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE |  | FALSE | 29 |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36
FALSE |  | FALSE | 306 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | FALSE | 66 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 57 | Pour 2nd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 60 | Form 3rd floor including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 62 | Pour 3rd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 65 | Form roof slab including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 149 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 67 | Pour roof slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 68 | Cure roof slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 69 | Strip forms from roof slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 78 | Install exterior sheathing and metal studs | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | FALSE | 99 |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | FALSE | 64 |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 128 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 90 |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 34 |  | 96 | Install interior doors and hardware | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 99 | Install millwork and wood trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | FALSE | 73 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | FALSE | 37 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 107 | Install hardware and accessories | Project5_FX06_TamperBaselineShift | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | FALSE | 47 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 138 | Complete elevator inspection and certification | Project5_FX06_TamperBaselineShift | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 140 | Perform local building agency inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 141 | Perform Fire Marshal's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 306 |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93
FALSE |  | FALSE | 29 |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36
FALSE |  | FALSE | 306 |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0
FALSE |  | FALSE | 306 |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 255 |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0
FALSE |  | FALSE | 66 |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0
FALSE |  | FALSE | 202 |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 57 | Pour 2nd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 60 | Form 3rd floor including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 135 |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 62 | Pour 3rd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0
FALSE |  | FALSE | 220 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 65 | Form roof slab including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 149 |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 67 | Pour roof slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 68 | Cure roof slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 69 | Strip forms from roof slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 78 | Install exterior sheathing and metal studs | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0
FALSE |  | FALSE | 134 |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0
FALSE |  | FALSE | 99 |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0
FALSE |  | FALSE | 64 |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0
FALSE |  | FALSE | 115 |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0
FALSE |  | FALSE | 97 |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 128 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 90 |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 70 |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0
FALSE |  | FALSE | 34 |  | 96 | Install interior doors and hardware | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 99 | Install millwork and wood trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0
FALSE |  | FALSE | 60 |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0
FALSE |  | FALSE | 73 |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0
FALSE |  | FALSE | 81 |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 55 |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0
FALSE |  | FALSE | 37 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 107 | Install hardware and accessories | Project5_FX06_TamperBaselineShift | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 108 | Complete interior and exterior sod and plantings | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 45 |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0
FALSE |  | FALSE | 42 |  | 109 | Pave, curb, and stripe parking lot | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0
FALSE |  | FALSE | 47 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 138 | Complete elevator inspection and certification | Project5_FX06_TamperBaselineShift | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 140 | Perform local building agency inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0
FALSE |  | FALSE | 29 |  | 141 | Perform Fire Marshal's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Critical Path (Tasks & Milestones)
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Critical Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | Standard | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | Standard | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | Standard | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | Standard | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned
Critical Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Planned | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Near-Critical (<10 Days Float)
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
Near CP - Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX06_TamperBaselineShift | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX06_TamperBaselineShift | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Complete Tasks
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX06_TamperBaselineShift | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX06_TamperBaselineShift | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX06_TamperBaselineShift | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX06_TamperBaselineShift | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX06_TamperBaselineShift | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX06_TamperBaselineShift | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 7 | Obtain building permits | Project5_FX06_TamperBaselineShift | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX06_TamperBaselineShift | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
High Float 44d
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE | FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE | FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE | FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE | FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE | FALSE |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE | FALSE |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | FALSE |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE | FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE | FALSE |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE | FALSE |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE | FALSE |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE | FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE | FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE | FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | FALSE |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE | FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE | FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE | FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE | FALSE |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE | FALSE |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE | FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE | FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
Number of Lags
Total number of activities that have lags in their predecessors. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
Hidden Duration (Planned)
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 1 | 5 | 5 | FALSE | 97 |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE | None | TRUE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE | None | TRUE | 2 | 0 |  | 0 |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Hard Constraints
Number of activities with hard or two-way constraints.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0 | 0
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Activities with Lags
Number of activities that have lag in their predecessors. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FF Predecessors
Number of activities with Finish-to-Finish (FF) logic links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 7 | Obtain building permits | Project5_FX06_TamperBaselineShift | 4 | 0 | 2026-03-05 | 2026-03-10 | 2026-03-05 | 2026-03-10 | Normal | Complete | 100 | 0
FALSE |  | 9 | Submit monthly requests for payment | Project5_FX06_TamperBaselineShift | 1 | 0 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Normal | Complete | 100 | 0
FALSE |  | 19 | Install temporary power | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 20 | Install temporary water service | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-05 | 2026-03-06 | 2026-03-05 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 21 | Set up site office | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-09 | 2026-03-11 | 2026-03-09 | 2026-03-11 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 4 | Submit bond and insurance documents | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-25 | 2026-03-26 | 2026-03-25 | 2026-03-26 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 5 | Prepare and submit project schedule | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-27 | 2026-03-30 | 2026-03-27 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 29
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 57 | Pour 2nd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-02-12 | 2027-02-17 | 2026-09-01 | 2026-09-04 | Normal | Planned | 0 | 29
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 29
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 60 | Form 3rd floor including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-01 | 2027-03-05 | 2026-09-16 | 2026-09-22 | Normal | Planned | 0 | 29
FALSE |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 62 | Pour 3rd floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-08 | 2027-03-11 | 2026-09-23 | 2026-09-28 | Normal | Planned | 0 | 29
FALSE |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 29
FALSE |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE |  | 65 | Form roof slab including all floor openings | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-23 | 2027-03-29 | 2026-10-08 | 2026-10-14 | Normal | Planned | 0 | 29
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 67 | Pour roof slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-30 | 2027-04-02 | 2026-10-15 | 2026-10-20 | Normal | Planned | 0 | 29
FALSE |  | 68 | Cure roof slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-04-05 | 2027-04-13 | 2026-10-21 | 2026-10-29 | Normal | Planned | 0 | 29
FALSE |  | 69 | Strip forms from roof slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-04-14 | 2027-04-15 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 29
FALSE |  | 78 | Install exterior sheathing and metal studs | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-04-16 | 2027-05-06 | 2026-11-03 | 2026-11-23 | Normal | Planned | 0 | 29
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 29
FALSE |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 29
FALSE |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 29
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 96 | Install interior doors and hardware | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-08-20 | 2027-09-02 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 34
FALSE |  | 99 | Install millwork and wood trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 29
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 107 | Install hardware and accessories | Project5_FX06_TamperBaselineShift | 26 | 26 | 2027-10-08 | 2027-11-12 | 2027-05-11 | 2027-05-31 | Normal | Planned | 0 | 29
FALSE |  | 108 | Complete interior and exterior sod and plantings | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 42
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 109 | Pave, curb, and stripe parking lot | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-22 | 2027-11-04 | 2027-05-25 | 2027-06-07 | Normal | Planned | 0 | 42
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 138 | Complete elevator inspection and certification | Project5_FX06_TamperBaselineShift | 3 | 3 | 2027-11-19 | 2027-11-23 | 2027-06-14 | 2027-06-16 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 140 | Perform local building agency inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-25 | 2027-11-25 | 2027-06-18 | 2027-06-18 | Normal | Planned | 0 | 29
FALSE |  | 141 | Perform Fire Marshal's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-26 | 2027-11-26 | 2027-06-21 | 2027-06-21 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0 | 0
FALSE |  | 142 | Complete punch list items from all inspections | Project5_FX06_TamperBaselineShift | 10 | 10 | 2028-01-07 | 2028-01-20 | 2027-06-22 | 2027-07-05 | Normal | Planned | 0 | 0
FALSE |  | 143 | Obtain certificate of occupancy | Project5_FX06_TamperBaselineShift | 2 | 2 | 2028-01-21 | 2028-01-24 | 2027-07-06 | 2027-07-07 | Normal | Planned | 0 | 0
FALSE |  | 144 | Issue final completion documents including warranties | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-21 | 2028-01-21 | 2027-07-08 | 2027-07-08 | Normal | Planned | 0 | 1
FALSE |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Merge Hotspot
Number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 55 | Form 2nd floor including all floor openings | Project5_FX06_TamperBaselineShift | 17 | 17 | 2027-01-20 | 2027-02-11 | 2026-08-25 | 2026-08-31 | Normal | Planned | 0 | 29
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
FALSE |  | 139 | Perform architect's inspection | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-24 | 2027-11-24 | 2027-06-17 | 2027-06-17 | Normal | Planned | 0 | 29
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0 | 0
Diverge Hotspot
Number of activities with a high number of successor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 58 | Cure 2nd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-02-18 | 2027-02-26 | 2026-09-07 | 2026-09-15 | Normal | Planned | 0 | 29
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 63 | Cure 3rd floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-12 | 2027-03-22 | 2026-09-29 | 2026-10-07 | Normal | Planned | 0 | 29
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 82 | Install exterior masonry work | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-05-07 | 2027-06-10 | 2026-11-24 | 2026-12-28 | Normal | Planned | 0 | 29
FALSE |  | 94 | Install window wall aluminum and glass | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-06-11 | 2027-07-15 | 2026-12-29 | 2027-02-01 | Normal | Planned | 0 | 29
FALSE |  | 95 | Install interior stud walls and drywall | Project5_FX06_TamperBaselineShift | 25 | 25 | 2027-07-16 | 2027-08-19 | 2027-02-02 | 2027-03-08 | Normal | Planned | 0 | 29
FALSE |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
Logic Hotspot™
Number of activities with a high number of predecessors as well as a high number of successors.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 135 | Remove debris from building and do final clean-up | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-11-15 | 2027-11-18 | 2027-06-08 | 2027-06-11 | Normal | Planned | 0 | 29
Open Ends w/o Constraints
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
Open Ends
Number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 3 | Receive notice to proceed and sign contract | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-03-02 | 2026-03-04 | 2026-03-02 | 2026-03-04 | Normal | Complete | 100 | 0
FALSE |  | 6 | Prepare and submit schedule of values | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
1. Logic
Number of activities that are missing a predecessor, a successor or both. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 106 | Install building carpet | Project5_FX06_TamperBaselineShift | 41 | 41 | 2027-10-08 | 2027-12-03 | 2027-05-11 | 2027-06-07 | Normal | Planned | 0 | 37
FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
FALSE |  | 145 | Issue final request for payment | Project5_FX06_TamperBaselineShift | 1 | 1 | 2028-01-25 | 2028-01-25 | 2027-07-09 | 2027-07-09 | Normal | Planned | 0 | 0
3. Lags
Number of lags in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
5. Hard Constraint
Number of activities with hard or two-way constraints. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 131 | Set HVAC trim and test and balance system | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-12-10 | 2028-01-06 | 2027-05-20 | 2027-08-15 | Normal | Planned | 0 | 0
6. High Float
Number of activities with total float greater than 2 months. Should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 27 | 27 | 2026-11-23 | 2026-12-29 | 2026-08-18 | 2026-08-31 | Normal | Planned | 0 | 202
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 81 | Lay masonry at core, mechanical, and toilets | Project5_FX06_TamperBaselineShift | 20 | 20 | 2026-12-30 | 2027-01-26 | 2026-09-01 | 2026-09-28 | Normal | Planned | 0 | 202
FALSE |  | 111 | Set elevator equipment in shafts | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-01-27 | 2027-02-23 | 2026-09-29 | 2026-10-26 | Normal | Planned | 0 | 220
FALSE |  | 127 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-01-27 | 2027-02-09 | 2026-09-29 | 2026-10-12 | Normal | Planned | 0 | 202
FALSE |  | 112 | Set equipment in mechanical room | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-02-24 | 2027-03-09 | 2026-10-27 | 2026-11-09 | Normal | Planned | 0 | 220
FALSE |  | 59 | Strip forms from 2nd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-01 | 2027-03-02 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 134
FALSE |  | 70 | Form 1st floor | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 71 | Install electrical underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 72 | Install plumbing underground | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-03-03 | 2027-03-09 | 2026-10-01 | 2026-10-07 | Normal | Planned | 0 | 134
FALSE |  | 73 | Install rebar and in-floor utilities | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-03 | 2027-03-08 | 2026-09-25 | 2026-09-30 | Normal | Planned | 0 | 135
FALSE |  | 74 | Pour 1st floor slab | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-03-10 | 2027-03-15 | 2026-10-08 | 2026-10-13 | Normal | Planned | 0 | 134
FALSE |  | 113 | Test and align doors and equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-03-10 | 2027-03-23 | 2026-11-10 | 2026-11-23 | Normal | Planned | 0 | 220
FALSE |  | 75 | Cure 1st floor slab | Project5_FX06_TamperBaselineShift | 7 | 7 | 2027-03-16 | 2027-03-24 | 2026-10-19 | 2026-10-27 | Normal | Planned | 0 | 134
FALSE |  | 64 | Strip forms from 3rd floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-23 | 2027-03-24 | 2026-10-15 | 2026-10-16 | Normal | Planned | 0 | 45
FALSE |  | 76 | Strip forms from 1st floor slab | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-03-25 | 2027-03-26 | 2026-11-03 | 2026-11-04 | Normal | Planned | 0 | 134
FALSE |  | 80 | Rough-in plumbing at toilets and masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 120 | Rough-in electrical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 134
FALSE |  | 128 | Rough-in mechanical in masonry walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-03-29 | 2027-04-23 | 2026-11-05 | 2026-12-02 | Normal | Planned | 0 | 149
FALSE |  | 84 | Install tile in toilet rooms | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-04-26 | 2027-05-07 | 2026-12-03 | 2026-12-16 | Normal | Planned | 0 | 134
FALSE |  | 86 | Clean toilet room tile | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-05-10 | 2027-05-14 | 2026-12-17 | 2026-12-23 | Normal | Planned | 0 | 134
FALSE |  | 83 | Install roof drains | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-11 | 2027-06-14 | 2027-01-04 | 2027-01-05 | Normal | Planned | 0 | 99
FALSE |  | 85 | Clean masonry | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-11 | 2027-06-17 | 2026-12-29 | 2027-01-04 | Normal | Planned | 0 | 115
FALSE |  | 88 | Install flashing at parapet walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-06-11 | 2027-06-16 | 2026-12-29 | 2027-01-01 | Normal | Planned | 0 | 97
FALSE |  | 97 | Install store front doors and hardware | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-06-11 | 2027-07-01 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 64
FALSE |  | 89 | Pour lightweight concrete roof fill | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-06-17 | 2027-06-18 | 2027-01-06 | 2027-01-07 | Normal | Planned | 0 | 97
FALSE |  | 116 | Tie-in fire line riser and set valves | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-06-18 | 2027-07-01 | 2027-01-05 | 2027-01-18 | Normal | Planned | 0 | 115
FALSE |  | 90 | Install seamless roofing material | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-06-28 | 2027-07-02 | 2027-01-15 | 2027-01-21 | Normal | Planned | 0 | 97
FALSE |  | 91 | Spread stone ballast on seamless roof | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-07-05 | 2027-07-09 | 2027-01-22 | 2027-01-28 | Normal | Planned | 0 | 97
FALSE |  | 92 | Set rooftop equipment | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-12 | 2027-07-23 | 2027-01-29 | 2027-02-11 | Normal | Planned | 0 | 97
FALSE |  | 101 | Install conduit at ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-02 | 2027-02-22 | Normal | Planned | 0 | 60
FALSE |  | 115 | Rough-in plumbing in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-02 | 2027-03-01 | Normal | Planned | 0 | 70
FALSE |  | 121 | Rough-in electrical in drywall walls | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-07-16 | 2027-08-12 | 2027-02-23 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 129 | Rough-in mechanical in drywall walls | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-07-16 | 2027-07-29 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 128
FALSE |  | 130 | Install duct in building chase | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-07-16 | 2027-08-05 | 2027-02-12 | 2027-03-04 | Normal | Planned | 0 | 90
FALSE |  | 122 | Pull wire in conduit and set area transformers | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-06 | 2027-08-26 | 2027-03-23 | 2027-04-12 | Normal | Planned | 0 | 60
FALSE |  | 117 | Set plumbing fixtures and trim | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-13 | 2027-09-02 | 2027-03-02 | 2027-03-22 | Normal | Planned | 0 | 70
FALSE |  | 102 | Install duct in ceiling plenum space | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-20 | 2027-09-09 | 2027-03-09 | 2027-03-29 | Normal | Planned | 0 | 55
FALSE |  | 133 | Install hard tile flooring in common areas | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-08-20 | 2027-08-26 | 2027-03-09 | 2027-03-15 | Normal | Planned | 0 | 81
FALSE |  | 123 | Install and terminate electrical devices | Project5_FX06_TamperBaselineShift | 15 | 15 | 2027-08-27 | 2027-09-16 | 2027-04-13 | 2027-05-03 | Normal | Planned | 0 | 60
FALSE |  | 124 | Make electrical terminations for HVAC equipment | Project5_FX06_TamperBaselineShift | 2 | 2 | 2027-08-27 | 2027-08-30 | 2027-05-18 | 2027-05-19 | Normal | Planned | 0 | 73
FALSE |  | 134 | Clean hard tile floors | Project5_FX06_TamperBaselineShift | 4 | 4 | 2027-08-27 | 2027-09-01 | 2027-03-16 | 2027-03-19 | Normal | Planned | 0 | 81
FALSE |  | 103 | Install ceiling grid | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-10 | 2027-09-23 | 2027-03-30 | 2027-04-12 | Normal | Planned | 0 | 55
FALSE |  | 104 | Install ceiling tile | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-04-13 | 2027-04-26 | Normal | Planned | 0 | 55
FALSE |  | 105 | Hang wallpaper | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 55
FALSE |  | 125 | Install light fixtures - test and clean | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-09-24 | 2027-10-07 | 2027-05-04 | 2027-05-17 | Normal | Planned | 0 | 55
FALSE |  | 118 | Flush, test, and clean piping and fixtures | Project5_FX06_TamperBaselineShift | 10 | 10 | 2027-10-08 | 2027-10-21 | 2027-05-11 | 2027-05-24 | Normal | Planned | 0 | 45
FALSE |  | 136 | Substantial completion date | Project5_FX06_TamperBaselineShift | 1 | 1 | 2027-11-19 | 2027-11-19 | 2027-06-14 | 2027-06-14 | Normal | Planned | 0 | 47
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Submit shop drawings and order long lead items - steel | Project5_FX06_TamperBaselineShift | 16 | 0 | 2026-03-06 | 2026-03-27 | 2026-03-06 | 2026-03-19 | Normal | Complete | 100 | 0
FALSE |  | 22 | Set line and grade benchmarks | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-03-12 | 2026-03-25 | 2026-03-12 | 2026-03-16 | Normal | Complete | 100 | 0
FALSE |  | 23 | Prepare site - lay down yard and temporary fencing | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-03-26 | 2026-03-27 | 2026-03-17 | 2026-03-18 | Normal | Complete | 100 | 0
FALSE |  | 17 | Detail, fabricate and deliver steel | Project5_FX06_TamperBaselineShift | 60 | 0 | 2026-03-30 | 2026-06-19 | 2026-03-20 | 2026-06-11 | Normal | Complete | 100 | 0
FALSE |  | 8 | Submit preliminary shop drawings | Project5_FX06_TamperBaselineShift | 23 | 0 | 2026-04-02 | 2026-05-04 | 2026-03-11 | 2026-03-24 | Normal | Complete | 100 | 0
FALSE |  | 25 | Clear and grub site | Project5_FX06_TamperBaselineShift | 3 | 0 | 2026-04-06 | 2026-04-08 | 2026-03-19 | 2026-03-23 | Normal | Complete | 100 | 0
FALSE |  | 26 | Stone site access and temporary parking area | Project5_FX06_TamperBaselineShift | 2 | 0 | 2026-04-13 | 2026-04-14 | 2026-03-24 | 2026-03-25 | Normal | Complete | 100 | 0
FALSE |  | 27 | Rough grade site (cut and fill) | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-04-15 | 2026-04-21 | 2026-03-26 | 2026-04-01 | Normal | Complete | 100 | 0
FALSE |  | 28 | Install storm drainage | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-04-22 | 2026-05-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 29 | Install exterior fire line and building fire riser | Project5_FX06_TamperBaselineShift | 43 | 0 | 2026-04-22 | 2026-06-19 | 2026-04-02 | 2026-04-15 | Normal | Complete | 100 | 0
FALSE |  | 12 | Submit shop drawings and order long lead items - roofing | Project5_FX06_TamperBaselineShift | 19 | 0 | 2026-05-05 | 2026-05-29 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 13 | Submit shop drawings and order long lead items - elevator | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 14 | Submit shop drawings and order long lead items - plumbing | Project5_FX06_TamperBaselineShift | 9 | 0 | 2026-05-05 | 2026-05-15 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 16 | Submit shop drawings and order long lead items - HVAC | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-05-05 | 2026-05-18 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 15 | Submit shop drawings and order long lead items - electric | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-08 | 2026-06-19 | 2026-03-25 | 2026-04-07 | Normal | Complete | 100 | 0
FALSE |  | 30 | Perform final site grading | Project5_FX06_TamperBaselineShift | 10 | 0 | 2026-06-22 | 2026-07-03 | 2026-04-16 | 2026-04-29 | Normal | Complete | 100 | 0
FALSE |  | 31 | Erect building batter boards and layout building | Project5_FX06_TamperBaselineShift | 20 | 0 | 2026-07-06 | 2026-07-31 | 2026-04-30 | 2026-05-06 | Normal | Complete | 100 | 0
FALSE |  | 33 | Excavate foundations | Project5_FX06_TamperBaselineShift | 5 | 0 | 2026-08-03 | 2026-08-07 | 2026-05-07 | 2026-05-20 | Normal | Complete | 100 | 0
FALSE |  | 34 | Excavate elevator pit | Project5_FX06_TamperBaselineShift | 15 | 1 | 2026-08-10 | 2026-08-28 | 2026-05-21 | 2026-05-22 | Normal | InProgress | 93 | 306
FALSE |  | 35 | Form column piers and spread foundations | Project5_FX06_TamperBaselineShift | 25 | 16 | 2026-08-17 | 2026-09-18 | 2026-05-21 | 2026-05-26 | Normal | InProgress | 36 | 29
FALSE |  | 36 | Rough-in electric and plumbing in elevator | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-08-31 | 2026-09-03 | 2026-05-25 | 2026-05-28 | Normal | Planned | 0 | 306
FALSE |  | 37 | Form elevator pit walls | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-04 | 2026-09-09 | 2026-06-02 | 2026-06-05 | Normal | Planned | 0 | 306
FALSE |  | 40 | Pour concrete elevator walls | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-06-09 | 2026-06-09 | Normal | Planned | 0 | 306
FALSE |  | 38 | Set reinforcing and anchor bolts | Project5_FX06_TamperBaselineShift | 4 | 4 | 2026-09-21 | 2026-09-24 | 2026-05-27 | 2026-06-01 | Normal | Planned | 0 | 29
FALSE |  | 39 | Pour column piers and foundations | Project5_FX06_TamperBaselineShift | 21 | 21 | 2026-09-25 | 2026-10-23 | 2026-06-02 | 2026-06-08 | Normal | Planned | 0 | 29
FALSE |  | 42 | Cure piers and foundations | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-10-26 | 2026-11-03 | 2026-06-09 | 2026-06-17 | Normal | Planned | 0 | 29
FALSE |  | 44 | Strip column piers and foundation forms | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-11-04 | 2026-11-06 | 2026-06-18 | 2026-06-22 | Normal | Planned | 0 | 29
FALSE |  | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-11-09 | 2026-11-20 | 2026-06-23 | 2026-07-06 | Normal | Planned | 0 | 29
FALSE |  | 41 | Cure elevator wall concrete | Project5_FX06_TamperBaselineShift | 7 | 7 | 2026-11-23 | 2026-12-01 | 2026-06-23 | 2026-07-01 | Normal | Planned | 0 | 255
FALSE |  | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 17 | 17 | 2026-11-23 | 2026-12-15 | 2026-07-07 | 2026-07-20 | Normal | Planned | 0 | 29
FALSE |  | 43 | Strip wall forms | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-02 | 2026-12-02 | 2026-07-02 | 2026-07-02 | Normal | Planned | 0 | 255
FALSE |  | 45 | Install pneumatic tube in elevator pit | Project5_FX06_TamperBaselineShift | 3 | 3 | 2026-12-03 | 2026-12-07 | 2026-07-03 | 2026-07-07 | Normal | Planned | 0 | 255
FALSE |  | 46 | Prepare and pour concrete floor in elevator pit | Project5_FX06_TamperBaselineShift | 1 | 1 | 2026-12-08 | 2026-12-08 | 2026-07-08 | 2026-07-08 | Normal | Planned | 0 | 255
FALSE |  | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-16 | 2026-12-29 | 2026-07-21 | 2026-08-03 | Normal | Planned | 0 | 29
FALSE |  | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Project5_FX06_TamperBaselineShift | 5 | 5 | 2026-12-16 | 2026-12-22 | 2026-07-07 | 2026-07-13 | Normal | Planned | 0 | 66
FALSE |  | 52 | Install stairs and miscellaneous iron railing | Project5_FX06_TamperBaselineShift | 10 | 10 | 2026-12-30 | 2027-01-12 | 2026-08-04 | 2026-08-17 | Normal | Planned | 0 | 29
FALSE |  | 53 | Touch-up paint on steel | Project5_FX06_TamperBaselineShift | 5 | 5 | 2027-01-13 | 2027-01-19 | 2026-08-18 | 2026-08-24 | Normal | Planned | 0 | 29

## TP4_DataCenter_v3_FX01_Mil4
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View | TP4_DataCenter_v3_FX01_MilestoneLate: Detailed View
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Created | Actual Start | Actual Finish | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | 2026-02-02 |  |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | 19 | 30 | InProgress
FALSE |  | 2026-02-09 |  |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | 25 | 0 | InProgress
FALSE |  |  |  |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | 0 | 0 | Planned
FALSE |  |  |  |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | 0 | 13 | Planned
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | TRUE | None | 1 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | 0 | 0 | Planned
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | TRUE | None | 1 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
High Float 10% of Rem Project Duration
Number of activities that have a total float value higher than 10% of the remaining duration of the project. This number should not exceed 20%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 48 | 30 |  | -1 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE | FALSE | 48 | 13 |  | -1 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
Zero Days Float
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | TRUE | 0 |  | -1 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE | TRUE | 0 |  | -1 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links (>2) that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 4 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline finish dates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Tasks & Milestones (To Go)
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Milestones (To-Go)
Number of milestones to-go. Includes % of to-go activities that are milestones (vs. normal activities).
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Normal Tasks (To-Go)
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Normal Tasks (To-Go, In Progress)
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 30 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | FALSE | 13 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 30 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | FALSE | 13 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
Critical Path (Tasks & Milestones)
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Critical Path (Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Critical Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Critical Path (Normal In Progress)
Number of critical, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Status | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type
FALSE |  | TRUE | 0 | 25 | InProgress |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal
Critical Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | InProgress | 25
FALSE |  | TRUE | 0 | Normal |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Planned | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Near-Critical (<10 Days Float)
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Near CP - Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Total Milestones
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-29 | Milestone | Complete | 100 | 0
BEI - Complete Milestones
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-29 | Milestone | Complete | 100 | 0
BEI - Complete Milestones (adjusted)
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-29 | Milestone | Complete | 100 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE | TRUE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 4 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Actual Start | Actual Finish | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-02-02 |  |  | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE | 2026-02-09 |  |  | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  |  |  | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  |  |  | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | TRUE | 1 | 0 |  | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | TRUE | 1 | 0 |  | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-29 | Milestone | Complete | 100 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
FALSE |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Merge Hotspot
Number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
Diverge Hotspot
Number of activities with a high number of successor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
Open Ends w/o Constraints
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-29 | Milestone | Complete | 100 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Open Ends
Number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2025-12-29 | Milestone | Complete | 100 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX01_MilestoneLate | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
9. Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
FALSE |  | 22 | Network cabling | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX01_MilestoneLate | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX01_MilestoneLate | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX01_MilestoneLate | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX01_MilestoneLate | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0

## TP4_DataCenter_v3_FX02_Ear5
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View | TP4_DataCenter_v3_FX02_EarlyFinish: Detailed View
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Created | Actual Start | Actual Finish | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | 2026-02-02 |  |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | 19 | 30 | InProgress
FALSE |  | 2026-02-09 |  |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | 25 | 0 | InProgress
FALSE |  |  |  |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | 0 | 0 | Planned
FALSE |  |  |  |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | 0 | 13 | Planned
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | TRUE | None | 1 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | 0 | 0 | Planned
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | TRUE | None | 1 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
High Float 10% of Rem Project Duration
Number of activities that have a total float value higher than 10% of the remaining duration of the project. This number should not exceed 20%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 48 | 30 |  | -1 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE | FALSE | 48 | 13 |  | -1 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
Zero Days Float
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | TRUE | 0 |  | -1 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE | TRUE | 0 |  | -1 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links (>2) that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 4 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline finish dates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Tasks & Milestones (To Go)
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Milestones (To-Go)
Number of milestones to-go. Includes % of to-go activities that are milestones (vs. normal activities).
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Normal Tasks (To-Go)
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Normal Tasks (To-Go, In Progress)
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 30 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | FALSE | 13 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 30 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | FALSE | 13 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
Critical Path (Tasks & Milestones)
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Critical Path (Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Critical Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Critical Path (Normal In Progress)
Number of critical, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Status | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type
FALSE |  | TRUE | 0 | 25 | InProgress |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal
Critical Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | InProgress | 25
FALSE |  | TRUE | 0 | Normal |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Planned | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Near-Critical (<10 Days Float)
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Near CP - Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-30 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-30 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-30 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-30 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-30 | Normal | Complete | 100 | 0
BEI - Total Milestones
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
BEI - Complete Milestones
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
BEI - Complete Milestones (adjusted)
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE | TRUE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 4 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Actual Start | Actual Finish | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-02-02 |  |  | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE | 2026-02-09 |  |  | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  |  |  | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  |  |  | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | TRUE | 1 | 0 |  | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | TRUE | 1 | 0 |  | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-30 | Normal | Complete | 100 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
FALSE |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Merge Hotspot
Number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
Diverge Hotspot
Number of activities with a high number of successor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
Open Ends w/o Constraints
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Open Ends
Number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX02_EarlyFinish | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
9. Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
FALSE |  | 22 | Network cabling | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX02_EarlyFinish | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX02_EarlyFinish | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX02_EarlyFinish | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX02_EarlyFinish | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0

## TP4_DataCenter_v3_FX03_Dur6
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View | TP4_DataCenter_v3_FX03_DurationCut: Detailed View
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Created | Actual Start | Actual Finish | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | 2026-02-02 |  |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | 19 | 30 | InProgress
FALSE |  | 2026-02-09 |  |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | 25 | 0 | InProgress
FALSE |  |  |  |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | 0 | 0 | Planned
FALSE |  |  |  |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | 0 | 13 | Planned
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | TRUE | None | 1 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | 0 | 0 | Planned
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | TRUE | None | 1 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
High Float 10% of Rem Project Duration
Number of activities that have a total float value higher than 10% of the remaining duration of the project. This number should not exceed 20%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 48 | 30 |  | -1 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE | FALSE | 48 | 13 |  | -1 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
Zero Days Float
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | TRUE | 0 |  | -1 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE | TRUE | 0 |  | -1 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE | TRUE | 0 |  | -1 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Critical Merge Hotspot
The total number of activities with a high number of predecessor links (>2) that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 4 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline finish dates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Tasks & Milestones (To Go)
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Milestones (To-Go)
Number of milestones to-go. Includes % of to-go activities that are milestones (vs. normal activities).
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Normal Tasks (To-Go)
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Normal Tasks (To-Go, In Progress)
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 30 | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 30 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | FALSE | 13 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 30 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | FALSE | 13 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
Critical Path (Tasks & Milestones)
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Critical Path (Milestones)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | Standard | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned
Critical Path (Normal Tasks)
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | Standard | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress
FALSE |  | TRUE | 0 | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | Standard | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | Standard | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | Standard | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned
Critical Path (Normal In Progress)
Number of critical, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Status | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type
FALSE |  | TRUE | 0 | 25 | InProgress |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal
Critical Milestone-to-Task Ratio (To-Go)
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | InProgress | 25
FALSE |  | TRUE | 0 | Normal |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Planned | 0
Zero Days Float
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Near-Critical (<10 Days Float)
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0
Near CP - Float Ratio™
Average of activity float divided by remaining duration.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25
FALSE |  | TRUE | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
BEI - Total Tasks
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Complete Tasks
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Incomplete Tasks
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
BEI - Complete Tasks (adjusted)
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
BEI - Total Milestones
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
BEI - Complete Milestones
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
BEI - Complete Milestones (adjusted)
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
High Float 10%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Zero Days Float
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE | TRUE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Max Float
The largest float value (in days) for a grouping.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
Critical Merge Hotspot
The total number of activities with a high number of predecessor links that are also critical.
Excluded | Number of Predecessors | Number of Successors | Number of Leads | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 4 | 1 | 0 | 0 | 0 | TRUE | 0 |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0
Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Actual Start | Actual Finish | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-02-02 |  |  | 19 |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE | 2026-02-09 |  |  | 25 |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  |  |  | 0 |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  |  |  | 0 |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
Missing Logic
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | TRUE | 1 | 0 |  | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | TRUE | 1 | 0 |  | 0 |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Missing Predecessors
Number of activities that are missing a predecessor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
Missing Successors
Number of normal activities that are missing a successor.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
FS Predecessors
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 12 | Design & permits | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-01-05 | 2026-01-23 | 2026-01-05 | 2026-01-23 | Normal | Complete | 100 | 0
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 16 | Fire suppression | TP4_DataCenter_v3_FX03_DurationCut | 15 | 0 | 2026-02-09 | 2026-02-27 | 2026-02-09 | 2026-02-27 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
FALSE |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Merge Hotspot
Number of activities with a high number of predecessor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
Diverge Hotspot
Number of activities with a high number of successor links.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 13 | Demolition & shell prep | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-01-26 | 2026-02-06 | 2026-01-26 | 2026-02-06 | Normal | Complete | 100 | 0
Open Ends w/o Constraints
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
Open Ends
Number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 11 | Notice to proceed | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | Milestone | Complete | 100 | 0
FALSE |  | 26 | Substantial completion | TP4_DataCenter_v3_FX03_DurationCut | 0 | 0 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | Milestone | Planned | 0 | 0
9. Invalid Forecast Dates
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
10. Resources
Number of activities that do not have resources/costs assigned
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 15 | Mechanical / HVAC rough-in | TP4_DataCenter_v3_FX03_DurationCut | 25 | 19 | 2026-02-09 | 2026-03-13 | 2026-02-09 | 2026-03-13 | Normal | InProgress | 25 | 0
FALSE |  | 17 | Raised floor & containment | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-16 | 2026-04-03 | 2026-03-16 | 2026-04-03 | Normal | Planned | 0 | 0
FALSE |  | 21 | UPS & battery installation | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-03-25 | 2026-04-14 | 2026-03-23 | 2026-04-10 | Normal | Planned | 0 | 13
FALSE |  | 22 | Network cabling | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 23 | CRAC units set & pipe | TP4_DataCenter_v3_FX03_DurationCut | 20 | 20 | 2026-04-06 | 2026-05-01 | 2026-04-06 | 2026-05-01 | Normal | Planned | 0 | 0
FALSE |  | 24 | Commissioning L1-L3 | TP4_DataCenter_v3_FX03_DurationCut | 15 | 15 | 2026-05-04 | 2026-05-22 | 2026-05-04 | 2026-05-22 | Normal | Planned | 0 | 0
FALSE |  | 25 | Integrated systems test | TP4_DataCenter_v3_FX03_DurationCut | 10 | 10 | 2026-05-25 | 2026-06-05 | 2026-05-25 | 2026-06-05 | Normal | Planned | 0 | 0
11. Missed Activities
Number of activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 19 | Generator & switchgear procurement | TP4_DataCenter_v3_FX03_DurationCut | 20 | 16 | 2026-02-02 | 2026-02-27 | 2026-01-26 | 2026-02-20 | Normal | InProgress | 19 | 30
FALSE |  | 14 | Electrical rough-in | TP4_DataCenter_v3_FX03_DurationCut | 22 | 0 | 2026-02-09 | 2026-03-10 | 2026-02-09 | 2026-03-06 | Normal | Complete | 100 | 0
FALSE |  | 18 | Power distribution units | TP4_DataCenter_v3_FX03_DurationCut | 10 | 0 | 2026-03-11 | 2026-03-24 | 2026-03-09 | 2026-03-20 | Normal | Complete | 100 | 0

## Phase Analysis
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
 | time axis 2012-08-01 to 2029-04-01
Phase Analyzer | Status Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | WBS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 3 | 4 | 1 | 1 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 7 | 7 | 7 | 9 | 9 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | New Activity - Created (Snapshot) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Start | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-09-10 | 2027-09-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Specific Task Finish | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-10-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Score | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis | Secondary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
 | time axis 2012-08-01 to 2029-04-01
Phase Analyzer | Status Date
Phase Analyzer | WBS
Phase Analyzer | New Activity - Created (Snapshot)
Phase Analyzer | New Activity - Already Finished (Snapshot) - check/compare
Phase Analyzer | New Activity - Finished in Status Period (Snapshot) - check/compare
Phase Analyzer | Specific Task Start
Phase Analyzer | Specific Task Finish
Phase Analyzer | Score

## 9-2027 Details
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
9/2027: Detailed View | 9/2027: Detailed View
Specific Task Start
Provides the start date of a specific task.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 24
FALSE |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29

## 10-2027 Details
Fuse® Analyst Report
Workbook: AlltheProjects - 15976 Activities
Quick Add Metrics
Created on: 8/7/2026
Created by: dpolitte
10/2027: Detailed View | 10/2027: Detailed View | 10/2027: Detailed View
Specific Task Start
Provides the start date of a specific task.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 24
FALSE |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
Specific Task Finish
Provides the finish date of a specific task.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 100 | Paint walls and woodwork | Project5_FX04_TamperDuration | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29
FALSE |  | 100 | Paint walls and woodwork | Project5_FX05_TamperLogicDrop | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 24
FALSE |  | 100 | Paint walls and woodwork | Project5_FX06_TamperBaselineShift | 20 | 20 | 2027-09-10 | 2027-10-07 | 2027-04-13 | 2027-05-10 | Normal | Planned | 0 | 29