## TP4_DataCenter_v1
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v1 (1/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v2 (2/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v3 (3/31/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v5
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v5 (5/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project2 (5/24/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project5_TAMPERED
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project2 2 (5/24/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project3 (6/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project4
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project4 (7/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project5
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5 (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Large-Test-File
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File (2/7/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Large-Test-File2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Large-Test-File-Leveled
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File Leveled (2/7/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Large-Test-File-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File 2 (2/7/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Large-Test-File2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Large Test File2 2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## SRA-Large-Test-File2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
SRA Large Test File2 2 (3/10/2025 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Jacked-Up-Schedule-1
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Jacked Up Schedule 1 (7/30/2026 8:00:00 AM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Jacked-up-Schedule-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Jacked up Schedule 2 (7/30/2026 8:00:00 AM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File_updated3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated3 (10/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File_updated4-24-hour-cal
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated4 24 hour calendar (11/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File (7/7/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File_updated
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated (8/11/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File_updated_with_logic_r
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated_with_logic_reestablished (8/11/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File_updated2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated2 (9/10/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File_updated3-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated3 2 (10/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Hard_File_updated4-24-hour-cal2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated4 24 hour calendar 2 (11/12/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## EVM1
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
EVM1 (9/1/2012 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## EVM2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
EVM2 (9/12/2012 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project2-3
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project2 3 (5/24/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project3-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project3 2 (6/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project4-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project4 2 (7/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project5_TAMPERED-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_TAMPERED 2 (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v1-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v1 2 (1/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v2-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v2 2 (2/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v3-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v3 2 (3/31/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v4-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v4 2 (4/30/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## TP4_DataCenter_v5-2
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v5 2 (5/29/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | N/A
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | N/A
| Wrong Status - Actual Finishes | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish But Still In-Progress | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| High Float 10% | F | N/A
| Negative Float | F | N/A
| Tasks & Milestones (To Go) | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Normal Tasks (To-Go, In Progress) | F | N/A
| Critical Path (Tasks & Milestones) | F | N/A
| Critical Path (Milestones) | F | N/A
| Critical Path (Normal Tasks) | F | N/A
| Critical Path (Normal In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | N/A
| Zero Days Float | F | N/A
| Near-Critical (<10 Days Float) | F | N/A
| CP Logic Density™ | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| Status Date | F | N/A
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Normal Tasks (To-Go) | F | N/A
| Riding Data Date | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Duration Ratio Metric (DRM) | F | N/A
| DRM Graph | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| BEI - Value Activities | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Critical Path To-Go | F | N/A
| Status Date | F | N/A
| Total Activities | F | N/A
| Milestones | F | N/A
| Normal Tasks | F | N/A
| Summaries | F | N/A
| Hammocks | F | N/A
| Recurring Normal Tasks | F | N/A
| Total Tasks & Milestones | F | N/A
| Completed Tasks & Milestones | F | N/A
| Completed Milestones | F | N/A
| Completed Tasks | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Milestones (To-Go) | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Summaries (To-Go) | F | N/A
| Hammocks (To-Go) | F | N/A
| Recurring Tasks (To-Go) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Milestones) | F | N/A
| Riding Data Date | F | N/A
| Status Date | F | N/A
| Total Activities (To-Go) - % of Total | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Summary-to-Task Ratio (To-Go) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Manual Tasks (To-Go) | F | N/A
| Critical Tasks and Milestones (To-Go) | F | N/A
| Wrong Status (To-Go) | F | N/A
| Invalid Forecast Dates | F | N/A
| Missing WBS (To-Go) | F | N/A
| All Activities (To Go) | F | N/A
| Tasks & Milestones (To-Go) - % of Total To-Go | F | N/A
| Estimated Duration | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Avg. Original Duration | F | N/A
| Avg. Remaining Duration | F | N/A
| High Baseline Duration (44d) | F | N/A
| High Planned Duration (44d) | F | N/A
| Insufficient Detail™ | F | N/A
| Critical Activities (To-Go) | F | N/A
| Avg. Critical Original Duration | F | N/A
| Avg. Critical Remaining Duration | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical w/Insufficient Detail™ | F | N/A
| Activities (To-Go) | F | N/A
| Total Constraints | F | N/A
| Start No Earlier Than | F | N/A
| Start No Later Than | F | N/A
| Finish No Earlier Than | F | N/A
| Finish No Later Than | F | N/A
| Hard Constraints | F | N/A
| Must Start On | F | N/A
| Must Finish On | F | N/A
| As Late As Possible | F | N/A
| Deadlines | F | N/A
| Mandatory Start | F | N/A
| Mandatory Finish | F | N/A
| Open Ends with Constraints | F | N/A
| Open Ends w/o Constraints | F | N/A
| Unsatisfied Constraints | F | N/A
| No Constraints | F | N/A
| No Constraints | F | N/A
| Logic Density™ | F | N/A
| Logic Density™ - Predecessors | F | N/A
| Logic Density™ - Successors | F | N/A
| Summary Links | F | N/A
| All Activities w/Predecessors | F | N/A
| SS Predecessors | F | N/A
| SF Predecessors | F | N/A
| FF Predecessors | F | N/A
| FS Predecessors | F | N/A
| All Activities w/Successors | F | N/A
| SS Successors | F | N/A
| FF Successors | F | N/A
| SF Successors | F | N/A
| FS Successors | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Logic Density™ - Predecessors | F | N/A
| All Activities w/Predecessors | F | N/A
| Total # Predecessors | F | N/A
| Activities Missing Predecessors | F | N/A
| Activities w/Leads on Predecessor | F | N/A
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | N/A
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | N/A
| Max Predecessor Lag (days) | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical w/Hidden Duration (Planned) | F | N/A
| Merge Hotspot (Predecessors >2) | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Logic Density™ - Successors | F | N/A
| All Activities w/Successors | F | N/A
| Activities Missing Successors | F | N/A
| Total # Successors | F | N/A
| Activities w/Leads on Successor | F | N/A
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | N/A
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | N/A
| Logic Hotspot™ | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Actually Finished - Tasks & Milestones | F | N/A
| Completed Ahead - Tasks & Milestones | F | N/A
| Completed On-Schedule - Tasks & Milestones | F | N/A
| Completed Delayed - Tasks & Milestones | F | N/A
| Avg Days Finished Early - Tasks & Milestones | F | N/A
| Avg Days Finished Late - Tasks & Milestones | F | N/A
| Avg Finish Variance - Tasks & Milestones | F | N/A
| Actually Finished - Tasks | F | N/A
| Completed Ahead - Tasks | F | N/A
| Completed On-Schedule - Tasks | F | N/A
| Completed Delayed - Tasks | F | N/A
| Accelerated Durations Early/On-Schedule - Tasks | F | N/A
| Accelerated Durations Late - Tasks | F | N/A
| Extended Durations - Tasks | F | N/A
| Actually Finished - Milestones | F | N/A
| Completed Ahead - Milestones | F | N/A
| Completed On-Schedule - Milestones | F | N/A
| Completed Delayed - Milestones | F | N/A
| Actually Started - Tasks | F | N/A
| In-Progress Started Ahead - Tasks | F | N/A
| In-Progress Started On-Schedule - Tasks | F | N/A
| In-Progress Started Delayed - Tasks | F | N/A
| In-Progress Delayed Finish - Tasks | F | N/A
| Avg Days Started Early | F | N/A
| Avg Days Started Late | F | N/A
| Avg Start Variance | F | N/A
| Expected Finish | F | N/A
| In-Progress Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks & Milestones | F | N/A
| Planned Ahead Start - Tasks & Milestones | F | N/A
| Planned On Schedule Start - Tasks & Milestones | F | N/A
| Planned Delayed Start - Tasks & Milestones | F | N/A
| Riding Data Date - Tasks & Milestones | F | N/A
| Planned Schedule Overrun - Tasks & Milestones | F | N/A
| Scheduled to Start - Tasks | F | N/A
| Planned Ahead Start - Tasks | F | N/A
| Planned On Schedule Start - Tasks | F | N/A
| Planned Delayed Start - Tasks | F | N/A
| Planned Delayed Finish - Tasks | F | N/A
| Scheduled to Start - Milestones | F | N/A
| Planned Ahead Start - Milestones | F | N/A
| Planned On Schedule Start - Milestones | F | N/A
| Planned Delayed Start - Milestones | F | N/A
| Planned Delayed Finish - Milestones | F | N/A
| Schedule Baseline Activities | F | N/A
| Scheduled/Baselined to Start | F | N/A
| Scheduled/Baselined to Finish | F | N/A
| Start/ed | F | N/A
| Finish/ed | F | N/A
| Start Variance (Phase) | F | N/A
| Start Compliance™ (Phase) | F | N/A
| Finish Variance (Phase) | F | N/A
| Finish Compliance™ (Phase) | F | N/A
| Started Delayed (>30 days) | F | N/A
| Completed Delayed (>30 days) | F | N/A
| SPI(t) | F | N/A
| Scheduled Activities | F | N/A
| Scheduled to Start | F | N/A
| Scheduled to Finish | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Longest Path - Critical Activities and Milestones | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Logic Density™ | F | N/A
| CP Logic Density™ | F | N/A
| Critical w/Missing Logic | F | N/A
| Critical w/Hard Constraints | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Critical LOE | F | N/A
| Critical w/High Baseline Duration (44d) | F | N/A
| Critical w/High Planned Duration (44d) | F | N/A
| Critical with Predecessor Lag | F | N/A
| Critical with Successor Lag | F | N/A
| Critical with Hard Constraints | F | N/A
| Negative Float with Predecessor Lag | F | N/A
| Negative Float with Successor Lag | F | N/A
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Actual Starts | F | N/A
| Current Baselined to Start & Started | F | N/A
| Past Baselined to Start & Started | F | N/A
| Future Baseline to Start & Started | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Actual Finishes | F | N/A
| Current Baselined to Finish & Finished | F | N/A
| Past Baselined to Finish & Finished | F | N/A
| Future Baselined to Finish & Finished | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| Baselined to Start - To Time Now | F | N/A
| Scheduled to Start - To Time Now | F | N/A
| Started | F | N/A
| Started Late | F | N/A
| Started Delayed (<=30 days) | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A
| Started Delayed (>60 days) | F | N/A
| BEI - Value Task Starts | F | N/A
| Baselined to Finish - To Time Now | F | N/A
| Scheduled to Finish - To Time Now | F | N/A
| Finished | F | N/A
| Finished Late | F | N/A
| Completed Delayed (<=30 days) | F | N/A
| Completed Delayed (Between 31 to 60 days) | F | N/A
| Completed Delayed (>60 days) | F | N/A
| BEI - Value Task Finishes | F | N/A
| Started - Future | F | N/A
| Not Baselined to Start | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Started | F | N/A
| Current Baseline to Start & Started Past (Early Starts) | F | N/A
| Current Baseline to Start & Started Future (Late Starts) | F | N/A
| Current Baseline to Start & Not Started (Incomplete) | F | N/A
| Baselined to Start - Check | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Finish & Finished Past - Check | F | N/A
| Current Baseline to Finish & Finished Future - Check | F | N/A
| Current Baseline to Finish & Not Finished - Check | F | N/A
| Baselined to Finish - Check | F | N/A
| Future Baseline to Finish & Finished - Check | F | N/A
| Current Baseline to Start & Started (BL Plan) | F | N/A
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A
| Current Baseline to Start & Not Started (Incompletes) | F | N/A
| Current Baseline to Finish & Finished (BL Plan) | F | N/A
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A
| Current Baseline to Finish & Not Finished (Incompletes) | F | N/A
| Baselined to Start | F | N/A
| Scheduled to Start | F | N/A
| Started - Scheduled | F | N/A
| Started - Baseline Comparison | F | N/A
| BEI - Value Task Starts | F | N/A
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | N/A
| Scheduled to Finish | F | N/A
| Finished | F | N/A
| BEI - Value Task Finishes | F | N/A
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | N/A
| Started (incl. Future Baseline Starts) - Scheduled | F | N/A
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | N/A
| Started Late (from Baseline) | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | N/A
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | N/A
| Finished Late | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Completed Ahead | F | N/A
| Completed Delayed | F | N/A
| Completed On-Schedule | F | N/A
| Accelerated | F | N/A
| Days Variance | F | N/A
| Days Early | F | N/A
| Days Late | F | N/A
| Avg Days Early | F | N/A
| Avg Days Late | F | N/A
| Avg Variance | F | N/A
| Actually Finished | F | N/A
| Took Longer than Planned | F | N/A
| Took Less Than Planned | F | N/A
| Completed (w/Baseline Duration) | F | N/A
| Completed (w/o Baseline Duration) | F | N/A
| Completed (w/Baseline Dur=0) | F | N/A
| Baseline-to-Date Completed Tasks | F | N/A
| Missed Durations | F | N/A
| Missed Durations & Late Actual Finish | F | N/A
| Baselined Tasks | F | N/A
| Baselined to Start - TOTAL | F | N/A
| Complete Task Starts - Cumulative | F | N/A
| Incomplete Task Starts - Cumulative (in work) | F | N/A
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | N/A
| Complete Task Finishes - Cumulative (in work) | F | N/A
| Incomplete Task Finishes - Cumulative | F | N/A
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| BEI - Complete Tasks (adjusted) | F | N/A
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Total Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | N/A
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | N/A
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | N/A
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | N/A
| Total Activities - DRM | F | N/A
| Total Activities - DRM Graph | F | N/A
| Status Date | F | N/A
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | N/A
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A
| BEI - Value Task Finishes - Cumulative | F | N/A
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | N/A
| FEI - Value Task Finish - Cumulative | F | N/A
| BEI - Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | N/A
| BEI - Complete Tasks | F | N/A
| BEI - Incomplete Tasks | F | N/A
| BEI - CP Tasks - Planned Cumulative | F | N/A
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | N/A
| Invalid Forecast Dates | F | N/A
| Expected Finish | F | N/A
| Missing WBS | F | N/A
| Milestones with Duration>0 | F | N/A
| Activities with Duration=0 | F | N/A
| Estimated Duration | F | N/A
| Missing Logic | F | N/A
| Missing Predecessors | F | N/A
| Missing Successors | F | N/A
| Open Start | F | N/A
| Open Finish | F | N/A
| Unsatisfied Constraints | F | N/A
| Summary Links | F | N/A
| Hard Constraints | F | N/A
| Critical w/Hidden Duration | F | N/A
| Negative Float | F | N/A
| Status Date | F | N/A
| High Float 10% | F | N/A
| High Float 44d | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| Hidden Duration (Planned) | F | N/A
| Critical Logic Hotspot™ | F | N/A
| Critical Merge Hotspot | F | N/A
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | N/A
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | N/A
| Deadlines | F | N/A
| Longest Path (Normal Tasks) | F | N/A
| Longest Path (Tasks & Milestones) | F | N/A
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Critical Milestones (To-Go) | F | N/A
| Longest Path (Milestones) | F | N/A
| Normal Tasks | F | N/A
| Normal Tasks (To-Go) | F | N/A
| Critical Tasks (To-Go) | F | N/A
| Critical Tasks (In Progress) | F | N/A
| Zero Days Float | F | N/A
| Negative Float | F | N/A
| CP Logic Density™ | F | N/A
| Time Now | F | N/A
| Forecast to be Finished | F | N/A
| Completed On Time | F | N/A
| Completed Late | F | N/A
| Not Completed | F | N/A
| Baseline Finish Compliance | F | N/A
| Forecast to be Started | F | N/A
| Started On Time | F | N/A
| Started Late | F | N/A
| Not Started | F | N/A
| Baseline Start Compliance | F | N/A
1 | Completed Activities | F | N/A
HSD01 | Time Now | F | N/A
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | N/A
HSD04 | Started Late | F | N/A
HSD05 | Forecast to be Finished but not Finished yet | F | N/A
HSD06 | Finished Late | F | N/A
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | N/A
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | N/A
HSD10 | Cumulative Finish Impact (Days) | F | N/A
HSD10 | Net Finish Impact (Days) | F | N/A
HSD20 | Project Finish | F | N/A
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A
SEM01 | Workoff Burden | F | N/A
SEM02 | BRI Current | F | N/A
SEM03 | BRI Cumulative | F | N/A
SEM04 | BPI Current | F | N/A
SEM05 | BEI Current | F | N/A
SEM06 | BEI Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | Workoff Burden - Starts To-Go (Total) | F | N/A
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | N/A
SEM07 | Workoff Burden - Finishes To-Go (Total) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | N/A
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | N/A
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | N/A
SEM07 | To Go - Planned Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Task Finishes - Count | F | N/A
SEM07 | To Go - Baselined Task Starts - Count | F | N/A
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | N/A
SEM07 | TC-BEI | F | N/A
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN05 | Newly Critical Activities | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A
SN06 | Activities No Longer Critical | F | N/A

## Project5_FX04_TamperDuration
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_FX04_TamperDuration (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-27
| Specific Task Start | F | 2027-09-10
| Specific Task Finish | F | 2027-10-07
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 44d | F | 56 | 57%
| Zero Days Float | F | 4 | 4%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 43 | 43%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 99 | 79%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 100%
| Normal Tasks (To-Go, In Progress) | F | 2 | 2%
| Critical Path (Tasks & Milestones) | F | 4 | 4%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 4 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Near-Critical (<10 Days Float) | F | 5 | 5%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| Status Date | F | 2026-08-27
| Milestone #1 - 100 | F | 2027-09-10
| Float Milestone #1 - 100 | F | 29
| Milestone #2 - 101 | F | 2027-07-16
| Float to Milestone #2 - 101 | F | 60
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 55
| Milestone #4 - 103 | F | 2027-09-23
| Float to Milestone #4 - 103 | F | 55
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 104 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 4 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Duration Ratio Metric (DRM) | F | 27
| DRM Graph | F | 27
| Baselined to Start | F | 99
| Scheduled to Start | F | 99
| Baselined to Finish | F | 99
| Scheduled to Finish | F | 99
| BEI - Value Activities | F | 0.59
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Critical Path To-Go | F | 4 | 4%
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-08-27
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 4 | 4%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 99 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 10
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 4 | 4%
| Avg. Critical Original Duration | F | 8
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 99 | 79%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 1%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 5 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 96 | 97%
| No Constraints | F | 96 | 97%
| Logic Density™ | F | 2.86
| Logic Density™ - Predecessors | F | 1.48
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 97 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 99 | 100%
| All Activities w/Successors | F | 94 | 95%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 94 | 95%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.49
| All Activities w/Predecessors | F | 97 | 100%
| Total # Predecessors | F | 145
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 94 | 100%
| Activities Missing Successors | F | 5 | 5%
| Total # Successors | F | 136
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 27 | 21%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 33%
| Completed Delayed - Tasks & Milestones | F | 18 | 67%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 39
| Avg Finish Variance - Tasks & Milestones | F | 26
| Actually Finished - Tasks | F | 27 | 21%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 33%
| Completed Delayed - Tasks | F | 18 | 67%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 7 | 6%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 2 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 85
| Avg Start Variance | F | 85
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 97 | 77%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 97 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 97 | 77%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 97 | 100%
| Planned Delayed Finish - Tasks | F | 97 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 99
| Scheduled/Baselined to Finish | F | 99
| Start/ed | F | 29
| Finish/ed | F | 27
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 10 | 56%
| Completed Delayed (>30 days) | F | 11 | 61%
| SPI(t) | F | 0.91
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 99 | 79%
| Scheduled to Finish | F | 99 | 79%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 43 | 43%
| High Float 44d | F | 56 | 57%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.81
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 5%
| Critical w/Hard Constraints | F | 1 | 1%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 1%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Current Baselined to Start & Started | F | 29
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Current Baselined to Finish & Finished | F | 27
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start - To Time Now | F | 48 | 38%
| Scheduled to Start - To Time Now | F | 48 | 38%
| Started | F | 29
| Started Late | F | 18
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| BEI - Value Task Starts | F | 0.6
| Baselined to Finish - To Time Now | F | 46 | 37%
| Scheduled to Finish - To Time Now | F | 46 | 37%
| Finished | F | 27
| Finished Late | F | 18
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Finishes | F | 0.59
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 29
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 97
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 27
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 99
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Baselined to Start | F | 48
| Scheduled to Start | F | 48 | 100%
| Started - Scheduled | F | 29 | 60%
| Started - Baseline Comparison | F | 29 | 60%
| BEI - Value Task Starts | F | 0.6
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 46
| Scheduled to Finish | F | 46
| Finished | F | 27
| BEI - Value Task Finishes | F | 0.59
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 29 | 23%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 29 | 23%
| Started Late (from Baseline) | F | 18
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 27 | 21%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 27 | 21%
| Finished Late | F | 18
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 29 | 60%
| Incomplete Task Starts - Cumulative (in work) | F | 19 | 40%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 27 | 59%
| Incomplete Task Finishes - Cumulative | F | 19 | 59%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - Value Tasks (adjusted) | F | 0.59
| BEI - Complete Tasks (adjusted) | F | 27 | 59%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Incomplete Tasks | F | 19 | 41%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.59
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| Total Activities - DRM | F | 27
| Total Activities - DRM Graph | F | 27
| Status Date | F | 2026-08-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 55
| Milestone #4 - 103 | F | 2027-09-09
| Float to Milestone #4 - 103 | F | 55
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 105 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| BEI - Value Tasks | F | 0.59
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 10% | F | 43 | 43%
| High Float 44d | F | 56 | 57%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 99 | 88%
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-08-27
| Forecast to be Finished | F | 46 | 37%
| Completed On Time | T | 9 | 20%
| Completed Late | F | 18 | 39%
| Not Completed | F | 19 | 41%
| Baseline Finish Compliance | T | 20%
| Forecast to be Started | F | 48 | 38%
| Started On Time | T | 11 | 23%
| Started Late | F | 18 | 38%
| Not Started | F | 19 | 40%
| Baseline Start Compliance | F | 25%
1 | Completed Activities | F | 27
HSD01 | Time Now | F | 2026-08-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 19 | 15%
HSD04 | Started Late | F | 18 | 38%
HSD05 | Forecast to be Finished but not Finished yet | T | 19 | 15%
HSD06 | Finished Late | F | 18 | 39%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-01-25
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 2 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.59
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.59
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 97
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 78
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 99
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | TC-BEI | T | 1.24
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.61
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project5_FX05_TamperLogicDrop
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_FX05_TamperLogicDrop (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-27
| Specific Task Start | F | 2027-09-10
| Specific Task Finish | F | 2027-10-07
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 8 | 8%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 8 | 8%
| Missing Predecessors | F | 1 | 1%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 44d | F | 58 | 59%
| Zero Days Float | F | 1 | 1%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 47 | 47%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 99 | 79%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 100%
| Normal Tasks (To-Go, In Progress) | F | 2 | 2%
| Critical Path (Tasks & Milestones) | F | 1 | 1%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 1 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 1 | 1%
| Near-Critical (<10 Days Float) | F | 1 | 1%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| Status Date | F | 2026-08-27
| Milestone #1 - 100 | F | 2027-09-10
| Float Milestone #1 - 100 | F | 24
| Milestone #2 - 101 | F | 2027-07-16
| Float to Milestone #2 - 101 | F | 60
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 55
| Milestone #4 - 103 | F | 2027-09-23
| Float to Milestone #4 - 103 | F | 55
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 104 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 1 | 50%
| Longest Path (Normal Tasks) | F | 1 | 50%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 1 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.26
| FEI - Value Task Finish - Cumulative | F | 1.25
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Duration Ratio Metric (DRM) | F | 27
| DRM Graph | F | 27
| Baselined to Start | F | 99
| Scheduled to Start | F | 99
| Baselined to Finish | F | 99
| Scheduled to Finish | F | 99
| BEI - Value Activities | F | 0.59
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Critical Path To-Go | F | 1 | 1%
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 1 | 50%
| Longest Path (Normal Tasks) | F | 1 | 50%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-08-27
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 1 | 1%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 8 | 8%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 99 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 10
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 1 | 1%
| Avg. Critical Original Duration | F | 20
| Avg. Critical Remaining Duration | F | 20
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 99 | 79%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 1%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 1%
| Open Ends w/o Constraints | F | 7 | 6%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 96 | 97%
| No Constraints | F | 96 | 97%
| Logic Density™ | F | 2.82
| Logic Density™ - Predecessors | F | 1.46
| Logic Density™ - Successors | F | 1.35
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 96 | 99%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 98 | 99%
| All Activities w/Successors | F | 92 | 93%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 92 | 93%
| Missing Logic | F | 8 | 8%
| Missing Predecessors | F | 1 | 1%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.47
| All Activities w/Predecessors | F | 96 | 100%
| Total # Predecessors | F | 143
| Activities Missing Predecessors | F | 1 | 1%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.35
| All Activities w/Successors | F | 92 | 100%
| Activities Missing Successors | F | 7 | 7%
| Total # Successors | F | 134
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 27 | 21%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 33%
| Completed Delayed - Tasks & Milestones | F | 18 | 67%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 39
| Avg Finish Variance - Tasks & Milestones | F | 26
| Actually Finished - Tasks | F | 27 | 21%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 33%
| Completed Delayed - Tasks | F | 18 | 67%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 7 | 6%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 2 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 85
| Avg Start Variance | F | 85
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 97 | 77%
| Planned Ahead Start - Tasks & Milestones | F | 4 | 4%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 93 | 96%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 97 | 77%
| Planned Ahead Start - Tasks | F | 4 | 4%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 93 | 96%
| Planned Delayed Finish - Tasks | F | 93 | 96%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 99
| Scheduled/Baselined to Finish | F | 99
| Start/ed | F | 29
| Finish/ed | F | 27
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 10 | 56%
| Completed Delayed (>30 days) | F | 11 | 61%
| SPI(t) | F | 0.91
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 99 | 79%
| Scheduled to Finish | F | 99 | 79%
| Longest Path - Critical Activities and Milestones | F | 1 | 1%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 1 | 1%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 47 | 47%
| High Float 44d | F | 58 | 59%
| Zero Days Float | F | 1 | 1%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 1 | 1%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 1 | 1%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.78
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 8%
| Critical w/Hard Constraints | F | 1 | 1%
| Zero Days Float | F | 1 | 1%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 1%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Current Baselined to Start & Started | F | 29
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Current Baselined to Finish & Finished | F | 27
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start - To Time Now | F | 48 | 38%
| Scheduled to Start - To Time Now | F | 48 | 38%
| Started | F | 29
| Started Late | F | 18
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| BEI - Value Task Starts | F | 0.6
| Baselined to Finish - To Time Now | F | 46 | 37%
| Scheduled to Finish - To Time Now | F | 46 | 37%
| Finished | F | 27
| Finished Late | F | 18
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Finishes | F | 0.59
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.26
| FEI - Value Task Finish - Cumulative | F | 1.25
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 29
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 97
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 27
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 99
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Baselined to Start | F | 48
| Scheduled to Start | F | 48 | 100%
| Started - Scheduled | F | 29 | 60%
| Started - Baseline Comparison | F | 29 | 60%
| BEI - Value Task Starts | F | 0.6
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 46
| Scheduled to Finish | F | 46
| Finished | F | 27
| BEI - Value Task Finishes | F | 0.59
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 29 | 23%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 29 | 23%
| Started Late (from Baseline) | F | 18
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 27 | 21%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 27 | 21%
| Finished Late | F | 18
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 29 | 60%
| Incomplete Task Starts - Cumulative (in work) | F | 19 | 40%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 27 | 59%
| Incomplete Task Finishes - Cumulative | F | 19 | 59%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - Value Tasks (adjusted) | F | 0.59
| BEI - Complete Tasks (adjusted) | F | 27 | 59%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Incomplete Tasks | F | 19 | 41%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.59
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| Total Activities - DRM | F | 27
| Total Activities - DRM Graph | F | 27
| Status Date | F | 2026-08-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 55
| Milestone #4 - 103 | F | 2027-09-09
| Float to Milestone #4 - 103 | F | 55
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 105 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.26
| FEI - Value Task Finish - Cumulative | F | 1.25
| BEI - Value Tasks | F | 0.59
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 8 | 8%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 8 | 8%
| Missing Predecessors | F | 1 | 1%
| Missing Successors | F | 7 | 7%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 10% | F | 47 | 47%
| High Float 44d | F | 58 | 59%
| Zero Days Float | F | 1 | 1%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 1 | 50%
| Longest Path (Tasks & Milestones) | F | 1 | 50%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 99 | 88%
| Critical Tasks (To-Go) | F | 1 | 1%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 1 | 1%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-08-27
| Forecast to be Finished | F | 46 | 37%
| Completed On Time | T | 9 | 20%
| Completed Late | F | 18 | 39%
| Not Completed | F | 19 | 41%
| Baseline Finish Compliance | T | 20%
| Forecast to be Started | F | 48 | 38%
| Started On Time | T | 11 | 23%
| Started Late | F | 18 | 38%
| Not Started | F | 19 | 40%
| Baseline Start Compliance | F | 25%
1 | Completed Activities | F | 27
HSD01 | Time Now | F | 2026-08-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 19 | 15%
HSD04 | Started Late | F | 18 | 38%
HSD05 | Forecast to be Finished but not Finished yet | T | 19 | 15%
HSD06 | Finished Late | F | 18 | 39%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-01-06
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 2 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.59
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.59
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.19
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.19
SEM07 | To Go - Planned Task Starts - Count | T | 93
SEM07 | To Go - BEI - Task Finishes - Count | T | 95
SEM07 | To Go - Baselined Task Starts - Count | T | 93
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.19
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 74
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 76
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.19
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.19
SEM07 | To Go - Planned Task Starts - Count | T | 93
SEM07 | To Go - BEI - Task Finishes - Count | T | 95
SEM07 | To Go - Baselined Task Starts - Count | T | 93
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.19
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 93
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 74
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 95
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 76
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 74
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 76
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.19
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.19
SEM07 | To Go - Planned Task Starts - Count | T | 93
SEM07 | To Go - BEI - Task Finishes - Count | T | 95
SEM07 | To Go - Baselined Task Starts - Count | T | 93
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.19
SEM07 | TC-BEI | T | 1.19
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.56
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## Project5_FX06_TamperBaselineSh
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Project5_FX06_TamperBaselineShift (8/27/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-08-27
| Specific Task Start | F | 2027-09-10
| Specific Task Finish | F | 2027-10-07
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 44d | F | 56 | 57%
| Zero Days Float | F | 4 | 4%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 43 | 43%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 99 | 79%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 100%
| Normal Tasks (To-Go, In Progress) | F | 2 | 2%
| Critical Path (Tasks & Milestones) | F | 4 | 4%
| Critical Path (Milestones) | F | 0 | 0%
| Critical Path (Normal Tasks) | F | 4 | 100%
| Critical Path (Normal In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Near-Critical (<10 Days Float) | F | 5 | 5%
| CP Logic Density™ | F | 3
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| Status Date | F | 2026-08-27
| Milestone #1 - 100 | F | 2027-09-10
| Float Milestone #1 - 100 | F | 29
| Milestone #2 - 101 | F | 2027-07-16
| Float to Milestone #2 - 101 | F | 60
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 55
| Milestone #4 - 103 | F | 2027-09-23
| Float to Milestone #4 - 103 | F | 55
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 104 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Critical Milestones (To-Go) | F | 0 | 0%
| Critical Normal Tasks (To-Go) | F | 4 | 100%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Duration Ratio Metric (DRM) | F | 27
| DRM Graph | F | 27
| Baselined to Start | F | 99
| Scheduled to Start | F | 99
| Baselined to Finish | F | 99
| Scheduled to Finish | F | 99
| BEI - Value Activities | F | 0.59
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Critical Path To-Go | F | 4 | 4%
| Status Date | F | 2026-08-27
| Total Activities | F | 144
| Milestones | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Summaries | F | 18 | 13%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 126 | 88%
| Completed Tasks & Milestones | F | 27 | 21%
| Completed Milestones | F | 0
| Completed Tasks | F | 27 | 21%
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Milestones (To-Go) | F | 0 | 0%
| Normal Tasks (To-Go) | F | 99 | 88%
| Summaries (To-Go) | F | 14 | 12%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Milestones) | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-08-27
| Total Activities (To-Go) - % of Total | F | 113 | 78%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Summary-to-Task Ratio (To-Go) | F | 1:07 | 0.14
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 4 | 4%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 99 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 99 | 88%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 10
| Avg. Remaining Duration | F | 9
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 0 | 0%
| Critical Activities (To-Go) | F | 4 | 4%
| Avg. Critical Original Duration | F | 8
| Avg. Critical Remaining Duration | F | 8
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0%
| Activities (To-Go) | F | 99 | 79%
| Total Constraints | F | 3 | 3%
| Start No Earlier Than | F | 2 | 2%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 1 | 1%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 5 | 5%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 96 | 97%
| No Constraints | F | 96 | 97%
| Logic Density™ | F | 2.86
| Logic Density™ - Predecessors | F | 1.48
| Logic Density™ - Successors | F | 1.37
| Summary Links | F | 0 | 0%
| All Activities w/Predecessors | F | 97 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 99 | 100%
| All Activities w/Successors | F | 94 | 95%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 94 | 95%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.49
| All Activities w/Predecessors | F | 97 | 100%
| Total # Predecessors | F | 145
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 1 | 1%
| Total # Predecessor Lags | F | 1
| Max # of Predecessor Lags on an Activity | F | 1
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 5
| Hidden Duration (Planned) | F | 1 | 1%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 10 | 10%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 1%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.37
| All Activities w/Successors | F | 94 | 100%
| Activities Missing Successors | F | 5 | 5%
| Total # Successors | F | 136
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 1 | 1%
| Total# of Successor Lags | F | 1
| Max # of Successor Lags on Activity | F | 1
| Diverge Hotspot (Successors >2) | F | 11 | 11%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 27 | 21%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 9 | 33%
| Completed Delayed - Tasks & Milestones | F | 18 | 67%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 39
| Avg Finish Variance - Tasks & Milestones | F | 26
| Actually Finished - Tasks | F | 27 | 21%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 9 | 33%
| Completed Delayed - Tasks | F | 18 | 67%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 2 | 2%
| Extended Durations - Tasks | F | 7 | 6%
| Actually Finished - Milestones | F | 0
| Completed Ahead - Milestones | F | 0
| Completed On-Schedule - Milestones | F | 0
| Completed Delayed - Milestones | F | 0
| Actually Started - Tasks | F | 2 | 2%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 | 0%
| In-Progress Started Delayed - Tasks | F | 2 | 100%
| In-Progress Delayed Finish - Tasks | F | 2 | 100%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 85
| Avg Start Variance | F | 85
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 97 | 77%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 0 | 0%
| Planned Delayed Start - Tasks & Milestones | F | 97 | 100%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 97 | 77%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 0 | 0%
| Planned Delayed Start - Tasks | F | 97 | 100%
| Planned Delayed Finish - Tasks | F | 97 | 100%
| Scheduled to Start - Milestones | F | 0
| Planned Ahead Start - Milestones | F | 0
| Planned On Schedule Start - Milestones | F | 0
| Planned Delayed Start - Milestones | F | 0
| Planned Delayed Finish - Milestones | F | 0
| Schedule Baseline Activities | F | 126 | 100%
| Scheduled/Baselined to Start | F | 99
| Scheduled/Baselined to Finish | F | 99
| Start/ed | F | 29
| Finish/ed | F | 27
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 10 | 56%
| Completed Delayed (>30 days) | F | 11 | 61%
| SPI(t) | F | 0.91
| Scheduled Activities | F | 126 | 100%
| Scheduled to Start | F | 99 | 79%
| Scheduled to Finish | F | 99 | 79%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| High Float 10% | F | 43 | 43%
| High Float 44d | F | 56 | 57%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 4 | 4%
| Critical Milestones (To-Go) | F | 0
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Logic Density™ | F | 2.81
| CP Logic Density™ | F | 3
| Critical w/Missing Logic | F | 1 | 5%
| Critical w/Hard Constraints | F | 1 | 1%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 1 | 1%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start | F | 126
| Scheduled to Start | F | 126
| Actual Starts | F | 29
| Current Baselined to Start & Started | F | 29
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 126
| Scheduled to Finish | F | 126
| Actual Finishes | F | 27
| Current Baselined to Finish & Finished | F | 27
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| Baselined to Start - To Time Now | F | 48 | 38%
| Scheduled to Start - To Time Now | F | 48 | 38%
| Started | F | 29
| Started Late | F | 18
| Started Delayed (<=30 days) | F | 8 | 44%
| Started Delayed (Between 31 to 60 days) | F | 4 | 22%
| Started Delayed (>60 days) | F | 6 | 33%
| BEI - Value Task Starts | F | 0.6
| Baselined to Finish - To Time Now | F | 46 | 37%
| Scheduled to Finish - To Time Now | F | 46 | 37%
| Finished | F | 27
| Finished Late | F | 18
| Completed Delayed (<=30 days) | F | 7 | 39%
| Completed Delayed (Between 31 to 60 days) | F | 6 | 33%
| Completed Delayed (>60 days) | F | 5 | 28%
| BEI - Value Task Finishes | F | 0.59
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 29
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 97
| Baselined to Start - Check | F | 126
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 27
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 99
| Baselined to Finish - Check | F | 126
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 29
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 97
| Current Baseline to Finish & Finished (BL Plan) | F | 27
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 99
| Baselined to Start | F | 48
| Scheduled to Start | F | 48 | 100%
| Started - Scheduled | F | 29 | 60%
| Started - Baseline Comparison | F | 29 | 60%
| BEI - Value Task Starts | F | 0.6
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 46
| Scheduled to Finish | F | 46
| Finished | F | 27
| BEI - Value Task Finishes | F | 0.59
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-08-27
| Started (incl. Future Baseline Starts) - Scheduled | F | 29 | 23%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 29 | 23%
| Started Late (from Baseline) | F | 18
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 27 | 21%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 27 | 21%
| Finished Late | F | 18
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 18 | 67%
| Completed On-Schedule | F | 9 | 33%
| Accelerated | F | 0 | 0%
| Days Variance | F | 705 | 2611%
| Days Early | F | 0 | 0%
| Days Late | F | 705 | 2611%
| Avg Days Early | F | 0
| Avg Days Late | F | 39
| Avg Variance | F | 26
| Actually Finished | F | 27 | 21%
| Took Longer than Planned | F | 7 | 26%
| Took Less Than Planned | F | 6 | 22%
| Completed (w/Baseline Duration) | F | 27 | 21%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 27 | 59%
| Missed Durations | F | 7 | 26%
| Missed Durations & Late Actual Finish | F | 7 | 26%
| Baselined Tasks | F | 126
| Baselined to Start - TOTAL | F | 126
| Complete Task Starts - Cumulative | F | 29 | 60%
| Incomplete Task Starts - Cumulative (in work) | F | 19 | 40%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 126
| Complete Task Finishes - Cumulative (in work) | F | 27 | 59%
| Incomplete Task Finishes - Cumulative | F | 19 | 59%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - Value Tasks (adjusted) | F | 0.59
| BEI - Complete Tasks (adjusted) | F | 27 | 59%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| BEI - Complete Milestones (adjusted) | F | N/A
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| BEI - Value Tasks | F | 0.59
| BEI - Total Tasks | F | 46
| BEI - Incomplete Tasks | F | 19 | 41%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | N/A
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| BEI - Total Milestones | F | 0
| BEI - Complete Milestones | F | N/A
| BEI - Incomplete Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.59
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-08-27
| Total Activities - DRM | F | 27
| Total Activities - DRM Graph | F | 27
| Status Date | F | 2026-08-27
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | 2027-08-20
| Float to Milestone #3 - 102 | F | 55
| Milestone #4 - 103 | F | 2027-09-09
| Float to Milestone #4 - 103 | F | 55
| Milestone #5 - 104 | F | 2027-09-24
| Float to Milestone #5 - 105 | F | 55
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-08-27
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.6
| BEI - Value Task Finishes - Cumulative | F | 0.59
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1.24
| FEI - Value Task Finish - Cumulative | F | 1.24
| BEI - Value Tasks | F | 0.59
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | N/A
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.59
| BEI - Complete Tasks | F | 27 | 59%
| BEI - Incomplete Tasks | F | 19 | 41%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 5 | 5%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 5 | 5%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | 0 | 0%
| Hard Constraints | F | 1 | 1%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-08-27
| High Float 10% | F | 43 | 43%
| High Float 44d | F | 56 | 57%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 1 | 1%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | 0 | 0%
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | 0 | 0%
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 4 | 100%
| Longest Path (Tasks & Milestones) | F | 4 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | N/A | 0
| Critical Milestones (To-Go) | F | 0
| Longest Path (Milestones) | F | 0 | 0%
| Normal Tasks | F | 126 | 88%
| Normal Tasks (To-Go) | F | 99 | 88%
| Critical Tasks (To-Go) | F | 4 | 4%
| Critical Tasks (In Progress) | F | 0 | 0%
| Zero Days Float | F | 4 | 4%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 3
| Time Now | F | 2026-08-27
| Forecast to be Finished | F | 46 | 37%
| Completed On Time | T | 9 | 20%
| Completed Late | F | 18 | 39%
| Not Completed | F | 19 | 41%
| Baseline Finish Compliance | T | 20%
| Forecast to be Started | F | 48 | 38%
| Started On Time | T | 11 | 23%
| Started Late | F | 18 | 38%
| Not Started | F | 19 | 40%
| Baseline Start Compliance | F | 25%
1 | Completed Activities | F | 27
HSD01 | Time Now | F | 2026-08-27
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 19 | 15%
HSD04 | Started Late | F | 18 | 38%
HSD05 | Forecast to be Finished but not Finished yet | T | 19 | 15%
HSD06 | Finished Late | F | 18 | 39%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2028-01-25
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | T | 2 | 100%
SEM02 | BRI Current | T | 0
SEM03 | BRI Cumulative | F | 0.59
SEM04 | BPI Current | T | 0
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.59
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 97
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 78
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 99
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | T | 19
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 78
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | T | 19
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 80
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | T | 1.24
SEM07 | To Go - Planned Task Starts - Count | T | 97
SEM07 | To Go - BEI - Task Finishes - Count | T | 99
SEM07 | To Go - Baselined Task Starts - Count | T | 97
SEM07 | To Go - BEI - Value Task Starts - Cumulative | T | 1.24
SEM07 | TC-BEI | T | 1.24
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.61
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v3_FX01_Milesto
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v3_FX01_MilestoneLate (3/31/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-03-31
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 11%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 9 | 60%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Normal Tasks (To-Go, In Progress) | F | 2 | 22%
| Critical Path (Tasks & Milestones) | F | 7 | 78%
| Critical Path (Milestones) | F | 1 | 14%
| Critical Path (Normal Tasks) | F | 6 | 86%
| Critical Path (Normal In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Near-Critical (<10 Days Float) | F | 7 | 78%
| CP Logic Density™ | F | 2.86
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| Status Date | F | 2026-03-31
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Critical Milestones (To-Go) | F | 1 | 14%
| Critical Normal Tasks (To-Go) | F | 6 | 86%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Duration Ratio Metric (DRM) | F | 5
| DRM Graph | F | 5
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| BEI - Value Activities | F | 0.75
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Critical Path To-Go | F | 7 | 78%
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-03-31
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 7 | 78%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 9 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 18
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 4 | 50%
| Critical Activities (To-Go) | F | 6 | 75%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 17
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 38%
| Activities (To-Go) | F | 8 | 62%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 11%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 9 | 100%
| No Constraints | F | 9 | 100%
| Logic Density™ | F | 2.78
| Logic Density™ - Predecessors | F | 1.67
| Logic Density™ - Successors | F | 1.11
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 7 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 9 | 100%
| All Activities w/Successors | F | 8 | 89%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 8 | 89%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.86
| All Activities w/Predecessors | F | 7 | 100%
| Total # Predecessors | F | 13
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 14%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.11
| All Activities w/Successors | F | 8 | 100%
| Activities Missing Successors | F | 1 | 11%
| Total # Successors | F | 10
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 6 | 40%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 3 | 50%
| Completed Delayed - Tasks & Milestones | F | 3 | 50%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 5
| Avg Finish Variance - Tasks & Milestones | F | 3
| Actually Finished - Tasks | F | 5 | 38%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 60%
| Completed Delayed - Tasks | F | 2 | 40%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 1 | 8%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 0 | 0%
| Completed Delayed - Milestones | F | 1 | 100%
| Actually Started - Tasks | F | 2 | 15%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 50%
| In-Progress Started Delayed - Tasks | F | 1 | 50%
| In-Progress Delayed Finish - Tasks | F | 1 | 50%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 4
| Avg Start Variance | F | 4
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 7 | 47%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 6 | 86%
| Planned Delayed Start - Tasks & Milestones | F | 1 | 14%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 6 | 46%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 5 | 83%
| Planned Delayed Start - Tasks | F | 1 | 17%
| Planned Delayed Finish - Tasks | F | 1 | 17%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 9
| Scheduled/Baselined to Finish | F | 9
| Start/ed | F | 8
| Finish/ed | F | 6
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.67
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 9 | 60%
| Scheduled to Finish | F | 9 | 60%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.86
| Critical w/Missing Logic | F | 1 | 11%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Current Baselined to Start & Started | F | 7
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Current Baselined to Finish & Finished | F | 5
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 9 | 69%
| Scheduled to Start - To Time Now | F | 9 | 69%
| Started | F | 7
| Started Late | F | 2
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.78
| Baselined to Finish - To Time Now | F | 7 | 54%
| Scheduled to Finish - To Time Now | F | 7 | 54%
| Finished | F | 5
| Finished Late | F | 2
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.71
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 6
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 5
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 8
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Baselined to Start | F | 9
| Scheduled to Start | F | 9 | 100%
| Started - Scheduled | F | 7 | 78%
| Started - Baseline Comparison | F | 7 | 78%
| BEI - Value Task Starts | F | 0.78
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 7
| Scheduled to Finish | F | 7
| Finished | F | 5
| BEI - Value Task Finishes | F | 0.71
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-03-31
| Started (incl. Future Baseline Starts) - Scheduled | F | 7 | 54%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 7 | 54%
| Started Late (from Baseline) | F | 2
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 5 | 38%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 5 | 38%
| Finished Late | F | 2
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 3 | 50%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 3 | 50%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 7 | 78%
| Incomplete Task Starts - Cumulative (in work) | F | 2 | 22%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 5 | 71%
| Incomplete Task Finishes - Cumulative | F | 2 | 71%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - Value Tasks (adjusted) | F | 0.71
| BEI - Complete Tasks (adjusted) | F | 5 | 71%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Incomplete Tasks | F | 2 | 29%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.71
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| Total Activities - DRM | F | 5
| Total Activities - DRM Graph | F | 5
| Status Date | F | 2026-03-31
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0.71
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 14%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 8 | 89%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.86
| Time Now | F | 2026-03-31
| Forecast to be Finished | F | 7 | 54%
| Completed On Time | F | 4 | 57%
| Completed Late | F | 3 | 43%
| Not Completed | F | 2 | 29%
| Baseline Finish Compliance | F | 57%
| Forecast to be Started | F | 9 | 69%
| Started On Time | F | 6 | 67%
| Started Late | F | 3 | 33%
| Not Started | F | 2 | 22%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 5
HSD01 | Time Now | F | 2026-03-31
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 2 | 15%
HSD04 | Started Late | F | 3 | 33%
HSD05 | Forecast to be Finished but not Finished yet | T | 2 | 15%
HSD06 | Finished Late | F | 3 | 43%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.67
SEM03 | BRI Cumulative | F | 0.71
SEM04 | BPI Current | F | 0.67
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 4
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 4
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 6
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.25
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v3_FX02_EarlyFi
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v3_FX02_EarlyFinish (3/31/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-03-31
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 11%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 9 | 60%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Normal Tasks (To-Go, In Progress) | F | 2 | 22%
| Critical Path (Tasks & Milestones) | F | 7 | 78%
| Critical Path (Milestones) | F | 1 | 14%
| Critical Path (Normal Tasks) | F | 6 | 86%
| Critical Path (Normal In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Near-Critical (<10 Days Float) | F | 7 | 78%
| CP Logic Density™ | F | 2.86
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| Status Date | F | 2026-03-31
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Critical Milestones (To-Go) | F | 1 | 14%
| Critical Normal Tasks (To-Go) | F | 6 | 86%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Duration Ratio Metric (DRM) | F | 5
| DRM Graph | F | 5
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| BEI - Value Activities | F | 0.75
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Critical Path To-Go | F | 7 | 78%
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-03-31
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 7 | 78%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 9 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 18
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 4 | 50%
| Critical Activities (To-Go) | F | 6 | 75%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 17
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 38%
| Activities (To-Go) | F | 8 | 62%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 11%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 9 | 100%
| No Constraints | F | 9 | 100%
| Logic Density™ | F | 2.78
| Logic Density™ - Predecessors | F | 1.67
| Logic Density™ - Successors | F | 1.11
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 7 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 9 | 100%
| All Activities w/Successors | F | 8 | 89%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 8 | 89%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.86
| All Activities w/Predecessors | F | 7 | 100%
| Total # Predecessors | F | 13
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 14%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.11
| All Activities w/Successors | F | 8 | 100%
| Activities Missing Successors | F | 1 | 11%
| Total # Successors | F | 10
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 6 | 40%
| Completed Ahead - Tasks & Milestones | F | 1 | 17%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 67%
| Completed Delayed - Tasks & Milestones | F | 1 | 17%
| Avg Days Finished Early - Tasks & Milestones | F | 6
| Avg Days Finished Late - Tasks & Milestones | F | 4
| Avg Finish Variance - Tasks & Milestones | F | 0
| Actually Finished - Tasks | F | 5 | 38%
| Completed Ahead - Tasks | F | 1 | 20%
| Completed On-Schedule - Tasks | F | 3 | 60%
| Completed Delayed - Tasks | F | 1 | 20%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 1 | 8%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 2 | 15%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 50%
| In-Progress Started Delayed - Tasks | F | 1 | 50%
| In-Progress Delayed Finish - Tasks | F | 1 | 50%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 4
| Avg Start Variance | F | 4
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 7 | 47%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 6 | 86%
| Planned Delayed Start - Tasks & Milestones | F | 1 | 14%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 6 | 46%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 5 | 83%
| Planned Delayed Start - Tasks | F | 1 | 17%
| Planned Delayed Finish - Tasks | F | 1 | 17%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 9
| Scheduled/Baselined to Finish | F | 9
| Start/ed | F | 8
| Finish/ed | F | 6
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.78
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 9 | 60%
| Scheduled to Finish | F | 9 | 60%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.86
| Critical w/Missing Logic | F | 1 | 11%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Current Baselined to Start & Started | F | 7
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Current Baselined to Finish & Finished | F | 5
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 9 | 69%
| Scheduled to Start - To Time Now | F | 9 | 69%
| Started | F | 7
| Started Late | F | 2
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.78
| Baselined to Finish - To Time Now | F | 7 | 54%
| Scheduled to Finish - To Time Now | F | 7 | 54%
| Finished | F | 5
| Finished Late | F | 1
| Completed Delayed (<=30 days) | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.71
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 6
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 5
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 8
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Baselined to Start | F | 9
| Scheduled to Start | F | 9 | 100%
| Started - Scheduled | F | 7 | 78%
| Started - Baseline Comparison | F | 7 | 78%
| BEI - Value Task Starts | F | 0.78
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 7
| Scheduled to Finish | F | 7
| Finished | F | 5
| BEI - Value Task Finishes | F | 0.71
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-03-31
| Started (incl. Future Baseline Starts) - Scheduled | F | 7 | 54%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 7 | 54%
| Started Late (from Baseline) | F | 2
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 5 | 38%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 5 | 38%
| Finished Late | F | 1
| Completed Ahead | F | 1 | 20%
| Completed Delayed | F | 1 | 20%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 1 | 20%
| Days Variance | F | -2 | -40%
| Days Early | F | 6 | 120%
| Days Late | F | 4 | 80%
| Avg Days Early | F | 6
| Avg Days Late | F | 4
| Avg Variance | F | 0
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 1 | 17%
| Took Less Than Planned | F | 1 | 17%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Completed Ahead | F | 1 | 20%
| Completed Delayed | F | 1 | 20%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 1 | 20%
| Days Variance | F | -2 | -40%
| Days Early | F | 6 | 120%
| Days Late | F | 4 | 80%
| Avg Days Early | F | 6
| Avg Days Late | F | 4
| Avg Variance | F | 0
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 1 | 17%
| Took Less Than Planned | F | 1 | 17%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 7 | 78%
| Incomplete Task Starts - Cumulative (in work) | F | 2 | 22%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 5 | 71%
| Incomplete Task Finishes - Cumulative | F | 2 | 71%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - Value Tasks (adjusted) | F | 0.71
| BEI - Complete Tasks (adjusted) | F | 5 | 71%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Incomplete Tasks | F | 2 | 29%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.71
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| Total Activities - DRM | F | 5
| Total Activities - DRM Graph | F | 5
| Status Date | F | 2026-03-31
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0.71
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 14%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 8 | 89%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.86
| Time Now | F | 2026-03-31
| Forecast to be Finished | F | 7 | 54%
| Completed On Time | F | 5 | 71%
| Completed Late | F | 2 | 29%
| Not Completed | F | 2 | 29%
| Baseline Finish Compliance | F | 71%
| Forecast to be Started | F | 9 | 69%
| Started On Time | F | 6 | 67%
| Started Late | F | 3 | 33%
| Not Started | F | 2 | 22%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 5
HSD01 | Time Now | F | 2026-03-31
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 2 | 15%
HSD04 | Started Late | F | 3 | 33%
HSD05 | Forecast to be Finished but not Finished yet | T | 2 | 15%
HSD06 | Finished Late | F | 2 | 29%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.67
SEM03 | BRI Cumulative | F | 0.71
SEM04 | BPI Current | F | 0.67
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 4
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 4
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 6
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.25
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%

## TP4_DataCenter_v3_FX03_Duratio
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities | AlltheProjects - 15976 Activities
Metric History
Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026 | Created on: 8/7/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
TP4_DataCenter_v3_FX03_DurationCut (3/31/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | %
| Status Date | F | 2026-03-31
| Specific Task Start | F | N/A
| Specific Task Finish | F | N/A
| Wrong Status - Actual Starts | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish But Still In-Progress | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| High Float 10% | F | 1 | 11%
| Negative Float | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 9 | 60%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Normal Tasks (To-Go, In Progress) | F | 2 | 22%
| Critical Path (Tasks & Milestones) | F | 7 | 78%
| Critical Path (Milestones) | F | 1 | 14%
| Critical Path (Normal Tasks) | F | 6 | 86%
| Critical Path (Normal In Progress) | F | 1 | 14%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06
| Negative Float | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Near-Critical (<10 Days Float) | F | 7 | 78%
| CP Logic Density™ | F | 2.86
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| Status Date | F | 2026-03-31
| Milestone #1 - 100 | F | N/A
| Float Milestone #1 - 100 | F | N/A
| Milestone #2 - 101 | F | N/A
| Float to Milestone #2 - 101 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 104 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Critical Milestones (To-Go) | F | 1 | 14%
| Critical Normal Tasks (To-Go) | F | 6 | 86%
| Riding Data Date | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Duration Ratio Metric (DRM) | F | 5
| DRM Graph | F | 5
| Baselined to Start | F | 8
| Scheduled to Start | F | 8
| Baselined to Finish | F | 8
| Scheduled to Finish | F | 8
| BEI - Value Activities | F | 0.75
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Critical Path To-Go | F | 7 | 78%
| Status Date | F | 2026-03-31
| Total Activities | F | 15
| Milestones | F | 2 | 13%
| Normal Tasks | F | 13 | 87%
| Summaries | F | 0 | 0%
| Hammocks | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0%
| Total Tasks & Milestones | F | 15 | 100%
| Completed Tasks & Milestones | F | 6 | 40%
| Completed Milestones | F | 1 | 50%
| Completed Tasks | F | 5 | 38%
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Milestones (To-Go) | F | 1 | 11%
| Normal Tasks (To-Go) | F | 8 | 89%
| Summaries (To-Go) | F | 0 | 0%
| Hammocks (To-Go) | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Milestones) | F | 1 | 14%
| Riding Data Date | F | 0 | 0%
| Status Date | F | 2026-03-31
| Total Activities (To-Go) - % of Total | F | 9 | 60%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Summary-to-Task Ratio (To-Go) | F | N/A | 0
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Manual Tasks (To-Go) | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 7 | 78%
| Wrong Status (To-Go) | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Missing WBS (To-Go) | F | 0 | 0%
| All Activities (To Go) | F | 9 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 9 | 100%
| Estimated Duration | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Avg. Original Duration | F | 18
| Avg. Remaining Duration | F | 16
| High Baseline Duration (44d) | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0%
| Insufficient Detail™ | F | 4 | 50%
| Critical Activities (To-Go) | F | 6 | 75%
| Avg. Critical Original Duration | F | 18
| Avg. Critical Remaining Duration | F | 17
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 3 | 38%
| Activities (To-Go) | F | 8 | 62%
| Total Constraints | F | 0 | 0%
| Start No Earlier Than | F | 0 | 0%
| Start No Later Than | F | 0 | 0%
| Finish No Earlier Than | F | 0 | 0%
| Finish No Later Than | F | 0 | 0%
| Hard Constraints | F | 0 | 0%
| Must Start On | F | 0 | 0%
| Must Finish On | F | 0 | 0%
| As Late As Possible | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Mandatory Start | F | 0 | 0%
| Mandatory Finish | F | 0 | 0%
| Open Ends with Constraints | F | 0 | 0%
| Open Ends w/o Constraints | F | 1 | 11%
| Unsatisfied Constraints | F | 0 | 0%
| No Constraints | F | 9 | 100%
| No Constraints | F | 9 | 100%
| Logic Density™ | F | 2.78
| Logic Density™ - Predecessors | F | 1.67
| Logic Density™ - Successors | F | 1.11
| Summary Links | F | N/A | 0%
| All Activities w/Predecessors | F | 7 | 100%
| SS Predecessors | F | 0 | 0%
| SF Predecessors | F | 0 | 0%
| FF Predecessors | F | 0 | 0%
| FS Predecessors | F | 9 | 100%
| All Activities w/Successors | F | 8 | 89%
| SS Successors | F | 0 | 0%
| FF Successors | F | 0 | 0%
| SF Successors | F | 0 | 0%
| FS Successors | F | 8 | 89%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.86
| All Activities w/Predecessors | F | 7 | 100%
| Total # Predecessors | F | 13
| Activities Missing Predecessors | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0%
| Total # Predecessor Leads | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0%
| Total # Predecessor Lags | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A
| Min Predecessor Lag (days) | F | 0
| Max Predecessor Lag (days) | F | 0
| Hidden Duration (Planned) | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A
| Critical Merge Hotspot | F | 1 | 14%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Logic Density™ - Successors | F | 1.11
| All Activities w/Successors | F | 8 | 100%
| Activities Missing Successors | F | 1 | 11%
| Total # Successors | F | 10
| Activities w/Leads on Successor | F | 0 | 0%
| Total# of Successor Leads | F | N/A
| Max # of Successor Leads on Activity | F | N/A
| Activities w/Lags on Successor | F | 0 | 0%
| Total# of Successor Lags | F | N/A
| Max # of Successor Lags on Activity | F | N/A
| Diverge Hotspot (Successors >2) | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 6 | 40%
| Completed Ahead - Tasks & Milestones | F | 0 | 0%
| Completed On-Schedule - Tasks & Milestones | F | 4 | 67%
| Completed Delayed - Tasks & Milestones | F | 2 | 33%
| Avg Days Finished Early - Tasks & Milestones | F | 0
| Avg Days Finished Late - Tasks & Milestones | F | 4
| Avg Finish Variance - Tasks & Milestones | F | 1
| Actually Finished - Tasks | F | 5 | 38%
| Completed Ahead - Tasks | F | 0 | 0%
| Completed On-Schedule - Tasks | F | 3 | 60%
| Completed Delayed - Tasks | F | 2 | 40%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0%
| Extended Durations - Tasks | F | 1 | 8%
| Actually Finished - Milestones | F | 1 | 50%
| Completed Ahead - Milestones | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 | 0%
| Actually Started - Tasks | F | 2 | 15%
| In-Progress Started Ahead - Tasks | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 1 | 50%
| In-Progress Started Delayed - Tasks | F | 1 | 50%
| In-Progress Delayed Finish - Tasks | F | 1 | 50%
| Avg Days Started Early | F | 0
| Avg Days Started Late | F | 4
| Avg Start Variance | F | 4
| Expected Finish | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 7 | 47%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0%
| Planned On Schedule Start - Tasks & Milestones | F | 6 | 86%
| Planned Delayed Start - Tasks & Milestones | F | 1 | 14%
| Riding Data Date - Tasks & Milestones | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0%
| Scheduled to Start - Tasks | F | 6 | 46%
| Planned Ahead Start - Tasks | F | 0 | 0%
| Planned On Schedule Start - Tasks | F | 5 | 83%
| Planned Delayed Start - Tasks | F | 1 | 17%
| Planned Delayed Finish - Tasks | F | 1 | 17%
| Scheduled to Start - Milestones | F | 1 | 50%
| Planned Ahead Start - Milestones | F | 0 | 0%
| Planned On Schedule Start - Milestones | F | 1 | 100%
| Planned Delayed Start - Milestones | F | 0 | 0%
| Planned Delayed Finish - Milestones | F | 0 | 0%
| Schedule Baseline Activities | F | 15 | 100%
| Scheduled/Baselined to Start | F | 9
| Scheduled/Baselined to Finish | F | 9
| Start/ed | F | 8
| Finish/ed | F | 6
| Start Variance (Phase) | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100%
| Finish Variance (Phase) | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100%
| Started Delayed (>30 days) | F | 0 | 0%
| Completed Delayed (>30 days) | F | 0 | 0%
| SPI(t) | F | 0.67
| Scheduled Activities | F | 15 | 100%
| Scheduled to Start | F | 9 | 60%
| Scheduled to Finish | F | 9 | 60%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 7 | 78%
| Critical Milestones (To-Go) | F | 1 | 100%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Milestone-to-Task Ratio (To-Go) | F | 1:08 | 0.13
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Logic Density™ | F | 2.67
| CP Logic Density™ | F | 2.86
| Critical w/Missing Logic | F | 1 | 11%
| Critical w/Hard Constraints | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Critical LOE | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A
| Critical CEI - Total Tasks | F | 0
| Critical CEI - Complete Tasks | F | N/A
| Critical CEI - Incomplete Tasks | F | N/A
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start | F | 13
| Scheduled to Start | F | 13
| Actual Starts | F | 7
| Current Baselined to Start & Started | F | 7
| Past Baselined to Start & Started | F | 0
| Future Baseline to Start & Started | F | 0
| Baselined to Finish | F | 13
| Scheduled to Finish | F | 13
| Actual Finishes | F | 5
| Current Baselined to Finish & Finished | F | 5
| Past Baselined to Finish & Finished | F | 0
| Future Baselined to Finish & Finished | F | 0
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| Baselined to Start - To Time Now | F | 9 | 69%
| Scheduled to Start - To Time Now | F | 9 | 69%
| Started | F | 7
| Started Late | F | 2
| Started Delayed (<=30 days) | F | 2 | 100%
| Started Delayed (Between 31 to 60 days) | F | 0 | 0%
| Started Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Starts | F | 0.78
| Baselined to Finish - To Time Now | F | 7 | 54%
| Scheduled to Finish - To Time Now | F | 7 | 54%
| Finished | F | 5
| Finished Late | F | 2
| Completed Delayed (<=30 days) | F | 2 | 100%
| Completed Delayed (Between 31 to 60 days) | F | 0 | 0%
| Completed Delayed (>60 days) | F | 0 | 0%
| BEI - Value Task Finishes | F | 0.71
| Started - Future | F | 0
| Not Baselined to Start | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Started | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 6
| Baselined to Start - Check | F | 13
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Finish & Finished - Check | F | 5
| Current Baseline to Finish & Finished Past - Check | F | 0
| Current Baseline to Finish & Finished Future - Check | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 8
| Baselined to Finish - Check | F | 13
| Future Baseline to Finish & Finished - Check | F | 0
| Current Baseline to Start & Started (BL Plan) | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 6
| Current Baseline to Finish & Finished (BL Plan) | F | 5
| Future Baseline to Finish & Finished (Early Finishes) | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 8
| Baselined to Start | F | 9
| Scheduled to Start | F | 9 | 100%
| Started - Scheduled | F | 7 | 78%
| Started - Baseline Comparison | F | 7 | 78%
| BEI - Value Task Starts | F | 0.78
| HMI - Value Task Starts | F | N/A
| CEI - Value Task Starts | F | N/A
| Baselined to Finish | F | 7
| Scheduled to Finish | F | 7
| Finished | F | 5
| BEI - Value Task Finishes | F | 0.71
| HMI - Value Task Finishes | F | N/A
| CEI - Value Task Finishes | F | N/A
| Status Date | F | 2026-03-31
| Started (incl. Future Baseline Starts) - Scheduled | F | 7 | 54%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 7 | 54%
| Started Late (from Baseline) | F | 2
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 5 | 38%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 5 | 38%
| Finished Late | F | 2
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 2 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Completed Ahead | F | 0 | 0%
| Completed Delayed | F | 2 | 40%
| Completed On-Schedule | F | 3 | 60%
| Accelerated | F | 0 | 0%
| Days Variance | F | 8 | 160%
| Days Early | F | 0 | 0%
| Days Late | F | 8 | 160%
| Avg Days Early | F | 0
| Avg Days Late | F | 4
| Avg Variance | F | 2
| Actually Finished | F | 5 | 33%
| Took Longer than Planned | F | 2 | 33%
| Took Less Than Planned | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 5 | 38%
| Completed (w/o Baseline Duration) | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | 5 | 71%
| Missed Durations | F | 1 | 20%
| Missed Durations & Late Actual Finish | F | 1 | 20%
| Baselined Tasks | F | 13
| Baselined to Start - TOTAL | F | 13
| Complete Task Starts - Cumulative | F | 7 | 78%
| Incomplete Task Starts - Cumulative (in work) | F | 2 | 22%
| Old Incomplete Task Starts in Status Period | F | N/A
| Baselined to Finish | F | 13
| Complete Task Finishes - Cumulative (in work) | F | 5 | 71%
| Incomplete Task Finishes - Cumulative | F | 2 | 71%
| Old Incomplete Task Finishes in Status Period | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - Value Tasks (adjusted) | F | 0.71
| BEI - Complete Tasks (adjusted) | F | 5 | 71%
| BEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| BEI - Value Milestones (adjusted) | F | 1
| BEI - Complete Milestones (adjusted) | F | 1 | 100%
| BEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Complete Tasks | F | N/A
| HMI - Completed Early Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - Value Tasks (adjusted) | F | N/A
| HMI - Complete Tasks (adjusted) | F | N/A
| HMI - Complete Future Tasks (adjusted) | F | N/A
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Completed Early Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| HMI - Value Milestones (adjusted) | F | N/A
| HMI - Complete Milestones (adjusted) | F | N/A
| HMI - Complete Future Milestones (adjusted) | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| CEI - Complete Tasks (adjusted) | F | N/A
| CEI - Complete Future Tasks (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| CEI - Complete Milestones (adjusted) | F | N/A
| CEI - Complete Future Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| BEI - Value Tasks | F | 0.71
| BEI - Total Tasks | F | 7
| BEI - Incomplete Tasks | F | 2 | 29%
| HMI - Value Tasks | F | N/A
| HMI - Total Tasks | F | 0
| HMI - Incomplete Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Total Tasks | F | 0
| CEI - Incomplete Tasks | F | N/A
| BEI - Complete Milestones | F | 1 | 100%
| HMI - Complete Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| BEI - Value Milestones | F | 1
| BEI - Total Milestones | F | 1
| BEI - Complete Milestones | F | 1 | 100%
| BEI - Incomplete Milestones | F | 0 | 0%
| HMI - Value Milestones | F | N/A
| HMI - Total Milestones | F | 0
| HMI - Complete Milestones | F | N/A
| HMI - Incomplete Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| CEI - Total Milestones | F | 0
| CEI - Complete Milestones | F | N/A
| CEI - Incomplete Milestones | F | N/A
| BEI - Value Tasks (adjusted) | F | 0.71
| HMI - Value Tasks (adjusted) | F | N/A
| CEI - Value Tasks (adjusted) | F | N/A
| BEI - Value Milestones (adjusted) | F | 1
| HMI - Value Milestones (adjusted) | F | N/A
| CEI - Value Milestones (adjusted) | F | N/A
| Status Date | F | 2026-03-31
| Total Activities - DRM | F | 5
| Total Activities - DRM Graph | F | 5
| Status Date | F | 2026-03-31
| Milestone #1 - 5158 | F | N/A
| Float Milestone #1 - 5158 | F | N/A
| Milestone #2 - 4786 | F | N/A
| Float to Milestone #2 - 4786 | F | N/A
| Milestone #3 - 102 | F | N/A
| Float to Milestone #3 - 102 | F | N/A
| Milestone #4 - 103 | F | N/A
| Float to Milestone #4 - 103 | F | N/A
| Milestone #5 - 104 | F | N/A
| Float to Milestone #5 - 105 | F | N/A
| New Activities Since Previous Status Date | F | 0
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| Status Date | F | 2026-03-31
| Margin - Margin Task Name #1 | F | N/A
| Margin - Margin Task Name #2 | F | N/A
| Margin - Margin Task Name #3 | F | N/A
| Margin - Margin Task Name #4 | F | N/A
| Margin - Margin Task Name #5 | F | N/A
| Margin - Margin Task Name #6 | F | N/A
| Margin - Margin Task Name #7 | F | N/A
| BEI - Value Task Starts - Cumulative | F | 0.78
| BEI - Value Task Finishes - Cumulative | F | 0.71
| HMI - Value Task Starts - by Status Dates | F | N/A
| HMI - Value Task Finishes - by Status Dates | F | N/A
| CEI - Value Task Starts - by Status Dates | F | N/A
| CEI - Value Task Finishes - by Status Dates | F | N/A
| FEI - Value Task Starts - Cumulative | F | 1
| FEI - Value Task Finish - Cumulative | F | 1
| BEI - Value Tasks | F | 0.71
| HMI - Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| BEI - Value Milestones | F | 1
| HMI - Value Milestones | F | N/A
| CEI - Value Milestones | F | N/A
| BEI - Value Tasks | F | 0.71
| BEI - Complete Tasks | F | 5 | 71%
| BEI - Incomplete Tasks | F | 2 | 29%
| BEI - CP Tasks - Planned Cumulative | F | 0
| BEI - CP Value Tasks | F | N/A
| HMI - Value Tasks | F | N/A
| HMI - Complete Tasks | F | N/A
| HMI - Incomplete Tasks | F | N/A
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A
| HMI - CP Value Tasks | F | N/A
| CEI - Value Tasks | F | N/A
| CEI - Complete Tasks | F | N/A
| CEI - Incomplete Tasks | F | N/A
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A
| CEI - CP Value Tasks | F | N/A
| Wrong Status | F | 0 | 0%
| Invalid Forecast Dates | F | 4 | 44%
| Expected Finish | F | 0 | 0%
| Missing WBS | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0%
| Activities with Duration=0 | F | 0 | 0%
| Estimated Duration | F | 0 | 0%
| Missing Logic | F | 1 | 11%
| Missing Predecessors | F | 0 | 0%
| Missing Successors | F | 1 | 11%
| Open Start | F | 0 | 0%
| Open Finish | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0%
| Summary Links | F | N/A | 0%
| Hard Constraints | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0%
| Negative Float | F | 0 | 0%
| Status Date | F | 2026-03-31
| High Float 10% | F | 1 | 11%
| High Float 44d | F | 0 | 0%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0%
| Critical Merge Hotspot | F | 1 | 14%
| Merge Hotspot w/Predecessor Lags | F | N/A
| Critical Diverge Hotspot | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A
| Riding Data Date | F | 0 | 0%
| Deadlines | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 6 | 86%
| Longest Path (Tasks & Milestones) | F | 7 | 100%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:06 | 0.17
| Critical Milestones (To-Go) | F | 1 | 100%
| Longest Path (Milestones) | F | 1 | 14%
| Normal Tasks | F | 13 | 87%
| Normal Tasks (To-Go) | F | 8 | 89%
| Critical Tasks (To-Go) | F | 6 | 75%
| Critical Tasks (In Progress) | F | 1 | 17%
| Zero Days Float | F | 7 | 78%
| Negative Float | F | 0 | 0%
| CP Logic Density™ | F | 2.86
| Time Now | F | 2026-03-31
| Forecast to be Finished | F | 7 | 54%
| Completed On Time | F | 4 | 57%
| Completed Late | F | 3 | 43%
| Not Completed | F | 2 | 29%
| Baseline Finish Compliance | F | 57%
| Forecast to be Started | F | 9 | 69%
| Started On Time | F | 6 | 67%
| Started Late | F | 3 | 33%
| Not Started | F | 2 | 22%
| Baseline Start Compliance | F | 100%
1 | Completed Activities | F | 5
HSD01 | Time Now | F | 2026-03-31
HSD02 | Label | F | N/A
HSD03 | Forecast to be Started but not Started yet | T | 2 | 15%
HSD04 | Started Late | F | 3 | 33%
HSD05 | Forecast to be Finished but not Finished yet | T | 2 | 15%
HSD06 | Finished Late | F | 3 | 43%
HSD06 | Total days delay in the half step (Days) | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0
HSD08 | Total days ahead in the half step (Days) | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0
HSD10 | Cumulative Finish Impact (Days) | F | 0
HSD10 | Net Finish Impact (Days) | F | 0
HSD20 | Project Finish | F | 2026-06-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | 0 | 0%
SEM01 | Workoff Burden | F | 0 | 0%
SEM02 | BRI Current | F | 0.67
SEM03 | BRI Cumulative | F | 0.71
SEM04 | BPI Current | F | 0.67
SEM05 | BEI Current | T | 0.67
SEM06 | BEI Cumulative | T | 0.71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | Workoff Burden - Starts To-Go (Total) | F | 4
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | F | 4
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 6
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | F | 4
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 6
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1
SEM07 | To Go - Planned Task Starts - Count | T | 4
SEM07 | To Go - BEI - Task Finishes - Count | T | 6
SEM07 | To Go - Baselined Task Starts - Count | T | 4
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1
SEM07 | TC-BEI | F | 1
SEM08 | FRI Current | F | N/A
SEM09 | Delta (BEI vs TC-BEI) | T | -0.25
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0%