## What the results mean
Topic | Severity | Finding | What it means | Evidence
Planned-date realism | BAD | The planned finish for 'QJ29ZvAvtEjBcpqHDer1' (2029-04-19) is only about 1% likely to be met — the plan is optimistic. | Fewer than about 1 outcome in 7 finishes by the planned date. Do not commit to this date as-is: add visible schedule contingency or retire risk first. | Planned finish: 2029-04-19; Chance of meeting it: 1%
Commitment dates | INFO | For an even-odds date, plan on 2030-08-05; to promise with 80% confidence, plan on 2030-08-28. | Standard practice (Hulett, GAO, NASA): manage the team to the 50/50 date and commit externally at the 80% date — the gap between them is your schedule contingency. | P50 (even odds): 2030-08-05; P80 (commitment): 2030-08-28
Contingency needed | WARN | Protecting an 80%-confidence promise takes about 354 working days of schedule contingency beyond the current plan. | Add it as explicit, visible schedule margin before the committed milestone — not hidden padding inside activity durations. | Planned finish: 2029-04-19; P80 finish: 2030-08-28; Contingency: 354 working days
Predictability | INFO | The realistic finish window spans about 321 working days (2029-06-25 to 2030-09-17). | The wider this window, the less predictable the finish. Narrow it by firming up the drivers named below — they contribute the most spread. | P10 (early): 2029-06-25; P90 (late): 2030-09-17; Window: 321 working days
Costliest risks | WARN | The discrete risks that cost the most time when they hit: 'Test Risk' (occurs in 86% of runs, costs ~304 working days); 'Test Risk 2' (occurs in 63% of runs, costs ~39 working days). | These are the highest-value mitigation targets — reduce their likelihood or blunt their impact, then re-run to see the finish window tighten. | Test Risk: 86% occurrence, ~304 working days impact; Test Risk 2: 63% occurrence, ~39 working days impact
Sampling precision | INFO | 2,000 iterations is screening precision. | Fine for exploration; use 2,500+ iterations for decisions and about 10,000 for final reports (Hulett). | Iterations: 2,000

## Run setup
Field | Value
Focus event | 152 - QJ29ZvAvtEjBcpqHDer1
Occurrence mode | random_each
Correlation | 0
Risk register | on
Sampling | mc
Probabilistic branches | off
Conditional branches | off
Iterations | 2000
Schedule | Longstar Master IMS

## Per-task durations
UID | Task | Factor | Best case d | Worst case d
150 | 7cu6yvdJV8ndF0CYMHk8 | 3
152 | QJ29ZvAvtEjBcpqHDer1 | 2
155 | 1yu6CrDX9QU5hWE1UWMV | 1
156 | 0RXSkgYJdrs7AeQvgU3w | 1
157 | DYCfhHgWVvjY4WPSrw6q | 1
166 | KkWbk0R1FXz2L56lHFvV | 4 | 1.76 | 3.08
168 | MT1CsCIMkhjJER6f3fjG | 5
173 | vJHK0TlIBzGpfYqdt8YI | 5
177 | V4ys3lAm8KEbtjGqLAuR | 5
178 | Cncpm0GACo0ppNIEy1Gp | 4
180 | 9Vp3PBZnh9TpV8TGBWRG | 1
193 | nJh7oj8wCJYW8hyepdLI | 2
194 | wTcNF86mfD2cPQPmQB1c | 3
196 | kzYOxx4jS6vhIcTyxNFn | 1
197 | LZAvhCOF77OBkAngJSDi | 4
198 | X7Nxs9NuQXJ5Bf6aQwVp | 4
199 | TiaYdQ98Ovd3qBAfSAyG | 3
200 | yynHcCtrZd0Ye6iQJb2E | 3
202 | mjF0YLun5LIdlxtu3zFl | 4
203 | 2a1x42QofxcVsgjcXtkr | 5
204 | 8T22gllTunmLl2jY7IMk | 4
205 | dm3U5Xjvi5rN2LqWegXW | 4
206 | ZOAcdJHtChBG5MUjo5uw | 1
209 | 0FNuAiL5ZzPZSZ3dZfoV | 2
428 | pxWL5EoMWeaDmapfAV7m | 3 | 1.3 | 2.42
436 | OGXVzK31PKUn8DxCdn94 | 1 | 17.05 | 37.51
576 | m8O5CFAYfVbtxxZI5qQW | 4 | 11.82 | 20.69
605 | HP2TrbmUH5Qc4V2P2k1T | 3 | 11.95 | 22.19
632 | tuv9OmQcJHKkVCVrbrrv | 5 | 5.72 | 9.54
633 | FgJ5XjjThZN85XQOJ0nJ | 3 | 13.79 | 25.61
634 | o4DRQRcsScdVmCSXNbxF | 3 | 7.17 | 13.31
635 | ztvy5zkS4z9HirKgvHGY | 2 | 10.56 | 21.12
636 | ZpIfqMwIaczq2BqznW2q | 4 | 6.24 | 10.92
637 | 3VAZwvp2NS6usl0wrvOM | 1 | 3.63 | 7.99
638 | 34zoFClD9RS7gLTCPZs0 | 1 | 2.5 | 5.49
640 | 10AmMHkCz4b8n0xqbyCt | 2 | 2.69 | 5.39
641 | KUqcSNVxncHPLVJNV5ca | 3 | 0.81 | 1.51
642 | chCwawHUqn0ea2ArCnKB | 1 | 0.21 | 0.46
643 | xZBRzE3QVYmQCjnzxLQv | 3 | 3 | 5.56
644 | tUTeQ74YpmkuuOiouSXU | 3 | 3.17 | 5.89
645 | mSrjcTZmK12EdJmOEYFi | 3 | 0.62 | 1.14
646 | Haue3rYYySw3jbXWnBeq | 4 | 2.96 | 5.18
647 | 6jlP0Y4QQ5KPQWxvolLg | 3 | 0.72 | 1.34
656 | lzPFAx9Fh8cDxyQ3uxFX | 2 | 0.78 | 1.56
658 | PyBKEPMZMe2YeOC66yut | 4 | 8.26 | 14.45
664 | H1KB0K8mM12Opvc4oDP1 | 5 | 2.82 | 4.7
665 | FIEbexlYHnOcZkEBs7WM | 2 | 2.93 | 5.87
666 | OcAHNnZWZgiwxfUiheGU | 1 | 1.92 | 4.22
667 | HPj21Hyun1nWvxJOQMhf | 4 | 24.89 | 43.55
671 | ZM52W2kHJJCM7052Da3J | 2 | 1.03 | 2.06
672 | AcRvLPQ7WrNfvcLBOWzV | 5 | 1.18 | 1.96
678 | N57z7OkXN935WcKbC4jO | 1 | 0.52 | 1.14
700 | PZaQwD8fp0dlxZIxEZEd | 4 | 258.9 | 453.07
745 | aO52oWR4hBrrP5GVCo2a | 3 | 5.79 | 10.75
746 | qMC0J8brk1dsdpzlKrk7 | 2 | 6.55 | 13.1
747 | nul8vpOEtI2Q6W5Q0Qo9 | 1 | 6.14 | 13.5
748 | M1HHh2K01o23jS8vpDxS | 2 | 6.5 | 13.01
749 | Q6UXOpf9Kvzek7IGY0vp | 2 | 5.59 | 11.17
750 | lsyrPytnmjLTpXFywa7Z | 3 | 8.12 | 15.08
751 | AADJzuTGAb4gWytj7CQi | 3 | 11.86 | 22.04
752 | r0c0rFS4EkOGynasmiCG | 4 | 29.66 | 51.9
753 | 8158sxzbHZvZEVAAqewP | 5 | 62.41 | 104.01
754 | hfPeDXfQSV7Nx9zb2rD7 | 1 | 3.23 | 7.11
755 | DQUdswbbJv1Qpkj0EGFX | 4 | 6.24 | 10.92
756 | ae3T3d3nFoXZXK7gqkAr | 5 | 18.14 | 30.24
757 | wbc1AZ0GUhXzQk6SoWIe | 3 | 4.47 | 8.29
758 | FbN1rrQYTlsz1haWZnFy | 5 | 5.18 | 8.64
759 | cZuo3MY7iyDrOJC1qVJx | 1 | 2.24 | 4.92
760 | 7IpOsslq7gyebnCTulxX | 4 | 52.08 | 91.14
761 | x6fNhJzs4uMW9trtiNEW | 5 | 0.9 | 1.5
762 | nRInnITHYgcDsU5KDg6m | 3 | 4.45 | 8.27
763 | hLK2cdXSS7IhOZR53PgI | 2 | 3.13 | 6.25
764 | wTf98lLeHiXAkWj17mAH | 5 | 53.09 | 88.48
765 | qOEfFivvitnF8cw9csOP | 1 | 0.54 | 1.18
786 | 5RJIBxVgSA4dodMzOCsx | 5 | 1.07 | 1.78
795 | 85yV4lhIxXIziyB5R2QA | 2 | 0.55 | 1.1
844 | 1qfp8o9PQxr9vZvO7S5k | 1 | 0.46 | 1.01
866 | 0rLFG0X22Uukcn0axQTO | 5 | 45.22 | 75.36
900 | ANUK0HdVlI2Jd5hSzs0f | 1
901 | HcFqHITfVdYMyzVb3S8v | 5 | 18.42 | 30.7
902 | nIjAIVHCOoi1ijXym0cI | 4 | 2.39 | 4.19
903 | UDGopgZ2sb1QsQEooZ9G | 2 | 4.2 | 8.4
904 | 4CH3NSJx1luiHbrrAEJg | 4 | 1.52 | 2.66
905 | MxRWNVEH6ZVBPqNnA2hI | 3 | 4.07 | 7.57
906 | PL0zn2U2NPPXQqakkHLb | 2 | 2.8 | 5.6
907 | 5mTVpVcHzmsYLVY8xpKs | 1 | 2.44 | 5.37
916 | d4bxhxtQW3GaLrDrUlf9 | 5 | 17.51 | 29.19
917 | mbDdHZHm9OoYye329Ue6 | 4 | 1.04 | 1.82
1458 | W2l89btZYbaZZjxZTUR4 | 5 | 10.96 | 18.27
1459 | MxsNofofvf6CR0hsGInx | 1 | 0.48 | 1.06
1462 | 2Cc6AJ3gtv1XGHwG4F9W | 5 | 1.31 | 2.19
1464 | VN7GLU7alOC9oD3kkW9q | 4 | 30.5 | 53.37
1465 | i7zbkIpCuBMJlMsq6ma0 | 2 | 0.6 | 1.2
1468 | 8e77YoSi4abIbMILI8hH | 2 | 2.9 | 5.8
1469 | MZooHRTMNCHrNy0nPaCQ | 2 | 0.68 | 1.36
1470 | PdTqfNwd2IKBXe26tWkB | 5 | 1.34 | 2.24
1471 | FsiT4ZMTOq9hGqZQQdYf | 3 | 9.56 | 17.76
1472 | KG0YDAdikr58WjA79FVb | 4 | 6.35 | 11.12
1475 | suCYO4gIoCSrnZchT6aQ | 5 | 3.27 | 5.44
1476 | gbuDNYIgLq2nB3WERl4p | 5 | 33.19 | 55.32
1477 | BC1NYB3fqAlfckX7ECXI | 1 | 0.34 | 0.76
1478 | UR7xa7LgN3sMlpzxRjvW | 3 | 1.64 | 3.04
1485 | R0QJsNVi0JzXq4FadBdS | 5 | 19.64 | 32.73
1489 | pYq4lU1lCt1U75q3gu6M | 2 | 7.37 | 14.75
1490 | hF9FI1LNvFfgTTXhqPsR | 5 | 70.1 | 116.84
1491 | XpTPefWn9TT3C06gw8rA | 4 | 0.92 | 1.61
1495 | 0kid3Dd3U5gCQNrt2pwY | 5 | 0.99 | 1.65
1496 | 5t2MhilpkZRDQA3VTcGS | 3 | 34.89 | 64.81
1497 | q56IdotBOPeXlK3605d6 | 1 | 0.5 | 1.09
1504 | ndaml8HRsqEWzWIKrI7h | 2 | 3.26 | 6.53
1505 | 4c3z8pWafVxAWNC1MpC9 | 5 | 92.29 | 153.81
1506 | zNKWNUMZ7wFR6LBQ8bZ2 | 5 | 1.24 | 2.07
1508 | SDZ1pqYbdynEzXZrWujj | 5 | 24.62 | 41.04
1509 | xdWSZU8MxGE52WBHNu6X | 3 | 0.83 | 1.55
1518 | qXbL36bdYftxHm1TCntK | 3 | 0.6 | 1.1
1531 | KX1eD2ASIZaZBZuqoVp4 | 4 | 0.81 | 1.41
1532 | fQ3wcWF8uEWMRGpUCxEA | 2 | 0.54 | 1.08
1533 | juvdtwZkjArAkPOzLrhN | 5 | 13.9 | 23.16
1534 | SuchbNnj1ndABAEPQlrb | 5 | 9.56 | 15.93
1537 | HoYmSEeaxBfAYgcISNXh | 4 | 3.96 | 6.93
1538 | 1Xm6i4dPIyAKJzF1jRtD | 4 | 37.21 | 65.11
1541 | ss8yD9dhZfTIp9UxqHnG | 2 | 0.49 | 0.98
1542 | VmFPpoMfVfLEXeRBF7Um | 3 | 5.56 | 10.32
1543 | P2oxmSB7jXG6Ib9VEZ89 | 4 | 8.86 | 15.51
1547 | K0gsOWDMqaySswr72BAQ | 3 | 0.76 | 1.42
1548 | 4jCrHn72KCapTPEI9TzQ | 2 | 1.25 | 2.5
1549 | s8gTUDwRZFDpCO4enZqk | 5 | 285.63 | 476.06
1550 | UoQFPyMNVa9QPyq2kgrl | 1 | 4.12 | 9.05
1561 | 8BMHpFsmSFY1BvBQKfdD | 4 | 9.21 | 16.11
1562 | lBuCdKTmKHrCdvS4FVbB | 2 | 24.2 | 48.4
1563 | TUxQ6kz9ittb2zcmlLCL | 2 | 5.75 | 11.5
1564 | OkMyUpJo7fqJaif9Jvyb | 3 | 3.35 | 6.23
1565 | 9BGxipQLCi4kED7E7faW | 4 | 3.34 | 5.85
1566 | KFj0hxHWvExDoqTqgDeg | 4 | 92.5 | 161.88
1567 | GV5or0ucuouXZiqAkH0N | 4 | 9.24 | 16.17
1568 | JI4xSRBKV4FYnRXdw7Wz | 3 | 5.42 | 10.08
1569 | DVuFJt4FGQSIgeZkA41d | 1 | 1.42 | 3.11
1570 | 9hmrS48cr19KgrseY4yN | 1 | 0.9 | 1.98
3681 | wdhUrQuIMTMPn1LoqO1m | 1 | 8.46 | 18.62
3683 | JW3LUw009FZ7ddD6CdLX | 2 | 13.05 | 26.1
3684 | g3f8U3i4iakOhylueut6 | 5 | 5.9 | 9.84
3686 | 7zhxjkpiLTAH9tiW1eYy | 5 | 21.84 | 36.4
3687 | 0zzWvesUS18qEUfjK5NH | 4 | 4.17 | 7.29
3688 | zSUYYsBrfiOGi6qJakS6 | 5 | 4.76 | 7.94
3689 | X7sWUqInOJZ9zcVzmfT1 | 3 | 3.58 | 6.66
3690 | 8YDpqEvemQaMsfVmGpF8 | 4 | 4.55 | 7.97
3692 | xRsKOxB8zGAnVTXugcHQ | 4 | 16.94 | 29.65
3693 | Hn8rBaTvxeP9Vb10zF48 | 4 | 4.1 | 7.18
3695 | lT6NpgfSYqKHtVYFLSzF | 5 | 25.47 | 42.45
3696 | gijouZuJR1ZVcSfHKSTf | 3 | 4.21 | 7.81
3697 | 1158ttL4JEmZYV6RmdcS | 4 | 4.69 | 8.2
3698 | AKCwPpEPQi4iH3XDRpiM | 4 | 5.18 | 9.07
3700 | WE9bFDn3y5M7oiID5UPj | 1 | 9.19 | 20.22
3701 | CXSHp4tESy2S0nMNpo3C | 3 | 3.74 | 6.96
3702 | sTuPByKbZEfSXxt0Z2G9 | 3 | 4.43 | 8.23
3704 | 3CXbrhXJooXd98jlpAkg | 1 | 6.84 | 15.04
3705 | RO9RShNcg0h7x9fD24Zk | 2 | 1.95 | 3.9
3706 | w8MhGnhxyXFIHvJdw6bc | 2 | 3.5 | 7
3707 | dJNKgtiJ1M8pNoPOlZcZ | 4 | 4.56 | 7.98
3708 | 84VtM14FQkMGurZDdBLv | 3 | 3.48 | 6.46
3710 | KOKaQwRJEoC6vlU3mKjm | 4 | 17.03 | 29.81
3711 | XXu8BmtFqx4o2r8a6o98 | 3 | 3.84 | 7.14
3712 | sZwrgRbHYjKWcIa9rVK3 | 5 | 5.16 | 8.6
3713 | 4NbryuRKpmrExDEDqArG | 1 | 2.22 | 4.87
3714 | Fbm1iHrhCX8z8SNRXJuq | 5 | 6.08 | 10.12
3716 | bdy5zVX59rD935sK6M5v | 2 | 11.5 | 22.99
3717 | 5PdqCAMtbYgi5VsFO6ls | 1 | 9.07 | 19.95
3719 | B9ymEBZ7zimHMMqNS20Q | 1 | 5.5 | 12.09
3721 | 45j7fpB55qVEeWfRBgCv | 3 | 0.7 | 1.3
3722 | hYa6Ppkzu6veYWmxHffd | 3 | 18.44 | 34.26
3724 | ZCOxRRLLrh9Pa7VnBAyk | 4 | 18.9 | 33.08
3725 | 8cgOIQk4rBKvjXdBm8mF | 1 | 33.46 | 73.61
3727 | rGcF2XgkgPtqRDM3KJ2D | 5 | 28.87 | 48.12
3728 | Hgqc9wbzS3SDikBm20zt | 4 | 27.69 | 48.45
3730 | TswICWhG0Mjj1DenbPW5 | 3 | 20.96 | 38.94
3731 | 02LiOyWN4DF8GOeNSP5s | 2 | 9.73 | 19.46
3732 | x85AkT9s5HT2a4U2goND | 5 | 21.48 | 35.8
3734 | cAszcoDUs4YPdXAiXa4B | 3
3735 | rgqtw8hyurrfag2amXLA | 4 | 85.77 | 150.09
3736 | eIMYQUSTObIc5Lp6kKBE | 1 | 13.4 | 29.49
3737 | z19Wnme0hJcfEI4IfIQR | 3 | 15.64 | 29.06
3739 | Ba23bBwg4xGpRd3Ht4kS | 1 | 10.62 | 23.36
3740 | lRtbtcrLyr1QGd0laoJi | 4 | 21.13 | 36.97
3741 | V05WnFKB5t2LuixhoKHO | 4 | 23.24 | 40.67
3742 | LRjVz0hoZuIRlQgcLYzs | 3 | 19.45 | 36.13
3776 | GHLE38QRMYNBeSYAGB18 | 5 | 30.43 | 50.72
3777 | YuGKQIQDxLVYRZzgUQjw | 3 | 5.7 | 10.58
3809 | ukioB4iHiwrfEXpseTiK | 3 | 11.03 | 20.49
3810 | CJxWy7PnZPcI4EPHEeme | 2 | 3.99 | 7.98
3811 | wGtgxCT3lCK6u2EOL8xN | 1 | 1.72 | 3.8
3813 | sYeTNUsya13QYMbMJg21 | 4 | 20.74 | 36.29
3814 | c3HTuVFoRVefrW72mxSE | 3 | 2.05 | 3.81
3815 | nJJAkVwt0aHLNZMMtbkw | 4 | 2.14 | 3.75
3817 | LqjKPVRVNU7j1iAlkL3t | 3 | 1.44 | 2.68
3818 | Cmm1EfLtBPedDjXV8dAv | 5 | 4.39 | 7.32
3819 | FSVjbKFfUmqE2fpbGGPv | 3 | 1.67 | 3.09
3820 | FhKtXXrOwkDfPm4RFzRW | 3 | 7.74 | 14.38
3821 | cHjYAw102skS4vR6DXqX | 3 | 17.14 | 31.84
3849 | PKYN5IsyqbTocjyswPFM | 2 | 7.78 | 15.56
3858 | pWvg9Owxac1jXAINT5hs | 1 | 9.52 | 20.96
3859 | xrpLG6wlwOL4sRwHPU5B | 3 | 20.18 | 37.48
3861 | rvfyADOJtzNcPT3VL85f | 4 | 96.89 | 169.55
3862 | FUtleP4nAJHYxzLOWKZH | 2 | 11.32 | 22.64
3865 | ZK3GDclfde20Vh8DU71K | 4 | 25.44 | 44.52
3866 | 8Zrc7ItBhrTjO1TWxqmf | 3 | 10.88 | 20.2
3867 | l8TRHVr9p6bfQBwzbTty | 3 | 3.63 | 6.75
3868 | NCkZSbtMfUxIg95lxXXn | 2 | 5.12 | 10.24
3869 | wbVbYxDNomEEsv0XDKnQ | 4 | 3.98 | 6.97
3900 | fYbjIfZDvkbYu7p7dq3N | 2 | 7.15 | 14.29
3901 | Jj1toL1YzUk95oK7OfgU | 4 | 3.45 | 6.03
3908 | y9tKov3jCEzWGyA9B1wJ | 3 | 3.63 | 6.73
3909 | VvjZ0oHXTTG06m5XlL1B | 4 | 7.98 | 13.97
3910 | pNRX5rV0uvvHnR27z1AO | 3 | 5.19 | 9.63
3911 | R3AK39H17lCC16PE9DkR | 3 | 5.5 | 10.22
3912 | BSEXS69UjCPQ6j2zF47p | 4 | 10.63 | 18.61
3913 | nUmJBAacPI2xORV8OCED | 5 | 20.56 | 34.28
3914 | e7efPn2W4IFyilt2hNai | 4 | 20.02 | 35.03
3915 | jOX8xbQ5VzQq8YZ9EVJS | 5 | 5.45 | 9.09
3916 | xcLTkuiw0V5a2mOSGmcP | 1 | 4.8 | 10.55
3917 | hmttcJptV92JIo4OpANW | 3 | 3.97 | 7.37
3919 | 70MdVf3krr3KZdDhEaoj | 4 | 0.98 | 1.71
3920 | mBVNyTIN7rvKyNQxzyxZ | 3 | 6.12 | 11.36
3921 | jEuseC90wYhkn0V4svXs | 4 | 2.3 | 4.02
3922 | yD55zWPn8USsNa4i8nCC | 5 | 6.19 | 10.32
3923 | FwZ3BvPGTUfvQ1CE4iRh | 5 | 19.89 | 33.15
3924 | N1CigBiMQE2J41ZAMkt0 | 2 | 13.21 | 26.42
3925 | hSr4t1vn7GiB6Kp7YK0M | 2 | 2.35 | 4.7
3926 | vGJMK6sejFbKR6Gom2up | 5 | 6.24 | 10.4
3927 | 3RLmiC17tI4E2ggNuRe0 | 5 | 5.52 | 9.2
3928 | hCBFci3gUopMkWW2dQQj | 4 | 4.35 | 7.62
3931 | GleHIX38gd9vOXaUQYVA | 1 | 14.49 | 31.88
3932 | RKLg9Drqo40Q82TFH1VL | 5 | 1.23 | 2.06
3933 | FbGZSJQTtuDZR2p8qmxq | 5 | 35.44 | 59.07
3934 | 10Oh1H5M5HjeoWxU1u0w | 4 | 0.9 | 1.57
3935 | IRdaiLeeauelAg4QWklz | 1 | 15.82 | 34.82
3936 | hwXDQy0MWIQ4jzjNT4oM | 3 | 0.71 | 1.33
3938 | 2iJ091mlhEkJyqoddB4L | 1 | 4.08 | 8.97
3939 | cuQ4HC0Kn3S6GTvqv7QE | 4 | 33.69 | 58.95
3940 | 8UqvtHTIMRT16eupajKq | 3 | 0.78 | 1.44
3944 | HRTLaCTjRjqysGxmE6ve | 3 | 26.94 | 50.04
3945 | bJfaWXH8yBacWp0eqnXx | 4 | 0.95 | 1.67
3948 | 6ze4BjeYc1B5uifD0Fqa | 2 | 5.26 | 10.52
3951 | BNWJw3sHADBJTHA2Ybu0 | 3 | 12.1 | 22.46
3952 | HkhDGF3pWO8GORFQnyh9 | 3 | 3.63 | 6.73
3953 | dYr7YcYkpYYUeESNUSkl | 4 | 1.73 | 3.02
3954 | r37KEs6OIDoMKT5Yz5nA | 4 | 0.86 | 1.51
3967 | BaECEBO5p44IeRhOgeK2 | 5 | 22.64 | 37.72
3974 | xzlIrgrrtbLscLWLbbQq | 1 | 0.54 | 1.19
3980 | po54OWwjtqomy5uOkFBU | 2 | 27.12 | 54.24
3981 | YTm9sByrDxPUc7AlWXh1 | 2 | 8.59 | 17.17
3993 | LBRozXrRhpq69SKlxnDb | 4 | 10.15 | 17.77
3994 | DvOjAQ6C9aXKnpaAVD1H | 4 | 4.58 | 8.02
3995 | AUkl27NW1i9i5huez8Rg | 2 | 2.96 | 5.93
3996 | Bw8X4DjnSuQgBiA6BEKp | 3 | 3.46 | 6.42
3998 | 5UhDwyM7phAycUkk1Nye | 4 | 8.51 | 14.9
3999 | v6kjlf8aEDhSJHzOK2Uo | 4 | 4.04 | 7.07
4000 | Y3aJp60cYMHromf8xgAE | 3 | 3.04 | 5.64
4001 | Cjtbc2cmKWchyZlcOxo3 | 5 | 4.72 | 7.86
4003 | gjf3v6NdOQannovTvAoE | 2 | 11.94 | 23.88
4004 | fF1Y54WMybWnXZsBJgYM | 5 | 1.04 | 1.74
4005 | NxZ8rMz5ZnJaz6z1SXKM | 3 | 2.62 | 4.88
4006 | fOTuJvqH3OcilXcZuEM5 | 4 | 4.07 | 7.13
4040 | g5zNgGHP8U11wPTJKhcB | 1 | 7.82 | 17.2
4041 | f0PORH3GhEIXFjYfGbTd | 5 | 106.88 | 178.14
4042 | SyfMayqY4a7i0nZLPz6Y | 4 | 99.93 | 174.87
4045 | mDphgqAAxA2RnvA52x8A | 5 | 22.01 | 36.69
4046 | 5HyQBVwuqRdeW1HhaSOP | 4 | 9.16 | 16.03
4047 | WZVyPUJ7ZWyAZGgKP4Y9 | 2 | 47.99 | 95.99
4048 | ybbKhm9jdtNbVzABGZ8L | 5 | 22.36 | 37.28
4049 | kP1jeiEwkYg4HRpUjG4p | 3 | 2.79 | 5.17
4052 | JSSXcLTdD9VQNM766DgK | 5 | 18.45 | 30.75
4053 | uYiMgxVAxCr7KnHZ9xA2 | 3 | 7.83 | 14.53
4055 | dWrJCmOwv1i72p29KBXE | 4 | 1.51 | 2.65
4056 | a1SRK7UWhIIMlkKKriy9 | 2 | 0.6 | 1.2
4057 | NKnvgqAHKv63TOKudyZQ | 3 | 0.63 | 1.17
4058 | cbANjhwCBqAluf1RM04K | 5 | 0.86 | 1.44
4060 | 6S9Iuo5kzbvnNzJK2SoM | 3 | 1.67 | 3.11
4061 | ViM2psfxppAdWr3IoYdq | 2 | 1.85 | 3.71
4062 | RvsEFsErXikPrAOovPaZ | 1 | 0.31 | 0.68
4063 | ma6GKJ3GzeKmeF4AshaM | 2 | 2.36 | 4.73
4064 | OALhjNOvEaqSDAmsS5Il | 4 | 0.86 | 1.51
4074 | H2vE7zxiBRw3YTdo2zSW | 1 | 17.3 | 38.05
4075 | dGbNHsOLhslKk8CjhyjE | 5 | 1.03 | 1.71
4078 | ybbKeBChK3D60QzH8ONZ | 3 | 51.26 | 95.2
4136 | bllhlvXmXgF1yFG9Nwfe | 1 | 8.16 | 17.96
4137 | rnRXxVdKdR5NUADIB31n | 3 | 0.81 | 1.51
4138 | 75WgU7H7MCC8DDgOcnsD | 3 | 19.35 | 35.94
4139 | 9SKpfzivi43NDDuHUq0B | 1 | 2.18 | 4.81
4142 | VTqJrDLpWuaSlvRQajcM | 5 | 12.02 | 20.04
4143 | UwGhtpl5Mnq9WQrcrXRR | 4 | 9.24 | 16.17
4145 | S2ZZUpnRVAnUNmaYAkv9 | 2 | 5.5 | 11
4146 | rTeXGnIwGPt6ES3ynSHq | 1 | 2.1 | 4.63
4147 | hQaW5HIstT5bbsPEBxyQ | 2 | 6.53 | 13.06
4196 | 2ZwOzHGH45ywtPvfASSG | 4 | 4.94 | 8.65
4198 | k6X8NWhjfeQOPZdDpmna | 5 | 19.12 | 31.86
4202 | N5DTU5adYVhKR5So2Uvc | 3 | 63.01 | 117.01
4204 | CRzwy8942pbCOpcOMW2v | 2 | 12.35 | 24.7
4212 | yktUOUuzQyzOVBFBfL42 | 3 | 25.99 | 48.27
4215 | I07WrBLpDQufO3mvIdSu | 2 | 0.55 | 1.1
4218 | T5g2El1CSAmFZNlboxQh | 5 | 1.01 | 1.68
4231 | 8h0WH2qeIC7tfvcerCPa | 5 | 0.83 | 1.38
4235 | QiaATNQSPId7svzcuO8r | 1 | 30.38 | 66.85
4242 | RIVyyga7UReDeuixs5m9 | 3 | 53.54 | 99.42
4243 | LpPx7AWOh1V8dzWVWc6j | 2 | 0.51 | 1.02
4246 | ANAzXnUTz1PCb3xsov4Y | 4 | 7.05 | 12.33
4248 | E1RJwJWM8qrsKP3o7Toy | 2 | 0.56 | 1.12
4251 | IBg36OMMKUy3vwEnRNF0 | 3 | 0.86 | 1.6
4253 | hnujWIe1JDNg9VHs3TWw | 4 | 0.85 | 1.48
4255 | TAfq40Sin0H6Q2YT0OS5 | 2
4258 | GzQkXlTiYJMdE6nBDVeb | 2 | 2.93 | 5.87
4536 | zU98x2LHVd7UXovDFMXu | 4 | 13.36 | 23.38
4571 | grLKm3VpZ98OhRQH2gBq | 1 | 14.44 | 31.77
4572 | 5hxJeLGqqaIlIue4XwRC | 5 | 0.87 | 1.46
4575 | nPe6rBdPLk408ntp39jn | 3 | 0.68 | 1.26
4579 | xoTCeJS6YwjvMvm1YAvH | 5 | 0.91 | 1.52
4580 | llDwDvQQbSyeeXMs3M2a | 5 | 0.97 | 1.62
4581 | FxGRGf2kppDMdfFrZkS4 | 1 | 14.29 | 31.44
4583 | QzcCl72pVAI4zSVR8VAE | 2 | 0.44 | 0.88
4584 | H2uIo7s6dGmX6mrjT7jd | 5 | 7.96 | 13.26
4585 | Z4QB23UBk58Dyd3318zD | 2 | 4.42 | 8.84
4586 | kRWFuIGKur6ToFmAr9JC | 2 | 0.56 | 1.13
4587 | 5uS9ktvplxYkrLheR3Q9 | 5 | 20.89 | 34.82
4593 | XK8YU5H8vMrR7jBOr6fS | 2 | 54.65 | 109.3
4594 | EUFkYGsAZWO3vgZroOTA | 3 | 0.71 | 1.31
4595 | 0i30zTvKTrSo3R9n999e | 1 | 0.86 | 1.89
4605 | jXRAJqcdCYbTQqzq5oVG | 4 | 12.14 | 21.25
4606 | e1c7TqZJ2saEXqSPx9Ca | 3 | 0.72 | 1.34
4608 | tlJeJHdE7OwhwWyVvZ8P | 3 | 2.88 | 5.34
4609 | PoeQu0I6Io83IRbk7WtS | 5 | 4.54 | 7.56
4610 | UGUZlny6Ut8S0mLRTL2X | 1 | 0.42 | 0.94
4611 | 1TZOFiOcsBCmkfhi03Iw | 1 | 2.48 | 5.44
4612 | ZwEXlYv6PrV1t0gzfqom | 3 | 6.93 | 12.87
4613 | z0DGpsje53b33zXA5t1P | 3 | 11.8 | 21.9
4614 | cqs4HA7sR83mroZvcBiw | 2 | 0.6 | 1.2
4616 | FR5tuVwQGmPNYmz6BeMP | 3 | 1.04 | 1.94
4617 | OziRB3N5b7cM46iEETGg | 4 | 4.31 | 7.55
4618 | mRqsjEijsp2iSp4l7aof | 4 | 5.4 | 9.45
4619 | 8asUr7UOO8nabPagFvw9 | 1 | 18.84 | 41.46
4620 | UWR5akRFo4eKiDyQVnYr | 2 | 9.96 | 19.92
4621 | pGB9dynKUfIMuzj3AWVv | 4 | 0.72 | 1.26
4622 | Bm2ajkWBwO6Cvc6RoPdK | 5 | 6.48 | 10.8
4623 | sDTQ4X48dvup817zb0Do | 5 | 18.89 | 31.48
4624 | 3CGv61AS00FFpM5LrRat | 3 | 13.02 | 24.18
4625 | NkJyZ342jkgJkVCalD4F | 2 | 1.3 | 2.59
4630 | pjdWghPSPBEOfTIZFZhV | 1 | 2 | 4.4
4631 | EXJQS9o5Eq3lGkaYsCap | 2 | 0.55 | 1.1
4632 | VGp2Ji3lCAas2O4B01f5 | 5 | 0.87 | 1.46
4633 | STHfhyBuM5qFiEzHSgws | 1 | 8.16 | 17.95
4634 | cbBLoWE0dwfwOCS04ga7 | 5 | 13.51 | 22.52
4635 | vrd0V7BeylNxhzgI26F9 | 3 | 5.94 | 11.04
4636 | DgPDbwa39NNm3em6lmtZ | 5 | 0.92 | 1.53
4663 | X9pjxOrdX8ZwQAfQziSu | 2 | 0.58 | 1.16
4664 | DAxARpEpHAwipBCK81bc | 2 | 4.87 | 9.73
4667 | gXRr1908PexMoLIDosFv | 3 | 64.67 | 120.11
4668 | G3SLCzd88WLMRnAF5Et7 | 5 | 0.41 | 0.69
4669 | aeClBbTsJ3qrKHWqQ1Rw | 1 | 17.9 | 39.37
4679 | rpzkOhA603pApmNdMeVE | 3 | 0.36 | 0.66
5214 | KnSim1DOJ7A0BYyW8QOP | 2
5215 | KawuX1icbWQB8WlKVKy9 | 4 | 44.05 | 77.08
5216 | xOecB4tLtQXauOnWGD4l | 5 | 1.33 | 2.22
5218 | 8GMyARBjPLtiSR4txAaa | 5
5219 | Uz3hspiJXkYJElXZ00I5 | 5 | 56.04 | 93.4
5220 | QAqXx5k5ldQJaugZyYbR | 3 | 0.65 | 1.21
5222 | 4u5ocGGr0fcTRpzuglXZ | 1
5223 | 3nEJb4lsc7akFmF6ULw7 | 2 | 35.38 | 70.75
5224 | PvORb6t1pqf23aOFbh3S | 1 | 0.5 | 1.11
5225 | b44Ij1WE7Qrra8bO7ZTN | 2 | 0.67 | 1.33
5241 | v6EKIZLcnDHW8CXOrD7y | 2 | 12.27 | 24.54
5242 | JYCfpao49G3jD8M94S66 | 5 | 9.99 | 16.65
5243 | 0XN39P602kPVdw6rXYZi | 2 | 6.29 | 12.59
5244 | Nwqnc6xsOuQ8oMDbKNfv | 3 | 11.04 | 20.5
5263 | URhzXaXmWu6rBPIMitrn | 1 | 15.36 | 33.78
5264 | 2BYRPY9ftrCpjg2j3vxJ | 5
5265 | ATYnDTN93dB3aTXfzslo | 1 | 2.31 | 5.07
5266 | G5H4IlBy3M3Zxs38gcIH | 3 | 7.76 | 14.4
5267 | 3RI5G3ymKjaLn96cfboa | 5 | 12.15 | 20.25
5268 | fG9nayiE82fFlNFtuyfN | 2 | 10.2 | 20.4
5269 | UP8sWsDXCDMiwOqWz3ib | 5 | 5.41 | 9.02
5270 | 0UA65kBzwzHULCayr1Gq | 1 | 3.47 | 7.63
5271 | mtztJWmm2OBnfmSsuoGt | 5 | 9.82 | 16.37
5272 | kvS9pO69DNwaLvofAQcb | 5 | 13.98 | 23.3
5273 | fGHKYfAaAseAkWqOpGpv | 1 | 4.76 | 10.48
5274 | zjsmmZ1Zvuz0mxAk4wzH | 1 | 5.05 | 11.11
5275 | lBTJLZ8EG6vqarjSz7m6 | 3
5276 | yja2Gk0YbNXya3vsxrwh | 4
5278 | OmCdw3tKtVsW24V2aNqQ | 4 | 8.06 | 14.1
5280 | q0a2rl5NSMPQe2o4IYAd | 3 | 2.37 | 4.39
5281 | 3GO4XZOZrW4CEje40UJT | 3 | 3.39 | 6.3
5282 | qBzS7vPbhPVzs7sVXgmM | 1 | 1.74 | 3.83
5283 | fU0pzeQGz2MN3lZmznFh | 5 | 5.11 | 8.52
5284 | epM0xPGW4QTSpblHVWYc | 2 | 5.96 | 11.92
5285 | ffNcVsnPBySsZbQiEShc | 4 | 9.05 | 15.83
5286 | Yb8sH9U5B9gBzfVjcJKN | 4 | 4.6 | 8.05
5287 | bhDhrVJ9ZVKMNyReuPKm | 4 | 3.94 | 6.9
5288 | RIVzpLwElpoiAIgfwKiL | 3
5290 | NEvSl0zKCrGJ6lqshTZO | 3
5294 | A0MDYkkQxesjEWQub0UM | 3
5298 | c4SSanbHhynqs8RkqT3I | 5 | 3.49 | 5.82
5299 | HB5wL9z8KlZFeAas0WUQ | 3 | 7.32 | 13.6
5301 | hHw9byxBfgMW8zXuSsdj | 1
5302 | 2rc67Y2hzAhRvE7YihWA | 3 | 6.31 | 11.71
5303 | SgeIRg4ykwxbNqD9urWV | 2 | 1.37 | 2.74
5304 | KRXQrBZsFBKS9k4FvAsp | 1 | 1.5 | 3.31
5305 | TyGQYH0bANBrFjXmh15D | 4 | 1.7 | 2.98
5306 | yar7ts7ASIpTQqyvnwQd | 2 | 3.75 | 7.5
5307 | yRByGMPgEQcCecr5HzAA | 5 | 4.04 | 6.74
5308 | JBAsTSNPb9OQmIAmtadV | 2 | 17.1 | 34.2
5309 | xRRT514kq8kwyv7njrs5 | 2 | 2.97 | 5.94
5310 | RMnJ5j2lLGlokfxLAfSa | 3 | 1.48 | 2.74
5311 | BowxNbb4uXSnAk8z8ZkC | 4 | 1.47 | 2.58
5312 | mmXMEY1kphvE51vXPbq6 | 4
5314 | SRtjKDi8lC5PBWdNdIAU | 4 | 8.09 | 14.15
5316 | LCfcLPfxTjnSY0dCrjlE | 4 | 7.1 | 12.42
5317 | pw6YyMXR7oeqsrtIHdqo | 5 | 9.35 | 15.58
5318 | KMG5hXAC4X2MZPfyVOSc | 5 | 5.1 | 8.5
5319 | mDGXCmTQB2ITo8MYwlYq | 3 | 3.92 | 7.28
5320 | hu6UActfLD0rLfdNqC55 | 3 | 3.48 | 6.46
5321 | pG9QTaeiPcJe7Bm3iI1s | 4 | 4.3 | 7.52
5322 | oNpYocgOFdrRcJiQE0H5 | 3 | 4 | 7.42
5323 | Tt5dEbDabBigq84Eat5c | 5 | 4.64 | 7.74
5324 | INz2wzhVzgQCZLXqwTZc | 4 | 3.88 | 6.79
5325 | D5c4JntP5EU4thbOE4hi | 5 | 0.9 | 1.5
5327 | iRZmxts3rKQ38tplQw52 | 1 | 13.5 | 29.71
5328 | ngeJL3ilFttQtHxnOEwX | 2 | 0.65 | 1.3
5329 | GYUaK0PI1fV4kag2egD8 | 2 | 0.62 | 1.24
5333 | NEZJUiuEFBeqDBEbXbzQ | 4
5336 | FIhKbBOHnlTp0loBBfvV | 5 | 3.27 | 5.44
5337 | TPAbtCx4KhMQiN0iVD1F | 5 | 0.49 | 0.81
5338 | NXWa8B3rzsUFws6lYttF | 2 | 3.14 | 6.28
5339 | o98eRuEZGwoxxa1Byl7H | 1 | 2.52 | 5.56
5340 | lQJTDBnvPE8mTPnPre3v | 2 | 4.55 | 9.11
5341 | nevxwfefPkBzu42CDbNd | 2 | 4.23 | 8.46
5342 | s0JiBiXDLP6oybWmkZ43 | 2 | 3.28 | 6.56
5343 | NROXqcLUoQ0RLz64rMVc | 5 | 4.58 | 7.64
5344 | Kw3Fj6kwk5uOl7tQyqrL | 2
5360 | ARncD9Nx3De5DONPy9Bs | 1 | 1.04 | 2.3
5368 | NKJL1ZJN3KgUArkbA4qS | 3 | 1.86 | 3.46
5376 | zSTdFwWI5FOaluV37lYS | 4 | 45.18 | 79.07
5382 | VlX4WunUzdS7Nqvh5ftn | 5 | 18.05 | 30.08
5383 | u1aficyBQ2O9A8MnpdfZ | 5 | 22.11 | 36.86
5384 | d8i6C63YfOF3EovUl19W | 4 | 8.01 | 14.01
5385 | ohwsmv9qOoV0RNzIdjJI | 3 | 11.7 | 21.74
5386 | tSuemAovBYAaHNhFiwaF | 2 | 7.19 | 14.38
5392 | TRJmldmXNRf3NwsZhgng | 1 | 8.8 | 19.37
5393 | 3qvg7di25vdBD8UUvM1a | 4 | 15.91 | 27.85
5394 | ungpeNo64cspVo3BuO9g | 4 | 8.84 | 15.47
5395 | KZXvYFda88KgX9w7a3ES | 1 | 7.06 | 15.52
5396 | FNjsTUKVT29tBcVlvaM6 | 1 | 6.25 | 13.75
5398 | EMMfZLgDhvN5O0lAfznQ | 2 | 9.73 | 19.46
5399 | 5K7jeUOrZ3wka9S2O1Dn | 3 | 10.5 | 19.5
5400 | I2IZFfCcy2hUSTtihPWq | 2 | 8.91 | 17.82
5401 | WWZjxA63YxH38hnYmVKG | 5 | 10.02 | 16.7
5403 | wP2WbhW6upJb7JmdzCw1 | 3 | 6.78 | 12.58
5404 | UrewlDJ3J2c8Ueci7p9E | 1 | 2.54 | 5.6
5447 | ijJ4zfbEfOInLYX7Vu9Z | 2 | 3.08 | 6.17
5448 | cS9oDqhLQ00Df4o4XStO | 5 | 5.02 | 8.37
5449 | 6It4K5O7iZJhLoLO2jyi | 3 | 3.62 | 6.72
5450 | maMtUzorvxHWuMFIlXlq | 1 | 2.54 | 5.6
5452 | u9nFTwEoKsBrgeg8njOT | 1 | 95 | 208.99
5505 | nVzBMSNTKKq9KPWblsw1 | 4 | 1 | 1.75
5507 | 1r4d5DbY2YIgMhg8HKuO | 5 | 3.09 | 5.14
5508 | wHSntGHJkj4aA0wA3fA2 | 5 | 13.28 | 22.12
5510 | LTFwTsrnxYhrGNFUv7CM | 5 | 13.5 | 22.5
5511 | Od3mMFxB7LjrJLF1slz4 | 5 | 11.03 | 18.39
5512 | Des2hDKSMjcJndTJRzoQ | 2 | 6.94 | 13.88
5513 | z1vb48lrGwUUDjKbD3gr | 3 | 6.86 | 12.74
5514 | leNXdZKmybH4tpy20cQU | 4 | 4.02 | 7.04
5517 | IHfroMkwx3TZoTXYbBOK | 1 | 13.44 | 29.58
5518 | V0a5XEJ0jxIkhnpEDg8e | 3 | 33.67 | 62.53
5519 | D5sl3M5NpO77EU7TPYT0 | 1 | 18.62 | 40.96
5523 | APkwTVep7mUhgmcCl4NB | 3
5527 | Mw5Re8SivA42laH7UhJE | 3
5535 | XVk7S0ldLHQUWflKhMBn | 1 | 4.67 | 10.27
5536 | cYU0DBZylLxVRoLEp7Bc | 5 | 48.86 | 81.44
5539 | kRsO3PSMDsMxji3dmdNc | 2 | 376.53 | 753.06
5540 | GKx3XnA1BSbhTsgdKbqP | 3 | 12.42 | 23.08
5541 | LhqIvyBzzdwllIHwrPz2 | 2 | 2.92 | 5.83
5542 | 4ivItsonCrTGke19i41Z | 3 | 11.3 | 20.98
5543 | XaHBDo6QUBfyTg5ESk7j | 4 | 15.92 | 27.86
5545 | 7UVU8IboY6NG7sqZCrUC | 2 | 3.84 | 7.68
5546 | Shs5wuYOFSkTF1YslX8w | 5 | 5.96 | 9.93
5547 | KglXvc5QwlHEboIvY96Q | 4 | 3.2 | 5.6
5548 | Zfzda0CfmpiN8ZL93G3t | 5 | 5.41 | 9.02
5549 | PgYJem7PJFdGgV04ojeL | 5 | 1.21 | 2.01
5556 | fOMVaiOa0jnHOJyDUdVQ | 2 | 15.4 | 30.79
5558 | RXAxJx3BHWNVdWFPfZ2a | 2 | 8.53 | 17.05
5559 | jJoy8dUJMWD3ZuNw52D0 | 4 | 6.49 | 11.35
5560 | wu3sL1wqoiodUr5mG52N | 1 | 1.96 | 4.32
5561 | Vb2zzMF18WNANxlCzGiz | 1 | 2.12 | 4.66
5562 | vp7j6GBYm2dAMLvxEFuE | 5 | 0.95 | 1.59
5569 | 35aiC9HLOSrIl2OBwDvd | 4 | 22.23 | 38.91
5571 | lfRAbO0c5jl7NaC6s7pm | 1 | 10.86 | 23.89
5572 | jk3Vm36iIGViuk9dpLfQ | 1 | 2.46 | 5.42
5573 | u3MfiduPa05JsS2ly7WD | 4 | 3.37 | 5.89
5574 | 3iKE3riinMPRUpVpTfwx | 2 | 3.32 | 6.64
5575 | 48yotl4pDzxbk5y0VDbK | 3 | 0.74 | 1.38
5582 | 6tLu8emqwotxTkeBbEpy | 2 | 12.81 | 25.62
5584 | 6WMzJdzS7tY0wFFuXnrc | 5 | 6.54 | 10.9
5585 | KljMWvDEBGSuBTW4zQhZ | 3 | 4.63 | 8.59
5586 | Z3ZWpIsgJCSKUX161hV0 | 4 | 2.98 | 5.21
5587 | OXOUsYDejGVlgqn4Z1vl | 4 | 5.1 | 8.93
5588 | MFjHKzinVVI0Ndx8qx0B | 4 | 0.94 | 1.65
5595 | REFTk0AP9RBTibJWVhuH | 5 | 27.95 | 46.59
5597 | zKJsJYNcPRFZ7wBjvprv | 5 | 15.23 | 25.38
5599 | T0Oh47cWIVU9y2MKPB0U | 4 | 10.61 | 18.56
5600 | oTkX6bjokLXQ590hdeFy | 5 | 14.06 | 23.43
5601 | xa7cRxeKgQxZnuHNAYMQ | 1 | 4.34 | 9.56
5602 | QlxDegibloFbHrPNJwyW | 4 | 11.03 | 19.31
5603 | dwMYG7lg76TqxtTxZNCR | 3 | 3.28 | 6.1
5613 | cc9QdsdOkkgaQ8ateKZX | 2 | 0.74 | 1.48
5614 | COTl0owSvMhEdF9iuXCz | 3 | 0.38 | 0.72
5615 | 0lLRNnxfg3utwoPLwt26 | 4 | 1.6 | 2.8
5616 | 5Z54Ad8GhuwKLjQHaz2Y | 5 | 0.96 | 1.6
5617 | fALGtnsfw381gf0W53Ia | 5 | 0.27 | 0.45
5628 | JolyrZVyKy7n75ZL5gZI | 4 | 1.98 | 3.47
5629 | ghMhRqrbgVxCQv51dU2T | 4 | 0.42 | 0.73
5630 | eU3bwvC6wgraOvc5hiLt | 3
5631 | gvTQVNdftDRXYXclyMFo | 2 | 1.72 | 3.43
5632 | DfRDIp64TG1m6LE7SSYQ | 2
5633 | 2UPBwQymcCOUpuUjnBTe | 1 | 1.11 | 2.44
5634 | gm5pLWvICR0pU7aShOGD | 4 | 0.83 | 1.46
5637 | agdOsAK6kuG5dvRDXVyv | 4
5638 | jBSFjjY1RfmWgqa8tOlO | 4 | 9.86 | 17.25
5639 | ymvGdGMdlU958QTwMU9V | 1 | 0.22 | 0.47
5640 | AvXXkRY6V61W0WFfD9tU | 3 | 3.64 | 6.76
5641 | QjWOhv4eRSTZWx0ATAUl | 1 | 10 | 22
5669 | bBSx7g3AuM8uxZcIYlIi | 4 | 30.35 | 53.12
5691 | glUuWw43f2R9t2hl6VHO | 3 | 5.14 | 9.56
5692 | KeXnvnZRx0KMyut3yw5s | 4
5693 | VdKRFLdSc60knizSqFXc | 3 | 10.41 | 19.33
5694 | Gb0taOZcQ8l0cdHliY6j | 5 | 10.53 | 17.55
5695 | ePp2idADlztrdEpItyCc | 5
5696 | npE0RnxADwI7cDPG1fDa | 5 | 4.02 | 6.7
5697 | 4nIBzBv3LSP60HeOLv0f | 5 | 5.3 | 8.83
5730 | ypyrsmMFJqJ9aPla6UhQ | 2 | 2.35 | 4.69
5731 | uQF6Ff0bc2cqy3b37ZQc | 1 | 0.44 | 0.97
5732 | OQKwpwUgImWCC2Fp5G0Q | 2 | 4.28 | 8.56
5733 | wyOxVAS94HubPKo2yHJm | 2 | 4.24 | 8.47
5734 | iq9bjqBZvH9Bj6912271 | 5 | 6.49 | 10.82
5735 | Z8zFgfwvHK2hwW2AW8Qa | 3 | 0.71 | 1.33
5736 | QgUmTWGvxjzq3xqrWPJK | 4 | 5.29 | 9.25
5737 | iDzIA8f8DQgg2wVNkaUu | 4 | 6.65 | 11.63
5738 | ME2oX9BwgLu5cggaunhg | 1 | 2.5 | 5.5
5739 | IivOSmNLtmlF9JKFLUrl | 4 | 0.7 | 1.23
5740 | eRxCjL3dV2CpHvAG84r7 | 1 | 5.9 | 12.99
5741 | 8Y4jq7dOt4lN4NYBT6r1 | 4 | 9.65 | 16.88
5742 | 88bEv4EMiOL2y8w1ttIM | 4 | 3.97 | 6.94
5743 | 0Uz4krHDVCdAlMd5aRwh | 5 | 1.16 | 1.94
5744 | cSBfnbrbVLLFYTMEfBKA | 5 | 6.58 | 10.96
5745 | ZY99Y6JX4jBylnfeedvo | 1 | 2.27 | 4.99
5746 | 9Uq3Ix5n2BJf2VZJ21kx | 1
5773 | OCcI80TDGF8LlIXj66uV | 3 | 2.06 | 3.84
5774 | Dvlkt7hdSzdJ7ChIr4xD | 2 | 1.11 | 2.22
5775 | D3NIdGcGrWNhiaQ0dYbY | 3 | 1.41 | 2.63
5780 | XCMvjmTKbAUuCZwuNlSF | 1 | 2.96 | 6.52
5782 | EYY3j1SjnoLUV06T0QHs | 1 | 1.67 | 3.67
5783 | BOvEGIzyTacp1vvD9v7M | 4 | 0.76 | 1.33
5786 | d3N6cqydEgoPO1XBMSTu | 3 | 4.91 | 9.11
5787 | r6JEZEKCpBbNZRe1W7Ef | 5 | 101.46 | 169.1
5854 | 2kqOvhRPajU4Q0ZPsUnx | 5 | 8.24 | 13.73
5855 | ufnWeMCBRu1ZyXfLmzt1 | 5 | 51.71 | 86.19
5857 | g9TizAnooUcHoXglcd4n | 3
5858 | 9N3N0HBhBeb82jbbU7Vx | 4
5859 | RMhsXtyk4773BtipN2HO | 5 | 0.86 | 1.44
5860 | AMUT2hrMeOWSIoK5dO6S | 1 | 4.84 | 10.66
5861 | adMwYb1cwVT0ja23ZKPV | 1 | 4.72 | 10.4
5862 | rkVKH7eSVnkv5Rz0hIbo | 4 | 22.76 | 39.83
5863 | axx1H8vuWtNbWz6aJYpW | 2 | 13.75 | 27.49
5864 | ZuXAUp7kzm7PDgs0Clm4 | 3 | 11.73 | 21.79
5865 | pfx92tyIHO0nDV8Eg4vj | 2 | 1.64 | 3.29
5866 | qnFTkxNSvGIYOwHhqElS | 5 | 4.44 | 7.4
5867 | 6vMprMC9ZRYTg9c055cw | 1 | 0.95 | 2.09
5868 | qP5P60WlJm98gR28uFOw | 4 | 0.75 | 1.32
5869 | 5FBVtcv48JlyNzpes7ps | 2 | 2.93 | 5.87
5871 | owx5unCKcaLauhH4kWyj | 5 | 5.56 | 9.27
5872 | qImIYF1Y50rp0FNnsaoS | 5 | 10.78 | 17.97
5873 | FfFQqcMQ2fY5X0GvK0Xd | 5 | 22.48 | 37.47
5874 | fHTDjpnY2Gm0gViXPiAD | 3 | 1.26 | 2.34
5875 | TQZary26m4SvJkpuQUlv | 3 | 0.55 | 1.03
5876 | 5ZRJqmbhPGswffOWtWat | 1 | 0.4 | 0.87
5880 | z8rht75g90pc62Jd1j8e | 3 | 9.29 | 17.25
5881 | ZPPJV7wrbqyTumtl84NX | 4 | 13.02 | 22.78
5882 | PdfqDNDAaUS1Z9tfvPSB | 4 | 11.3 | 19.77
5883 | 3J3dFKPf8v7HKW1lSal4 | 5 | 15.28 | 25.47
5885 | p0UOLQYQkw5raD9Hf7AI | 2 | 3.05 | 6.1
5886 | mfBVa7VrtMT45ZcRp9ur | 5 | 4.56 | 7.6
5887 | xjL6okqGZuFc1ChaUzA0 | 4 | 5.06 | 8.85
5888 | 0NLdruhvCSk61FiIPSJA | 3 | 3.65 | 6.79
5889 | vcqfMiWzgD0sBRK91JrP | 1 | 1.4 | 3.09
5890 | r7iAplKyl5D3dW7yC0Jk | 5 | 4.49 | 7.48
5891 | 55B0pL3dU2GPDxU6IZLg | 1 | 0.38 | 0.82
5892 | zyPP7s8BBmPhydQ5fB2g | 2 | 0.57 | 1.14
5893 | JSBvauC3wpirasqwMrC9 | 2 | 0.61 | 1.21
5894 | AO4SgiivKvvxQJupi2GS | 2 | 0.41 | 0.82
5974 | cJ7VeFZezCBnvYlHxCmb | 5 | 1.29 | 2.14
5985 | AUKn3E7aViOsULw8HdKV | 1 | 48.29 | 106.24
5999 | hTF24jclc5ogfsrVWXZd | 4 | 32.49 | 56.85
6000 | dvNXA0SZWky1SGhKE7td | 3 | 3.57 | 6.63
6001 | z8HVZ6SyP3QpkaT54VAm | 3 | 0.69 | 1.29
6002 | rmlzSal3Nkh8gQGzhscw | 2 | 0.46 | 0.92
6004 | xOhJcEwgSz1TAvNHU4tB | 2 | 16.65 | 33.3
6005 | gw3ZFSF3nzLqLqYBiqR7 | 1 | 2.47 | 5.43
6006 | HEKaqqmbwSXnCRXB6fED | 2 | 0.56 | 1.13
6007 | vdBzwsumrXxpXNAKvnKh | 3 | 0.64 | 1.18
6009 | NVgukc0KZBShUa0wIlyx | 5 | 28.46 | 47.43
6010 | tIYqVtlT4yOF2YQ2FRYY | 2 | 5.27 | 10.54
6011 | 9Y3pHbqvwzl2AwHfvrBG | 5 | 4.41 | 7.35
6012 | Z1jpWQx4GyFcVoEVg0i0 | 1 | 1.9 | 4.18
6014 | hYHiAVYfHXdDTdWEk9J8 | 3 | 9.72 | 18.06
6015 | MXdxqc8Y6tIByFeEqluF | 1 | 5 | 11.01
6016 | gwhB80Lv7eu4PoYwev8o | 1 | 1.94 | 4.26
6017 | VCyTBN0y7V3erCRNMvm4 | 4 | 3.34 | 5.85
6074 | fkBL64dyW7paLwgGr0ue | 4 | 167.94 | 293.9
6075 | pe2nScqRc5pgTwGaT5Zd | 2 | 123.47 | 246.95
6077 | 9YjbRTuPDmKPhAucMUDE | 3
6080 | jFrzSNmYyPDtKSvRlBw2 | 3 | 0.64 | 1.18
6081 | VjHQD510O4fPJGbP9Knq | 3 | 0.7 | 1.3
6082 | YsSSuERf5VIDKO5m8eZo | 2 | 0.68 | 1.37
6083 | 3dsblDK1X9ztc27EZU3v | 2 | 0.54 | 1.08
6084 | deZM0xh115wln716GUoI | 4 | 0.75 | 1.32
6090 | LkexiRQNUDyJAwm8EPYV | 3 | 25.35 | 47.09
6130 | 3AAePL8Vt5bI7qDxsaDX | 5 | 18.31 | 30.51
6136 | bVRB0EhNo1xoyHBU8R0I | 2 | 0.59 | 1.18
6137 | gagQpjsDXV4QnJ1bUthb | 2 | 1.19 | 2.39
6139 | VECMPYMi2oWf71g3eai1 | 2 | 16.24 | 32.48
6140 | mO0F0FFUdRVKYlb84WcT | 3 | 12.84 | 23.84
6147 | BUcWclFVChflBnUDJ9UM | 5 | 51.6 | 86
6148 | V03eKqopjAXoUvRodLvQ | 3 | 9.46 | 17.58
6171 | ZR4zae2ZYhCMcZhj7T05 | 5 | 13.6 | 22.66
6172 | QgFskomqU31VYtYzB2O0 | 3 | 12.19 | 22.63
6173 | nRc7GqDGMG4VP1O5IlEd | 2 | 9.06 | 18.12
6174 | dvLkHNDhuFTU7AO5XWky | 5 | 15.19 | 25.32
6176 | B6x3R7fnpOwupecmo90D | 5 | 10 | 16.66
6177 | vkZhJMfsZWiMPLTjgcam | 2 | 5.79 | 11.58
6178 | XEU5rnQh2VnDpMl1eT0o | 5 | 9.14 | 15.23
6179 | xksMzlhYjvKZ4p1XJwSB | 4 | 8.92 | 15.61
6180 | oR7r0RquVFe2h8pCK9HY | 5 | 9.13 | 15.21
6181 | UJ3hrxCJ5NslZjdDLEyu | 4 | 15.98 | 27.96
6182 | JQHbjwkPqIslt5thIOgQ | 1 | 2.08 | 4.57
6183 | 5NqxhAyIl3JXTpWWvSnV | 3 | 1.13 | 2.09
6184 | vx8CoW16lw8uEEVKaVp7 | 1 | 2.42 | 5.32
6185 | A91LND4pEy61zvjvAsaQ | 1 | 0.5 | 1.11
6187 | kIPGiItVAbHq2ks8DK41 | 4 | 3.76 | 6.58
6202 | X3XRH6pSpuIgaacqwHSp | 4 | 10.95 | 19.17
6251 | Ha7ZmVRhPp4EjAGEFQOQ | 4 | 51.88 | 90.79
6255 | 6Rcxv4eHz2WhxfD2wxtd | 4 | 45.41 | 79.46
6259 | q6ww59eaDtL5Df1J4lsR | 4 | 11.78 | 20.61
6263 | aKytB1b2oD2t1WVaznUP | 4 | 13.86 | 24.26
6338 | whnkqeDzsaW1H7xphaZA | 2 | 30.97 | 61.93
6418 | W9pbV5i9WFkdVEGtW75H | 1 | 21.26 | 46.77
6419 | NORPsF566zq8VZyN1UzF | 4 | 8.52 | 14.91
6420 | 043wOhyyEd8vJkuUBkFf | 2 | 21.98 | 43.97
6421 | JZROXyECnTBG3SBjYZJ8 | 1 | 40.52 | 89.13
6427 | NeAxFJaqSLize8VPNJ6N | 2 | 0.59 | 1.19
6430 | IYyY3jK4t9QuDyuxqyQ5 | 2 | 7.57 | 15.13
6431 | mXx66gQ5BZWpD3idmZgM | 3 | 8.34 | 15.5
6432 | vMoeJo3Rc30lMwFim6rn | 3 | 7.7 | 14.3
6433 | zONKYXhH5yZJE26xvIWD | 4 | 3.02 | 5.29
6434 | cc8WGEqtonq4zOxPHtWc | 4 | 49.64 | 86.87
6435 | Ql00ScpYzqtI9PQP57zu | 5 | 119.32 | 198.87
6438 | sSGfho0IWOHZYw1Z8jLl | 5 | 14.81 | 24.69
6439 | JoFd6fDKN7NWznuQx6gK | 2 | 31.46 | 62.92
6440 | u5F2XJPKXxmZ5m99Yx5A | 2 | 0.68 | 1.37
6444 | XymP4MvJgra2aDdoc9vw | 3 | 27.35 | 50.79
6445 | Wo6GLLiu9tXQyZ8t43hX | 5 | 46.66 | 77.78
6457 | PFYaNHtSBj97Eh5ysTvH | 1 | 2.7 | 5.93
6458 | pDFztlVdvvSj2i4Cz5Z9 | 2 | 3 | 6
6459 | ylmwXTiOnCLJpwlHTaRg | 5 | 10.58 | 17.64
6460 | CystLMJtc4xxgICiEMDQ | 2 | 4.75 | 9.49
6461 | 7ypQo0ZyAHzCHmFRlywg | 4 | 9.53 | 16.67
6462 | BWDOi71UCejcEb1fgeoY | 5 | 6.08 | 10.12
6463 | OelD6citgJccZhV0UyvH | 5 | 6.55 | 10.92
6464 | McSTYqZ3LCfaYSSmZoTn | 2 | 3.79 | 7.57
6465 | WAyiiuxKOgY7bZWYUV9d | 2 | 3.1 | 6.2
6467 | n3qEWBmgcrCNzbacKk03 | 1 | 2.5 | 5.49
6468 | BqsEZH5IWCI59bWKml0D | 4 | 4.31 | 7.55
6469 | TtC6fzAb8zClFAVfKkP8 | 4 | 3.95 | 6.92
6470 | UrgnPc0HjVwpN7twGsWX | 2 | 3.01 | 6.01
6471 | xmZvSzAhf2D9ir29atKO | 5 | 7.06 | 11.76
6472 | j0VQ7fJsNHb1HpOVRoJN | 5 | 7.07 | 11.79
6473 | FN1N5cBOnOQJN0lvtY6J | 4 | 4.4 | 7.7
6474 | k77H7bJ7aRKhBrZeZFzu | 5 | 9.05 | 15.09
6475 | TkBVMCiZTEhYxjcnMNRI | 2 | 3.68 | 7.36
6476 | HdsfOo0UbW7iVGjY7L1O | 4 | 10.27 | 17.98
6477 | m1G8PrmdvRxZwBbLlVUQ | 4 | 5.56 | 9.73
6478 | ZDDqpCGw2ELQiAxZVJFo | 1 | 3.22 | 7.08
6479 | i51TyrBkECB0t7wKJruE | 4 | 6.69 | 11.7
6480 | XeKgBzwPereNdZmXnTFt | 4 | 4.02 | 7.04
6509 | sp3XFaPtGgzrVeC1wvvV | 2 | 4.49 | 8.98
6510 | dar9hgzhSUYJxC1MeoTS | 5 | 11.02 | 18.38
6513 | IG8fHoH3vjERJ6iSB3Rj | 3 | 23.67 | 43.97
6514 | imV319lPgBwI8oLVT5sB | 1 | 0.46 | 1
6515 | a8Kdm3F6uLeIN4SEhwX9 | 1 | 0.43 | 0.95
6516 | qmbk7ROGAo4AwJOySAlG | 1 | 1.88 | 4.12
6517 | YGaikKlMVGc6fqtUBZ7h | 1 | 2.34 | 5.15
6518 | 0rDsNLFYCabTnyCcopAQ | 3 | 5.61 | 10.43
6519 | UldK3RoYRJH5Hsfv02Lh | 3 | 1.07 | 1.99
6520 | UaqqB30tdDFCsCHRRpeh | 4 | 1.55 | 2.72
6521 | LDY9CVOjImzsQ4NE65Qz | 4 | 0.92 | 1.61
6522 | WYJvDx3FrKALT2lj4FIo | 5 | 1.97 | 3.28
6523 | TvM5XBX3OaVljTSOZ4e2 | 4 | 1.86 | 3.25
6524 | cvaJgvK8KpGYV8ykH12h | 4 | 1.69 | 2.95
6525 | GtEwLNkefPtnncnl90X4 | 3 | 2.18 | 4.06
6531 | iX155TL3hNg9Ca4Bsb4A | 2 | 21.86 | 43.72
6532 | 15e7xcLR1b1jSikaz0S2 | 1 | 14.26 | 31.36
6533 | b0mutjzKj8FRw4zkbb8K | 5 | 27.05 | 45.09
6534 | 8Gl2bk4Fxxo2fsClDJqG | 1 | 13.98 | 30.74
6535 | dWze9AnK8NrEMD9LOEyU | 2 | 16.82 | 33.65
6540 | BF294XdCZHw2CEg81bOs | 1 | 8.93 | 19.64
6541 | X8phwYugZBkIbn0OysQW | 4 | 16.57 | 28.99
6542 | fphO3nZhiS43G9CLfKfB | 3 | 12.77 | 23.72
6562 | Z3AfJmLBpOLyJb1GhvwC | 3 | 6.76 | 12.56
6563 | 7FPcbor42GN7O6Ym4IZM | 5 | 10.14 | 16.9
6565 | XyBOyY3JpPW2h1I7PEur | 2 | 12.89 | 25.78
6566 | gAyE6SkFHV1MNEAJitQ7 | 1 | 0.51 | 1.12
6605 | Qtljmhuq3GHp8HrV3pPP | 5 | 6.55 | 10.92
6606 | pKonEcYtBOhP3mqLQIUx | 4 | 4.15 | 7.27
6607 | IhYDHpDNbof6PVOjQ9lw | 2 | 2.54 | 5.08
6608 | ifCvUSq9UjUAw7FKKXTR | 2 | 7.87 | 15.74
6618 | LspmB73Oe2b9O1GVbm64 | 2
6621 | pXe0ZxltUhDf1quSL5q2 | 2 | 9.16 | 18.32
6622 | EmEy5gJckBYofEEYNXFv | 5 | 20.18 | 33.63
6623 | BVU87KMg9Rhzc6j5yKVh | 2 | 11.57 | 23.15
6624 | sVpbcWAee9M5eeft5sdO | 2 | 7.9 | 15.79
6625 | it5qGsWYKIf8fEL1a2TB | 2 | 3.43 | 6.85
6626 | 9d2gtkuh8SmNZwArNzpn | 2 | 5 | 10.01
6627 | QBgG0JxqOymB6vyjKsRZ | 4 | 21.48 | 37.59
6628 | PAI9VZBMaYriaY1wvhOi | 2 | 7.96 | 15.91
6629 | n59ds33sZr9JNOobmYWE | 1 | 10.07 | 22.15
6630 | y36QmeQSyS7BZflkeM7e | 1 | 5.19 | 11.42
6631 | Ghk1eKq5exIyUH3hdAeR | 1 | 10.15 | 22.33
6632 | 5y36mClzGR7vkSsODb4C | 2 | 6.89 | 13.79
6633 | uS272glxjETpDiVeJyGv | 2 | 13.14 | 26.28
6634 | 65ghvPiwU0AxSKrC11rG | 5 | 25.06 | 41.76
6640 | QUv6m7GotPkUb98mhJX7 | 3 | 10.09 | 18.73
6643 | sKnPCsxlq51dE8cz52fo | 3 | 6.52 | 12.1
6644 | 0NVu6ABxwy3imKaZ2MTJ | 2 | 6.25 | 12.49
6646 | CmmxWTpZgFyyAwkQnNh3 | 3 | 6.78 | 12.6
6647 | hWzCSsDre5WTTpryk1b0 | 4 | 4.77 | 8.34
6648 | Z5T3n0GGVz8PB0IY5TXC | 1 | 3.94 | 8.68
6649 | TeFWDZJ3h8q4yVNptUYE | 2 | 16.84 | 33.68
6650 | FvuNLI4Jaew3VjPpwL3e | 1 | 10.54 | 23.18
6651 | T3J0AzovT4qFTLJ7Lgki | 3 | 10.17 | 18.89
6652 | 0afM7N7hGdWHQjlFenVR | 1 | 4.16 | 9.16
6653 | K0AYRckqpyO0HzRrxXG6 | 5 | 13.94 | 23.24
6654 | MMK0qYycfTMCrFAZcf8J | 2 | 9.89 | 19.79
6655 | gl8c5oVG5KfrLbsQSFL4 | 4 | 8.15 | 14.27
6656 | tqprQgHoroqT051BXug3 | 4 | 10.41 | 18.21
6657 | uq5fluI8KT8LkPx57ktn | 3 | 8.06 | 14.98
6658 | ktg0XNnAmjjc1caqICt2 | 4 | 4.7 | 8.22
6659 | NN3Qiea1foOxv05JqXnT | 3 | 6.16 | 11.44
6660 | pWIs4hM6SgH2pFjSQ3qo | 5 | 4.46 | 7.43
6661 | bQxmmL7mcUsEGpKkQTDo | 2 | 17.01 | 34.02
6662 | CVNpv9CNU8XhfLmVwl8x | 4 | 22.42 | 39.23
6663 | LVExlIxeJ6XB3yqm0Dzs | 2 | 16.25 | 32.51
6664 | Io9oZ1dPqEE9GDlMTPxh | 2 | 17.15 | 34.3
6665 | ycT0qtEFjd4p02S4Ehf1 | 4 | 20.52 | 35.91
6666 | sX3PHseynvzwKI9my2AH | 5 | 19.83 | 33.04
6667 | 0dYk2X7XWh2rSSHkHo2L | 1 | 3.74 | 8.23
6668 | NGuTznXCCG5yuIi6lGQO | 4 | 0.98 | 1.72
6669 | t8MCocRefa6DhiQNsJVn | 5 | 1.04 | 1.74
6670 | vWxPVjk5e7KHTev8998h | 3 | 0.83 | 1.53
6671 | 0oTh3tmNX3iVSaVNVmGK | 5 | 5.45 | 9.09
6672 | BKyGOzVPyPwKpI9CyseJ | 1 | 1.58 | 3.47
6673 | sIWmvaXMX3ZF9ctRNm7s | 5 | 29.5 | 49.17
6680 | ttlvn3uwilh7nqgbHtE7 | 4 | 31.46 | 55.05
6681 | NHiN8b86HRxpkLb9JGGD | 5 | 10.54 | 17.57
6682 | 695WEwNqpcHeAbXSBRci | 2 | 1.08 | 2.16
6684 | TL3Mtv3QlGNejnoXktH7 | 3 | 0.84 | 1.56
6686 | IDiuvzfQRXyu7MCMX1jW | 1 | 2.19 | 4.83
6687 | RiyOBd4mBIE5Cq6C0A4h | 2 | 0.53 | 1.06
6689 | fEYxMDiPOAwjjU8zha5c | 1 | 147.2 | 323.84
6690 | bopLkaAZbmZjIM9EGI6L | 4 | 475.78 | 832.61
6691 | xLErpFHjPEH3ifHRbBMY | 4 | 389.06 | 680.85
6692 | g8WcEZ6I6SGdlePHrYPP | 2 | 163.19 | 326.38
6695 | Bx0BPJ0BcPw49QEL7Psq | 1 | 122.49 | 269.48
6696 | XbFIp383UbA72xJPH4hJ | 5 | 90.29 | 150.48
6697 | gpkN7vTMpz4ZZxhDAmeL | 1 | 63.6 | 139.91
6698 | eRsel9yyFaDkcYLZgvjC | 1 | 75.78 | 166.7
6699 | k8943lu4TS9ZW2TcUvha | 5 | 260.35 | 433.92
6872 | SjyWialEYK436pEnV5Nr | 5 | 0.9 | 1.5
6873 | gSZIbC6fsU6IM6McOJy8 | 4 | 0.87 | 1.53
6874 | 1XFpbhK6U752FQe8voXZ | 5 | 1.01 | 1.68
6878 | VU7w4voCV7rMMsz4AnPW | 4 | 0.88 | 1.54
6879 | Vbp0cBOXY9azJeyTE4S4 | 4 | 2.66 | 4.66
6880 | ZuauWvCPNW7n2NMscMO2 | 3 | 2.52 | 4.68
6881 | XekYY8n1P4vELtk4BUks | 4 | 0.79 | 1.39
6890 | QKIolSsTnUWZiIhR6M5v | 2 | 17.99 | 35.98
6955 | CPACk87DS0kpO7pXcdwS | 4 | 8.94 | 15.64
6958 | 6Ul4V6iAcnpVqewOp14Y | 1 | 1.72 | 3.8
6959 | w9Vvv79ftt4PUqInNFyD | 1 | 2.12 | 4.65
6960 | xIgpHAurEQ244gHa2T5q | 4 | 3.86 | 6.75
6961 | NOksVV7sTymsgwMrnh6x | 3 | 6.57 | 12.21
6977 | F0juzsyqTnJm6sTJe4ff | 4 | 12.41 | 21.71
6978 | z4sj2SQJw3pdZet8Am0U | 5 | 9.59 | 15.99
6979 | ZYA6dvbLVog9FL6DNJRb | 1 | 2.28 | 5.03
6985 | eGeEyEDP9xa0SwHKf7WR | 3 | 4.71 | 8.75
6987 | 50so1NYgvDTnEeNkdrjv | 4 | 2.17 | 3.79
6988 | bmsC3uFxKZ3RPA57Ivjb | 3 | 2.39 | 4.45
6989 | okOYULy0nclsZMYhl4sg | 2 | 1.75 | 3.49
6991 | RAhO7UtYgqwLkhTknwrO | 1 | 2.43 | 5.35
6997 | MBGoTUikAECGvIHYk1uV | 4 | 18.8 | 32.9
6998 | CyWehBzIvIWKBi1qju4z | 1 | 7.32 | 16.1
6999 | AnycnugTW971av3hMZXE | 2 | 4.59 | 9.18
7000 | yP1oDcnUQTy3g68ZLgu0 | 1 | 3.03 | 6.67
7001 | WpRQh8HvPfyDha8FH5FR | 5 | 8.8 | 14.67
7010 | l7MAqMN94R7DBQRgok6z | 1 | 2.16 | 4.76
7015 | U0mup1noPd6mH1CxWGtr | 5
7016 | pVOP21cemlwRUbhUeRME | 5
7107 | fjlRoMsMUGjOnNWoUkGJ | 3
7108 | wFwSqsIrP0eolc7owrIn | 1
7110 | fycPVr34q6lr2y2bEJNl | 2
7111 | gs1r9nT3BBBdW42nHT47 | 3
7112 | a270fhhuENq55tFKO8IB | 3
7114 | pZqvbi91bBhqyjB86evl | 2
7115 | mxRJVREYCLlOZtWGohdT | 3
7116 | 4gFjRlWXKNF16b9sFMXr | 1
7117 | zFlqKdf38AVahGy9Q9X8 | 2
7118 | 6jNHf85fMsjQD6qn9QnY | 4
7119 | OQnmDeJwrgb4ibYKrZjo | 5
7120 | ewfCDE69jjk4Zb5M5CES | 2
7121 | V4W6CQQo6lTjRlhYdPDq | 4
7122 | ZQwX0qpiGy3bERfpXjQ0 | 1
7123 | 0fpNMQTy9Zfk1YAC7GK2 | 4
7124 | yYQOOagkBr46kWICPuG6 | 4
7125 | a4xeGKWGk9YyWLffVRQZ | 5
7126 | XIH51zzlt2AXqf8IkYxf | 3
7129 | kvNY0frGkARL99AbSHw0 | 1
7132 | osdxrWYmqQZxyGZXe9Pr | 1
7184 | gKjyagqR1BEsAZjZk4l5 | 4
7185 | 9DFzvUnK8UE41lq7OD40 | 3
7192 | rcBSOCAYFUxP7jsyoqGw | 3 | 6.52 | 12.12
7194 | mB0uoGZ1D1fuFzk350Kb | 3 | 16.27 | 30.22
7199 | G7LfPy6euQCIQjteO0x8 | 1 | 9.89 | 21.76
7201 | UKbpgMkpfrIPVoEOJEeO | 1 | 4.78 | 10.5
7202 | vy1jnuopIHJe5PhTsUNw | 5 | 4.8 | 8
7203 | KqVHIBvrHNAu5GlarotD | 4 | 2.47 | 4.33
7204 | BUAmcwglNtP3GEkJsPLR | 5 | 0.97 | 1.62
7206 | bMXBNIC1fF7AjliDPdfr | 1 | 11.92 | 26.22
7207 | 51ZGrscW6XrNzeOMbLyw | 2 | 2.19 | 4.38
7208 | 5Vu53Z23NG8K3uSzUcYA | 5 | 3.04 | 5.07
7209 | r8OmtZddpdGbVxNEynIO | 2 | 0.61 | 1.22
7212 | IA5BwO4PzPuXs5yI3XzH | 1 | 1.58 | 3.47
7213 | GkAhONTSL0EMIVzc5bXh | 5 | 2.79 | 4.65
7214 | ysGFXohNyFRFQ06jmkjW | 5 | 0.92 | 1.53
7220 | nvywSXdnd0LSUGSiB3or | 3 | 8.26 | 15.34
7221 | PYoR7OoHLcblZDJJ1hTC | 5 | 22.87 | 38.12
7222 | W1KVKgORO9KqmU1uQFqG | 5 | 0.92 | 1.53
7227 | QiFvht1v2EB9ODLdNK6M | 4 | 24.74 | 43.3
7228 | SSqxRWtJ8NkhLwkx3Zp5 | 4 | 13.86 | 24.26
7233 | rgerXXfH5cOVWHlSbXtk | 1 | 0.88 | 1.93
7234 | 4Nk8AWONEAABjENRSl4s | 2 | 1.94 | 3.89
7235 | uR7e5eYUOS8ur8CkZgir | 3 | 1.6 | 2.96
7236 | OqdHv6QLhEyFdmarh5Mg | 2 | 3.56 | 7.13
7237 | xLl9f1S8pVLgozw4LZw4 | 2 | 5.15 | 10.3
7238 | hj0QAuvemNr4BSx0wqCM | 3 | 6.94 | 12.9
7239 | sGRMuNmZsu5Ap3rRR6Ja | 2 | 1 | 1.99
7241 | RP09WyAKLetAyeWXIWbd | 5 | 1.06 | 1.77
7242 | PNiOufePi0cnwKsaAHa8 | 3 | 1.92 | 3.58
7243 | nppwsC1hz1MTRepHit5q | 3 | 2.46 | 4.56
7245 | ysJ2Wz17vAaH50NFOd3r | 3 | 1.79 | 3.33
7246 | w8OYvCOBO1azAOar59yv | 1 | 1.25 | 2.74
7247 | QmLDbLdk9YgltF6FQxKi | 4 | 1.58 | 2.76
7249 | T3rEQsXy5TFYVzdnmRkQ | 2 | 12.05 | 24.11
7250 | G5mdz8DmOa8TGNlmxmOk | 5 | 19.81 | 33.02
7252 | R4hlQqYwslHcXudIUORM | 3 | 15.69 | 29.15
7253 | 5Q6OCjUddDwnqpg2shNG | 3 | 3.56 | 6.6
7254 | aZsc8OQGYCtOtLNUDl4p | 4 | 5.27 | 9.23
7255 | GiGIxdlKVFOGW1rlVkpg | 4 | 4.01 | 7.01
7256 | ZTFxKau19KKCcFlUDIYg | 4 | 5.83 | 10.21
7257 | EmkT3sq6aGy3vx96JSsX | 2 | 1.34 | 2.69
7258 | PBxke5bv0Yk6xXbQcvVe | 1 | 0.42 | 0.94
7259 | Dcjo2uskRMoBajU90pQq | 4 | 49.29 | 86.25
7260 | DPsh83rHAyIaiD8XYnO0 | 3 | 230.03 | 427.21
7261 | isfym7y8CMuc9Vq3Mbcl | 2 | 0.47 | 0.94
7263 | mjGxmWsUF3dJi6MlhQpM | 1 | 0.49 | 1.08
7265 | uNFJkQaxxZ7oOYaM8QxX | 4 | 11.54 | 20.2
7266 | y7TR6NxR4uOKxinxsnEt | 2 | 7.4 | 14.81
7267 | f0BUmD79ZhKqjjzrwXUq | 3 | 9.62 | 17.86
7268 | sP1zO7OhzT9CUKqdzecJ | 2 | 7.16 | 14.33
7269 | 7v5GPnNw6yREyKfoeMiZ | 4 | 3.88 | 6.79
7271 | 7ZvC3KC1rMxIYvbhicKJ | 4 | 7.23 | 12.66
7278 | 4Ma7Z2LiPmWBC9UI6vyb | 3 | 3.37 | 6.27
7282 | sTVLhyKAe9uIrxTuOSsB | 2 | 1.23 | 2.46
7283 | GyFcZSlU29ifaVubQEBd | 3 | 1.32 | 2.44
7284 | AoDPK2hmzwZjnwdc6ENo | 1 | 0.43 | 0.95
7285 | UP4KQN3vFTNJJtYiVHhd | 4 | 7.99 | 13.99
7289 | YNbMTserJcwdDTx8O6lt | 5 | 5.62 | 9.38
7290 | rpRUKocvSOF2GnoJsxWr | 5 | 1.8 | 3
7291 | ThxkR8uStFOgKr5Kajlm | 3 | 0.62 | 1.14
7292 | 6vEOHVPLFOaXnW1xcDp6 | 2 | 5.44 | 10.87
7296 | PnFVdPiNKahDkradYWdd | 5 | 6.11 | 10.18
7297 | JA5LCeR4tD4Vqq2Jfy9o | 4 | 1.37 | 2.39
7298 | uHK4wyA8DzlXgqm5UKoq | 4 | 0.68 | 1.19
7299 | ymtRqRQZa4AjGraGOZVd | 3 | 8.18 | 15.18
7300 | JMkMoXIhBdn9ICcOd798 | 4 | 4.35 | 7.62
7301 | mVBynbXAicTgOFud0Dl3 | 4 | 4.49 | 7.85
7302 | 6S1rSJxqNAmNyzjZVL7L | 3 | 2.88 | 5.34
7307 | eye8r8DevGvPITcdrMUe | 4 | 4.34 | 7.6
7308 | BXoPyB4GmzJwvFdrkJ7b | 2 | 0.52 | 1.03
7313 | boaUnlKi0h6sKdwgAbmA | 2 | 3.47 | 6.94
7314 | zaliCdoIQDW2tx8wBQyt | 5 | 1.1 | 1.83
7318 | vWglY3BMmZCigDWMEMyY | 5 | 3.64 | 6.07
7319 | Fr6VbOwwg75s6X3Xcfql | 4 | 3.83 | 6.71
7320 | MRmQHJYBr9cc2OfLUSYd | 1 | 0.39 | 0.86
7321 | CTokiQfH6gyOyeZJGrxP | 4 | 0.78 | 1.37
7324 | GVXYroUMjcAFUHa4B19H | 2 | 0.66 | 1.32
7325 | wl82vK5NXqnnsHIySTFp | 3 | 0.76 | 1.4
7376 | FfEUU5kpALOu6FlmjosD | 1 | 208.94 | 459.68
7378 | YjoFZZooPnFRzsk2Ba2E | 4 | 290.46 | 508.31
7379 | 7GajZBAFakrGWC1WlgE6 | 2 | 63.22 | 126.43
7380 | wkyoOF6gHS9pA0Dm9pZY | 2 | 72.12 | 144.24
7381 | Ao7wteklS85dOuCCMM3I | 3 | 77.79 | 144.47
7383 | chM988R4AoJxJINOHhOy | 3 | 0.67 | 1.25
7384 | xn1TRUhUfNd3ygHlAMk1 | 1 | 6 | 13.19
7385 | cYlWo9e2zkkP7jtt7iLZ | 2 | 0.53 | 1.07
7386 | F9n9tFj3S3xXbwXNgAjU | 5 | 4.23 | 7.05
7391 | UumEMUqxjwvZXtHBx1rg | 4 | 2.46 | 4.31
7392 | ylVP19AJuwY485wgDJEG | 2 | 4.81 | 9.62
7393 | RzIyrLZKRoqlWdOJYpGf | 3 | 2.39 | 4.45
7394 | zHoRZ9fggWfe9FGnA954 | 4 | 7.22 | 12.64
7395 | PMjQe1vYJ6mxUbNABucF | 3 | 2.04 | 3.78
7396 | gQKdIVV4LZyvHUAfFFFg | 5 | 8.32 | 13.86
7398 | ItOQSxoXEYWD5clVNK0n | 5 | 2.76 | 4.6
7399 | cXpFrNuZR7O8wPV6KZK3 | 3 | 6.4 | 11.9
7401 | H3MyBOTVJ4MGxcXcavMD | 2 | 1.04 | 2.08
7402 | pMiEhGou1QDK96DPu7Q8 | 3 | 0.71 | 1.33
7404 | EvHLT3cR3tYYGwcq6SC1 | 4 | 4.06 | 7.1
7405 | 5GpI6xkgfIoVOnU9egD8 | 1 | 5.64 | 12.41
7406 | WxzG2sAIbVYYiem4v3mk | 1 | 5.24 | 11.54
7408 | uKngouP2QMMQmu6HFm0I | 4 | 7.94 | 13.9
7409 | C7eZzAQkBbKewE4wmmOD | 4 | 8.23 | 14.41
7410 | VCdEPtbQjRcgNUnNprkZ | 2 | 6.49 | 12.97
7411 | OzHccTXr25Mf4pmiIMuT | 2 | 7.54 | 15.07
7412 | obz02flxb00pYjKUpMNx | 4 | 10.52 | 18.41
7414 | DrM34eAIT9imz4vRHbHm | 3 | 1.5 | 2.78
7415 | RsULMViXRZoYahxlMUQ4 | 4 | 19.35 | 33.87
7416 | U8irVJqpjJwQWU5FcpMo | 3 | 2.41 | 4.47
7417 | yrCdbpyUp4mqkbXiv5Nc | 2 | 3.2 | 6.4
7418 | Iw5sTi596kP8d52cBWYm | 5 | 4.99 | 8.31
7419 | s9reBpLseCBnslseiKA6 | 5 | 2.22 | 3.7
7421 | 5PvQN5TGe8y7KbK2rRhO | 4 | 6.72 | 11.76
7422 | fj19MvsSAfWHeVGXiA1H | 1 | 2.31 | 5.08
7423 | hs9Gt4WgG9pENnEIaC7X | 3 | 10.27 | 19.07
7424 | WqCakGr8mHgCENNWHHjW | 3 | 3.9 | 7.24
7425 | Pv27HXd826jlfuUJmTLH | 4 | 14.38 | 25.17
7426 | UjcYgNHyPV73fWy2GGNA | 3 | 4.17 | 7.75
7427 | 5QMAV8W19uO0knxuRgYc | 2 | 3.45 | 6.9
7428 | C3roUkJ3GEdxAvfnxnUE | 4 | 5.43 | 9.51
7429 | GMfJSktlv5oUXA5LFNgA | 3 | 3.14 | 5.84
7431 | YKkcKAxBNBkRs3Gs0cxp | 3 | 5.01 | 9.31
7432 | HbmHLQTrqR87hE03VIdq | 2 | 1.75 | 3.49
7433 | FxBsJSw4ZNEIyIQA8bL9 | 3 | 6.98 | 12.96
7434 | MkjgnYEnwrIrITdXMEl9 | 1
7438 | y2P0mgWq1uFkM4aVxtQJ | 2 | 7.48 | 14.95
7439 | nsJKxwZOWJc3LdYsNOwr | 5 | 4.17 | 6.94
7440 | 3ZzL4TktDwncii0hY2dA | 1 | 4.06 | 8.93
7442 | B8zfbswYxyRxHa21jaE6 | 2 | 9.34 | 18.67
7443 | lvFKaF8Jtq8DkkB0s9nv | 2 | 9.91 | 19.82
7444 | 419IszMaZW6XNIQptprk | 4 | 20.22 | 35.38
7445 | oNfFp4VAwKEpoSujTbHZ | 4 | 9.58 | 16.77
7447 | CAsJ3atkVCS14hehUB9Y | 2 | 2.5 | 5
7448 | 8tMCh2h8AwE53TPPkfEv | 3 | 2.13 | 3.95
7449 | LaZxXVdUnGzqswRGUiV5 | 5 | 6.57 | 10.95
7450 | F3vtt1T8lz7mQWFPgUKT | 1 | 0.72 | 1.6
7451 | nShmtMdGhMi3SzNeAZjW | 1
7454 | JYERhD3wllXGZEgPk4Fl | 5 | 4.72 | 7.86
7455 | hQlezwT73UjuGPZkyuVr | 1 | 4 | 8.81
7456 | 3cfjdZ38xGBNf8roD7He | 3 | 5.94 | 11.04
7457 | abNwDWOnFoe0xwhiRueS | 1 | 0.47 | 1.03
7458 | cMhUMuxC0sax27543As7 | 4 | 20.46 | 35.81
7459 | xf7OMyoiQ38QdcweBYiq | 4 | 18.85 | 32.98
7510 | 4i5VLTIa98HteWhFzYjv | 3 | 1.99 | 3.69
7511 | tHPdmsBqm9kHM69dtq3h | 1 | 3.52 | 7.74
7512 | hmOTDv9qQbSDcHudIm9x | 2 | 4.32 | 8.64
7513 | NbiRgc4Tdvxa900kw7Xq | 3 | 4.78 | 8.88
7514 | 4jhJaLUHxegkfPxUyChC | 3 | 9.56 | 17.74
7528 | 8SnF5zCB4rJyZyQZLLZc | 5 | 9.5 | 15.82
7529 | ugdLGMeRoSNQZE98ehwR | 2 | 4.55 | 9.11
7530 | tZgNvNsEFqNHmYVKXpMu | 3 | 4.71 | 8.75
7531 | WsQS39Ko43y2ykuRUNnk | 5 | 8.96 | 14.92
7532 | tNKjUDGuH9lZvW14y0xJ | 1 | 11.6 | 25.51
7533 | HKUUjAeDBFLcgj42uw3c | 2 | 12.66 | 25.32
7534 | s7VTtgJqjYjf9pbLYcYj | 1 | 3.4 | 7.48
7535 | uGgP1gHCy12zlVFcLeTG | 3 | 3.26 | 6.05
7536 | kbIucnV7qsI0ZjxbK1cH | 5 | 5.9 | 9.84
7537 | ZiOXL4e3BgetRuJ4aYKK | 3 | 0.53 | 0.99
7539 | ROucR7pug9aGzObG8pvW | 4 | 0.86 | 1.51
7540 | njszlznNRnCyRW2hgoMI | 5 | 9.2 | 15.33
7541 | R63tw5xkvmDGiWpIPQRa | 3 | 0.71 | 1.31
7542 | E3YdLEfamF0eZCISJiqw | 3 | 6.59 | 12.25
7543 | nhpJxewK7uClQLzGXJQJ | 5 | 1.13 | 1.89
7544 | cfuUTFyz3WOPAOOiNQOb | 3 | 0.58 | 1.08
7546 | tdocr3pqURBYHZWcAyMG | 1 | 0.36 | 0.78
7547 | 2p5uMAQ0v8mT9pq4KeWp | 4
7548 | TdNnLE8G4vf1vBjggzLw | 4 | 0.86 | 1.5
7549 | yUAt6Fi3Vichq9Ai1DSh | 4 | 0.84 | 1.47
7550 | fUEnUBwdI1z3bgOngjaQ | 1

## Risk register
ID | Name | Probability % | Impact d | Affected | Consequence | Hits | Mean delta d
R1 | Test Risk | 86 | 321 | 7443 | 5 | 1726 | 304
R2 | Test Risk 2 | 63 | 45 | 7433 | 3 | 1263 | 39.1

## Probabilistic branches
ID | Name | Probability % | Tie (after->before) | BC/ML/WC d | Fired % | Mean rework d | Mean delta d | Status

## Conditional branches
ID | Name | Condition | Plan A (primary) | Plan B (fallback) | Plan A % | Plan B % | Mean A d | Mean B d | Mean delta d | Status

## Focus-finish results
Measure | Value
Deterministic finish | 2029-04-19
Deterministic percentile | 1
P10 | 2029-06-25
P50 | 2030-08-05
P80 | 2030-08-28
P90 | 2030-09-17
Mean | 2030-06-11
Std deviation (working days) | 108.17
Std deviation (calendar days) | 151.4

## OAT sensitivity
UID | Task | Best case d | Worst case d | ML d | Opportunity wd | Risk wd | Total wd
7443 | lvFKaF8Jtq8DkkB0s9nv | 16.52 | 321 | 16.52 | 0 | 304.5 | 304.5
5539 | kRsO3PSMDsMxji3dmdNc | 376.53 | 753.06 | 627.55 | 0 | 108.7 | 108.7
7433 | FxBsJSw4ZNEIyIQA8bL9 | 9.97 | 45 | 9.97 | 0 | 35 | 35
6513 | IG8fHoH3vjERJ6iSB3Rj | 23.67 | 43.97 | 33.82 | 10.2 | 10.2 | 20.4
7415 | RsULMViXRZoYahxlMUQ4 | 19.35 | 33.87 | 24.19 | 4.8 | 9.7 | 14.5
6997 | MBGoTUikAECGvIHYk1uV | 18.8 | 32.9 | 23.5 | 4.7 | 9.4 | 14.1
5571 | lfRAbO0c5jl7NaC6s7pm | 10.86 | 23.89 | 21.72 | 10.9 | 2.2 | 13.1
7425 | Pv27HXd826jlfuUJmTLH | 14.38 | 25.17 | 17.98 | 3.6 | 7.2 | 10.8
7443 | lvFKaF8Jtq8DkkB0s9nv | 9.91 | 19.82 | 16.52 | 6.6 | 3.3 | 9.9
7442 | B8zfbswYxyRxHa21jaE6 | 9.34 | 18.67 | 15.56 | 6.2 | 3.1 | 9.3
7423 | hs9Gt4WgG9pENnEIaC7X | 10.27 | 19.07 | 14.67 | 4.4 | 4.4 | 8.8
5558 | RXAxJx3BHWNVdWFPfZ2a | 8.53 | 17.05 | 14.21 | 5.7 | 2.8 | 8.5
7411 | OzHccTXr25Mf4pmiIMuT | 7.54 | 15.07 | 12.56 | 5 | 2.5 | 7.5
6510 | dar9hgzhSUYJxC1MeoTS | 11.02 | 18.38 | 12.25 | 1.2 | 6.1 | 7.3
7410 | VCdEPtbQjRcgNUnNprkZ | 6.49 | 12.97 | 10.81 | 4.3 | 2.2 | 6.5
7409 | C7eZzAQkBbKewE4wmmOD | 8.23 | 14.41 | 10.29 | 2.1 | 4.1 | 6.2
7408 | uKngouP2QMMQmu6HFm0I | 7.94 | 13.9 | 9.93 | 2 | 4 | 6
7433 | FxBsJSw4ZNEIyIQA8bL9 | 6.98 | 12.96 | 9.97 | 3 | 3 | 6
901 | HcFqHITfVdYMyzVb3S8v | 18.42 | 30.7 | 20.47 | 0 | 5.7 | 5.7
7399 | cXpFrNuZR7O8wPV6KZK3 | 6.4 | 11.9 | 9.15 | 2.8 | 2.7 | 5.5
7421 | 5PvQN5TGe8y7KbK2rRhO | 6.72 | 11.76 | 8.4 | 1.7 | 3.4 | 5.1
5744 | cSBfnbrbVLLFYTMEfBKA | 6.58 | 10.96 | 7.31 | 0.7 | 3.7 | 4.4
7449 | LaZxXVdUnGzqswRGUiV5 | 6.57 | 10.95 | 7.3 | 0.7 | 3.7 | 4.4
5584 | 6WMzJdzS7tY0wFFuXnrc | 6.54 | 10.9 | 7.27 | 0.7 | 3.6 | 4.3
5734 | iq9bjqBZvH9Bj6912271 | 6.49 | 10.82 | 7.21 | 0.7 | 3.6 | 4.3
903 | UDGopgZ2sb1QsQEooZ9G | 4.2 | 8.4 | 7 | 2.8 | 1.4 | 4.2
5545 | 7UVU8IboY6NG7sqZCrUC | 3.84 | 7.68 | 6.4 | 2.6 | 1.3 | 3.9
5585 | KljMWvDEBGSuBTW4zQhZ | 4.63 | 8.59 | 6.61 | 1.9 | 2 | 3.9
5587 | OXOUsYDejGVlgqn4Z1vl | 5.1 | 8.93 | 6.38 | 1.3 | 2.5 | 3.8
7428 | C3roUkJ3GEdxAvfnxnUE | 5.43 | 9.51 | 6.79 | 1 | 2.7 | 3.7
905 | MxRWNVEH6ZVBPqNnA2hI | 4.07 | 7.57 | 5.82 | 1.8 | 1.8 | 3.6
7418 | Iw5sTi596kP8d52cBWYm | 4.99 | 8.31 | 5.54 | 0.6 | 2.8 | 3.4
7417 | yrCdbpyUp4mqkbXiv5Nc | 3.2 | 6.4 | 5.33 | 2.1 | 1.1 | 3.2
5738 | ME2oX9BwgLu5cggaunhg | 2.5 | 5.5 | 5 | 2.5 | 0.5 | 3
5742 | 88bEv4EMiOL2y8w1ttIM | 3.97 | 6.94 | 4.96 | 1 | 2 | 3
7404 | EvHLT3cR3tYYGwcq6SC1 | 4.06 | 7.1 | 5.07 | 1 | 2 | 3
7396 | gQKdIVV4LZyvHUAfFFFg | 8.32 | 13.86 | 9.24 | 0 | 2.8 | 2.8
7429 | GMfJSktlv5oUXA5LFNgA | 3.14 | 5.84 | 4.49 | 1.4 | 1.3 | 2.7
7444 | 419IszMaZW6XNIQptprk | 20.22 | 35.38 | 25.27 | 0 | 2.6 | 2.6
5730 | ypyrsmMFJqJ9aPla6UhQ | 2.35 | 4.69 | 3.91 | 1.6 | 0.8 | 2.4
5745 | ZY99Y6JX4jBylnfeedvo | 2.27 | 4.99 | 4.54 | 1.9 | 0.5 | 2.4
5586 | Z3ZWpIsgJCSKUX161hV0 | 2.98 | 5.21 | 3.72 | 0.7 | 1.5 | 2.2
7416 | U8irVJqpjJwQWU5FcpMo | 2.41 | 4.47 | 3.44 | 1 | 1 | 2
7405 | 5GpI6xkgfIoVOnU9egD8 | 5.64 | 12.41 | 11.28 | 0.8 | 1.1 | 1.9
902 | nIjAIVHCOoi1ijXym0cI | 2.39 | 4.19 | 2.99 | 0.6 | 1.2 | 1.8
7432 | HbmHLQTrqR87hE03VIdq | 1.75 | 3.49 | 2.91 | 1.2 | 0.6 | 1.8
7448 | 8tMCh2h8AwE53TPPkfEv | 2.13 | 3.95 | 3.04 | 0.7 | 0.9 | 1.6
7419 | s9reBpLseCBnslseiKA6 | 2.22 | 3.7 | 2.47 | 0.3 | 1.2 | 1.5
5546 | Shs5wuYOFSkTF1YslX8w | 5.96 | 9.93 | 6.62 | 0 | 1.4 | 1.4
7414 | DrM34eAIT9imz4vRHbHm | 1.5 | 2.78 | 2.14 | 0.6 | 0.6 | 1.2
5548 | Zfzda0CfmpiN8ZL93G3t | 5.41 | 9.02 | 6.01 | 0 | 1.1 | 1.1
1570 | 9hmrS48cr19KgrseY4yN | 0.9 | 1.98 | 1.8 | 0.7 | 0.2 | 0.9
7450 | F3vtt1T8lz7mQWFPgUKT | 0.72 | 1.6 | 1.45 | 0.7 | 0.1 | 0.8
906 | PL0zn2U2NPPXQqakkHLb | 2.8 | 5.6 | 4.67 | 0 | 0.7 | 0.7
907 | 5mTVpVcHzmsYLVY8xpKs | 2.44 | 5.37 | 4.88 | 0.2 | 0.5 | 0.7
5588 | MFjHKzinVVI0Ndx8qx0B | 0.94 | 1.65 | 1.18 | 0.2 | 0.5 | 0.7
5743 | 0Uz4krHDVCdAlMd5aRwh | 1.16 | 1.94 | 1.29 | 0.1 | 0.6 | 0.7
5735 | Z8zFgfwvHK2hwW2AW8Qa | 0.71 | 1.33 | 1.02 | 0.3 | 0.3 | 0.6
5739 | IivOSmNLtmlF9JKFLUrl | 0.7 | 1.23 | 0.88 | 0.2 | 0.4 | 0.6
6514 | imV319lPgBwI8oLVT5sB | 0.46 | 1 | 0.91 | 0.5 | 0.1 | 0.6
7402 | pMiEhGou1QDK96DPu7Q8 | 0.71 | 1.33 | 1.02 | 0.3 | 0.3 | 0.6
5731 | uQF6Ff0bc2cqy3b37ZQc | 0.44 | 0.97 | 0.88 | 0.4 | 0.1 | 0.5
4679 | rpzkOhA603pApmNdMeVE | 0.36 | 0.66 | 0.51 | 0.2 | 0.1 | 0.3
7406 | WxzG2sAIbVYYiem4v3mk | 5.24 | 11.54 | 10.49 | 0 | 0.3 | 0.3
7447 | CAsJ3atkVCS14hehUB9Y | 2.5 | 5 | 4.17 | 0 | 0.2 | 0.2
7427 | 5QMAV8W19uO0knxuRgYc | 3.45 | 6.9 | 5.75 | 0 | 0.1 | 0.1
150 | 7cu6yvdJV8ndF0CYMHk8 | 0 | 0 | 0 | 0 | 0 | 0
152 | QJ29ZvAvtEjBcpqHDer1 | 0 | 0 | 0 | 0 | 0 | 0
155 | 1yu6CrDX9QU5hWE1UWMV | 0 | 0 | 0 | 0 | 0 | 0
156 | 0RXSkgYJdrs7AeQvgU3w | 0 | 0 | 0 | 0 | 0 | 0
157 | DYCfhHgWVvjY4WPSrw6q | 0 | 0 | 0 | 0 | 0 | 0
166 | KkWbk0R1FXz2L56lHFvV | 1.76 | 3.08 | 2.2 | 0 | 0 | 0
168 | MT1CsCIMkhjJER6f3fjG | 0 | 0 | 0 | 0 | 0 | 0
173 | vJHK0TlIBzGpfYqdt8YI | 0 | 0 | 0 | 0 | 0 | 0
177 | V4ys3lAm8KEbtjGqLAuR | 0 | 0 | 0 | 0 | 0 | 0
178 | Cncpm0GACo0ppNIEy1Gp | 0 | 0 | 0 | 0 | 0 | 0
180 | 9Vp3PBZnh9TpV8TGBWRG | 0 | 0 | 0 | 0 | 0 | 0
193 | nJh7oj8wCJYW8hyepdLI | 0 | 0 | 0 | 0 | 0 | 0
194 | wTcNF86mfD2cPQPmQB1c | 0 | 0 | 0 | 0 | 0 | 0
196 | kzYOxx4jS6vhIcTyxNFn | 0 | 0 | 0 | 0 | 0 | 0
197 | LZAvhCOF77OBkAngJSDi | 0 | 0 | 0 | 0 | 0 | 0
198 | X7Nxs9NuQXJ5Bf6aQwVp | 0 | 0 | 0 | 0 | 0 | 0
199 | TiaYdQ98Ovd3qBAfSAyG | 0 | 0 | 0 | 0 | 0 | 0
200 | yynHcCtrZd0Ye6iQJb2E | 0 | 0 | 0 | 0 | 0 | 0
202 | mjF0YLun5LIdlxtu3zFl | 0 | 0 | 0 | 0 | 0 | 0
203 | 2a1x42QofxcVsgjcXtkr | 0 | 0 | 0 | 0 | 0 | 0
204 | 8T22gllTunmLl2jY7IMk | 0 | 0 | 0 | 0 | 0 | 0
205 | dm3U5Xjvi5rN2LqWegXW | 0 | 0 | 0 | 0 | 0 | 0
206 | ZOAcdJHtChBG5MUjo5uw | 0 | 0 | 0 | 0 | 0 | 0
209 | 0FNuAiL5ZzPZSZ3dZfoV | 0 | 0 | 0 | 0 | 0 | 0
428 | pxWL5EoMWeaDmapfAV7m | 1.3 | 2.42 | 1.86 | 0 | 0 | 0
436 | OGXVzK31PKUn8DxCdn94 | 17.05 | 37.51 | 34.1 | 0 | 0 | 0
576 | m8O5CFAYfVbtxxZI5qQW | 11.82 | 20.69 | 14.78 | 0 | 0 | 0
605 | HP2TrbmUH5Qc4V2P2k1T | 11.95 | 22.19 | 17.07 | 0 | 0 | 0
632 | tuv9OmQcJHKkVCVrbrrv | 5.72 | 9.54 | 6.36 | 0 | 0 | 0
633 | FgJ5XjjThZN85XQOJ0nJ | 13.79 | 25.61 | 19.7 | 0 | 0 | 0
634 | o4DRQRcsScdVmCSXNbxF | 7.17 | 13.31 | 10.24 | 0 | 0 | 0
635 | ztvy5zkS4z9HirKgvHGY | 10.56 | 21.12 | 17.6 | 0 | 0 | 0
636 | ZpIfqMwIaczq2BqznW2q | 6.24 | 10.92 | 7.8 | 0 | 0 | 0
637 | 3VAZwvp2NS6usl0wrvOM | 3.63 | 7.99 | 7.26 | 0 | 0 | 0
638 | 34zoFClD9RS7gLTCPZs0 | 2.5 | 5.49 | 4.99 | 0 | 0 | 0
640 | 10AmMHkCz4b8n0xqbyCt | 2.69 | 5.39 | 4.49 | 0 | 0 | 0
641 | KUqcSNVxncHPLVJNV5ca | 0.81 | 1.51 | 1.16 | 0 | 0 | 0
642 | chCwawHUqn0ea2ArCnKB | 0.21 | 0.46 | 0.42 | 0 | 0 | 0
643 | xZBRzE3QVYmQCjnzxLQv | 3 | 5.56 | 4.28 | 0 | 0 | 0
644 | tUTeQ74YpmkuuOiouSXU | 3.17 | 5.89 | 4.53 | 0 | 0 | 0
645 | mSrjcTZmK12EdJmOEYFi | 0.62 | 1.14 | 0.88 | 0 | 0 | 0
646 | Haue3rYYySw3jbXWnBeq | 2.96 | 5.18 | 3.7 | 0 | 0 | 0
647 | 6jlP0Y4QQ5KPQWxvolLg | 0.72 | 1.34 | 1.03 | 0 | 0 | 0
656 | lzPFAx9Fh8cDxyQ3uxFX | 0.78 | 1.56 | 1.3 | 0 | 0 | 0
658 | PyBKEPMZMe2YeOC66yut | 8.26 | 14.45 | 10.32 | 0 | 0 | 0
664 | H1KB0K8mM12Opvc4oDP1 | 2.82 | 4.7 | 3.12 | 0 | 0 | 0
665 | FIEbexlYHnOcZkEBs7WM | 2.93 | 5.87 | 4.89 | 0 | 0 | 0
666 | OcAHNnZWZgiwxfUiheGU | 1.92 | 4.22 | 3.84 | 0 | 0 | 0
667 | HPj21Hyun1nWvxJOQMhf | 24.89 | 43.55 | 31.11 | 0 | 0 | 0
671 | ZM52W2kHJJCM7052Da3J | 1.03 | 2.06 | 1.72 | 0 | 0 | 0
672 | AcRvLPQ7WrNfvcLBOWzV | 1.18 | 1.96 | 1.31 | 0 | 0 | 0
678 | N57z7OkXN935WcKbC4jO | 0.52 | 1.14 | 1.04 | 0 | 0 | 0
700 | PZaQwD8fp0dlxZIxEZEd | 258.9 | 453.07 | 323.62 | 0 | 0 | 0
745 | aO52oWR4hBrrP5GVCo2a | 5.79 | 10.75 | 8.27 | 0 | 0 | 0
746 | qMC0J8brk1dsdpzlKrk7 | 6.55 | 13.1 | 10.92 | 0 | 0 | 0
747 | nul8vpOEtI2Q6W5Q0Qo9 | 6.14 | 13.5 | 12.27 | 0 | 0 | 0
748 | M1HHh2K01o23jS8vpDxS | 6.5 | 13.01 | 10.84 | 0 | 0 | 0
749 | Q6UXOpf9Kvzek7IGY0vp | 5.59 | 11.17 | 9.31 | 0 | 0 | 0
750 | lsyrPytnmjLTpXFywa7Z | 8.12 | 15.08 | 11.6 | 0 | 0 | 0
751 | AADJzuTGAb4gWytj7CQi | 11.86 | 22.04 | 16.95 | 0 | 0 | 0
752 | r0c0rFS4EkOGynasmiCG | 29.66 | 51.9 | 37.07 | 0 | 0 | 0
753 | 8158sxzbHZvZEVAAqewP | 62.41 | 104.01 | 69.34 | 0 | 0 | 0
754 | hfPeDXfQSV7Nx9zb2rD7 | 3.23 | 7.11 | 6.46 | 0 | 0 | 0
755 | DQUdswbbJv1Qpkj0EGFX | 6.24 | 10.92 | 7.8 | 0 | 0 | 0
756 | ae3T3d3nFoXZXK7gqkAr | 18.14 | 30.24 | 20.16 | 0 | 0 | 0
757 | wbc1AZ0GUhXzQk6SoWIe | 4.47 | 8.29 | 6.38 | 0 | 0 | 0
758 | FbN1rrQYTlsz1haWZnFy | 5.18 | 8.64 | 5.76 | 0 | 0 | 0
759 | cZuo3MY7iyDrOJC1qVJx | 2.24 | 4.92 | 4.47 | 0 | 0 | 0
760 | 7IpOsslq7gyebnCTulxX | 52.08 | 91.14 | 65.1 | 0 | 0 | 0
761 | x6fNhJzs4uMW9trtiNEW | 0.9 | 1.5 | 1 | 0 | 0 | 0
762 | nRInnITHYgcDsU5KDg6m | 4.45 | 8.27 | 6.36 | 0 | 0 | 0
763 | hLK2cdXSS7IhOZR53PgI | 3.13 | 6.25 | 5.21 | 0 | 0 | 0
764 | wTf98lLeHiXAkWj17mAH | 53.09 | 88.48 | 58.99 | 0 | 0 | 0
765 | qOEfFivvitnF8cw9csOP | 0.54 | 1.18 | 1.07 | 0 | 0 | 0
786 | 5RJIBxVgSA4dodMzOCsx | 1.07 | 1.78 | 1.19 | 0 | 0 | 0
795 | 85yV4lhIxXIziyB5R2QA | 0.55 | 1.1 | 0.92 | 0 | 0 | 0
844 | 1qfp8o9PQxr9vZvO7S5k | 0.46 | 1.01 | 0.92 | 0 | 0 | 0
866 | 0rLFG0X22Uukcn0axQTO | 45.22 | 75.36 | 50.24 | 0 | 0 | 0
900 | ANUK0HdVlI2Jd5hSzs0f | 0 | 0 | 0 | 0 | 0 | 0
904 | 4CH3NSJx1luiHbrrAEJg | 1.52 | 2.66 | 1.9 | 0 | 0 | 0
916 | d4bxhxtQW3GaLrDrUlf9 | 17.51 | 29.19 | 19.46 | 0 | 0 | 0
917 | mbDdHZHm9OoYye329Ue6 | 1.04 | 1.82 | 1.3 | 0 | 0 | 0
1458 | W2l89btZYbaZZjxZTUR4 | 10.96 | 18.27 | 12.18 | 0 | 0 | 0
1459 | MxsNofofvf6CR0hsGInx | 0.48 | 1.06 | 0.96 | 0 | 0 | 0
1462 | 2Cc6AJ3gtv1XGHwG4F9W | 1.31 | 2.19 | 1.46 | 0 | 0 | 0
1464 | VN7GLU7alOC9oD3kkW9q | 30.5 | 53.37 | 38.12 | 0 | 0 | 0
1465 | i7zbkIpCuBMJlMsq6ma0 | 0.6 | 1.2 | 1 | 0 | 0 | 0
1468 | 8e77YoSi4abIbMILI8hH | 2.9 | 5.8 | 4.83 | 0 | 0 | 0
1469 | MZooHRTMNCHrNy0nPaCQ | 0.68 | 1.36 | 1.13 | 0 | 0 | 0
1470 | PdTqfNwd2IKBXe26tWkB | 1.34 | 2.24 | 1.49 | 0 | 0 | 0
1471 | FsiT4ZMTOq9hGqZQQdYf | 9.56 | 17.76 | 13.66 | 0 | 0 | 0
1472 | KG0YDAdikr58WjA79FVb | 6.35 | 11.12 | 7.94 | 0 | 0 | 0
1475 | suCYO4gIoCSrnZchT6aQ | 3.27 | 5.44 | 3.63 | 0 | 0 | 0
1476 | gbuDNYIgLq2nB3WERl4p | 33.19 | 55.32 | 36.88 | 0 | 0 | 0
1477 | BC1NYB3fqAlfckX7ECXI | 0.34 | 0.76 | 0.69 | 0 | 0 | 0
1478 | UR7xa7LgN3sMlpzxRjvW | 1.64 | 3.04 | 2.34 | 0 | 0 | 0
1485 | R0QJsNVi0JzXq4FadBdS | 19.64 | 32.73 | 21.82 | 0 | 0 | 0
1489 | pYq4lU1lCt1U75q3gu6M | 7.37 | 14.75 | 12.29 | 0 | 0 | 0
1490 | hF9FI1LNvFfgTTXhqPsR | 70.1 | 116.84 | 77.89 | 0 | 0 | 0
1491 | XpTPefWn9TT3C06gw8rA | 0.92 | 1.61 | 1.15 | 0 | 0 | 0
1495 | 0kid3Dd3U5gCQNrt2pwY | 0.99 | 1.65 | 1.1 | 0 | 0 | 0
1496 | 5t2MhilpkZRDQA3VTcGS | 34.89 | 64.81 | 49.85 | 0 | 0 | 0
1497 | q56IdotBOPeXlK3605d6 | 0.5 | 1.09 | 0.99 | 0 | 0 | 0
1504 | ndaml8HRsqEWzWIKrI7h | 3.26 | 6.53 | 5.44 | 0 | 0 | 0
1505 | 4c3z8pWafVxAWNC1MpC9 | 92.29 | 153.81 | 102.54 | 0 | 0 | 0
1506 | zNKWNUMZ7wFR6LBQ8bZ2 | 1.24 | 2.07 | 1.38 | 0 | 0 | 0
1508 | SDZ1pqYbdynEzXZrWujj | 24.62 | 41.04 | 27.36 | 0 | 0 | 0
1509 | xdWSZU8MxGE52WBHNu6X | 0.83 | 1.55 | 1.19 | 0 | 0 | 0
1518 | qXbL36bdYftxHm1TCntK | 0.6 | 1.1 | 0.85 | 0 | 0 | 0
1531 | KX1eD2ASIZaZBZuqoVp4 | 0.81 | 1.41 | 1.01 | 0 | 0 | 0
1532 | fQ3wcWF8uEWMRGpUCxEA | 0.54 | 1.08 | 0.9 | 0 | 0 | 0
1533 | juvdtwZkjArAkPOzLrhN | 13.9 | 23.16 | 15.44 | 0 | 0 | 0
1534 | SuchbNnj1ndABAEPQlrb | 9.56 | 15.93 | 10.62 | 0 | 0 | 0
1537 | HoYmSEeaxBfAYgcISNXh | 3.96 | 6.93 | 4.95 | 0 | 0 | 0
1538 | 1Xm6i4dPIyAKJzF1jRtD | 37.21 | 65.11 | 46.51 | 0 | 0 | 0
1541 | ss8yD9dhZfTIp9UxqHnG | 0.49 | 0.98 | 0.82 | 0 | 0 | 0
1542 | VmFPpoMfVfLEXeRBF7Um | 5.56 | 10.32 | 7.94 | 0 | 0 | 0
1543 | P2oxmSB7jXG6Ib9VEZ89 | 8.86 | 15.51 | 11.08 | 0 | 0 | 0
1547 | K0gsOWDMqaySswr72BAQ | 0.76 | 1.42 | 1.09 | 0 | 0 | 0
1548 | 4jCrHn72KCapTPEI9TzQ | 1.25 | 2.5 | 2.08 | 0 | 0 | 0
1549 | s8gTUDwRZFDpCO4enZqk | 285.63 | 476.06 | 317.37 | 0 | 0 | 0
1550 | UoQFPyMNVa9QPyq2kgrl | 4.12 | 9.05 | 8.22 | 0 | 0 | 0
1561 | 8BMHpFsmSFY1BvBQKfdD | 9.21 | 16.11 | 11.51 | 0 | 0 | 0
1562 | lBuCdKTmKHrCdvS4FVbB | 24.2 | 48.4 | 40.33 | 0 | 0 | 0
1563 | TUxQ6kz9ittb2zcmlLCL | 5.75 | 11.5 | 9.58 | 0 | 0 | 0
1564 | OkMyUpJo7fqJaif9Jvyb | 3.35 | 6.23 | 4.79 | 0 | 0 | 0
1565 | 9BGxipQLCi4kED7E7faW | 3.34 | 5.85 | 4.18 | 0 | 0 | 0
1566 | KFj0hxHWvExDoqTqgDeg | 92.5 | 161.88 | 115.62 | 0 | 0 | 0
1567 | GV5or0ucuouXZiqAkH0N | 9.24 | 16.17 | 11.55 | 0 | 0 | 0
1568 | JI4xSRBKV4FYnRXdw7Wz | 5.42 | 10.08 | 7.75 | 0 | 0 | 0
1569 | DVuFJt4FGQSIgeZkA41d | 1.42 | 3.11 | 2.83 | 0 | 0 | 0
3681 | wdhUrQuIMTMPn1LoqO1m | 8.46 | 18.62 | 16.93 | 0 | 0 | 0
3683 | JW3LUw009FZ7ddD6CdLX | 13.05 | 26.1 | 21.75 | 0 | 0 | 0
3684 | g3f8U3i4iakOhylueut6 | 5.9 | 9.84 | 6.56 | 0 | 0 | 0

## Risk matrix
Consequence \ Probability | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 1
4 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 1 | 0
2 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0

## Opportunity matrix
Consequence \ Probability | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0