## Hard_File
Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report | Fuse® Metric History Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Metric History
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
|  | Hard_File (7/7/2026 5:00:00 PM) |  |  | Hard_File_updated (8/11/2026 5:00:00 PM)
Metric ID | Metric Name | Failed | X | % | Failed | X | %
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Specific Task Start | F | N/A |  | F | N/A
| Specific Task Finish | F | N/A |  | F | N/A
| Wrong Status - Actual Starts | F | 0 |  | F | 0 | 0%
| Wrong Status - Actual Finishes | F | 0 |  | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0% | F | 0 | 0%
| Expected Finish But Still In-Progress | F | 0 |  | F | 0 | 0%
| Missing WBS | F | 0 | 0% | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0% | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1% | F | 1 | 1%
| Estimated Duration | F | 68 | 80% | F | 65 | 82%
| Missing Logic | F | 7 | 6% | F | 8 | 8%
| Missing Predecessors | F | 1 | 1% | F | 0 | 0%
| Missing Successors | F | 6 | 5% | F | 7 | 7%
| Open Start | F | 0 |  | F | 0 | 0%
| Open Finish | F | 0 | 0% | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0% | F | 0 | 0%
| Summary Links | F | 0 | 0% | F | 0 | 0%
| Hard Constraints | F | 0 | 0% | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0% | F | 0 | 0%
| Negative Float | F | 0 | 0% | F | 0 | 0%
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| High Float 44d | F | 2 | 2% | F | 6 | 6%
| Zero Days Float | F | 78 | 71% | F | 74 | 72%
| Hidden Duration (Planned) | F | 0 | 0% | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0% | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0% | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A |  | F | N/A
| Critical Diverge Hotspot | F | 1 | 1% | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A |  | F | N/A
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Deadlines | F | 0 | 0% | F | 0 | 0%
| High Float 10% | F | 20 | 18% | F | 17 | 17%
| Negative Float | F | 0 | 0% | F | 0 | 0%
| Tasks & Milestones (To Go) | F | 110 | 100% | F | 103 | 94%
| Milestones (To-Go) | F | 25 | 23% | F | 24 | 23%
| Normal Tasks (To-Go) | F | 85 | 77% | F | 79 | 77%
| Normal Tasks (To-Go, In Progress) | F | 0 | 0% | F | 1 | 1%
| Critical Path (Tasks & Milestones) | F | 34 | 31% | F | 33 | 32%
| Critical Path (Milestones) | F | 7 | 21% | F | 6 | 18%
| Critical Path (Normal Tasks) | F | 27 | 79% | F | 27 | 82%
| Critical Path (Normal In Progress) | F | 0 | 0% | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 |  | F | 1:05
| Negative Float | F | 0 | 0% | F | 0 | 0%
| Zero Days Float | F | 78 | 71% | F | 74 | 72%
| Near-Critical (<10 Days Float) | F | 90 | 82% | F | 81 | 79%
| CP Logic Density™ | F | 2.21 |  | F | 2.12
| Critical CEI - Value Tasks | F | N/A |  | F | N/A
| Critical CEI - Complete Tasks | F | N/A |  | F | N/A | 27%
| Critical CEI - Incomplete Tasks | F | N/A |  | F | N/A | 73%
| BEI - Value Tasks | F | N/A |  | F | 0.27
| BEI - Total Tasks | F | 0 |  | F | 11
| BEI - Complete Tasks | F | N/A |  | F | 3 | 27%
| BEI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Milestone #1 - 100 | F | N/A |  | F | N/A
| Float Milestone #1 - 100 | F | N/A |  | F | N/A
| Milestone #2 - 101 | F | N/A |  | F | N/A
| Float to Milestone #2 - 101 | F | N/A |  | F | N/A
| Milestone #3 - 102 | F | N/A |  | F | N/A
| Float to Milestone #3 - 102 | F | N/A |  | F | N/A
| Milestone #4 - 103 | F | N/A |  | F | N/A
| Float to Milestone #4 - 103 | F | N/A |  | F | N/A
| Milestone #5 - 104 | F | N/A |  | F | N/A
| Float to Milestone #5 - 104 | F | N/A |  | F | N/A
| New Activities Since Previous Status Date | F | 0 |  | F | 0
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-20 |  | F | 2026-08-20
| Margin - Margin Task Name #3 | F | 2026-08-26 |  | F | 2026-08-26
| Margin - Margin Task Name #4 | F | 2026-08-18 |  | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | N/A |  | F | N/A
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 1 | 100% | F | 1 | 100%
| Margin - Margin Task Name #3 | F | 0 |  | F | 0
| Margin - Margin Task Name #4 | F | 1 | 100% | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | N/A |  | F | N/A
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Total Activities | F | 141 |  | F | 141
| Milestones | F | 25 | 18% | F | 25 | 18%
| Normal Tasks | F | 85 | 60% | F | 85 | 60%
| Summaries | F | 31 | 22% | F | 31 | 22%
| Hammocks | F | 0 | 0% | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0% | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78% | F | 110 | 78%
| Completed Tasks & Milestones | F | 0 | 0% | F | 7 | 6%
| Completed Milestones | F | 0 | 0% | F | 1 | 4%
| Completed Tasks | F | 0 | 0% | F | 6 | 7%
| Total Activities (To-Go) - % of Total | F | 141 | 100% | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78% | F | 103 | 77%
| Milestones (To-Go) | F | 25 | 18% | F | 24 | 18%
| Normal Tasks (To-Go) | F | 85 | 60% | F | 79 | 59%
| Summaries (To-Go) | F | 31 | 22% | F | 31 | 23%
| Hammocks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 34 | 79% | F | 33 | 83%
| Longest Path (Normal Tasks) | F | 27 | 63% | F | 27 | 68%
| Longest Path (Milestones) | F | 7 | 16% | F | 6 | 15%
| Critical Milestones (To-Go) | F | 7 | 21% | F | 6 | 18%
| Critical Normal Tasks (To-Go) | F | 27 | 79% | F | 27 | 82%
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Baselined to Start | F | 85 |  | F | 85
| Scheduled to Start | F | 85 |  | F | 85
| Actual Starts | F | 0 |  | F | 7
| Baselined to Finish | F | 85 |  | F | 85
| Scheduled to Finish | F | 85 |  | F | 85
| Actual Finishes | F | 0 |  | F | 6
| Started Delayed (<=30 days) | F | N/A |  | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A |  | F | N/A
| Started Delayed (>60 days) | F | N/A |  | F | N/A
| Completed Delayed (<=30 days) | F | N/A |  | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | N/A |  | F | 0 | 0%
| Completed Delayed (>60 days) | F | N/A |  | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | N/A |  | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | N/A |  | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.33
| HMI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.27
| CEI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.33
| CEI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.27
| FEI - Value Task Starts - Cumulative | F | 1 |  | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1 |  | F | 1.11
| Current Baseline to Start & Started (BL Plan) | F | N/A |  | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A |  | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A |  | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 85 |  | F | 78
| Current Baseline to Finish & Finished (BL Plan) | F | N/A |  | F | 6
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A |  | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A |  | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 85 |  | F | 79
| Duration Ratio Metric (DRM) | F | 0 |  | F | 6
| DRM Graph | F | 0 |  | F | 6
| Baselined to Start | F | 85 |  | F | 79
| Scheduled to Start | F | 85 |  | F | 79
| Baselined to Finish | F | 85 |  | F | 79
| Scheduled to Finish | F | 85 |  | F | 79
| BEI - Value Activities | F | N/A |  | F | 0.29
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78% | F | 103 | 77%
| Critical Path To-Go | F | 34 | 31% | F | 33 | 32%
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Total Activities | F | 141 |  | F | 141
| Milestones | F | 25 | 18% | F | 25 | 18%
| Normal Tasks | F | 85 | 60% | F | 85 | 60%
| Summaries | F | 31 | 22% | F | 31 | 22%
| Hammocks | F | 0 | 0% | F | 0 | 0%
| Recurring Normal Tasks | F | 0 | 0% | F | 0 | 0%
| Total Tasks & Milestones | F | 110 | 78% | F | 110 | 78%
| Completed Tasks & Milestones | F | 0 | 0% | F | 7 | 6%
| Completed Milestones | F | 0 | 0% | F | 1 | 4%
| Completed Tasks | F | 0 | 0% | F | 6 | 7%
| Total Activities (To-Go) - % of Total | F | 141 | 100% | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78% | F | 103 | 77%
| Milestones (To-Go) | F | 25 | 18% | F | 24 | 18%
| Normal Tasks (To-Go) | F | 85 | 60% | F | 79 | 59%
| Summaries (To-Go) | F | 31 | 22% | F | 31 | 23%
| Hammocks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Recurring Tasks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Longest Path (Tasks & Milestones) | F | 34 | 79% | F | 33 | 83%
| Longest Path (Normal Tasks) | F | 27 | 63% | F | 27 | 68%
| Longest Path (Milestones) | F | 7 | 16% | F | 6 | 15%
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Total Activities (To-Go) - % of Total | F | 141 | 100% | F | 134 | 95%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78% | F | 103 | 77%
| Summary-to-Task Ratio (To-Go) | F | 1:03 | 0.36 | F | 1:03 | 0.39
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.29 | F | 1:03 | 0.3
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26 | F | 1:05 | 0.22
| Manual Tasks (To-Go) | F | 0 | 0% | F | 0 | 0%
| Critical Tasks and Milestones (To-Go) | F | 34 | 31% | F | 33 | 32%
| Wrong Status (To-Go) | F | 0 |  | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0% | F | 0 | 0%
| Missing WBS (To-Go) | F | 0 | 0% | F | 0 | 0%
| All Activities (To Go) | F | 110 | 100% | F | 103 | 100%
| Tasks & Milestones (To-Go) - % of Total To-Go | F | 110 | 78% | F | 103 | 77%
| Estimated Duration | F | 68 | 80% | F | 65 | 82%
| Milestones with Duration>0 | F | 0 | 0% | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1% | F | 1 | 1%
| Avg. Original Duration | F | 2 |  | F | 1
| Avg. Remaining Duration | F | 2 |  | F | 1
| High Baseline Duration (44d) | F | 0 | 0% | F | 0 | 0%
| High Planned Duration (44d) | F | 0 | 0% | F | 0 | 0%
| Insufficient Detail™ | F | 2 | 2% | F | 1 | 1%
| Critical Activities (To-Go) | F | 27 | 32% | F | 27 | 34%
| Avg. Critical Original Duration | F | 1 |  | F | 1
| Avg. Critical Remaining Duration | F | 1 |  | F | 1
| Critical w/High Baseline Duration (44d) | F | 0 | 0% | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0% | F | 0 | 0%
| Critical w/Insufficient Detail™ | F | 0 | 0% | F | 0 | 0%
| Activities (To-Go) | F | 85 | 100% | F | 79 | 93%
| Total Constraints | F | 2 | 2% | F | 3 | 3%
| Start No Earlier Than | F | 1 | 1% | F | 2 | 2%
| Start No Later Than | F | 0 | 0% | F | 0 | 0%
| Finish No Earlier Than | F | 1 | 1% | F | 1 | 1%
| Finish No Later Than | F | 0 | 0% | F | 0 | 0%
| Hard Constraints | F | 0 | 0% | F | 0 | 0%
| Must Start On | F | 0 | 0% | F | 0 | 0%
| Must Finish On | F | 0 | 0% | F | 0 | 0%
| As Late As Possible | F | 0 | 0% | F | 0 | 0%
| Deadlines | F | 0 | 0% | F | 0 | 0%
| Mandatory Start | F | 0 | 0% | F | 0 | 0%
| Mandatory Finish | F | 0 | 0% | F | 0 | 0%
| Open Ends with Constraints | F | 1 | 1% | F | 1 | 1%
| Open Ends w/o Constraints | F | 6 | 5% | F | 7 | 6%
| Unsatisfied Constraints | F | 0 | 0% | F | 0 | 0%
| No Constraints | F | 108 | 98% | F | 100 | 97%
| No Constraints | F | 107 | 97% | F | 99 | 96%
| Logic Density™ | F | 2.07 |  | F | 2.08
| Logic Density™ - Predecessors | F | 1.04 |  | F | 1.05
| Logic Density™ - Successors | F | 1.04 |  | F | 1.03
| Summary Links | F | 0 | 0% | F | 0 | 0%
| All Activities w/Predecessors | F | 109 | 99% | F | 102 | 100%
| SS Predecessors | F | 0 | 0% | F | 0 | 0%
| SF Predecessors | F | 0 | 0% | F | 0 | 0%
| FF Predecessors | F | 0 | 0% | F | 0 | 0%
| FS Predecessors | F | 109 | 99% | F | 102 | 99%
| All Activities w/Successors | F | 104 | 95% | F | 96 | 93%
| SS Successors | F | 0 | 0% | F | 0 | 0%
| FF Successors | F | 0 | 0% | F | 0 | 0%
| SF Successors | F | 0 | 0% | F | 0 | 0%
| FS Successors | F | 104 | 95% | F | 96 | 93%
| Missing Logic | F | 7 | 6% | F | 8 | 8%
| Missing Predecessors | F | 1 | 1% | F | 1 | 1%
| Missing Successors | F | 6 | 5% | F | 7 | 7%
| Open Start | F | 0 | 0% | F | 0 | 0%
| Open Finish | F | 0 | 0% | F | 0 | 0%
| Logic Density™ - Predecessors | F | 1.04 |  | F | 1.06
| All Activities w/Predecessors | F | 109 | 100% | F | 102 | 100%
| Total # Predecessors | F | 114 |  | F | 108
| Activities Missing Predecessors | F | 1 | 1% | F | 0 | 0%
| Activities w/Leads on Predecessor | F | 0 | 0% | F | 0 | 0%
| Total # Predecessor Leads | F | N/A |  | F | N/A
| Max # Predecessor Leads on an Activity | F | N/A |  | F | N/A
| Activities w/Lags on Predecessor | F | 0 | 0% | F | 0 | 0%
| Total # Predecessor Lags | F | N/A |  | F | N/A
| Max # of Predecessor Lags on an Activity | F | N/A |  | F | N/A
| Min Predecessor Lag (days) | F | 0 |  | F | 0
| Max Predecessor Lag (days) | F | 0 |  | F | 0
| Hidden Duration (Planned) | F | 0 | 0% | F | 0 | 0%
| Critical w/Hidden Duration (Planned) | F | 0 | 0% | F | 0 | 0%
| Merge Hotspot (Predecessors >2) | F | 1 | 1% | F | 1 | 1%
| Merge Hotspot w/Predecessor Lags | F | N/A |  | F | N/A
| Merge Hotspot w/Predecessor Lags & Low Total Float | F | N/A |  | F | N/A
| Critical Merge Hotspot | F | 0 | 0% | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0% | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0% | F | 0 | 0%
| Logic Density™ - Successors | F | 1.04 |  | F | 1.03
| All Activities w/Successors | F | 104 | 100% | F | 96 | 100%
| Activities Missing Successors | F | 6 | 5% | F | 7 | 7%
| Total # Successors | F | 114 |  | F | 106
| Activities w/Leads on Successor | F | 0 | 0% | F | 0 | 0%
| Total# of Successor Leads | F | N/A |  | F | N/A
| Max # of Successor Leads on Activity | F | N/A |  | F | N/A
| Activities w/Lags on Successor | F | 0 | 0% | F | 0 | 0%
| Total# of Successor Lags | F | N/A |  | F | N/A
| Max # of Successor Lags on Activity | F | N/A |  | F | N/A
| Diverge Hotspot (Successors >2) | F | 1 | 1% | F | 1 | 1%
| Diverge Hotspot w/Successor Lags | F | N/A |  | F | N/A
| Diverge Hotspot w/Successor Lags & Low Total Float | F | N/A |  | F | N/A
| Critical Diverge Hotspot | F | 1 | 1% | F | 0 | 0%
| Logic Hotspot™ | F | 0 | 0% | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0% | F | 0 | 0%
| Actually Finished - Tasks & Milestones | F | 0 | 0% | F | 7 | 6%
| Completed Ahead - Tasks & Milestones | F | 0 |  | F | 3 | 43%
| Completed On-Schedule - Tasks & Milestones | F | 0 |  | F | 3 | 43%
| Completed Delayed - Tasks & Milestones | F | 0 |  | F | 1 | 14%
| Avg Days Finished Early - Tasks & Milestones | F | 0 |  | F | 21
| Avg Days Finished Late - Tasks & Milestones | F | 0 |  | F | 5
| Avg Finish Variance - Tasks & Milestones | F | 0 |  | F | -8
| Actually Finished - Tasks | F | 0 | 0% | F | 6 | 7%
| Completed Ahead - Tasks | F | 0 |  | F | 3 | 50%
| Completed On-Schedule - Tasks | F | 0 |  | F | 2 | 33%
| Completed Delayed - Tasks | F | 0 |  | F | 1 | 17%
| Accelerated Durations Early/On-Schedule - Tasks | F | 0 | 0% | F | 0 | 0%
| Accelerated Durations Late - Tasks | F | 0 | 0% | F | 0 | 0%
| Extended Durations - Tasks | F | 0 | 0% | F | 2 | 2%
| Actually Finished - Milestones | F | 0 | 0% | F | 1 | 4%
| Completed Ahead - Milestones | F | 0 |  | F | 0 | 0%
| Completed On-Schedule - Milestones | F | 0 |  | F | 1 | 100%
| Completed Delayed - Milestones | F | 0 |  | F | 0 | 0%
| Actually Started - Tasks | F | 0 | 0% | F | 1 | 1%
| In-Progress Started Ahead - Tasks | F | 0 |  | F | 0 | 0%
| In-Progress Started On-Schedule - Tasks | F | 0 |  | F | 1 | 100%
| In-Progress Started Delayed - Tasks | F | 0 |  | F | 0 | 0%
| In-Progress Delayed Finish - Tasks | F | 0 |  | F | 1 | 100%
| Avg Days Started Early | F | N/A |  | F | 0
| Avg Days Started Late | F | N/A |  | F | 0
| Avg Start Variance | F | 0 |  | F | 0
| Expected Finish | F | 0 | 0% | F | 0 | 0%
| In-Progress Schedule Overrun - Tasks & Milestones | F | 0 | 0% | F | 0 | 0%
| Scheduled to Start - Tasks & Milestones | F | 110 | 100% | F | 102 | 93%
| Planned Ahead Start - Tasks & Milestones | F | 0 | 0% | F | 3 | 3%
| Planned On Schedule Start - Tasks & Milestones | F | 110 | 100% | F | 84 | 82%
| Planned Delayed Start - Tasks & Milestones | F | 0 | 0% | F | 15 | 15%
| Riding Data Date - Tasks & Milestones | F | 0 | 0% | F | 0 | 0%
| Planned Schedule Overrun - Tasks & Milestones | F | 0 | 0% | F | 0 | 0%
| Scheduled to Start - Tasks | F | 85 | 100% | F | 78 | 92%
| Planned Ahead Start - Tasks | F | 0 | 0% | F | 2 | 3%
| Planned On Schedule Start - Tasks | F | 85 | 100% | F | 66 | 85%
| Planned Delayed Start - Tasks | F | 0 | 0% | F | 10 | 13%
| Planned Delayed Finish - Tasks | F | 0 | 0% | F | 10 | 13%
| Scheduled to Start - Milestones | F | 25 | 100% | F | 24 | 96%
| Planned Ahead Start - Milestones | F | 0 | 0% | F | 1 | 4%
| Planned On Schedule Start - Milestones | F | 25 | 100% | F | 18 | 75%
| Planned Delayed Start - Milestones | F | 0 | 0% | F | 5 | 21%
| Planned Delayed Finish - Milestones | F | 0 | 0% | F | 5 | 21%
| Schedule Baseline Activities | F | 110 | 100% | F | 110 | 100%
| Scheduled/Baselined to Start | F | 110 |  | F | 103
| Scheduled/Baselined to Finish | F | 110 |  | F | 103
| Start/ed | F | 0 |  | F | 8
| Finish/ed | F | 0 |  | F | 7
| Start Variance (Phase) | F | 0 | 0% | F | 0 | 0%
| Start Compliance™ (Phase) | F | 100% |  | F | 100%
| Finish Variance (Phase) | F | 0 | 0% | F | 0 | 0%
| Finish Compliance™ (Phase) | F | 100% |  | F | 100%
| Started Delayed (>30 days) | F | N/A |  | F | N/A
| Completed Delayed (>30 days) | F | N/A |  | F | 0 | 0%
| SPI(t) | F | N/A |  | F | 0.8
| Scheduled Activities | F | 110 | 100% | F | 110 | 100%
| Scheduled to Start | F | 110 | 100% | F | 103 | 94%
| Scheduled to Finish | F | 110 | 100% | F | 103 | 94%
| Longest Path - Critical Activities and Milestones | F | 34 | 31% | F | 33 | 32%
| Critical Milestones (To-Go) | F | 7 | 28% | F | 6 | 25%
| Critical Tasks (To-Go) | F | 27 | 32% | F | 27 | 34%
| Critical Tasks (In Progress) | F | 0 | 0% | F | 0 | 0%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26 | F | 1:05 | 0.22
| High Float 10% | F | 20 | 18% | F | 17 | 17%
| High Float 44d | F | 2 | 2% | F | 6 | 6%
| Zero Days Float | F | 78 | 71% | F | 74 | 72%
| Negative Float | F | 0 | 0% | F | 0 | 0%
| Longest Path - Critical Activities and Milestones | F | 34 | 31% | F | 33 | 32%
| Critical Milestones (To-Go) | F | 7 | 28% | F | 6 | 25%
| Critical Tasks (To-Go) | F | 27 | 32% | F | 27 | 34%
| Critical Tasks (In Progress) | F | 0 | 0% | F | 0 | 0%
| Milestone-to-Task Ratio (To-Go) | F | 1:03 | 0.29 | F | 1:03 | 0.3
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26 | F | 1:05 | 0.22
| Logic Density™ | F | 2.07 |  | F | 2.05
| CP Logic Density™ | F | 2.21 |  | F | 2.12
| Critical w/Missing Logic | F | 1 | 6% | F | 1 | 8%
| Critical w/Hard Constraints | F | 0 | 0% | F | 0 | 0%
| Zero Days Float | F | 78 | 71% | F | 74 | 72%
| Negative Float | F | 0 | 0% | F | 0 | 0%
| Critical LOE | F | N/A | 0% | F | N/A | 0%
| Critical w/High Baseline Duration (44d) | F | 0 | 0% | F | 0 | 0%
| Critical w/High Planned Duration (44d) | F | 0 | 0% | F | 0 | 0%
| Critical with Predecessor Lag | F | 0 | 0% | F | 0 | 0%
| Critical with Successor Lag | F | 0 | 0% | F | 0 | 0%
| Critical with Hard Constraints | F | 0 | 0% | F | 0 | 0%
| Negative Float with Predecessor Lag | F | 0 | 0% | F | 0 | 0%
| Negative Float with Successor Lag | F | 0 | 0% | F | 0 | 0%
| Critical CEI - Value Tasks | F | N/A |  | F | N/A
| Critical CEI - Total Tasks | F | 0 |  | F | 0
| Critical CEI - Complete Tasks | F | N/A |  | F | N/A | 27%
| Critical CEI - Incomplete Tasks | F | N/A |  | F | N/A | 73%
| Baselined to Start | F | 85 |  | F | 85
| Scheduled to Start | F | 85 |  | F | 85
| Actual Starts | F | 0 |  | F | 7
| Baselined to Finish | F | 85 |  | F | 85
| Scheduled to Finish | F | 85 |  | F | 85
| Actual Finishes | F | 0 |  | F | 6
| Started Delayed (<=30 days) | F | N/A |  | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A |  | F | N/A
| Started Delayed (>60 days) | F | N/A |  | F | N/A
| Completed Delayed (<=30 days) | F | N/A |  | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | N/A |  | F | 0 | 0%
| Completed Delayed (>60 days) | F | N/A |  | F | 0 | 0%
| Baselined to Start | F | 85 |  | F | 85
| Scheduled to Start | F | 85 |  | F | 85
| Actual Starts | F | 0 |  | F | 7
| Current Baselined to Start & Started | F | N/A |  | F | 7
| Past Baselined to Start & Started | F | N/A |  | F | 0
| Future Baseline to Start & Started | F | N/A |  | F | 0
| Baselined to Finish | F | 85 |  | F | 85
| Scheduled to Finish | F | 85 |  | F | 85
| Actual Finishes | F | 0 |  | F | 6
| Current Baselined to Finish & Finished | F | N/A |  | F | 6
| Past Baselined to Finish & Finished | F | N/A |  | F | 0
| Future Baselined to Finish & Finished | F | N/A |  | F | 0
| Started Delayed (<=30 days) | F | N/A |  | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A |  | F | N/A
| Started Delayed (>60 days) | F | N/A |  | F | N/A
| Completed Delayed (<=30 days) | F | N/A |  | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | N/A |  | F | 0 | 0%
| Completed Delayed (>60 days) | F | N/A |  | F | 0 | 0%
| Baselined to Start - To Time Now | F | 0 | 0% | F | 12 | 14%
| Scheduled to Start - To Time Now | F | 0 | 0% | F | 12 | 14%
| Started | F | 0 |  | F | 4
| Started Late | F | N/A |  | F | N/A
| Started Delayed (<=30 days) | F | N/A |  | F | N/A
| Started Delayed (Between 31 to 60 days) | F | N/A |  | F | N/A
| Started Delayed (>60 days) | F | N/A |  | F | N/A
| BEI - Value Task Starts | F | N/A |  | F | 0.33
| Baselined to Finish - To Time Now | F | 0 | 0% | F | 11 | 13%
| Scheduled to Finish - To Time Now | F | 0 | 0% | F | 11 | 13%
| Finished | F | 0 |  | F | 3
| Finished Late | F | N/A |  | F | 1
| Completed Delayed (<=30 days) | F | N/A |  | F | 1 | 100%
| Completed Delayed (Between 31 to 60 days) | F | N/A |  | F | 0 | 0%
| Completed Delayed (>60 days) | F | N/A |  | F | 0 | 0%
| BEI - Value Task Finishes | F | N/A |  | F | 0.27
| Started - Future | F | 0 |  | F | 3
| Not Baselined to Start | F | 0 | 0% | F | 0 | 0%
| BEI - Value Task Starts - Cumulative | F | N/A |  | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | N/A |  | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.33
| HMI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.27
| CEI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.33
| CEI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.27
| FEI - Value Task Starts - Cumulative | F | 1 |  | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1 |  | F | 1.11
| Past Baseline to Start & Started (Workoff Burden) | F | N/A |  | F | 0
| Current Baseline to Start & Started | F | N/A |  | F | 7
| Current Baseline to Start & Started Past (Early Starts) | F | N/A |  | F | 0
| Current Baseline to Start & Started Future (Late Starts) | F | N/A |  | F | 0
| Current Baseline to Start & Not Started (Incomplete) | F | 85 |  | F | 78
| Baselined to Start - Check | F | 85 |  | F | 85
| Future Baseline to Start & Started (Early Starts) | F | N/A |  | F | N/A
| Past Baseline to Finish & Finished - Check | F | N/A |  | F | 0
| Current Baseline to Finish & Finished - Check | F | N/A |  | F | 6
| Current Baseline to Finish & Finished Past - Check | F | N/A |  | F | 0
| Current Baseline to Finish & Finished Future - Check | F | N/A |  | F | 0
| Current Baseline to Finish & Not Finished - Check | F | 85 |  | F | 79
| Baselined to Finish - Check | F | 85 |  | F | 85
| Future Baseline to Finish & Finished - Check | F | N/A |  | F | 0
| Current Baseline to Start & Started (BL Plan) | F | N/A |  | F | 7
| Future Baseline to Start & Started (Early Starts) | F | N/A |  | F | N/A
| Past Baseline to Start & Started (Workoff Burden) | F | N/A |  | F | 0
| Current Baseline to Start & Not Started (Incompletes) | F | 85 |  | F | 78
| Current Baseline to Finish & Finished (BL Plan) | F | N/A |  | F | 6
| Future Baseline to Finish & Finished (Early Finishes) | F | N/A |  | F | 0
| Past Baseline to Finish & Finished (Workoff Burden) | F | N/A |  | F | 0
| Current Baseline to Finish & Not Finished (Incompletes) | F | 85 |  | F | 79
| Baselined to Start | F | 0 |  | F | 12
| Scheduled to Start | F | 0 |  | F | 12 | 100%
| Started - Scheduled | F | 0 |  | F | 4 | 33%
| Started - Baseline Comparison | F | 0 |  | F | 4 | 33%
| BEI - Value Task Starts | F | N/A |  | F | 0.33
| HMI - Value Task Starts | F | N/A |  | F | 0.27
| CEI - Value Task Starts | F | N/A |  | F | 0.27
| Baselined to Finish | F | 0 |  | F | 11
| Scheduled to Finish | F | 0 |  | F | 11
| Finished | F | 0 |  | F | 3
| BEI - Value Task Finishes | F | N/A |  | F | 0.27
| HMI - Value Task Finishes | F | N/A |  | F | 0.27
| CEI - Value Task Finishes | F | N/A |  | F | 0.27
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Started (incl. Future Baseline Starts) - Scheduled | F | 0 | 0% | F | 7 | 8%
| Started (incl. Future Baseline Starts) - Baseline Comparison | F | 0 | 0% | F | 7 | 8%
| Started Late (from Baseline) | F | N/A |  | F | N/A
| Finished (incl. Future Baseline Finishes) - Scheduled | F | 0 | 0% | F | 6 | 7%
| Finished (incl. Future Baseline Finishes) - Baseline Comparison | F | 0 | 0% | F | 6 | 7%
| Finished Late | F | N/A |  | F | 1
| Completed Ahead | F | 0 |  | F | 3 | 50%
| Completed Delayed | F | 0 |  | F | 1 | 17%
| Completed On-Schedule | F | 0 |  | F | 2 | 33%
| Accelerated | F | 0 |  | F | 0 | 0%
| Days Variance | F | 0 |  | F | -57 | -954%
| Days Early | F | 0 |  | F | 63 | 1044%
| Days Late | F | 0 |  | F | 5 | 90%
| Avg Days Early | F | 0 |  | F | 21
| Avg Days Late | F | 0 |  | F | 5
| Avg Variance | F | 0 |  | F | -10
| Actually Finished | F | 0 | 0% | F | 6 | 5%
| Took Longer than Planned | F | N/A |  | F | 2 | 29%
| Took Less Than Planned | F | N/A |  | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 0 | 0% | F | 6 | 7%
| Completed (w/o Baseline Duration) | F | 0 | 0% | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0% | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A |  | F | 3 | 27%
| Missed Durations | F | 0 |  | F | 2 | 33%
| Missed Durations & Late Actual Finish | F | 0 |  | F | 1 | 17%
| Completed Ahead | F | 0 |  | F | 3 | 50%
| Completed Delayed | F | 0 |  | F | 1 | 17%
| Completed On-Schedule | F | 0 |  | F | 2 | 33%
| Accelerated | F | 0 |  | F | 0 | 0%
| Days Variance | F | 0 |  | F | -57 | -954%
| Days Early | F | 0 |  | F | 63 | 1044%
| Days Late | F | 0 |  | F | 5 | 90%
| Avg Days Early | F | 0 |  | F | 21
| Avg Days Late | F | 0 |  | F | 5
| Avg Variance | F | 0 |  | F | -10
| Actually Finished | F | 0 | 0% | F | 6 | 5%
| Took Longer than Planned | F | N/A |  | F | 2 | 29%
| Took Less Than Planned | F | N/A |  | F | 0 | 0%
| Completed (w/Baseline Duration) | F | 0 | 0% | F | 6 | 7%
| Completed (w/o Baseline Duration) | F | 0 | 0% | F | 0 | 0%
| Completed (w/Baseline Dur=0) | F | 0 | 0% | F | 0 | 0%
| Baseline-to-Date Completed Tasks | F | N/A |  | F | 3 | 27%
| Missed Durations | F | 0 |  | F | 2 | 33%
| Missed Durations & Late Actual Finish | F | 0 |  | F | 1 | 17%
| Baselined Tasks | F | 85 |  | F | 85
| Baselined to Start - TOTAL | F | 85 |  | F | 85
| Complete Task Starts - Cumulative | F | 0 |  | F | 4 | 33%
| Incomplete Task Starts - Cumulative (in work) | F | N/A |  | F | 8 | 67%
| Old Incomplete Task Starts in Status Period | F | N/A |  | F | N/A
| Baselined to Finish | F | 85 |  | F | 85
| Complete Task Finishes - Cumulative (in work) | F | 0 |  | F | 3 | 27%
| Incomplete Task Finishes - Cumulative | F | N/A |  | F | 8 | 27%
| Old Incomplete Task Finishes in Status Period | F | N/A |  | F | N/A
| Old Completed Task Finishes in Status Period | F | N/A |  | F | N/A
| BEI - Value Tasks | F | N/A |  | F | 0.27
| BEI - Total Tasks | F | 0 |  | F | 11
| BEI - Complete Tasks | F | N/A |  | F | 3 | 27%
| BEI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| BEI - Value Tasks (adjusted) | F | N/A |  | F | 0.55
| BEI - Complete Tasks (adjusted) | F | 0 |  | F | 6 | 55%
| BEI - Complete Future Tasks (adjusted) | F | N/A |  | F | 3
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| BEI - Value Milestones | F | N/A |  | F | 0.33
| BEI - Total Milestones | F | 0 |  | F | 3
| BEI - Complete Milestones | F | N/A |  | F | 1 | 33%
| BEI - Incomplete Milestones | F | N/A |  | F | 2 | 67%
| BEI - Value Milestones (adjusted) | F | N/A |  | F | 0.33
| BEI - Complete Milestones (adjusted) | F | 0 |  | F | 1 | 33%
| BEI - Complete Future Milestones (adjusted) | F | N/A |  | F | N/A
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| HMI - Value Tasks | F | N/A |  | F | 0.27
| HMI - Total Tasks | F | 0 |  | F | 11
| HMI - Complete Tasks | F | N/A |  | F | 3 | 27%
| HMI - Completed Early Tasks | F | N/A |  | F | N/A | 0%
| HMI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| HMI - Value Tasks (adjusted) | F | N/A |  | F | 0.55
| HMI - Complete Tasks (adjusted) | F | N/A |  | F | 6 | 55%
| HMI - Complete Future Tasks (adjusted) | F | N/A |  | F | 3
| HMI - Value Milestones | F | N/A |  | F | 0.33
| HMI - Total Milestones | F | 0 |  | F | 3
| HMI - Complete Milestones | F | N/A |  | F | 1 | 33%
| HMI - Completed Early Milestones | F | N/A |  | F | N/A | 0%
| HMI - Incomplete Milestones | F | N/A |  | F | 2 | 67%
| HMI - Value Milestones (adjusted) | F | N/A |  | F | 0.33
| HMI - Complete Milestones (adjusted) | F | N/A |  | F | 1 | 33%
| HMI - Complete Future Milestones (adjusted) | F | N/A |  | F | 3
| CEI - Value Tasks | F | N/A |  | F | 0.27
| CEI - Total Tasks | F | 0 |  | F | 11
| CEI - Complete Tasks | F | N/A |  | F | 3 | 27%
| CEI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| CEI - Value Tasks (adjusted) | F | N/A |  | F | 0.55
| CEI - Complete Tasks (adjusted) | F | N/A |  | F | 6 | 55%
| CEI - Complete Future Tasks (adjusted) | F | N/A |  | F | 3
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| CEI - Value Milestones | F | N/A |  | F | 0.33
| CEI - Total Milestones | F | 0 |  | F | 3
| CEI - Complete Milestones | F | N/A |  | F | 1 | 33%
| CEI - Incomplete Milestones | F | N/A |  | F | 2 | 67%
| CEI - Value Milestones (adjusted) | F | N/A |  | F | 0.33
| CEI - Complete Milestones (adjusted) | F | N/A |  | F | 1 | 33%
| CEI - Complete Future Milestones (adjusted) | F | N/A |  | F | 0
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| BEI - Value Tasks | F | N/A |  | F | 0.27
| BEI - Total Tasks | F | 0 |  | F | 11
| BEI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| HMI - Value Tasks | F | N/A |  | F | 0.27
| HMI - Total Tasks | F | 0 |  | F | 11
| HMI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| CEI - Value Tasks | F | N/A |  | F | 0.27
| CEI - Total Tasks | F | 0 |  | F | 11
| CEI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| BEI - Complete Milestones | F | N/A |  | F | 1 | 33%
| HMI - Complete Tasks | F | N/A |  | F | 3 | 27%
| CEI - Complete Tasks | F | N/A |  | F | 3 | 27%
| BEI - Value Milestones | F | N/A |  | F | 0.33
| BEI - Total Milestones | F | 0 |  | F | 3
| BEI - Complete Milestones | F | N/A |  | F | 1 | 33%
| BEI - Incomplete Milestones | F | N/A |  | F | 2 | 67%
| HMI - Value Milestones | F | N/A |  | F | 0.33
| HMI - Total Milestones | F | 0 |  | F | 3
| HMI - Complete Milestones | F | N/A |  | F | 1 | 33%
| HMI - Incomplete Milestones | F | N/A |  | F | 2 | 67%
| CEI - Value Milestones | F | N/A |  | F | 0.33
| CEI - Total Milestones | F | 0 |  | F | 3
| CEI - Complete Milestones | F | N/A |  | F | 1 | 33%
| CEI - Incomplete Milestones | F | N/A |  | F | 2 | 67%
| BEI - Value Tasks (adjusted) | F | N/A |  | F | 0.55
| HMI - Value Tasks (adjusted) | F | N/A |  | F | 0.55
| CEI - Value Tasks (adjusted) | F | N/A |  | F | 0.55
| BEI - Value Milestones (adjusted) | F | N/A |  | F | 0.33
| HMI - Value Milestones (adjusted) | F | N/A |  | F | 0.33
| CEI - Value Milestones (adjusted) | F | N/A |  | F | 0.33
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Total Activities - DRM | F | 0 |  | F | 6
| Total Activities - DRM Graph | F | 0 |  | F | 6
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Milestone #1 - 5158 | F | N/A |  | F | N/A
| Float Milestone #1 - 5158 | F | N/A |  | F | N/A
| Milestone #2 - 4786 | F | N/A |  | F | N/A
| Float to Milestone #2 - 4786 | F | N/A |  | F | N/A
| Milestone #3 - 102 | F | N/A |  | F | N/A
| Float to Milestone #3 - 102 | F | N/A |  | F | N/A
| Milestone #4 - 103 | F | N/A |  | F | N/A
| Float to Milestone #4 - 103 | F | N/A |  | F | N/A
| Milestone #5 - 104 | F | N/A |  | F | N/A
| Float to Milestone #5 - 105 | F | N/A |  | F | N/A
| New Activities Since Previous Status Date | F | 0 |  | F | 0
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 1 |  | F | 1
| Margin - Margin Task Name #3 | F | 0 |  | F | 0
| Margin - Margin Task Name #4 | F | 1 |  | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | N/A |  | F | N/A
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| Margin - Margin Task Name #1 | F | N/A |  | F | N/A
| Margin - Margin Task Name #2 | F | 2026-08-20 |  | F | 2026-08-20
| Margin - Margin Task Name #3 | F | 2026-08-26 |  | F | 2026-08-26
| Margin - Margin Task Name #4 | F | 2026-08-18 |  | F | N/A
| Margin - Margin Task Name #5 | F | N/A |  | F | N/A
| Margin - Margin Task Name #6 | F | N/A |  | F | N/A
| Margin - Margin Task Name #7 | F | N/A |  | F | N/A
| BEI - Value Task Starts - Cumulative | F | N/A |  | F | 0.33
| BEI - Value Task Finishes - Cumulative | F | N/A |  | F | 0.27
| HMI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.33
| HMI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.27
| CEI - Value Task Starts - by Status Dates | F | N/A |  | F | 0.33
| CEI - Value Task Finishes - by Status Dates | F | N/A |  | F | 0.27
| FEI - Value Task Starts - Cumulative | F | 1 |  | F | 1.11
| FEI - Value Task Finish - Cumulative | F | 1 |  | F | 1.11
| BEI - Value Tasks | F | N/A |  | F | 0.27
| HMI - Value Tasks | F | N/A |  | F | 0.27
| CEI - Value Tasks | F | N/A |  | F | 0.27
| BEI - Value Milestones | F | N/A |  | F | 0.33
| HMI - Value Milestones | F | N/A |  | F | 0.33
| CEI - Value Milestones | F | N/A |  | F | 0.33
| BEI - Value Tasks | F | N/A |  | F | 0.27
| BEI - Complete Tasks | F | N/A |  | F | 3 | 27%
| BEI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| BEI - CP Tasks - Planned Cumulative | F | N/A |  | F | 0
| BEI - CP Value Tasks | F | N/A |  | F | N/A
| HMI - Value Tasks | F | N/A |  | F | 0.27
| HMI - Complete Tasks | F | N/A |  | F | 3 | 27%
| HMI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| HMI - CP Tasks - Planned to be Completed this Month | F | N/A |  | F | 0
| HMI - CP Value Tasks | F | N/A |  | F | N/A
| CEI - Value Tasks | F | N/A |  | F | 0.27
| CEI - Complete Tasks | F | N/A |  | F | 3 | 27%
| CEI - Incomplete Tasks | F | N/A |  | F | 8 | 73%
| CEI - CP Tasks - Planned to be Completed this Month | F | N/A |  | F | 0
| CEI - CP Value Tasks | F | N/A |  | F | N/A
| Wrong Status | F | 0 |  | F | 0 | 0%
| Invalid Forecast Dates | F | 0 | 0% | F | 0 | 0%
| Expected Finish | F | 0 | 0% | F | 0 | 0%
| Missing WBS | F | 0 | 0% | F | 0 | 0%
| Milestones with Duration>0 | F | 0 | 0% | F | 0 | 0%
| Activities with Duration=0 | F | 1 | 1% | F | 1 | 1%
| Estimated Duration | F | 68 | 80% | F | 65 | 82%
| Missing Logic | F | 7 | 6% | F | 8 | 8%
| Missing Predecessors | F | 1 | 1% | F | 0 | 0%
| Missing Successors | F | 6 | 5% | F | 7 | 7%
| Open Start | F | 0 | 0% | F | 0 | 0%
| Open Finish | F | 0 | 0% | F | 0 | 0%
| Unsatisfied Constraints | F | 0 | 0% | F | 0 | 0%
| Summary Links | F | 0 | 0% | F | 0 | 0%
| Hard Constraints | F | 0 | 0% | F | 0 | 0%
| Critical w/Hidden Duration | F | 0 | 0% | F | 0 | 0%
| Negative Float | F | 0 | 0% | F | 0 | 0%
| Status Date | F | 2026-07-07 |  | F | 2026-08-11
| High Float 10% | F | 20 | 18% | F | 17 | 17%
| High Float 44d | F | 2 | 2% | F | 6 | 6%
| Zero Days Float | F | 78 | 71% | F | 74 | 72%
| Negative Float | F | 0 | 0% | F | 0 | 0%
| Hidden Duration (Planned) | F | 0 | 0% | F | 0 | 0%
| Critical Logic Hotspot™ | F | 0 | 0% | F | 0 | 0%
| Critical Merge Hotspot | F | 0 | 0% | F | 0 | 0%
| Merge Hotspot w/Predecessor Lags | F | N/A |  | F | N/A
| Critical Diverge Hotspot | F | 1 | 1% | F | 0 | 0%
| Diverge Hotspot w/Successor Lags | F | N/A |  | F | N/A
| Riding Data Date | F | 0 | 0% | F | 0 | 0%
| Deadlines | F | 0 | 0% | F | 0 | 0%
| Longest Path (Normal Tasks) | F | 27 | 63% | F | 27 | 68%
| Longest Path (Tasks & Milestones) | F | 34 | 79% | F | 33 | 83%
| Critical Milestone-to-Task Ratio (To-Go) | F | 1:04 | 0.26 | F | 1:05 | 0.22
| Critical Milestones (To-Go) | F | 7 | 28% | F | 6 | 25%
| Longest Path (Milestones) | F | 7 | 16% | F | 6 | 15%
| Normal Tasks | F | 85 | 60% | F | 85 | 60%
| Normal Tasks (To-Go) | F | 85 | 60% | F | 79 | 59%
| Critical Tasks (To-Go) | F | 27 | 32% | F | 27 | 34%
| Critical Tasks (In Progress) | F | 0 | 0% | F | 0 | 0%
| Zero Days Float | F | 78 | 71% | F | 74 | 72%
| Negative Float | F | 0 | 0% | F | 0 | 0%
| CP Logic Density™ | F | 2.21 |  | F | 2.12
| Time Now | F | 2026-07-07 |  | F | 2026-08-11
| Forecast to be Finished | F | 0 | 0% | F | 11 | 13%
| Completed On Time | F | 0 |  | T | 2 | 18%
| Completed Late | F | 0 |  | F | 1 | 9%
| Not Completed | F | 0 |  | F | 8 | 73%
| Baseline Finish Compliance | F | N/A |  | T | 18%
| Forecast to be Started | F | 0 | 0% | F | 12 | 14%
| Started On Time | F | 0 |  | F | 4 | 33%
| Started Late | F | 0 |  | F | 0 | 0%
| Not Started | F | 0 |  | F | 8 | 67%
| Baseline Start Compliance | F | N/A |  | F | 33%
1 | Completed Activities | F | N/A |  | F | 6
HSD01 | Time Now | F | 2026-07-07 |  | F | 2026-08-11
HSD02 | Label | F | N/A |  | F | N/A
HSD03 | Forecast to be Started but not Started yet | F | 0 | 0% | T | 8 | 9%
HSD04 | Started Late | F | 0 |  | F | 0 | 0%
HSD05 | Forecast to be Finished but not Finished yet | F | 0 | 0% | T | 8 | 9%
HSD06 | Finished Late | F | 0 |  | F | 1 | 9%
HSD06 | Total days delay in the half step (Days) | F | N/A |  | F | N/A
HSD07 | Total days delay in the full update (Days) | F | 0 |  | T | 190
HSD08 | Total days ahead in the half step (Days) | F | N/A |  | F | N/A
HSD09 | Total days ahead in the full update (Days) | F | 0 |  | F | 73
HSD10 | Cumulative Finish Impact (Days) | F | 0 |  | F | -117
HSD10 | Net Finish Impact (Days) | F | 0 |  | F | 0
HSD20 | Project Finish | F | 2026-11-05 |  | F | 2026-11-05
SEM01 | Workoff Burden (Snapshot_Phase) | F | N/A |  | F | 0 | 0%
SEM01 | Workoff Burden | F | N/A |  | F | 0 | 0%
SEM02 | BRI Current | F | N/A |  | T | 0.11
SEM03 | BRI Cumulative | F | N/A |  | F | 0.27
SEM04 | BPI Current | F | N/A |  | T | 0.11
SEM05 | BEI Current | F | N/A |  | T | 0.11
SEM06 | BEI Cumulative | F | N/A |  | T | 0.27
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1 |  | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1 |  | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 85 |  | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 85 |  | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 85 |  | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1 |  | T | 1.11
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0 |  | T | 8
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 85 |  | T | 70
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0 |  | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 85 |  | T | 71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1 |  | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1 |  | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 85 |  | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 85 |  | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 85 |  | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1 |  | T | 1.11
SEM07 | Workoff Burden - Starts To-Go (Total) | T | 85 |  | T | 78
SEM07 | Past Baseline to Start & Not Finished (Workoff Burden) | F | 0 |  | T | 8
SEM07 | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | T | 85 |  | T | 70
SEM07 | Workoff Burden - Finishes To-Go (Total) | T | 85 |  | T | 79
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0 |  | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 85 |  | T | 71
SEM07 | Past Baseline to Start & Not Started (Workoff Burden) | F | 0 |  | T | 8
SEM07 | Future Baseline to Start & Already Delayed (Workoff Burden) | T | 85 |  | T | 70
SEM07 | Past Baseline to Finish & Not Finished (Workoff Burden) | F | 0 |  | T | 8
SEM07 | Future Baseline to Finish & Already Delayed (Workoff Burden) | T | 85 |  | T | 71
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1 |  | T | 1.11
SEM07 | To Go - BEI - Value Task Finishes - Cumulative | F | 1 |  | T | 1.11
SEM07 | To Go - Planned Task Starts - Count | T | 85 |  | T | 78
SEM07 | To Go - BEI - Task Finishes - Count | T | 85 |  | T | 79
SEM07 | To Go - Baselined Task Starts - Count | T | 85 |  | T | 78
SEM07 | To Go - BEI - Value Task Starts - Cumulative | F | 1 |  | T | 1.11
SEM07 | TC-BEI | F | 1 |  | T | 1.11
SEM08 | FRI Current | F | N/A |  | F | 0.11
SEM09 | Delta (BEI vs TC-BEI) | T | -1 |  | T | -0.67
SN05 | Newly Critical Activities | F | 0 | 0% | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0% | F | 0 | 0%
SN05 | Newly Critical Activities | F | 0 | 0% | F | 0 | 0%
SN06 | Activities No Longer Critical | F | 0 | 0% | F | 1 | 1%
SN06 | Activities No Longer Critical | F | 0 | 0% | F | 1 | 1%
SN06 | Activities No Longer Critical | F | 0 | 0% | F | 1 | 1%