## Projects
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects | Projects
Name | Start | Start | Finish | Finish | Time Now | Time Now | Baseline Start | Baseline Start | Baseline Finish | Baseline Finish | Activities | Activities | Budget Duration | Budget Duration | Actual Duration | Actual Duration | Remaining Duration | Remaining Duration | Total Duration | Total Duration | Budget Cost | Budget Cost | Actual Cost | Actual Cost | Remaining Cost | Remaining Cost | Total Cost | Total Cost
Project2 |  | 2026-03-02 08:00 |  | 2027-09-14 17:00 |  | 2026-05-24 17:00 |  | 2026-03-02 08:00 |  | 2027-07-09 17:00 |  | 144 |  | 494.375 |  | 60 |  | 342 |  | 402 |  | 0 |  | 0 |  | 0 |  | 0
Project5_TAMPERED | = | 2026-03-02 08:00 | p | 2028-01-26 17:00 | p | 2026-08-27 17:00 | = | 2026-03-02 08:00 | = | 2027-07-09 17:00 | = | 144 | = | 494.375 | p | 129 | p | 369 | p | 498 | = | 0 | = | 0 | = | 0 | = | 0

## Activities
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%) | Activities - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED

## Relationships
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Relationships - 5 (3%) | Relationships - 5 (3%) | Relationships - 5 (3%) | Relationships - 5 (3%) | Relationships - 5 (3%) | Relationships - 5 (3%) | Relationships - 5 (3%) | Relationships - 5 (3%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Project2 | Project5_TAMPERED
106 | Install building carpet | True | 135 | Remove debris from building and do final clean-up | True | FinishToStart (0) | O
113 | Test and align doors and equipment | False | 138 | Complete elevator inspection and certification | True | FinishToStart (0) | O
48 | Erect steel columns, beams and joist - 1st and 2nd floors | False | 41 | Cure elevator wall concrete | False | O | FinishToStart (0)
49 | Erect steel columns, beams and joist - 3rd floor and roof | False | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | False | O | FinishToStart (0)
131 | Set HVAC trim and test and balance system | True | 142 | Complete punch list items from all inspections | True | O | FinishToStart (0)

## Leads-Lags
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%) | Leads/Lags - 5 (3%)
Predecessor ID | Predecessor | Predecessor Critical | Successor ID | Successor | Successor Critical | Project2 Relationship Type | Project5_TAMPERED Relationship Type | Project2 Lead/Lag | Project5_TAMPERED Lead/Lag
106 | Install building carpet | True | 135 | Remove debris from building and do final clean-up | True | FinishToStart | O | 0 | O
113 | Test and align doors and equipment | False | 138 | Complete elevator inspection and certification | True | FinishToStart | O | 0 | O
48 | Erect steel columns, beams and joist - 1st and 2nd floors | False | 41 | Cure elevator wall concrete | False | O | FinishToStart | O | 0
49 | Erect steel columns, beams and joist - 3rd floor and roof | False | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | False | O | FinishToStart | O | 0
131 | Set HVAC trim and test and balance system | True | 142 | Complete punch list items from all inspections | True | O | FinishToStart | O | 0

## Resources
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%) | Resources - 17 (11%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Resource | Project2 | Project5_TAMPERED | Project5_TAMPERED
1 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | Roofing Contractor Management | 40 | q | 0
2 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | Electric Contractor Management | 80 | q | 0
3 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | Steel Erection Contractor Management | 80 | q | 0
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | Steel Erection Contractor | 80 | q | 0
5 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | Plumbing Contractor | 160 | q | 0
6 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | Site Grading Contractor | 80 | q | 0
7 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | G.C. Survey Crew | 40 | q | 0
8 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | Site Grading Contractor | 40 | q | 0
9 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | Site Grading Contractor | 16 | q | 8
10 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | G.C. Rough Carpenter Crew | 32 | p | 128
11 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | G.C. Concrete Crew | 40 | p | 168
12 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | Steel Erection Contractor | 80 | p | 136
13 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | Steel Erection Contractor | 60 | p | 162
14 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | G.C. Rough Carpenter Crew | 40 | p | 136
15 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | G.C. Labor Crew | 8 | p | 27.2
16 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | Carpet Contractor | 160 | p | 328
17 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | G.C. Finish Carpenter Crew | 120 | p | 208

## Calendars
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars | Calendars
Project2 | Project2 | Project2 | Project2 | Project2 | Project2 | Project2 | Project2 |  |  | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: Used for Microsoft Project 98 Baseline Calendar
Project2 | Project2 | Project2 | Project2 | Project2 | Project2 | Project2 | Project2 |  |  | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
| Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00 | [9 empty] | 0:00
1:00 | [9 empty] | 1:00
2:00 | [9 empty] | 2:00
3:00 | [9 empty] | 3:00
4:00 | [9 empty] | 4:00
5:00 | [9 empty] | 5:00
6:00 | [9 empty] | 6:00
7:00 | [9 empty] | 7:00
8:00 | [9 empty] | 8:00
9:00 | [9 empty] | 9:00
10:00 | [9 empty] | 10:00
11:00 | [9 empty] | 11:00
12:00 | [9 empty] | 12:00
13:00 | [9 empty] | 13:00
14:00 | [9 empty] | 14:00
15:00 | [9 empty] | 15:00
16:00 | [9 empty] | 16:00
17:00 | [9 empty] | 17:00
18:00 | [9 empty] | 18:00
19:00 | [9 empty] | 19:00
20:00 | [9 empty] | 20:00
21:00 | [9 empty] | 21:00
22:00 | [9 empty] | 22:00
23:00 | [9 empty] | 23:00
Calendar: ASIT_REFERENCE
Project2 | Project2 | Project2 | Project2 | Project2 | Project2 | Project2 | Project2 |  |  | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
This calendar does not exist in this project. | This calendar does not exist in this project. | This calendar does not exist in this project. | This calendar does not exist in this project. | This calendar does not exist in this project. | This calendar does not exist in this project. | This calendar does not exist in this project. | This calendar does not exist in this project. |  |  |  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
0:00
1:00
2:00
3:00
4:00
5:00
6:00
7:00
8:00
9:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
20:00
21:00
22:00
23:00

## Calendar Exceptions
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Calendar: Standard
Project2 | Project5_TAMPERED
Calendar: Used for Microsoft Project 98 Baseline Calendar
Project2 | Project5_TAMPERED
Calendar: ASIT_REFERENCE
Project2 | Project5_TAMPERED

## ID
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%) | ID - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Description
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%) | Description - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Activity-Type
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%) | Activity Type - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Baseline-Duration
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%) | Baseline Duration - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Original-Duration
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%) | Original Duration - 18 (13%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 70 | p | 15 | -21% | 85
2 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 5 | p | 15 | -300% | 20
3 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 45 | p | 47 | -104% | 92
4 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 10 | q | -5 | (-50%) | 5
5 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2 | p | 13 | -650% | 15
6 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 4 | p | 21 | -525% | 25
7 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 5 | p | 16 | -320% | 21
8 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 50 | p | 24 | -48% | 74
9 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 10 | p | 7 | -70% | 17
10 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 10 | p | 17 | -170% | 27
11 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 87 | p | 2 | -2% | 89
12 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 5 | p | 12 | -240% | 17
13 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 91 | q | -5 | (-5%) | 86
14 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 90 | p | 21 | -23% | 111
15 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 20 | p | 21 | -105% | 41
16 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 15 | p | 11 | -73% | 26
17 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 187 | p | 23 | -12% | 210
18 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 70 | p | 6 | -9% | 76

## Actual-Duration
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%) | Actual Duration - 12 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 56 | p | 20 | -36% | 76
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 14 | p | 5 | -36% | 19
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 0 | p | 10 |  | 10
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 40 | p | 20 | -50% | 60
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 42 | p | 43 | -102% | 85
6 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | 23 | p | 20 | -87% | 43
7 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | 0 | p | 10 |  | 10
8 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 0 | p | 20 |  | 20
9 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 0 | p | 26 |  | 26
10 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 0 | p | 5 |  | 5
11 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 0 | p | 14 |  | 14
12 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 0 | p | 9 |  | 9

## Remaining-Duration
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%) | Remaining Duration - 24 (17%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 20 | q | -20 | (-100%) | 0
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 5 | q | -5 | (-100%) | 0
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 10 | q | -10 | (-100%) | 0
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 20 | q | -20 | (-100%) | 0
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 28 | q | -28 | (-100%) | 0
6 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | 20 | q | -20 | (-100%) | 0
7 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | 10 | q | -10 | (-100%) | 0
8 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 5 | q | -5 | (-100%) | 0
9 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 45 | p | 21 | -47% | 66
10 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 10 | q | -10 | (-100%) | 0
11 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2 | q | -1 | (-50%) | 1
12 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 4 | p | 12 | -300% | 16
13 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 5 | p | 16 | -320% | 21
14 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 50 | p | 24 | -48% | 74
15 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 10 | p | 7 | -70% | 17
16 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 10 | p | 17 | -170% | 27
17 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 87 | p | 2 | -2% | 89
18 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 5 | p | 12 | -240% | 17
19 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 91 | q | -5 | (-5%) | 86
20 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 90 | p | 21 | -23% | 111
21 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 20 | p | 21 | -105% | 41
22 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 15 | p | 11 | -73% | 26
23 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 187 | p | 23 | -12% | 210
24 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 70 | p | 6 | -9% | 76

## Total-Float
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%) | Total Float - 113 (78%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 248 | q | -248 | (-100%) | 0
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 263 | q | -263 | (-100%) | 0
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 93 | q | -93 | (-100%) | 0
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 48 | q | -48 | (-100%) | 0
5 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 0 | p | 256 |  | 256
6 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 204 | p | 71 | -35% | 275
7 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 0 | p | 19 |  | 19
8 | 36 | Rough-in electric and plumbing in elevator | Normal | 4 | 5.4 | 5.4 |  | 204 | p | 71 | -35% | 275
9 | 37 | Form elevator pit walls | Normal | 4 | 5.5 | 5.5 |  | 203 | p | 72 | -35% | 275
10 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | 0 | p | 19 |  | 19
11 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 0 | p | 19 |  | 19
12 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 202 | p | 73 | -36% | 275
13 | 41 | Cure elevator wall concrete | Normal | 7 | 5.9 | 5.9 |  | 202 | p | 54 | -27% | 256
14 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | 0 | p | 19 |  | 19
15 | 43 | Strip wall forms | Normal | 1 | 5.11 | 5.11 |  | 202 | p | 54 | -27% | 256
16 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | 0 | p | 19 |  | 19
17 | 45 | Install pneumatic tube in elevator pit | Normal | 3 | 5.13 | 5.13 |  | 202 | p | 54 | -27% | 256
18 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 202 | p | 54 | -27% | 256
19 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 0 | p | 19 |  | 19
20 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | 0 | p | 19 |  | 19
21 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 0 | p | 19 |  | 19
22 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 144 | p | 12 | -8% | 156
23 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | 0 | p | 19 |  | 19
24 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | 0 | p | 19 |  | 19
25 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | 0 | p | 19 |  | 19
26 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 35 | p | 9 | -26% | 44
27 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 0 | p | 19 |  | 19
28 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 35 | p | 21 | -60% | 56
29 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | 0 | p | 19 |  | 19
30 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | 0 | p | 19 |  | 19
31 | 59 | Strip forms from 2nd floor slab | Normal | 2 | 7.5 | 7.5 |  | 73 | p | 22 | -30% | 95
32 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | 0 | p | 19 |  | 19
33 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | 0 | p | 19 |  | 19
34 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | 0 | p | 19 |  | 19
35 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | 0 | p | 19 |  | 19
36 | 64 | Strip forms from 3rd floor slab | Normal | 2 | 7.10 | 7.10 |  | 11 | p | 19 | -173% | 30
37 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | 0 | p | 19 |  | 19
38 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | 0 | p | 19 |  | 19
39 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | 0 | p | 19 |  | 19
40 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | 0 | p | 19 |  | 19
41 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | 0 | p | 19 |  | 19
42 | 70 | Form 1st floor | Normal | 4 | 7.16 | 7.16 |  | 78 | p | 22 | -28% | 100
43 | 71 | Install electrical underground | Normal | 5 | 7.17 | 7.17 |  | 73 | p | 22 | -30% | 95
44 | 72 | Install plumbing underground | Normal | 5 | 7.18 | 7.18 |  | 73 | p | 22 | -30% | 95
45 | 73 | Install rebar and in-floor utilities | Normal | 4 | 7.19 | 7.19 |  | 78 | p | 22 | -28% | 100
46 | 74 | Pour 1st floor slab | Normal | 4 | 7.20 | 7.20 |  | 73 | p | 22 | -30% | 95
47 | 75 | Cure 1st floor slab | Normal | 7 | 7.21 | 7.21 |  | 73 | p | 22 | -30% | 95
48 | 76 | Strip forms from 1st floor slab | Normal | 2 | 7.22 | 7.22 |  | 73 | p | 21 | -29% | 94
49 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 0 | p | 19 |  | 19
50 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | 0 | p | 19 |  | 19
51 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 60 | p | 14 | -23% | 74
52 | 80 | Rough-in plumbing at toilets and masonry walls | Normal | 20 | 9.1 | 9.1 |  | 93 | p | 25 | -27% | 118
53 | 81 | Lay masonry at core, mechanical, and toilets | Normal | 20 | 9.2 | 9.2 |  | 144 | p | 12 | -8% | 156
54 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | 0 | p | 19 |  | 19
55 | 83 | Install roof drains | Normal | 2 | 9.4 | 9.4 |  | 59 | p | 21 | -36% | 80
56 | 84 | Install tile in toilet rooms | Normal | 10 | 9.5 | 9.5 |  | 93 | p | 25 | -27% | 118
57 | 85 | Clean masonry | Normal | 5 | 9.6 | 9.6 |  | 90 | p | 25 | -28% | 115
58 | 86 | Clean toilet room tile | Normal | 5 | 9.7 | 9.7 |  | 93 | p | 25 | -27% | 118
59 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 59 | p | 21 | -36% | 80
60 | 88 | Install flashing at parapet walls | Normal | 4 | 10.1 | 10.1 |  | 61 | p | 21 | -34% | 82
61 | 89 | Pour lightweight concrete roof fill | Normal | 2 | 10.2 | 10.2 |  | 59 | p | 21 | -36% | 80
62 | 90 | Install seamless roofing material | Normal | 5 | 10.3 | 10.3 |  | 59 | p | 21 | -36% | 80
63 | 91 | Spread stone ballast on seamless roof | Normal | 5 | 10.4 | 10.4 |  | 59 | p | 21 | -36% | 80
64 | 92 | Set rooftop equipment | Normal | 10 | 10.5 | 10.5 |  | 59 | p | 21 | -36% | 80
65 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 0 | p | 19 |  | 19
66 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | 0 | p | 19 |  | 19
67 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | 0 | p | 19 |  | 19
68 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | 0 | p | 19 |  | 19
69 | 97 | Install store front doors and hardware | Normal | 15 | 11.4 | 11.4 |  | 20 | p | 19 | -95% | 39
70 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 7 | p | 21 | -300% | 28
71 | 99 | Install millwork and wood trim | Normal | 15 | 12.1 | 12.1 |  | 10 | p | 19 | -190% | 29
72 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | 0 | p | 19 |  | 19
73 | 101 | Install conduit at ceiling plenum space | Normal | 15 | 12.3 | 12.3 |  | 15 | p | 21 | -140% | 36
74 | 102 | Install duct in ceiling plenum space | Normal | 15 | 12.4 | 12.4 |  | 10 | p | 25 | -250% | 35
75 | 103 | Install ceiling grid | Normal | 10 | 12.5 | 12.5 |  | 10 | p | 25 | -250% | 35
76 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 30 | p | 25 | -83% | 55
77 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 10 | p | 25 | -250% | 35
78 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 0 | p | 28 |  | 28
79 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 5 | p | 14 | -280% | 19
80 | 108 | Complete interior and exterior sod and plantings | Normal | 10 | 12.10 | 12.10 |  | 7 | p | 25 | -357% | 32
81 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 7 | p | 25 | -357% | 32
82 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 144 | p | 40 | -28% | 184
83 | 111 | Set elevator equipment in shafts | Normal | 20 | 13.1 | 13.1 |  | 144 | p | 40 | -28% | 184
84 | 112 | Set equipment in mechanical room | Normal | 10 | 13.2 | 13.2 |  | 144 | p | 40 | -28% | 184
85 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 144 | p | 40 | -28% | 184
86 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 10 | p | 25 | -250% | 35
87 | 115 | Rough-in plumbing in drywall walls | Normal | 20 | 14.1 | 14.1 |  | 45 | p | 25 | -56% | 70
88 | 116 | Tie-in fire line riser and set valves | Normal | 10 | 14.2 | 14.2 |  | 90 | p | 25 | -28% | 115
89 | 117 | Set plumbing fixtures and trim | Normal | 15 | 14.3 | 14.3 |  | 45 | p | 25 | -56% | 70
90 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 10 | p | 25 | -250% | 35
91 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 17 | p | 21 | -124% | 38
92 | 120 | Rough-in electrical in masonry walls | Normal | 20 | 15.1 | 15.1 |  | 73 | p | 21 | -29% | 94
93 | 121 | Rough-in electrical in drywall walls | Normal | 20 | 15.2 | 15.2 |  | 30 | p | 21 | -70% | 51
94 | 122 | Pull wire in conduit and set area transformers | Normal | 15 | 15.3 | 15.3 |  | 15 | p | 21 | -140% | 36
95 | 123 | Install and terminate electrical devices | Normal | 15 | 15.4 | 15.4 |  | 15 | p | 21 | -140% | 36
96 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 17 | p | 21 | -124% | 38
97 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 15 | p | 23 | -153% | 38
98 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 17 | q | -3 | (-18%) | 14
99 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 151 | p | 5 | -3% | 156
100 | 128 | Rough-in mechanical in masonry walls | Normal | 20 | 16.2 | 16.2 |  | 114 | p | 10 | -9% | 124
101 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 64 | p | 25 | -39% | 89
102 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 71 | p | 11 | -15% | 82
103 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 17 | q | -17 | (-100%) | 0
104 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 19 | p | 19 | -100% | 38
105 | 133 | Install hard tile flooring in common areas | Normal | 5 | 17.1 | 17.1 |  | 56 | p | 25 | -45% | 81
106 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 56 | p | 25 | -45% | 81
107 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | 0 | p | 19 |  | 19
108 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 19 | p | 19 | -100% | 38
109 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 0 | p | 19 |  | 19
110 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | 0 | p | 19 |  | 19
111 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | 0 | p | 19 |  | 19
112 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | 0 | p | 19 |  | 19
113 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 0 | p | 19 |  | 19

## Free-Float
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%) | Free Float - 37 (26%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 248 | q | -248 | (-100%) | 0
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 204 | q | -204 | (-100%) | 0
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 93 | q | -93 | (-100%) | 0
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 48 | q | -48 | (-100%) | 0
5 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 0 | p | 256 |  | 256
6 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 0 | p | 19 |  | 19
7 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 58 | p | 14 | -24% | 72
8 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 0 | p | 19 |  | 19
9 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 35 | p | 9 | -26% | 44
10 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 35 | p | 2 | -6% | 37
11 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 0 | p | 19 |  | 19
12 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 60 | p | 14 | -23% | 74
13 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 59 | p | 21 | -36% | 80
14 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 0 | p | 19 |  | 19
15 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 7 | p | 21 | -300% | 28
16 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 30 | p | 6 | -20% | 36
17 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 10 | p | 6 | -60% | 16
18 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 0 | p | 28 |  | 28
19 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 5 | q | -5 | (-100%) | 0
20 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 7 | p | 6 | -86% | 13
21 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 144 | p | 40 | -28% | 184
22 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 144 | p | 40 | -28% | 184
23 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 10 | p | 25 | -250% | 35
24 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 10 | p | 6 | -60% | 16
25 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 17 | p | 21 | -124% | 38
26 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 0 | p | 38 |  | 38
27 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 15 | p | 4 | -27% | 19
28 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 17 | q | -3 | (-18%) | 14
29 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 80 | q | -5 | (-6%) | 75
30 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 64 | p | 25 | -39% | 89
31 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 54 | p | 28 | -52% | 82
32 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 17 | q | -17 | (-100%) | 0
33 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 19 | p | 19 | -100% | 38
34 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 56 | p | 6 | -11% | 62
35 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 19 | p | 19 | -100% | 38
36 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 0 | p | 19 |  | 19
37 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 0 | p | 19 |  | 19

## Calendar
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%) | Calendar - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Start
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%) | Start - 114 (79%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 2026-07-13 08:00 | p | 21 |  | 2026-08-03 08:00
2 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 2026-07-13 08:00 | p | 21 |  | 2026-08-03 08:00
3 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2026-07-27 08:00 | p | 14 |  | 2026-08-10 08:00
4 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 2026-07-27 08:00 | p | 21 |  | 2026-08-17 08:00
5 | 36 | Rough-in electric and plumbing in elevator | Normal | 4 | 5.4 | 5.4 |  | 2026-07-29 08:00 | p | 33 |  | 2026-08-31 08:00
6 | 37 | Form elevator pit walls | Normal | 4 | 5.5 | 5.5 |  | 2026-08-06 08:00 | p | 50 |  | 2026-09-25 08:00
7 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | 2026-07-31 08:00 | p | 52 |  | 2026-09-21 08:00
8 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 2026-08-06 08:00 | p | 50 |  | 2026-09-25 08:00
9 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 2026-08-13 08:00 | p | 74 |  | 2026-10-26 08:00
10 | 41 | Cure elevator wall concrete | Normal | 7 | 5.9 | 5.9 |  | 2026-08-27 08:00 | p | 88 |  | 2026-11-23 08:00
11 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | 2026-08-13 08:00 | p | 74 |  | 2026-10-26 08:00
12 | 43 | Strip wall forms | Normal | 1 | 5.11 | 5.11 |  | 2026-09-07 08:00 | p | 86 |  | 2026-12-02 08:00
13 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | 2026-08-24 08:00 | p | 72 |  | 2026-11-04 08:00
14 | 45 | Install pneumatic tube in elevator pit | Normal | 3 | 5.13 | 5.13 |  | 2026-09-08 08:00 | p | 86 |  | 2026-12-03 08:00
15 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 2026-09-11 08:00 | p | 88 |  | 2026-12-08 08:00
16 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 2026-08-27 08:00 | p | 74 |  | 2026-11-09 08:00
17 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | 2026-08-27 08:00 | p | 74 |  | 2026-11-09 08:00
18 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 2026-09-10 08:00 | p | 74 |  | 2026-11-23 08:00
19 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 2026-10-22 08:00 | p | 83 |  | 2027-01-13 08:00
20 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | 2026-09-24 08:00 | p | 83 |  | 2026-12-16 08:00
21 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | 2026-10-08 08:00 | p | 83 |  | 2026-12-30 08:00
22 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | 2026-10-22 08:00 | p | 83 |  | 2027-01-13 08:00
23 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 2026-09-10 08:00 | p | 97 |  | 2026-12-16 08:00
24 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 2026-10-29 08:00 | p | 83 |  | 2027-01-20 08:00
25 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 2026-09-10 08:00 | p | 97 |  | 2026-12-16 08:00
26 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | 2026-11-05 08:00 | p | 99 |  | 2027-02-12 08:00
27 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | 2026-11-11 08:00 | p | 99 |  | 2027-02-18 08:00
28 | 59 | Strip forms from 2nd floor slab | Normal | 2 | 7.5 | 7.5 |  | 2026-11-27 08:00 | p | 101 |  | 2027-03-08 08:00
29 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | 2026-11-20 08:00 | p | 101 |  | 2027-03-01 08:00
30 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | 2026-11-20 08:00 | p | 101 |  | 2027-03-01 08:00
31 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | 2026-11-27 08:00 | p | 101 |  | 2027-03-08 08:00
32 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | 2026-12-03 08:00 | p | 99 |  | 2027-03-12 08:00
33 | 64 | Strip forms from 3rd floor slab | Normal | 2 | 7.10 | 7.10 |  | 2026-12-21 08:00 | p | 99 |  | 2027-03-30 08:00
34 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | 2026-12-14 08:00 | p | 99 |  | 2027-03-23 08:00
35 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | 2026-12-14 08:00 | p | 99 |  | 2027-03-23 08:00
36 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | 2026-12-21 08:00 | p | 99 |  | 2027-03-30 08:00
37 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | 2026-12-25 08:00 | p | 101 |  | 2027-04-05 08:00
38 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | 2027-01-05 08:00 | p | 99 |  | 2027-04-14 08:00
39 | 70 | Form 1st floor | Normal | 4 | 7.16 | 7.16 |  | 2026-12-01 08:00 | p | 99 |  | 2027-03-10 08:00
40 | 71 | Install electrical underground | Normal | 5 | 7.17 | 7.17 |  | 2026-12-07 08:00 | p | 99 |  | 2027-03-16 08:00
41 | 72 | Install plumbing underground | Normal | 5 | 7.18 | 7.18 |  | 2026-12-07 08:00 | p | 99 |  | 2027-03-16 08:00
42 | 73 | Install rebar and in-floor utilities | Normal | 4 | 7.19 | 7.19 |  | 2026-12-01 08:00 | p | 99 |  | 2027-03-10 08:00
43 | 74 | Pour 1st floor slab | Normal | 4 | 7.20 | 7.20 |  | 2026-12-14 08:00 | p | 99 |  | 2027-03-23 08:00
44 | 75 | Cure 1st floor slab | Normal | 7 | 7.21 | 7.21 |  | 2026-12-23 08:00 | p | 99 |  | 2027-04-01 08:00
45 | 76 | Strip forms from 1st floor slab | Normal | 2 | 7.22 | 7.22 |  | 2027-01-07 08:00 | p | 99 |  | 2027-04-16 08:00
46 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 2027-01-07 08:00 | p | 99 |  | 2027-04-16 08:00
47 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | 2027-01-07 08:00 | p | 99 |  | 2027-04-16 08:00
48 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 2026-11-05 08:00 | p | 106 |  | 2027-02-19 08:00
49 | 80 | Rough-in plumbing at toilets and masonry walls | Normal | 20 | 9.1 | 9.1 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
50 | 81 | Lay masonry at core, mechanical, and toilets | Normal | 20 | 9.2 | 9.2 |  | 2026-11-05 08:00 | p | 106 |  | 2027-02-19 08:00
51 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | 2027-01-28 08:00 | p | 99 |  | 2027-05-07 08:00
52 | 83 | Install roof drains | Normal | 2 | 9.4 | 9.4 |  | 2027-03-10 08:00 | p | 99 |  | 2027-06-17 08:00
53 | 84 | Install tile in toilet rooms | Normal | 10 | 9.5 | 9.5 |  | 2027-02-08 08:00 | p | 99 |  | 2027-05-18 08:00
54 | 85 | Clean masonry | Normal | 5 | 9.6 | 9.6 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
55 | 86 | Clean toilet room tile | Normal | 5 | 9.7 | 9.7 |  | 2027-02-22 08:00 | p | 99 |  | 2027-06-01 08:00
56 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
57 | 88 | Install flashing at parapet walls | Normal | 4 | 10.1 | 10.1 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
58 | 89 | Pour lightweight concrete roof fill | Normal | 2 | 10.2 | 10.2 |  | 2027-03-12 08:00 | p | 101 |  | 2027-06-21 08:00
59 | 90 | Install seamless roofing material | Normal | 5 | 10.3 | 10.3 |  | 2027-03-23 08:00 | p | 99 |  | 2027-06-30 08:00
60 | 91 | Spread stone ballast on seamless roof | Normal | 5 | 10.4 | 10.4 |  | 2027-03-30 08:00 | p | 99 |  | 2027-07-07 08:00
61 | 92 | Set rooftop equipment | Normal | 10 | 10.5 | 10.5 |  | 2027-04-06 08:00 | p | 99 |  | 2027-07-14 08:00
62 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
63 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
64 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
65 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | 2027-06-03 08:00 | p | 99 |  | 2027-09-10 08:00
66 | 97 | Install store front doors and hardware | Normal | 15 | 11.4 | 11.4 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
67 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
68 | 99 | Install millwork and wood trim | Normal | 15 | 12.1 | 12.1 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
69 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | 2027-06-17 08:00 | p | 99 |  | 2027-09-24 08:00
70 | 101 | Install conduit at ceiling plenum space | Normal | 15 | 12.3 | 12.3 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
71 | 102 | Install duct in ceiling plenum space | Normal | 15 | 12.4 | 12.4 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
72 | 103 | Install ceiling grid | Normal | 10 | 12.5 | 12.5 |  | 2027-06-03 08:00 | p | 99 |  | 2027-09-10 08:00
73 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 2027-06-17 08:00 | p | 99 |  | 2027-09-24 08:00
74 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
75 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
76 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
77 | 108 | Complete interior and exterior sod and plantings | Normal | 10 | 12.10 | 12.10 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
78 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 2027-07-29 08:00 | p | 99 |  | 2027-11-05 08:00
79 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
80 | 111 | Set elevator equipment in shafts | Normal | 20 | 13.1 | 13.1 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
81 | 112 | Set equipment in mechanical room | Normal | 10 | 13.2 | 13.2 |  | 2026-12-31 08:00 | p | 106 |  | 2027-04-16 08:00
82 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 2027-01-14 08:00 | p | 106 |  | 2027-04-30 08:00
83 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 2027-03-11 08:00 | p | 99 |  | 2027-06-18 08:00
84 | 115 | Rough-in plumbing in drywall walls | Normal | 20 | 14.1 | 14.1 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
85 | 116 | Tie-in fire line riser and set valves | Normal | 10 | 14.2 | 14.2 |  | 2027-03-11 08:00 | p | 99 |  | 2027-06-18 08:00
86 | 117 | Set plumbing fixtures and trim | Normal | 15 | 14.3 | 14.3 |  | 2027-05-06 08:00 | p | 99 |  | 2027-08-13 08:00
87 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
88 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
89 | 120 | Rough-in electrical in masonry walls | Normal | 20 | 15.1 | 15.1 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
90 | 121 | Rough-in electrical in drywall walls | Normal | 20 | 15.2 | 15.2 |  | 2027-04-29 08:00 | p | 99 |  | 2027-08-06 08:00
91 | 122 | Pull wire in conduit and set area transformers | Normal | 15 | 15.3 | 15.3 |  | 2027-05-27 08:00 | p | 99 |  | 2027-09-03 08:00
92 | 123 | Install and terminate electrical devices | Normal | 15 | 15.4 | 15.4 |  | 2027-06-17 08:00 | p | 99 |  | 2027-09-24 08:00
93 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 2027-07-22 08:00 | p | 85 |  | 2027-10-15 08:00
94 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 2027-07-08 08:00 | p | 103 |  | 2027-10-19 08:00
95 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
96 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
97 | 128 | Rough-in mechanical in masonry walls | Normal | 20 | 16.2 | 16.2 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
98 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 2027-06-03 08:00 | p | 99 |  | 2027-09-10 08:00
99 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 2027-04-20 08:00 | p | 99 |  | 2027-07-28 08:00
100 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 2027-07-26 08:00 | p | 137 |  | 2027-12-10 08:00
101 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
102 | 133 | Install hard tile flooring in common areas | Normal | 5 | 17.1 | 17.1 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
103 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 2027-05-20 08:00 | p | 99 |  | 2027-08-27 08:00
104 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | 2027-08-12 08:00 | p | 109 |  | 2027-11-29 08:00
105 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 2027-08-18 08:00 | p | 107 |  | 2027-12-03 08:00
106 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 2027-08-18 08:00 | p | 107 |  | 2027-12-03 08:00
107 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | 2027-08-18 08:00 | p | 107 |  | 2027-12-03 08:00
108 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | 2027-08-23 08:00 | p | 107 |  | 2027-12-08 08:00
109 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | 2027-08-24 08:00 | p | 107 |  | 2027-12-09 08:00
110 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 2027-08-25 08:00 | p | 107 |  | 2027-12-10 08:00
111 | 142 | Complete punch list items from all inspections | Normal | 10 | 19 | 19 |  | 2027-08-26 08:00 | p | 134 |  | 2028-01-07 08:00
112 | 143 | Obtain certificate of occupancy | Normal | 2 | 20 | 20 |  | 2027-09-09 08:00 | p | 134 |  | 2028-01-21 08:00
113 | 144 | Issue final completion documents including warranties | Normal | 1 | 21 | 21 |  | 2027-09-13 08:00 | p | 134 |  | 2028-01-25 08:00
114 | 145 | Issue final request for payment | Normal | 1 | 22 | 22 |  | 2027-09-14 08:00 | p | 134 |  | 2028-01-26 08:00

## Finish
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%) | Finish - 116 (81%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 2026-07-10 17:00 | p | 21 |  | 2026-07-31 17:00
2 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 2026-07-10 17:00 | p | 21 |  | 2026-07-31 17:00
3 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 2026-09-11 17:00 | p | 88 |  | 2026-12-08 17:00
4 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 2026-07-24 17:00 | p | 14 |  | 2026-08-07 17:00
5 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2026-07-28 17:00 | p | 31 |  | 2026-08-28 17:00
6 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 2026-07-30 17:00 | p | 50 |  | 2026-09-18 17:00
7 | 36 | Rough-in electric and plumbing in elevator | Normal | 4 | 5.4 | 5.4 |  | 2026-08-03 17:00 | p | 31 |  | 2026-09-03 17:00
8 | 37 | Form elevator pit walls | Normal | 4 | 5.5 | 5.5 |  | 2026-08-11 17:00 | p | 50 |  | 2026-09-30 17:00
9 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | 2026-08-05 17:00 | p | 50 |  | 2026-09-24 17:00
10 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 2026-08-12 17:00 | p | 72 |  | 2026-10-23 17:00
11 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 2026-08-13 17:00 | p | 74 |  | 2026-10-26 17:00
12 | 41 | Cure elevator wall concrete | Normal | 7 | 5.9 | 5.9 |  | 2026-09-04 17:00 | p | 88 |  | 2026-12-01 17:00
13 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | 2026-08-21 17:00 | p | 74 |  | 2026-11-03 17:00
14 | 43 | Strip wall forms | Normal | 1 | 5.11 | 5.11 |  | 2026-09-07 17:00 | p | 86 |  | 2026-12-02 17:00
15 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | 2026-08-26 17:00 | p | 72 |  | 2026-11-06 17:00
16 | 45 | Install pneumatic tube in elevator pit | Normal | 3 | 5.13 | 5.13 |  | 2026-09-10 17:00 | p | 88 |  | 2026-12-07 17:00
17 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 2026-09-11 17:00 | p | 88 |  | 2026-12-08 17:00
18 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 2026-11-04 17:00 | p | 106 |  | 2027-02-18 17:00
19 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | 2026-09-09 17:00 | p | 72 |  | 2026-11-20 17:00
20 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 2026-09-23 17:00 | p | 83 |  | 2026-12-15 17:00
21 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 2026-11-04 17:00 | p | 106 |  | 2027-02-18 17:00
22 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | 2026-10-07 17:00 | p | 83 |  | 2026-12-29 17:00
23 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | 2026-10-21 17:00 | p | 83 |  | 2027-01-12 17:00
24 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | 2026-10-28 17:00 | p | 83 |  | 2027-01-19 17:00
25 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 2027-01-08 17:00 | p | 101 |  | 2027-04-19 17:00
26 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 2026-11-04 17:00 | p | 99 |  | 2027-02-11 17:00
27 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 2026-09-16 17:00 | p | 97 |  | 2026-12-22 17:00
28 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | 2026-11-10 17:00 | p | 99 |  | 2027-02-17 17:00
29 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | 2026-11-19 17:00 | p | 99 |  | 2027-02-26 17:00
30 | 59 | Strip forms from 2nd floor slab | Normal | 2 | 7.5 | 7.5 |  | 2026-11-30 17:00 | p | 99 |  | 2027-03-09 17:00
31 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | 2026-11-26 17:00 | p | 99 |  | 2027-03-05 17:00
32 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | 2026-11-26 17:00 | p | 99 |  | 2027-03-05 17:00
33 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | 2026-12-02 17:00 | p | 99 |  | 2027-03-11 17:00
34 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | 2026-12-11 17:00 | p | 101 |  | 2027-03-22 17:00
35 | 64 | Strip forms from 3rd floor slab | Normal | 2 | 7.10 | 7.10 |  | 2026-12-22 17:00 | p | 99 |  | 2027-03-31 17:00
36 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | 2026-12-18 17:00 | p | 101 |  | 2027-03-29 17:00
37 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | 2026-12-18 17:00 | p | 101 |  | 2027-03-29 17:00
38 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | 2026-12-24 17:00 | p | 99 |  | 2027-04-02 17:00
39 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | 2027-01-04 17:00 | p | 99 |  | 2027-04-13 17:00
40 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | 2027-01-06 17:00 | p | 99 |  | 2027-04-15 17:00
41 | 70 | Form 1st floor | Normal | 4 | 7.16 | 7.16 |  | 2026-12-04 17:00 | p | 101 |  | 2027-03-15 17:00
42 | 71 | Install electrical underground | Normal | 5 | 7.17 | 7.17 |  | 2026-12-11 17:00 | p | 101 |  | 2027-03-22 17:00
43 | 72 | Install plumbing underground | Normal | 5 | 7.18 | 7.18 |  | 2026-12-11 17:00 | p | 101 |  | 2027-03-22 17:00
44 | 73 | Install rebar and in-floor utilities | Normal | 4 | 7.19 | 7.19 |  | 2026-12-04 17:00 | p | 101 |  | 2027-03-15 17:00
45 | 74 | Pour 1st floor slab | Normal | 4 | 7.20 | 7.20 |  | 2026-12-17 17:00 | p | 99 |  | 2027-03-26 17:00
46 | 75 | Cure 1st floor slab | Normal | 7 | 7.21 | 7.21 |  | 2026-12-31 17:00 | p | 99 |  | 2027-04-09 17:00
47 | 76 | Strip forms from 1st floor slab | Normal | 2 | 7.22 | 7.22 |  | 2027-01-08 17:00 | p | 101 |  | 2027-04-19 17:00
48 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 2027-01-27 17:00 | p | 99 |  | 2027-05-06 17:00
49 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | 2027-01-27 17:00 | p | 99 |  | 2027-05-06 17:00
50 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 2027-03-11 17:00 | p | 99 |  | 2027-06-18 17:00
51 | 80 | Rough-in plumbing at toilets and masonry walls | Normal | 20 | 9.1 | 9.1 |  | 2027-02-05 17:00 | p | 101 |  | 2027-05-17 17:00
52 | 81 | Lay masonry at core, mechanical, and toilets | Normal | 20 | 9.2 | 9.2 |  | 2026-12-02 17:00 | p | 106 |  | 2027-03-18 17:00
53 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | 2027-03-03 17:00 | p | 99 |  | 2027-06-10 17:00
54 | 83 | Install roof drains | Normal | 2 | 9.4 | 9.4 |  | 2027-03-11 17:00 | p | 99 |  | 2027-06-18 17:00
55 | 84 | Install tile in toilet rooms | Normal | 10 | 9.5 | 9.5 |  | 2027-02-19 17:00 | p | 101 |  | 2027-05-31 17:00
56 | 85 | Clean masonry | Normal | 5 | 9.6 | 9.6 |  | 2027-03-10 17:00 | p | 99 |  | 2027-06-17 17:00
57 | 86 | Clean toilet room tile | Normal | 5 | 9.7 | 9.7 |  | 2027-02-26 17:00 | p | 101 |  | 2027-06-07 17:00
58 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 2027-04-19 17:00 | p | 99 |  | 2027-07-27 17:00
59 | 88 | Install flashing at parapet walls | Normal | 4 | 10.1 | 10.1 |  | 2027-03-09 17:00 | p | 99 |  | 2027-06-16 17:00
60 | 89 | Pour lightweight concrete roof fill | Normal | 2 | 10.2 | 10.2 |  | 2027-03-15 17:00 | p | 99 |  | 2027-06-22 17:00
61 | 90 | Install seamless roofing material | Normal | 5 | 10.3 | 10.3 |  | 2027-03-29 17:00 | p | 99 |  | 2027-07-06 17:00
62 | 91 | Spread stone ballast on seamless roof | Normal | 5 | 10.4 | 10.4 |  | 2027-04-05 17:00 | p | 99 |  | 2027-07-13 17:00
63 | 92 | Set rooftop equipment | Normal | 10 | 10.5 | 10.5 |  | 2027-04-19 17:00 | p | 99 |  | 2027-07-27 17:00
64 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
65 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | 2027-04-07 17:00 | p | 99 |  | 2027-07-15 17:00
66 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | 2027-05-12 17:00 | p | 99 |  | 2027-08-19 17:00
67 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
68 | 97 | Install store front doors and hardware | Normal | 15 | 11.4 | 11.4 |  | 2027-04-28 17:00 | p | 99 |  | 2027-08-05 17:00
69 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 2027-08-11 17:00 | p | 128 |  | 2027-12-17 17:00
70 | 99 | Install millwork and wood trim | Normal | 15 | 12.1 | 12.1 |  | 2027-06-02 17:00 | p | 99 |  | 2027-09-09 17:00
71 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | 2027-07-14 17:00 | p | 99 |  | 2027-10-21 17:00
72 | 101 | Install conduit at ceiling plenum space | Normal | 15 | 12.3 | 12.3 |  | 2027-04-28 17:00 | p | 99 |  | 2027-08-05 17:00
73 | 102 | Install duct in ceiling plenum space | Normal | 15 | 12.4 | 12.4 |  | 2027-06-02 17:00 | p | 99 |  | 2027-09-09 17:00
74 | 103 | Install ceiling grid | Normal | 10 | 12.5 | 12.5 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
75 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 2027-06-30 17:00 | p | 99 |  | 2027-10-07 17:00
76 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
77 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 2027-08-11 17:00 | p | 128 |  | 2027-12-17 17:00
78 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 2027-08-04 17:00 | p | 114 |  | 2027-11-26 17:00
79 | 108 | Complete interior and exterior sod and plantings | Normal | 10 | 12.10 | 12.10 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
80 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 2027-08-11 17:00 | p | 99 |  | 2027-11-18 17:00
81 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 2027-01-27 17:00 | p | 106 |  | 2027-05-13 17:00
82 | 111 | Set elevator equipment in shafts | Normal | 20 | 13.1 | 13.1 |  | 2026-12-30 17:00 | p | 106 |  | 2027-04-15 17:00
83 | 112 | Set equipment in mechanical room | Normal | 10 | 13.2 | 13.2 |  | 2027-01-13 17:00 | p | 106 |  | 2027-04-29 17:00
84 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 2027-01-27 17:00 | p | 106 |  | 2027-05-13 17:00
85 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
86 | 115 | Rough-in plumbing in drywall walls | Normal | 20 | 14.1 | 14.1 |  | 2027-05-05 17:00 | p | 99 |  | 2027-08-12 17:00
87 | 116 | Tie-in fire line riser and set valves | Normal | 10 | 14.2 | 14.2 |  | 2027-03-24 17:00 | p | 99 |  | 2027-07-01 17:00
88 | 117 | Set plumbing fixtures and trim | Normal | 15 | 14.3 | 14.3 |  | 2027-05-26 17:00 | p | 99 |  | 2027-09-02 17:00
89 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
90 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 2027-07-23 17:00 | p | 101 |  | 2027-11-01 17:00
91 | 120 | Rough-in electrical in masonry walls | Normal | 20 | 15.1 | 15.1 |  | 2027-02-05 17:00 | p | 101 |  | 2027-05-17 17:00
92 | 121 | Rough-in electrical in drywall walls | Normal | 20 | 15.2 | 15.2 |  | 2027-05-26 17:00 | p | 99 |  | 2027-09-02 17:00
93 | 122 | Pull wire in conduit and set area transformers | Normal | 15 | 15.3 | 15.3 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
94 | 123 | Install and terminate electrical devices | Normal | 15 | 15.4 | 15.4 |  | 2027-07-07 17:00 | p | 99 |  | 2027-10-14 17:00
95 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 2027-07-23 17:00 | p | 87 |  | 2027-10-18 17:00
96 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 2027-07-21 17:00 | p | 103 |  | 2027-11-01 17:00
97 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 2027-08-20 17:00 | p | 139 |  | 2028-01-06 17:00
98 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 2026-12-16 17:00 | p | 106 |  | 2027-04-01 17:00
99 | 128 | Rough-in mechanical in masonry walls | Normal | 20 | 16.2 | 16.2 |  | 2027-02-05 17:00 | p | 101 |  | 2027-05-17 17:00
100 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
101 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 2027-05-10 17:00 | p | 99 |  | 2027-08-17 17:00
102 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 2027-08-20 17:00 | p | 139 |  | 2028-01-06 17:00
103 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 2027-08-18 17:00 | p | 107 |  | 2027-12-03 17:00
104 | 133 | Install hard tile flooring in common areas | Normal | 5 | 17.1 | 17.1 |  | 2027-05-19 17:00 | p | 99 |  | 2027-08-26 17:00
105 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 2027-05-25 17:00 | p | 99 |  | 2027-09-01 17:00
106 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | 2027-08-17 17:00 | p | 107 |  | 2027-12-02 17:00
107 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 2027-08-18 17:00 | p | 107 |  | 2027-12-03 17:00
108 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 2027-08-25 17:00 | p | 107 |  | 2027-12-10 17:00
109 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | 2027-08-20 17:00 | p | 109 |  | 2027-12-07 17:00
110 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | 2027-08-23 17:00 | p | 107 |  | 2027-12-08 17:00
111 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | 2027-08-24 17:00 | p | 107 |  | 2027-12-09 17:00
112 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 2027-08-25 17:00 | p | 107 |  | 2027-12-10 17:00
113 | 142 | Complete punch list items from all inspections | Normal | 10 | 19 | 19 |  | 2027-09-08 17:00 | p | 134 |  | 2028-01-20 17:00
114 | 143 | Obtain certificate of occupancy | Normal | 2 | 20 | 20 |  | 2027-09-10 17:00 | p | 136 |  | 2028-01-24 17:00
115 | 144 | Issue final completion documents including warranties | Normal | 1 | 21 | 21 |  | 2027-09-13 17:00 | p | 134 |  | 2028-01-25 17:00
116 | 145 | Issue final request for payment | Normal | 1 | 22 | 22 |  | 2027-09-14 17:00 | p | 134 |  | 2028-01-26 17:00

## Actual-Start
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%) | Actual Start - 7 (5%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | O | p |  |  | 2026-06-08 08:00
2 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | O | p |  |  | 2026-06-22 08:00
3 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | O | p |  |  | 2026-07-06 08:00
4 | 32 | Foundations | Summary | 45 | 5 | 5 |  | O | p |  |  | 2026-08-03 08:00
5 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | O | p |  |  | 2026-08-03 08:00
6 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | O | p |  |  | 2026-08-10 08:00
7 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | O | p |  |  | 2026-08-17 08:00

## Actual-Finish
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%) | Actual Finish - 9 (6%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | O | p |  |  | 2026-06-19 17:00
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | O | p |  |  | 2026-05-29 17:00
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | O | p |  |  | 2026-06-19 17:00
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | O | p |  |  | 2026-06-19 17:00
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | O | p |  |  | 2026-07-31 17:00
6 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | O | p |  |  | 2026-06-19 17:00
7 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | O | p |  |  | 2026-07-03 17:00
8 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | O | p |  |  | 2026-07-31 17:00
9 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | O | p |  |  | 2026-08-07 17:00

## Baseline-Start
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%) | Baseline Start - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Baseline-Finish
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%) | Baseline Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Early-Start
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%) | Early Start - 114 (79%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 2026-07-13 08:00 | p | 21 |  | 2026-08-03 08:00
2 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 2026-07-13 08:00 | p | 21 |  | 2026-08-03 08:00
3 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2026-07-27 08:00 | p | 14 |  | 2026-08-10 08:00
4 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 2026-07-27 08:00 | p | 21 |  | 2026-08-17 08:00
5 | 36 | Rough-in electric and plumbing in elevator | Normal | 4 | 5.4 | 5.4 |  | 2026-07-29 08:00 | p | 33 |  | 2026-08-31 08:00
6 | 37 | Form elevator pit walls | Normal | 4 | 5.5 | 5.5 |  | 2026-08-06 08:00 | p | 50 |  | 2026-09-25 08:00
7 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | 2026-07-31 08:00 | p | 52 |  | 2026-09-21 08:00
8 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 2026-08-06 08:00 | p | 50 |  | 2026-09-25 08:00
9 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 2026-08-13 08:00 | p | 74 |  | 2026-10-26 08:00
10 | 41 | Cure elevator wall concrete | Normal | 7 | 5.9 | 5.9 |  | 2026-08-27 08:00 | p | 88 |  | 2026-11-23 08:00
11 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | 2026-08-13 08:00 | p | 74 |  | 2026-10-26 08:00
12 | 43 | Strip wall forms | Normal | 1 | 5.11 | 5.11 |  | 2026-09-07 08:00 | p | 86 |  | 2026-12-02 08:00
13 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | 2026-08-24 08:00 | p | 72 |  | 2026-11-04 08:00
14 | 45 | Install pneumatic tube in elevator pit | Normal | 3 | 5.13 | 5.13 |  | 2026-09-08 08:00 | p | 86 |  | 2026-12-03 08:00
15 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 2026-09-11 08:00 | p | 88 |  | 2026-12-08 08:00
16 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 2026-08-27 08:00 | p | 74 |  | 2026-11-09 08:00
17 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | 2026-08-27 08:00 | p | 74 |  | 2026-11-09 08:00
18 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 2026-09-10 08:00 | p | 74 |  | 2026-11-23 08:00
19 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 2026-10-22 08:00 | p | 83 |  | 2027-01-13 08:00
20 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | 2026-09-24 08:00 | p | 83 |  | 2026-12-16 08:00
21 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | 2026-10-08 08:00 | p | 83 |  | 2026-12-30 08:00
22 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | 2026-10-22 08:00 | p | 83 |  | 2027-01-13 08:00
23 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 2026-09-10 08:00 | p | 97 |  | 2026-12-16 08:00
24 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 2026-10-29 08:00 | p | 83 |  | 2027-01-20 08:00
25 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 2026-09-10 08:00 | p | 97 |  | 2026-12-16 08:00
26 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | 2026-11-05 08:00 | p | 99 |  | 2027-02-12 08:00
27 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | 2026-11-11 08:00 | p | 99 |  | 2027-02-18 08:00
28 | 59 | Strip forms from 2nd floor slab | Normal | 2 | 7.5 | 7.5 |  | 2026-11-27 08:00 | p | 101 |  | 2027-03-08 08:00
29 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | 2026-11-20 08:00 | p | 101 |  | 2027-03-01 08:00
30 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | 2026-11-20 08:00 | p | 101 |  | 2027-03-01 08:00
31 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | 2026-11-27 08:00 | p | 101 |  | 2027-03-08 08:00
32 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | 2026-12-03 08:00 | p | 99 |  | 2027-03-12 08:00
33 | 64 | Strip forms from 3rd floor slab | Normal | 2 | 7.10 | 7.10 |  | 2026-12-21 08:00 | p | 99 |  | 2027-03-30 08:00
34 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | 2026-12-14 08:00 | p | 99 |  | 2027-03-23 08:00
35 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | 2026-12-14 08:00 | p | 99 |  | 2027-03-23 08:00
36 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | 2026-12-21 08:00 | p | 99 |  | 2027-03-30 08:00
37 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | 2026-12-25 08:00 | p | 101 |  | 2027-04-05 08:00
38 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | 2027-01-05 08:00 | p | 99 |  | 2027-04-14 08:00
39 | 70 | Form 1st floor | Normal | 4 | 7.16 | 7.16 |  | 2026-12-01 08:00 | p | 99 |  | 2027-03-10 08:00
40 | 71 | Install electrical underground | Normal | 5 | 7.17 | 7.17 |  | 2026-12-07 08:00 | p | 99 |  | 2027-03-16 08:00
41 | 72 | Install plumbing underground | Normal | 5 | 7.18 | 7.18 |  | 2026-12-07 08:00 | p | 99 |  | 2027-03-16 08:00
42 | 73 | Install rebar and in-floor utilities | Normal | 4 | 7.19 | 7.19 |  | 2026-12-01 08:00 | p | 99 |  | 2027-03-10 08:00
43 | 74 | Pour 1st floor slab | Normal | 4 | 7.20 | 7.20 |  | 2026-12-14 08:00 | p | 99 |  | 2027-03-23 08:00
44 | 75 | Cure 1st floor slab | Normal | 7 | 7.21 | 7.21 |  | 2026-12-23 08:00 | p | 99 |  | 2027-04-01 08:00
45 | 76 | Strip forms from 1st floor slab | Normal | 2 | 7.22 | 7.22 |  | 2027-01-07 08:00 | p | 99 |  | 2027-04-16 08:00
46 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 2027-01-07 08:00 | p | 99 |  | 2027-04-16 08:00
47 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | 2027-01-07 08:00 | p | 99 |  | 2027-04-16 08:00
48 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 2026-11-05 08:00 | p | 106 |  | 2027-02-19 08:00
49 | 80 | Rough-in plumbing at toilets and masonry walls | Normal | 20 | 9.1 | 9.1 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
50 | 81 | Lay masonry at core, mechanical, and toilets | Normal | 20 | 9.2 | 9.2 |  | 2026-11-05 08:00 | p | 106 |  | 2027-02-19 08:00
51 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | 2027-01-28 08:00 | p | 99 |  | 2027-05-07 08:00
52 | 83 | Install roof drains | Normal | 2 | 9.4 | 9.4 |  | 2027-03-10 08:00 | p | 99 |  | 2027-06-17 08:00
53 | 84 | Install tile in toilet rooms | Normal | 10 | 9.5 | 9.5 |  | 2027-02-08 08:00 | p | 99 |  | 2027-05-18 08:00
54 | 85 | Clean masonry | Normal | 5 | 9.6 | 9.6 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
55 | 86 | Clean toilet room tile | Normal | 5 | 9.7 | 9.7 |  | 2027-02-22 08:00 | p | 99 |  | 2027-06-01 08:00
56 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
57 | 88 | Install flashing at parapet walls | Normal | 4 | 10.1 | 10.1 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
58 | 89 | Pour lightweight concrete roof fill | Normal | 2 | 10.2 | 10.2 |  | 2027-03-12 08:00 | p | 101 |  | 2027-06-21 08:00
59 | 90 | Install seamless roofing material | Normal | 5 | 10.3 | 10.3 |  | 2027-03-23 08:00 | p | 99 |  | 2027-06-30 08:00
60 | 91 | Spread stone ballast on seamless roof | Normal | 5 | 10.4 | 10.4 |  | 2027-03-30 08:00 | p | 99 |  | 2027-07-07 08:00
61 | 92 | Set rooftop equipment | Normal | 10 | 10.5 | 10.5 |  | 2027-04-06 08:00 | p | 99 |  | 2027-07-14 08:00
62 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
63 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | 2027-03-04 08:00 | p | 99 |  | 2027-06-11 08:00
64 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
65 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | 2027-06-03 08:00 | p | 99 |  | 2027-09-10 08:00
66 | 97 | Install store front doors and hardware | Normal | 15 | 11.4 | 11.4 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
67 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
68 | 99 | Install millwork and wood trim | Normal | 15 | 12.1 | 12.1 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
69 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | 2027-06-17 08:00 | p | 99 |  | 2027-09-24 08:00
70 | 101 | Install conduit at ceiling plenum space | Normal | 15 | 12.3 | 12.3 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
71 | 102 | Install duct in ceiling plenum space | Normal | 15 | 12.4 | 12.4 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
72 | 103 | Install ceiling grid | Normal | 10 | 12.5 | 12.5 |  | 2027-06-03 08:00 | p | 99 |  | 2027-09-10 08:00
73 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 2027-06-17 08:00 | p | 99 |  | 2027-09-24 08:00
74 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
75 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
76 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
77 | 108 | Complete interior and exterior sod and plantings | Normal | 10 | 12.10 | 12.10 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
78 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 2027-07-29 08:00 | p | 99 |  | 2027-11-05 08:00
79 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
80 | 111 | Set elevator equipment in shafts | Normal | 20 | 13.1 | 13.1 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
81 | 112 | Set equipment in mechanical room | Normal | 10 | 13.2 | 13.2 |  | 2026-12-31 08:00 | p | 106 |  | 2027-04-16 08:00
82 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 2027-01-14 08:00 | p | 106 |  | 2027-04-30 08:00
83 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 2027-03-11 08:00 | p | 99 |  | 2027-06-18 08:00
84 | 115 | Rough-in plumbing in drywall walls | Normal | 20 | 14.1 | 14.1 |  | 2027-04-08 08:00 | p | 99 |  | 2027-07-16 08:00
85 | 116 | Tie-in fire line riser and set valves | Normal | 10 | 14.2 | 14.2 |  | 2027-03-11 08:00 | p | 99 |  | 2027-06-18 08:00
86 | 117 | Set plumbing fixtures and trim | Normal | 15 | 14.3 | 14.3 |  | 2027-05-06 08:00 | p | 99 |  | 2027-08-13 08:00
87 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 2027-07-15 08:00 | p | 99 |  | 2027-10-22 08:00
88 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
89 | 120 | Rough-in electrical in masonry walls | Normal | 20 | 15.1 | 15.1 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
90 | 121 | Rough-in electrical in drywall walls | Normal | 20 | 15.2 | 15.2 |  | 2027-04-29 08:00 | p | 99 |  | 2027-08-06 08:00
91 | 122 | Pull wire in conduit and set area transformers | Normal | 15 | 15.3 | 15.3 |  | 2027-05-27 08:00 | p | 99 |  | 2027-09-03 08:00
92 | 123 | Install and terminate electrical devices | Normal | 15 | 15.4 | 15.4 |  | 2027-06-17 08:00 | p | 99 |  | 2027-09-24 08:00
93 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 2027-07-22 08:00 | p | 85 |  | 2027-10-15 08:00
94 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 2027-07-08 08:00 | p | 103 |  | 2027-10-19 08:00
95 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
96 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 2026-12-03 08:00 | p | 106 |  | 2027-03-19 08:00
97 | 128 | Rough-in mechanical in masonry walls | Normal | 20 | 16.2 | 16.2 |  | 2027-01-11 08:00 | p | 99 |  | 2027-04-20 08:00
98 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 2027-06-03 08:00 | p | 99 |  | 2027-09-10 08:00
99 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 2027-04-20 08:00 | p | 99 |  | 2027-07-28 08:00
100 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 2027-07-26 08:00 | p | 137 |  | 2027-12-10 08:00
101 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
102 | 133 | Install hard tile flooring in common areas | Normal | 5 | 17.1 | 17.1 |  | 2027-05-13 08:00 | p | 99 |  | 2027-08-20 08:00
103 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 2027-05-20 08:00 | p | 99 |  | 2027-08-27 08:00
104 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | 2027-08-12 08:00 | p | 109 |  | 2027-11-29 08:00
105 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 2027-08-18 08:00 | p | 107 |  | 2027-12-03 08:00
106 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 2027-08-18 08:00 | p | 107 |  | 2027-12-03 08:00
107 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | 2027-08-18 08:00 | p | 107 |  | 2027-12-03 08:00
108 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | 2027-08-23 08:00 | p | 107 |  | 2027-12-08 08:00
109 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | 2027-08-24 08:00 | p | 107 |  | 2027-12-09 08:00
110 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 2027-08-25 08:00 | p | 107 |  | 2027-12-10 08:00
111 | 142 | Complete punch list items from all inspections | Normal | 10 | 19 | 19 |  | 2027-08-26 08:00 | p | 134 |  | 2028-01-07 08:00
112 | 143 | Obtain certificate of occupancy | Normal | 2 | 20 | 20 |  | 2027-09-09 08:00 | p | 134 |  | 2028-01-21 08:00
113 | 144 | Issue final completion documents including warranties | Normal | 1 | 21 | 21 |  | 2027-09-13 08:00 | p | 134 |  | 2028-01-25 08:00
114 | 145 | Issue final request for payment | Normal | 1 | 22 | 22 |  | 2027-09-14 08:00 | p | 134 |  | 2028-01-26 08:00

## Early-Finish
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%) | Early Finish - 116 (81%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 2026-07-10 17:00 | p | 21 |  | 2026-07-31 17:00
2 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 2026-07-10 17:00 | p | 21 |  | 2026-07-31 17:00
3 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 2026-09-11 17:00 | p | 88 |  | 2026-12-08 17:00
4 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 2026-07-24 17:00 | p | 14 |  | 2026-08-07 17:00
5 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2026-07-28 17:00 | p | 31 |  | 2026-08-28 17:00
6 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 2026-07-30 17:00 | p | 50 |  | 2026-09-18 17:00
7 | 36 | Rough-in electric and plumbing in elevator | Normal | 4 | 5.4 | 5.4 |  | 2026-08-03 17:00 | p | 31 |  | 2026-09-03 17:00
8 | 37 | Form elevator pit walls | Normal | 4 | 5.5 | 5.5 |  | 2026-08-11 17:00 | p | 50 |  | 2026-09-30 17:00
9 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | 2026-08-05 17:00 | p | 50 |  | 2026-09-24 17:00
10 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 2026-08-12 17:00 | p | 72 |  | 2026-10-23 17:00
11 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 2026-08-13 17:00 | p | 74 |  | 2026-10-26 17:00
12 | 41 | Cure elevator wall concrete | Normal | 7 | 5.9 | 5.9 |  | 2026-09-04 17:00 | p | 88 |  | 2026-12-01 17:00
13 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | 2026-08-21 17:00 | p | 74 |  | 2026-11-03 17:00
14 | 43 | Strip wall forms | Normal | 1 | 5.11 | 5.11 |  | 2026-09-07 17:00 | p | 86 |  | 2026-12-02 17:00
15 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | 2026-08-26 17:00 | p | 72 |  | 2026-11-06 17:00
16 | 45 | Install pneumatic tube in elevator pit | Normal | 3 | 5.13 | 5.13 |  | 2026-09-10 17:00 | p | 88 |  | 2026-12-07 17:00
17 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 2026-09-11 17:00 | p | 88 |  | 2026-12-08 17:00
18 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 2026-11-04 17:00 | p | 106 |  | 2027-02-18 17:00
19 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | 2026-09-09 17:00 | p | 72 |  | 2026-11-20 17:00
20 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 2026-09-23 17:00 | p | 83 |  | 2026-12-15 17:00
21 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 2026-11-04 17:00 | p | 106 |  | 2027-02-18 17:00
22 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | 2026-10-07 17:00 | p | 83 |  | 2026-12-29 17:00
23 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | 2026-10-21 17:00 | p | 83 |  | 2027-01-12 17:00
24 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | 2026-10-28 17:00 | p | 83 |  | 2027-01-19 17:00
25 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 2027-01-08 17:00 | p | 101 |  | 2027-04-19 17:00
26 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 2026-11-04 17:00 | p | 99 |  | 2027-02-11 17:00
27 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 2026-09-16 17:00 | p | 97 |  | 2026-12-22 17:00
28 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | 2026-11-10 17:00 | p | 99 |  | 2027-02-17 17:00
29 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | 2026-11-19 17:00 | p | 99 |  | 2027-02-26 17:00
30 | 59 | Strip forms from 2nd floor slab | Normal | 2 | 7.5 | 7.5 |  | 2026-11-30 17:00 | p | 99 |  | 2027-03-09 17:00
31 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | 2026-11-26 17:00 | p | 99 |  | 2027-03-05 17:00
32 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | 2026-11-26 17:00 | p | 99 |  | 2027-03-05 17:00
33 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | 2026-12-02 17:00 | p | 99 |  | 2027-03-11 17:00
34 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | 2026-12-11 17:00 | p | 101 |  | 2027-03-22 17:00
35 | 64 | Strip forms from 3rd floor slab | Normal | 2 | 7.10 | 7.10 |  | 2026-12-22 17:00 | p | 99 |  | 2027-03-31 17:00
36 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | 2026-12-18 17:00 | p | 101 |  | 2027-03-29 17:00
37 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | 2026-12-18 17:00 | p | 101 |  | 2027-03-29 17:00
38 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | 2026-12-24 17:00 | p | 99 |  | 2027-04-02 17:00
39 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | 2027-01-04 17:00 | p | 99 |  | 2027-04-13 17:00
40 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | 2027-01-06 17:00 | p | 99 |  | 2027-04-15 17:00
41 | 70 | Form 1st floor | Normal | 4 | 7.16 | 7.16 |  | 2026-12-04 17:00 | p | 101 |  | 2027-03-15 17:00
42 | 71 | Install electrical underground | Normal | 5 | 7.17 | 7.17 |  | 2026-12-11 17:00 | p | 101 |  | 2027-03-22 17:00
43 | 72 | Install plumbing underground | Normal | 5 | 7.18 | 7.18 |  | 2026-12-11 17:00 | p | 101 |  | 2027-03-22 17:00
44 | 73 | Install rebar and in-floor utilities | Normal | 4 | 7.19 | 7.19 |  | 2026-12-04 17:00 | p | 101 |  | 2027-03-15 17:00
45 | 74 | Pour 1st floor slab | Normal | 4 | 7.20 | 7.20 |  | 2026-12-17 17:00 | p | 99 |  | 2027-03-26 17:00
46 | 75 | Cure 1st floor slab | Normal | 7 | 7.21 | 7.21 |  | 2026-12-31 17:00 | p | 99 |  | 2027-04-09 17:00
47 | 76 | Strip forms from 1st floor slab | Normal | 2 | 7.22 | 7.22 |  | 2027-01-08 17:00 | p | 101 |  | 2027-04-19 17:00
48 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 2027-01-27 17:00 | p | 99 |  | 2027-05-06 17:00
49 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | 2027-01-27 17:00 | p | 99 |  | 2027-05-06 17:00
50 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 2027-03-11 17:00 | p | 99 |  | 2027-06-18 17:00
51 | 80 | Rough-in plumbing at toilets and masonry walls | Normal | 20 | 9.1 | 9.1 |  | 2027-02-05 17:00 | p | 101 |  | 2027-05-17 17:00
52 | 81 | Lay masonry at core, mechanical, and toilets | Normal | 20 | 9.2 | 9.2 |  | 2026-12-02 17:00 | p | 106 |  | 2027-03-18 17:00
53 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | 2027-03-03 17:00 | p | 99 |  | 2027-06-10 17:00
54 | 83 | Install roof drains | Normal | 2 | 9.4 | 9.4 |  | 2027-03-11 17:00 | p | 99 |  | 2027-06-18 17:00
55 | 84 | Install tile in toilet rooms | Normal | 10 | 9.5 | 9.5 |  | 2027-02-19 17:00 | p | 101 |  | 2027-05-31 17:00
56 | 85 | Clean masonry | Normal | 5 | 9.6 | 9.6 |  | 2027-03-10 17:00 | p | 99 |  | 2027-06-17 17:00
57 | 86 | Clean toilet room tile | Normal | 5 | 9.7 | 9.7 |  | 2027-02-26 17:00 | p | 101 |  | 2027-06-07 17:00
58 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 2027-04-19 17:00 | p | 99 |  | 2027-07-27 17:00
59 | 88 | Install flashing at parapet walls | Normal | 4 | 10.1 | 10.1 |  | 2027-03-09 17:00 | p | 99 |  | 2027-06-16 17:00
60 | 89 | Pour lightweight concrete roof fill | Normal | 2 | 10.2 | 10.2 |  | 2027-03-15 17:00 | p | 99 |  | 2027-06-22 17:00
61 | 90 | Install seamless roofing material | Normal | 5 | 10.3 | 10.3 |  | 2027-03-29 17:00 | p | 99 |  | 2027-07-06 17:00
62 | 91 | Spread stone ballast on seamless roof | Normal | 5 | 10.4 | 10.4 |  | 2027-04-05 17:00 | p | 99 |  | 2027-07-13 17:00
63 | 92 | Set rooftop equipment | Normal | 10 | 10.5 | 10.5 |  | 2027-04-19 17:00 | p | 99 |  | 2027-07-27 17:00
64 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
65 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | 2027-04-07 17:00 | p | 99 |  | 2027-07-15 17:00
66 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | 2027-05-12 17:00 | p | 99 |  | 2027-08-19 17:00
67 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
68 | 97 | Install store front doors and hardware | Normal | 15 | 11.4 | 11.4 |  | 2027-04-28 17:00 | p | 99 |  | 2027-08-05 17:00
69 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 2027-08-11 17:00 | p | 128 |  | 2027-12-17 17:00
70 | 99 | Install millwork and wood trim | Normal | 15 | 12.1 | 12.1 |  | 2027-06-02 17:00 | p | 99 |  | 2027-09-09 17:00
71 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | 2027-07-14 17:00 | p | 99 |  | 2027-10-21 17:00
72 | 101 | Install conduit at ceiling plenum space | Normal | 15 | 12.3 | 12.3 |  | 2027-04-28 17:00 | p | 99 |  | 2027-08-05 17:00
73 | 102 | Install duct in ceiling plenum space | Normal | 15 | 12.4 | 12.4 |  | 2027-06-02 17:00 | p | 99 |  | 2027-09-09 17:00
74 | 103 | Install ceiling grid | Normal | 10 | 12.5 | 12.5 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
75 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 2027-06-30 17:00 | p | 99 |  | 2027-10-07 17:00
76 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
77 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 2027-08-11 17:00 | p | 128 |  | 2027-12-17 17:00
78 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 2027-08-04 17:00 | p | 114 |  | 2027-11-26 17:00
79 | 108 | Complete interior and exterior sod and plantings | Normal | 10 | 12.10 | 12.10 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
80 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 2027-08-11 17:00 | p | 99 |  | 2027-11-18 17:00
81 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 2027-01-27 17:00 | p | 106 |  | 2027-05-13 17:00
82 | 111 | Set elevator equipment in shafts | Normal | 20 | 13.1 | 13.1 |  | 2026-12-30 17:00 | p | 106 |  | 2027-04-15 17:00
83 | 112 | Set equipment in mechanical room | Normal | 10 | 13.2 | 13.2 |  | 2027-01-13 17:00 | p | 106 |  | 2027-04-29 17:00
84 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 2027-01-27 17:00 | p | 106 |  | 2027-05-13 17:00
85 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
86 | 115 | Rough-in plumbing in drywall walls | Normal | 20 | 14.1 | 14.1 |  | 2027-05-05 17:00 | p | 99 |  | 2027-08-12 17:00
87 | 116 | Tie-in fire line riser and set valves | Normal | 10 | 14.2 | 14.2 |  | 2027-03-24 17:00 | p | 99 |  | 2027-07-01 17:00
88 | 117 | Set plumbing fixtures and trim | Normal | 15 | 14.3 | 14.3 |  | 2027-05-26 17:00 | p | 99 |  | 2027-09-02 17:00
89 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 2027-07-28 17:00 | p | 99 |  | 2027-11-04 17:00
90 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 2027-07-23 17:00 | p | 101 |  | 2027-11-01 17:00
91 | 120 | Rough-in electrical in masonry walls | Normal | 20 | 15.1 | 15.1 |  | 2027-02-05 17:00 | p | 101 |  | 2027-05-17 17:00
92 | 121 | Rough-in electrical in drywall walls | Normal | 20 | 15.2 | 15.2 |  | 2027-05-26 17:00 | p | 99 |  | 2027-09-02 17:00
93 | 122 | Pull wire in conduit and set area transformers | Normal | 15 | 15.3 | 15.3 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
94 | 123 | Install and terminate electrical devices | Normal | 15 | 15.4 | 15.4 |  | 2027-07-07 17:00 | p | 99 |  | 2027-10-14 17:00
95 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 2027-07-23 17:00 | p | 87 |  | 2027-10-18 17:00
96 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 2027-07-21 17:00 | p | 103 |  | 2027-11-01 17:00
97 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 2027-08-20 17:00 | p | 139 |  | 2028-01-06 17:00
98 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 2026-12-16 17:00 | p | 106 |  | 2027-04-01 17:00
99 | 128 | Rough-in mechanical in masonry walls | Normal | 20 | 16.2 | 16.2 |  | 2027-02-05 17:00 | p | 101 |  | 2027-05-17 17:00
100 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 2027-06-16 17:00 | p | 99 |  | 2027-09-23 17:00
101 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 2027-05-10 17:00 | p | 99 |  | 2027-08-17 17:00
102 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 2027-08-20 17:00 | p | 139 |  | 2028-01-06 17:00
103 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 2027-08-18 17:00 | p | 107 |  | 2027-12-03 17:00
104 | 133 | Install hard tile flooring in common areas | Normal | 5 | 17.1 | 17.1 |  | 2027-05-19 17:00 | p | 99 |  | 2027-08-26 17:00
105 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 2027-05-25 17:00 | p | 99 |  | 2027-09-01 17:00
106 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | 2027-08-17 17:00 | p | 107 |  | 2027-12-02 17:00
107 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 2027-08-18 17:00 | p | 107 |  | 2027-12-03 17:00
108 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 2027-08-25 17:00 | p | 107 |  | 2027-12-10 17:00
109 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | 2027-08-20 17:00 | p | 109 |  | 2027-12-07 17:00
110 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | 2027-08-23 17:00 | p | 107 |  | 2027-12-08 17:00
111 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | 2027-08-24 17:00 | p | 107 |  | 2027-12-09 17:00
112 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 2027-08-25 17:00 | p | 107 |  | 2027-12-10 17:00
113 | 142 | Complete punch list items from all inspections | Normal | 10 | 19 | 19 |  | 2027-09-08 17:00 | p | 134 |  | 2028-01-20 17:00
114 | 143 | Obtain certificate of occupancy | Normal | 2 | 20 | 20 |  | 2027-09-10 17:00 | p | 136 |  | 2028-01-24 17:00
115 | 144 | Issue final completion documents including warranties | Normal | 1 | 21 | 21 |  | 2027-09-13 17:00 | p | 134 |  | 2028-01-25 17:00
116 | 145 | Issue final request for payment | Normal | 1 | 22 | 22 |  | 2027-09-14 17:00 | p | 134 |  | 2028-01-26 17:00

## Late-Start
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%) | Late Start - 115 (80%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 2026-10-15 08:00 | q | -129 |  | 2026-06-08 08:00
2 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 2026-07-13 08:00 | p | 21 |  | 2026-08-03 08:00
3 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 2026-07-13 08:00 | p | 21 |  | 2026-08-03 08:00
4 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2027-05-07 08:00 | q | -270 |  | 2026-08-10 08:00
5 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 2026-07-27 08:00 | p | 21 |  | 2026-08-17 08:00
6 | 36 | Rough-in electric and plumbing in elevator | Normal | 4 | 5.4 | 5.4 |  | 2027-05-11 08:00 | p | 132 |  | 2027-09-20 08:00
7 | 37 | Form elevator pit walls | Normal | 4 | 5.5 | 5.5 |  | 2027-05-18 08:00 | p | 150 |  | 2027-10-15 08:00
8 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | 2026-07-31 08:00 | p | 77 |  | 2026-10-16 08:00
9 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 2026-08-06 08:00 | p | 77 |  | 2026-10-22 08:00
10 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 2027-05-24 08:00 | p | 175 |  | 2027-11-15 08:00
11 | 41 | Cure elevator wall concrete | Normal | 7 | 5.9 | 5.9 |  | 2027-06-07 08:00 | p | 162 |  | 2027-11-16 08:00
12 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | 2026-08-13 08:00 | p | 99 |  | 2026-11-20 08:00
13 | 43 | Strip wall forms | Normal | 1 | 5.11 | 5.11 |  | 2027-06-16 08:00 | p | 162 |  | 2027-11-25 08:00
14 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | 2026-08-24 08:00 | p | 99 |  | 2026-12-01 08:00
15 | 45 | Install pneumatic tube in elevator pit | Normal | 3 | 5.13 | 5.13 |  | 2027-06-17 08:00 | p | 162 |  | 2027-11-26 08:00
16 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 2027-06-22 08:00 | p | 162 |  | 2027-12-01 08:00
17 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 2026-08-27 08:00 | p | 99 |  | 2026-12-04 08:00
18 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | 2026-08-27 08:00 | p | 99 |  | 2026-12-04 08:00
19 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 2026-09-10 08:00 | p | 99 |  | 2026-12-18 08:00
20 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 2027-05-12 08:00 | p | 99 |  | 2027-08-19 08:00
21 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | 2026-09-24 08:00 | p | 110 |  | 2027-01-12 08:00
22 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | 2026-10-08 08:00 | p | 110 |  | 2027-01-26 08:00
23 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | 2026-10-22 08:00 | p | 110 |  | 2027-02-09 08:00
24 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 2026-10-29 08:00 | p | 110 |  | 2027-02-16 08:00
25 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 2026-10-29 08:00 | p | 110 |  | 2027-02-16 08:00
26 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 2026-10-29 08:00 | p | 126 |  | 2027-03-04 08:00
27 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | 2026-11-05 08:00 | p | 126 |  | 2027-03-11 08:00
28 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | 2026-11-11 08:00 | p | 126 |  | 2027-03-17 08:00
29 | 59 | Strip forms from 2nd floor slab | Normal | 2 | 7.5 | 7.5 |  | 2027-03-10 08:00 | p | 131 |  | 2027-07-19 08:00
30 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | 2026-11-20 08:00 | p | 126 |  | 2027-03-26 08:00
31 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | 2026-11-20 08:00 | p | 126 |  | 2027-03-26 08:00
32 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | 2026-11-27 08:00 | p | 126 |  | 2027-04-02 08:00
33 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | 2026-12-03 08:00 | p | 126 |  | 2027-04-08 08:00
34 | 64 | Strip forms from 3rd floor slab | Normal | 2 | 7.10 | 7.10 |  | 2027-01-05 08:00 | p | 126 |  | 2027-05-11 08:00
35 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | 2026-12-14 08:00 | p | 126 |  | 2027-04-19 08:00
36 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | 2026-12-14 08:00 | p | 126 |  | 2027-04-19 08:00
37 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | 2026-12-21 08:00 | p | 126 |  | 2027-04-26 08:00
38 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | 2026-12-25 08:00 | p | 126 |  | 2027-04-30 08:00
39 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | 2027-01-05 08:00 | p | 126 |  | 2027-05-11 08:00
40 | 70 | Form 1st floor | Normal | 4 | 7.16 | 7.16 |  | 2027-03-19 08:00 | p | 131 |  | 2027-07-28 08:00
41 | 71 | Install electrical underground | Normal | 5 | 7.17 | 7.17 |  | 2027-03-18 08:00 | p | 131 |  | 2027-07-27 08:00
42 | 72 | Install plumbing underground | Normal | 5 | 7.18 | 7.18 |  | 2027-03-18 08:00 | p | 131 |  | 2027-07-27 08:00
43 | 73 | Install rebar and in-floor utilities | Normal | 4 | 7.19 | 7.19 |  | 2027-03-19 08:00 | p | 131 |  | 2027-07-28 08:00
44 | 74 | Pour 1st floor slab | Normal | 4 | 7.20 | 7.20 |  | 2027-03-25 08:00 | p | 131 |  | 2027-08-03 08:00
45 | 75 | Cure 1st floor slab | Normal | 7 | 7.21 | 7.21 |  | 2027-04-05 08:00 | p | 129 |  | 2027-08-12 08:00
46 | 76 | Strip forms from 1st floor slab | Normal | 2 | 7.22 | 7.22 |  | 2027-04-20 08:00 | p | 128 |  | 2027-08-26 08:00
47 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 2027-01-07 08:00 | p | 126 |  | 2027-05-13 08:00
48 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | 2027-01-07 08:00 | p | 126 |  | 2027-05-13 08:00
49 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 2027-01-28 08:00 | p | 126 |  | 2027-06-03 08:00
50 | 80 | Rough-in plumbing at toilets and masonry walls | Normal | 20 | 9.1 | 9.1 |  | 2027-05-20 08:00 | p | 134 |  | 2027-10-01 08:00
51 | 81 | Lay masonry at core, mechanical, and toilets | Normal | 20 | 9.2 | 9.2 |  | 2027-05-26 08:00 | p | 124 |  | 2027-09-27 08:00
52 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | 2027-01-28 08:00 | p | 126 |  | 2027-06-03 08:00
53 | 83 | Install roof drains | Normal | 2 | 9.4 | 9.4 |  | 2027-06-01 08:00 | p | 128 |  | 2027-10-07 08:00
54 | 84 | Install tile in toilet rooms | Normal | 10 | 9.5 | 9.5 |  | 2027-06-17 08:00 | p | 134 |  | 2027-10-29 08:00
55 | 85 | Clean masonry | Normal | 5 | 9.6 | 9.6 |  | 2027-07-08 08:00 | p | 134 |  | 2027-11-19 08:00
56 | 86 | Clean toilet room tile | Normal | 5 | 9.7 | 9.7 |  | 2027-07-01 08:00 | p | 134 |  | 2027-11-12 08:00
57 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 2027-05-28 08:00 | p | 130 |  | 2027-10-05 08:00
58 | 88 | Install flashing at parapet walls | Normal | 4 | 10.1 | 10.1 |  | 2027-05-28 08:00 | p | 130 |  | 2027-10-05 08:00
59 | 89 | Pour lightweight concrete roof fill | Normal | 2 | 10.2 | 10.2 |  | 2027-06-03 08:00 | p | 130 |  | 2027-10-11 08:00
60 | 90 | Install seamless roofing material | Normal | 5 | 10.3 | 10.3 |  | 2027-06-14 08:00 | p | 128 |  | 2027-10-20 08:00
61 | 91 | Spread stone ballast on seamless roof | Normal | 5 | 10.4 | 10.4 |  | 2027-06-21 08:00 | p | 128 |  | 2027-10-27 08:00
62 | 92 | Set rooftop equipment | Normal | 10 | 10.5 | 10.5 |  | 2027-06-28 08:00 | p | 128 |  | 2027-11-03 08:00
63 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 2027-03-04 08:00 | p | 126 |  | 2027-07-08 08:00
64 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | 2027-03-04 08:00 | p | 126 |  | 2027-07-08 08:00
65 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | 2027-04-08 08:00 | p | 126 |  | 2027-08-12 08:00
66 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | 2027-06-03 08:00 | p | 126 |  | 2027-10-07 08:00
67 | 97 | Install store front doors and hardware | Normal | 15 | 11.4 | 11.4 |  | 2027-05-06 08:00 | p | 126 |  | 2027-09-09 08:00
68 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 2027-04-29 08:00 | p | 130 |  | 2027-09-06 08:00
69 | 99 | Install millwork and wood trim | Normal | 15 | 12.1 | 12.1 |  | 2027-05-27 08:00 | p | 126 |  | 2027-09-30 08:00
70 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | 2027-06-17 08:00 | p | 126 |  | 2027-10-21 08:00
71 | 101 | Install conduit at ceiling plenum space | Normal | 15 | 12.3 | 12.3 |  | 2027-04-29 08:00 | p | 130 |  | 2027-09-06 08:00
72 | 102 | Install duct in ceiling plenum space | Normal | 15 | 12.4 | 12.4 |  | 2027-05-27 08:00 | p | 134 |  | 2027-10-08 08:00
73 | 103 | Install ceiling grid | Normal | 10 | 12.5 | 12.5 |  | 2027-06-17 08:00 | p | 134 |  | 2027-10-29 08:00
74 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 2027-07-29 08:00 | p | 134 |  | 2027-12-10 08:00
75 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 2027-07-29 08:00 | p | 134 |  | 2027-12-10 08:00
76 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 2027-07-15 08:00 | p | 139 |  | 2027-12-01 08:00
77 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 2027-07-22 08:00 | p | 119 |  | 2027-11-18 08:00
78 | 108 | Complete interior and exterior sod and plantings | Normal | 10 | 12.10 | 12.10 |  | 2027-07-26 08:00 | p | 134 |  | 2027-12-07 08:00
79 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 2027-08-09 08:00 | p | 134 |  | 2027-12-21 08:00
80 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 2027-06-23 08:00 | p | 162 |  | 2027-12-02 08:00
81 | 111 | Set elevator equipment in shafts | Normal | 20 | 13.1 | 13.1 |  | 2027-06-23 08:00 | p | 162 |  | 2027-12-02 08:00
82 | 112 | Set equipment in mechanical room | Normal | 10 | 13.2 | 13.2 |  | 2027-07-21 08:00 | p | 162 |  | 2027-12-30 08:00
83 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 2027-08-04 08:00 | p | 162 |  | 2028-01-13 08:00
84 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 2027-06-10 08:00 | p | 134 |  | 2027-10-22 08:00
85 | 115 | Rough-in plumbing in drywall walls | Normal | 20 | 14.1 | 14.1 |  | 2027-06-10 08:00 | p | 134 |  | 2027-10-22 08:00
86 | 116 | Tie-in fire line riser and set valves | Normal | 10 | 14.2 | 14.2 |  | 2027-07-15 08:00 | p | 134 |  | 2027-11-26 08:00
87 | 117 | Set plumbing fixtures and trim | Normal | 15 | 14.3 | 14.3 |  | 2027-07-08 08:00 | p | 134 |  | 2027-11-19 08:00
88 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 2027-07-29 08:00 | p | 134 |  | 2027-12-10 08:00
89 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 2027-04-22 08:00 | p | 130 |  | 2027-08-30 08:00
90 | 120 | Rough-in electrical in masonry walls | Normal | 20 | 15.1 | 15.1 |  | 2027-04-22 08:00 | p | 130 |  | 2027-08-30 08:00
91 | 121 | Rough-in electrical in drywall walls | Normal | 20 | 15.2 | 15.2 |  | 2027-06-10 08:00 | p | 130 |  | 2027-10-18 08:00
92 | 122 | Pull wire in conduit and set area transformers | Normal | 15 | 15.3 | 15.3 |  | 2027-06-17 08:00 | p | 130 |  | 2027-10-25 08:00
93 | 123 | Install and terminate electrical devices | Normal | 15 | 15.4 | 15.4 |  | 2027-07-08 08:00 | p | 130 |  | 2027-11-15 08:00
94 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 2027-08-16 08:00 | p | 114 |  | 2027-12-08 08:00
95 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 2027-07-29 08:00 | p | 134 |  | 2027-12-10 08:00
96 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 2027-06-18 08:00 | p | 115 |  | 2027-10-11 08:00
97 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 2027-07-02 08:00 | p | 115 |  | 2027-10-25 08:00
98 | 128 | Rough-in mechanical in masonry walls | Normal | 20 | 16.2 | 16.2 |  | 2027-06-18 08:00 | p | 115 |  | 2027-10-11 08:00
99 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 2027-09-01 08:00 | p | 134 |  | 2028-01-13 08:00
100 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 2027-07-28 08:00 | p | 114 |  | 2027-11-19 08:00
101 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 2027-08-18 08:00 | p | 114 |  | 2027-12-10 08:00
102 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 2027-07-30 08:00 | p | 136 |  | 2027-12-13 08:00
103 | 133 | Install hard tile flooring in common areas | Normal | 5 | 17.1 | 17.1 |  | 2027-07-30 08:00 | p | 136 |  | 2027-12-13 08:00
104 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 2027-08-06 08:00 | p | 136 |  | 2027-12-20 08:00
105 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | 2027-08-12 08:00 | p | 134 |  | 2027-12-24 08:00
106 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 2027-09-14 08:00 | p | 134 |  | 2028-01-26 08:00
107 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 2027-08-18 08:00 | p | 134 |  | 2027-12-30 08:00
108 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | 2027-08-18 08:00 | p | 134 |  | 2027-12-30 08:00
109 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | 2027-08-23 08:00 | p | 134 |  | 2028-01-04 08:00
110 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | 2027-08-24 08:00 | p | 134 |  | 2028-01-05 08:00
111 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 2027-08-25 08:00 | p | 134 |  | 2028-01-06 08:00
112 | 142 | Complete punch list items from all inspections | Normal | 10 | 19 | 19 |  | 2027-08-26 08:00 | p | 134 |  | 2028-01-07 08:00
113 | 143 | Obtain certificate of occupancy | Normal | 2 | 20 | 20 |  | 2027-09-10 08:00 | p | 136 |  | 2028-01-24 08:00
114 | 144 | Issue final completion documents including warranties | Normal | 1 | 21 | 21 |  | 2027-09-13 08:00 | p | 134 |  | 2028-01-25 08:00
115 | 145 | Issue final request for payment | Normal | 1 | 22 | 22 |  | 2027-09-14 08:00 | p | 134 |  | 2028-01-26 08:00

## Late-Finish
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%) | Late Finish - 120 (83%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 2027-06-02 17:00 | q | -348 |  | 2026-06-19 17:00
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 2027-06-02 17:00 | q | -369 |  | 2026-05-29 17:00
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 2026-10-28 17:00 | q | -131 |  | 2026-06-19 17:00
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 2026-08-26 17:00 | q | -68 |  | 2026-06-19 17:00
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 2026-07-10 17:00 | p | 21 |  | 2026-07-31 17:00
6 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 2026-07-10 17:00 | p | 21 |  | 2026-07-31 17:00
7 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 2027-06-22 17:00 | p | 162 |  | 2027-12-01 17:00
8 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 2026-07-24 17:00 | p | 14 |  | 2026-08-07 17:00
9 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 2027-05-10 17:00 | p | 130 |  | 2027-09-17 17:00
10 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 2026-07-30 17:00 | p | 77 |  | 2026-10-15 17:00
11 | 36 | Rough-in electric and plumbing in elevator | Normal | 4 | 5.4 | 5.4 |  | 2027-05-14 17:00 | p | 132 |  | 2027-09-23 17:00
12 | 37 | Form elevator pit walls | Normal | 4 | 5.5 | 5.5 |  | 2027-05-21 17:00 | p | 152 |  | 2027-10-20 17:00
13 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | 2026-08-05 17:00 | p | 77 |  | 2026-10-21 17:00
14 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 2026-08-12 17:00 | p | 99 |  | 2026-11-19 17:00
15 | 40 | Pour concrete elevator walls | Normal | 1 | 5.8 | 5.8 |  | 2027-05-24 17:00 | p | 175 |  | 2027-11-15 17:00
16 | 41 | Cure elevator wall concrete | Normal | 7 | 5.9 | 5.9 |  | 2027-06-15 17:00 | p | 162 |  | 2027-11-24 17:00
17 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | 2026-08-21 17:00 | p | 101 |  | 2026-11-30 17:00
18 | 43 | Strip wall forms | Normal | 1 | 5.11 | 5.11 |  | 2027-06-16 17:00 | p | 162 |  | 2027-11-25 17:00
19 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | 2026-08-26 17:00 | p | 99 |  | 2026-12-03 17:00
20 | 45 | Install pneumatic tube in elevator pit | Normal | 3 | 5.13 | 5.13 |  | 2027-06-21 17:00 | p | 162 |  | 2027-11-30 17:00
21 | 46 | Prepare and pour concrete floor in elevator pit | Normal | 1 | 5.14 | 5.14 |  | 2027-06-22 17:00 | p | 162 |  | 2027-12-01 17:00
22 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 2027-05-25 17:00 | p | 122 |  | 2027-09-24 17:00
23 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | 2026-09-09 17:00 | p | 99 |  | 2026-12-17 17:00
24 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 2026-09-23 17:00 | p | 110 |  | 2027-01-11 17:00
25 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 2027-05-25 17:00 | p | 122 |  | 2027-09-24 17:00
26 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | 2026-10-07 17:00 | p | 110 |  | 2027-01-25 17:00
27 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | 2026-10-21 17:00 | p | 110 |  | 2027-02-08 17:00
28 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | 2026-10-28 17:00 | p | 110 |  | 2027-02-15 17:00
29 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 2027-04-21 17:00 | p | 128 |  | 2027-08-27 17:00
30 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 2026-11-04 17:00 | p | 126 |  | 2027-03-10 17:00
31 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.2 | 7.2 |  | 2026-11-04 17:00 | p | 126 |  | 2027-03-10 17:00
32 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | 2026-11-10 17:00 | p | 126 |  | 2027-03-16 17:00
33 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | 2026-11-19 17:00 | p | 126 |  | 2027-03-25 17:00
34 | 59 | Strip forms from 2nd floor slab | Normal | 2 | 7.5 | 7.5 |  | 2027-03-11 17:00 | p | 131 |  | 2027-07-20 17:00
35 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | 2026-11-26 17:00 | p | 126 |  | 2027-04-01 17:00
36 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | 2026-11-26 17:00 | p | 126 |  | 2027-04-01 17:00
37 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | 2026-12-02 17:00 | p | 126 |  | 2027-04-07 17:00
38 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | 2026-12-11 17:00 | p | 126 |  | 2027-04-16 17:00
39 | 64 | Strip forms from 3rd floor slab | Normal | 2 | 7.10 | 7.10 |  | 2027-01-06 17:00 | p | 126 |  | 2027-05-12 17:00
40 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | 2026-12-18 17:00 | p | 126 |  | 2027-04-23 17:00
41 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | 2026-12-18 17:00 | p | 126 |  | 2027-04-23 17:00
42 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | 2026-12-24 17:00 | p | 126 |  | 2027-04-29 17:00
43 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | 2027-01-04 17:00 | p | 126 |  | 2027-05-10 17:00
44 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | 2027-01-06 17:00 | p | 126 |  | 2027-05-12 17:00
45 | 70 | Form 1st floor | Normal | 4 | 7.16 | 7.16 |  | 2027-03-24 17:00 | p | 131 |  | 2027-08-02 17:00
46 | 71 | Install electrical underground | Normal | 5 | 7.17 | 7.17 |  | 2027-03-24 17:00 | p | 131 |  | 2027-08-02 17:00
47 | 72 | Install plumbing underground | Normal | 5 | 7.18 | 7.18 |  | 2027-03-24 17:00 | p | 131 |  | 2027-08-02 17:00
48 | 73 | Install rebar and in-floor utilities | Normal | 4 | 7.19 | 7.19 |  | 2027-03-24 17:00 | p | 131 |  | 2027-08-02 17:00
49 | 74 | Pour 1st floor slab | Normal | 4 | 7.20 | 7.20 |  | 2027-03-30 17:00 | p | 129 |  | 2027-08-06 17:00
50 | 75 | Cure 1st floor slab | Normal | 7 | 7.21 | 7.21 |  | 2027-04-13 17:00 | p | 129 |  | 2027-08-20 17:00
51 | 76 | Strip forms from 1st floor slab | Normal | 2 | 7.22 | 7.22 |  | 2027-04-21 17:00 | p | 128 |  | 2027-08-27 17:00
52 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | 2027-01-27 17:00 | p | 126 |  | 2027-06-02 17:00
53 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | 2027-01-27 17:00 | p | 126 |  | 2027-06-02 17:00
54 | 79 | Masonry Work | Summary | 91 | 9 | 9 |  | 2027-07-14 17:00 | p | 134 |  | 2027-11-25 17:00
55 | 80 | Rough-in plumbing at toilets and masonry walls | Normal | 20 | 9.1 | 9.1 |  | 2027-06-16 17:00 | p | 134 |  | 2027-10-28 17:00
56 | 81 | Lay masonry at core, mechanical, and toilets | Normal | 20 | 9.2 | 9.2 |  | 2027-06-22 17:00 | p | 122 |  | 2027-10-22 17:00
57 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | 2027-03-03 17:00 | p | 126 |  | 2027-07-07 17:00
58 | 83 | Install roof drains | Normal | 2 | 9.4 | 9.4 |  | 2027-06-02 17:00 | p | 128 |  | 2027-10-08 17:00
59 | 84 | Install tile in toilet rooms | Normal | 10 | 9.5 | 9.5 |  | 2027-06-30 17:00 | p | 134 |  | 2027-11-11 17:00
60 | 85 | Clean masonry | Normal | 5 | 9.6 | 9.6 |  | 2027-07-14 17:00 | p | 134 |  | 2027-11-25 17:00
61 | 86 | Clean toilet room tile | Normal | 5 | 9.7 | 9.7 |  | 2027-07-07 17:00 | p | 134 |  | 2027-11-18 17:00
62 | 87 | Roofing | Summary | 33 | 10 | 10 |  | 2027-07-09 17:00 | p | 130 |  | 2027-11-16 17:00
63 | 88 | Install flashing at parapet walls | Normal | 4 | 10.1 | 10.1 |  | 2027-06-02 17:00 | p | 128 |  | 2027-10-08 17:00
64 | 89 | Pour lightweight concrete roof fill | Normal | 2 | 10.2 | 10.2 |  | 2027-06-04 17:00 | p | 130 |  | 2027-10-12 17:00
65 | 90 | Install seamless roofing material | Normal | 5 | 10.3 | 10.3 |  | 2027-06-18 17:00 | p | 130 |  | 2027-10-26 17:00
66 | 91 | Spread stone ballast on seamless roof | Normal | 5 | 10.4 | 10.4 |  | 2027-06-25 17:00 | p | 130 |  | 2027-11-02 17:00
67 | 92 | Set rooftop equipment | Normal | 10 | 10.5 | 10.5 |  | 2027-07-09 17:00 | p | 130 |  | 2027-11-16 17:00
68 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | 2027-06-16 17:00 | p | 126 |  | 2027-10-20 17:00
69 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | 2027-04-07 17:00 | p | 126 |  | 2027-08-11 17:00
70 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | 2027-05-12 17:00 | p | 126 |  | 2027-09-15 17:00
71 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | 2027-06-16 17:00 | p | 126 |  | 2027-10-20 17:00
72 | 97 | Install store front doors and hardware | Normal | 15 | 11.4 | 11.4 |  | 2027-05-26 17:00 | p | 126 |  | 2027-09-29 17:00
73 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 2027-08-20 17:00 | p | 159 |  | 2028-01-26 17:00
74 | 99 | Install millwork and wood trim | Normal | 15 | 12.1 | 12.1 |  | 2027-06-16 17:00 | p | 126 |  | 2027-10-20 17:00
75 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | 2027-07-14 17:00 | p | 126 |  | 2027-11-17 17:00
76 | 101 | Install conduit at ceiling plenum space | Normal | 15 | 12.3 | 12.3 |  | 2027-05-19 17:00 | p | 128 |  | 2027-09-24 17:00
77 | 102 | Install duct in ceiling plenum space | Normal | 15 | 12.4 | 12.4 |  | 2027-06-16 17:00 | p | 134 |  | 2027-10-28 17:00
78 | 103 | Install ceiling grid | Normal | 10 | 12.5 | 12.5 |  | 2027-06-30 17:00 | p | 134 |  | 2027-11-11 17:00
79 | 104 | Install ceiling tile | Normal | 10 | 12.6 | 12.6 |  | 2027-08-11 17:00 | p | 134 |  | 2027-12-23 17:00
80 | 105 | Hang wallpaper | Normal | 10 | 12.7 | 12.7 |  | 2027-08-11 17:00 | p | 134 |  | 2027-12-23 17:00
81 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 2027-08-11 17:00 | p | 168 |  | 2028-01-26 17:00
82 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 2027-08-11 17:00 | p | 134 |  | 2027-12-23 17:00
83 | 108 | Complete interior and exterior sod and plantings | Normal | 10 | 12.10 | 12.10 |  | 2027-08-06 17:00 | p | 136 |  | 2027-12-20 17:00
84 | 109 | Pave, curb, and stripe parking lot | Normal | 10 | 12.11 | 12.11 |  | 2027-08-20 17:00 | p | 136 |  | 2028-01-03 17:00
85 | 110 | Elevators | Summary | 40 | 13 | 13 |  | 2027-08-17 17:00 | p | 162 |  | 2028-01-26 17:00
86 | 111 | Set elevator equipment in shafts | Normal | 20 | 13.1 | 13.1 |  | 2027-07-20 17:00 | p | 162 |  | 2027-12-29 17:00
87 | 112 | Set equipment in mechanical room | Normal | 10 | 13.2 | 13.2 |  | 2027-08-03 17:00 | p | 162 |  | 2028-01-12 17:00
88 | 113 | Test and align doors and equipment | Normal | 10 | 13.3 | 13.3 |  | 2027-08-17 17:00 | p | 162 |  | 2028-01-26 17:00
89 | 114 | Plumbing | Summary | 100 | 14 | 14 |  | 2027-08-11 17:00 | p | 134 |  | 2027-12-23 17:00
90 | 115 | Rough-in plumbing in drywall walls | Normal | 20 | 14.1 | 14.1 |  | 2027-07-07 17:00 | p | 134 |  | 2027-11-18 17:00
91 | 116 | Tie-in fire line riser and set valves | Normal | 10 | 14.2 | 14.2 |  | 2027-07-28 17:00 | p | 134 |  | 2027-12-09 17:00
92 | 117 | Set plumbing fixtures and trim | Normal | 15 | 14.3 | 14.3 |  | 2027-07-28 17:00 | p | 134 |  | 2027-12-09 17:00
93 | 118 | Flush, test, and clean piping and fixtures | Normal | 10 | 14.4 | 14.4 |  | 2027-08-11 17:00 | p | 134 |  | 2027-12-23 17:00
94 | 119 | Electrical | Summary | 140 | 15 | 15 |  | 2027-08-17 17:00 | p | 128 |  | 2027-12-23 17:00
95 | 120 | Rough-in electrical in masonry walls | Normal | 20 | 15.1 | 15.1 |  | 2027-05-19 17:00 | p | 128 |  | 2027-09-24 17:00
96 | 121 | Rough-in electrical in drywall walls | Normal | 20 | 15.2 | 15.2 |  | 2027-07-07 17:00 | p | 128 |  | 2027-11-12 17:00
97 | 122 | Pull wire in conduit and set area transformers | Normal | 15 | 15.3 | 15.3 |  | 2027-07-07 17:00 | p | 128 |  | 2027-11-12 17:00
98 | 123 | Install and terminate electrical devices | Normal | 15 | 15.4 | 15.4 |  | 2027-07-28 17:00 | p | 128 |  | 2027-12-03 17:00
99 | 124 | Make electrical terminations for HVAC equipment | Normal | 2 | 15.5 | 15.5 |  | 2027-08-17 17:00 | p | 114 |  | 2027-12-09 17:00
100 | 125 | Install light fixtures - test and clean | Normal | 10 | 15.6 | 15.6 |  | 2027-08-11 17:00 | p | 134 |  | 2027-12-23 17:00
101 | 126 | Heating and Ventilating - AC | Summary | 187 | 16 | 16 |  | 2027-09-14 17:00 | p | 134 |  | 2028-01-26 17:00
102 | 127 | Set equipment in mechanical room | Normal | 10 | 16.1 | 16.1 |  | 2027-07-15 17:00 | p | 113 |  | 2027-11-05 17:00
103 | 128 | Rough-in mechanical in masonry walls | Normal | 20 | 16.2 | 16.2 |  | 2027-07-15 17:00 | p | 113 |  | 2027-11-05 17:00
104 | 129 | Rough-in mechanical in drywall walls | Normal | 10 | 16.3 | 16.3 |  | 2027-09-14 17:00 | p | 134 |  | 2028-01-26 17:00
105 | 130 | Install duct in building chase | Normal | 15 | 16.4 | 16.4 |  | 2027-08-17 17:00 | p | 114 |  | 2027-12-09 17:00
106 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | 2027-09-14 17:00 | p | 114 |  | 2028-01-06 17:00
107 | 132 | Final Clean-up and Occupancy | Summary | 70 | 17 | 17 |  | 2027-09-14 17:00 | p | 134 |  | 2028-01-26 17:00
108 | 133 | Install hard tile flooring in common areas | Normal | 5 | 17.1 | 17.1 |  | 2027-08-05 17:00 | p | 134 |  | 2027-12-17 17:00
109 | 134 | Clean hard tile floors | Normal | 4 | 17.2 | 17.2 |  | 2027-08-11 17:00 | p | 134 |  | 2027-12-23 17:00
110 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | 2027-08-17 17:00 | p | 134 |  | 2027-12-29 17:00
111 | 136 | Substantial completion date | Normal | 1 | 17.4 | 17.4 |  | 2027-09-14 17:00 | p | 134 |  | 2028-01-26 17:00
112 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | 2027-08-25 17:00 | p | 134 |  | 2028-01-06 17:00
113 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | 2027-08-20 17:00 | p | 136 |  | 2028-01-03 17:00
114 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | 2027-08-23 17:00 | p | 134 |  | 2028-01-04 17:00
115 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | 2027-08-24 17:00 | p | 134 |  | 2028-01-05 17:00
116 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | 2027-08-25 17:00 | p | 134 |  | 2028-01-06 17:00
117 | 142 | Complete punch list items from all inspections | Normal | 10 | 19 | 19 |  | 2027-09-08 17:00 | p | 134 |  | 2028-01-20 17:00
118 | 143 | Obtain certificate of occupancy | Normal | 2 | 20 | 20 |  | 2027-09-13 17:00 | p | 134 |  | 2028-01-25 17:00
119 | 144 | Issue final completion documents including warranties | Normal | 1 | 21 | 21 |  | 2027-09-13 17:00 | p | 134 |  | 2028-01-25 17:00
120 | 145 | Issue final request for payment | Normal | 1 | 22 | 22 |  | 2027-09-14 17:00 | p | 134 |  | 2028-01-26 17:00

## Expected-Finish
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%) | Expected Finish - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Suspend-Date
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%) | Suspend Date - 10 (7%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 2026-05-22 17:00 | p | 7 |  | 2026-05-29 17:00
2 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | O | p |  |  | 2026-06-19 17:00
3 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 2026-05-22 17:00 | p | 28 |  | 2026-06-19 17:00
4 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | 2026-05-22 17:00 | p | 28 |  | 2026-06-19 17:00
5 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | O | p |  |  | 2026-07-03 17:00
6 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | O | p |  |  | 2026-07-31 17:00
7 | 32 | Foundations | Summary | 45 | 5 | 5 |  | O | p |  |  | 2026-08-07 17:00
8 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | O | p |  |  | 2026-08-07 17:00
9 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | O | p |  |  | 2026-08-27 17:00
10 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | O | p |  |  | 2026-08-27 17:00

## Resume-Date
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%) | Resume Date - 10 (7%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 2026-05-25 08:00 | p | 4 |  | 2026-05-29 17:00
2 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | O | p |  |  | 2026-06-19 17:00
3 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 2026-05-25 08:00 | p | 25 |  | 2026-06-19 17:00
4 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | 2026-05-25 08:00 | p | 25 |  | 2026-06-19 17:00
5 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | O | p |  |  | 2026-07-03 17:00
6 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | O | p |  |  | 2026-07-31 17:00
7 | 32 | Foundations | Summary | 45 | 5 | 5 |  | O | p |  |  | 2026-08-07 17:00
8 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | O | p |  |  | 2026-08-07 17:00
9 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | O | p |  |  | 2026-08-28 08:00
10 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | O | p |  |  | 2026-08-28 08:00

## Activity-Status
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%) | Activity Status - 12 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | InProgress |  |  |  | Complete
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | InProgress |  |  |  | Complete
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | Planned |  |  |  | Complete
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | InProgress |  |  |  | Complete
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | InProgress |  |  |  | Complete
6 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | InProgress |  |  |  | Complete
7 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | Planned |  |  |  | Complete
8 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | Planned |  |  |  | Complete
9 | 32 | Foundations | Summary | 45 | 5 | 5 |  | Planned |  |  |  | InProgress
10 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | Planned |  |  |  | Complete
11 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | Planned |  |  |  | InProgress
12 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | Planned |  |  |  | InProgress

## Percent-Complete
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%) | Percent Complete - 12 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 0.74 | p | 0.26 | -35% | 1
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 0.74 | p | 0.26 | -35% | 1
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 0 | p | 1 |  | 1
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 0.67 | p | 0.33 | -49% | 1
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 0.6 | p | 0.4 | -67% | 1
6 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | 0.53 | p | 0.47 | -89% | 1
7 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | 0 | p | 1 |  | 1
8 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 0 | p | 1 |  | 1
9 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 0 | p | 0.28 |  | 0.28
10 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 0 | p | 1 |  | 1
11 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 0 | p | 0.93 |  | 0.93
12 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 0 | p | 0.36 |  | 0.36

## Physical---Complete
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%) | Physical % Complete - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Critical
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%) | Critical - 45 (31%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | P |  |  |  | O
2 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | P |  |  |  | O
3 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | P |  |  |  | O
4 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | P |  |  |  | O
5 | 32 | Foundations | Summary | 45 | 5 | 5 |  | P |  |  |  | O
6 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | P |  |  |  | O
7 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | P |  |  |  | O
8 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | P |  |  |  | O
9 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | P |  |  |  | O
10 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | P |  |  |  | O
11 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | P |  |  |  | O
12 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | P |  |  |  | O
13 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | P |  |  |  | O
14 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | P |  |  |  | O
15 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | P |  |  |  | O
16 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | P |  |  |  | O
17 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | P |  |  |  | O
18 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | P |  |  |  | O
19 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | P |  |  |  | O
20 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | P |  |  |  | O
21 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | P |  |  |  | O
22 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | P |  |  |  | O
23 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | P |  |  |  | O
24 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | P |  |  |  | O
25 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | P |  |  |  | O
26 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | P |  |  |  | O
27 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | P |  |  |  | O
28 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | P |  |  |  | O
29 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | P |  |  |  | O
30 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | P |  |  |  | O
31 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | P |  |  |  | O
32 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | P |  |  |  | O
33 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | P |  |  |  | O
34 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | P |  |  |  | O
35 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | P |  |  |  | O
36 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | P |  |  |  | O
37 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | P |  |  |  | O
38 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | P |  |  |  | O
39 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | O |  |  |  | P
40 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | P |  |  |  | O
41 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | P |  |  |  | O
42 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | P |  |  |  | O
43 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | P |  |  |  | O
44 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | P |  |  |  | O
45 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | P |  |  |  | O

## Longest-Path
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%) | Longest Path - 45 (31%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | P |  |  |  | O
2 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | P |  |  |  | O
3 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | P |  |  |  | O
4 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | P |  |  |  | O
5 | 32 | Foundations | Summary | 45 | 5 | 5 |  | P |  |  |  | O
6 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | P |  |  |  | O
7 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | P |  |  |  | O
8 | 38 | Set reinforcing and anchor bolts | Normal | 4 | 5.6 | 5.6 |  | P |  |  |  | O
9 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | P |  |  |  | O
10 | 42 | Cure piers and foundations | Normal | 7 | 5.10 | 5.10 |  | P |  |  |  | O
11 | 44 | Strip column piers and foundation forms | Normal | 3 | 5.12 | 5.12 |  | P |  |  |  | O
12 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | P |  |  |  | O
13 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors | Normal | 10 | 6.1 | 6.1 |  | P |  |  |  | O
14 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | P |  |  |  | O
15 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof | Normal | 10 | 6.4 | 6.4 |  | P |  |  |  | O
16 | 52 | Install stairs and miscellaneous iron railing | Normal | 10 | 6.5 | 6.5 |  | P |  |  |  | O
17 | 53 | Touch-up paint on steel | Normal | 5 | 6.6 | 6.6 |  | P |  |  |  | O
18 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | P |  |  |  | O
19 | 57 | Pour 2nd floor slab | Normal | 4 | 7.3 | 7.3 |  | P |  |  |  | O
20 | 58 | Cure 2nd floor slab | Normal | 7 | 7.4 | 7.4 |  | P |  |  |  | O
21 | 60 | Form 3rd floor including all floor openings | Normal | 5 | 7.6 | 7.6 |  | P |  |  |  | O
22 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.7 | 7.7 |  | P |  |  |  | O
23 | 62 | Pour 3rd floor slab | Normal | 4 | 7.8 | 7.8 |  | P |  |  |  | O
24 | 63 | Cure 3rd floor slab | Normal | 7 | 7.9 | 7.9 |  | P |  |  |  | O
25 | 65 | Form roof slab including all floor openings | Normal | 5 | 7.11 | 7.11 |  | P |  |  |  | O
26 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Normal | 5 | 7.12 | 7.12 |  | P |  |  |  | O
27 | 67 | Pour roof slab | Normal | 4 | 7.13 | 7.13 |  | P |  |  |  | O
28 | 68 | Cure roof slab | Normal | 7 | 7.14 | 7.14 |  | P |  |  |  | O
29 | 69 | Strip forms from roof slab | Normal | 2 | 7.15 | 7.15 |  | P |  |  |  | O
30 | 77 | Carpentry Work | Summary | 15 | 8 | 8 |  | P |  |  |  | O
31 | 78 | Install exterior sheathing and metal studs | Normal | 15 | 8.1 | 8.1 |  | P |  |  |  | O
32 | 82 | Install exterior masonry work | Normal | 25 | 9.3 | 9.3 |  | P |  |  |  | O
33 | 93 | Window wall and store front closures | Summary | 75 | 11 | 11 |  | P |  |  |  | O
34 | 94 | Install window wall aluminum and glass | Normal | 25 | 11.1 | 11.1 |  | P |  |  |  | O
35 | 95 | Install interior stud walls and drywall | Normal | 25 | 11.2 | 11.2 |  | P |  |  |  | O
36 | 96 | Install interior doors and hardware | Normal | 10 | 11.3 | 11.3 |  | P |  |  |  | O
37 | 100 | Paint walls and woodwork | Normal | 20 | 12.2 | 12.2 |  | P |  |  |  | O
38 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | P |  |  |  | O
39 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | O |  |  |  | P
40 | 135 | Remove debris from building and do final clean-up | Normal | 4 | 17.3 | 17.3 |  | P |  |  |  | O
41 | 137 | Complete Final Inspections | Summary | 6 | 18 | 18 |  | P |  |  |  | O
42 | 138 | Complete elevator inspection and certification | Normal | 3 | 18.1 | 18.1 |  | P |  |  |  | O
43 | 139 | Perform architect's inspection | Normal | 1 | 18.2 | 18.2 |  | P |  |  |  | O
44 | 140 | Perform local building agency inspection | Normal | 1 | 18.3 | 18.3 |  | P |  |  |  | O
45 | 141 | Perform Fire Marshal's inspection | Normal | 1 | 18.4 | 18.4 |  | P |  |  |  | O

## Primary-Constraint
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%) | Primary Constraint - 3 (2%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | None |  |  |  | StartOnOrAfter
2 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | None |  |  |  | StartOnOrAfter
3 | 131 | Set HVAC trim and test and balance system | Normal | 20 | 16.5 | 16.5 |  | None |  |  |  | MandatoryStart

## Secondary-Constraint
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%) | Secondary Constraint - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Baseline-Work
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%) | Baseline Work - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Actual-Work
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%) | Actual Work - 12 (8%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 792 | p | 280 | -35% | 1072
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 112 | p | 40 | -36% | 152
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 0 | p | 80 |  | 80
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 320 | p | 160 | -50% | 480
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 424 | p | 400 | -94% | 824
6 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | 184 | p | 160 | -87% | 344
7 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | 0 | p | 80 |  | 80
8 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 0 | p | 160 |  | 160
9 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 0 | p | 204 |  | 204
10 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 0 | p | 20 |  | 20
11 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 0 | p | 112 |  | 112
12 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 0 | p | 72 |  | 72

## Remaining-Work
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%) | Remaining Work - 21 (15%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 10 | Long Lead Procurement | Summary | 20 | 2 | 2 |  | 280 | q | -280 | (-100%) | 0
2 | 12 | Submit shop drawings and order long lead items - roofing | Normal | 5 | 2.2 | 2.2 |  | 40 | q | -40 | (-100%) | 0
3 | 15 | Submit shop drawings and order long lead items - electric | Normal | 10 | 2.5 | 2.5 |  | 80 | q | -80 | (-100%) | 0
4 | 17 | Detail, fabricate and deliver steel | Normal | 20 | 2.7 | 2.7 |  | 160 | q | -160 | (-100%) | 0
5 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 280 | q | -280 | (-100%) | 0
6 | 29 | Install exterior fire line and building fire riser | Normal | 20 | 4.5 | 4.5 |  | 160 | q | -160 | (-100%) | 0
7 | 30 | Perform final site grading | Normal | 10 | 4.6 | 4.6 |  | 80 | q | -80 | (-100%) | 0
8 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 40 | q | -40 | (-100%) | 0
9 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 332 | p | 176 | -53% | 508
10 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 40 | q | -40 | (-100%) | 0
11 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 16 | q | -8 | (-50%) | 8
12 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 32 | p | 96 | -300% | 128
13 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 40 | p | 128 | -320% | 168
14 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 328 | p | 158 | -48% | 486
15 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 80 | p | 56 | -70% | 136
16 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 60 | p | 102 | -170% | 162
17 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 600.88 | p | 115.2 | -19% | 716.08
18 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 48 | p | 115.2 | -240% | 163.2
19 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 1200 | p | 256 | -21% | 1456
20 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 160 | p | 168 | -105% | 328
21 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 120 | p | 88 | -73% | 208

## Total-Work
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%) | Total Work - 15 (10%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED
1 | 24 | Site Grading and Utilities | Summary | 28 | 4 | 4 |  | 704 | p | 120 | -17% | 824
2 | 31 | Erect building batter boards and layout building | Normal | 5 | 4.7 | 4.7 |  | 40 | p | 120 | -300% | 160
3 | 32 | Foundations | Summary | 45 | 5 | 5 |  | 332 | p | 380 | -114% | 712
4 | 33 | Excavate foundations | Normal | 10 | 5.1 | 5.1 |  | 40 | q | -20 | (-50%) | 20
5 | 34 | Excavate elevator pit | Normal | 2 | 5.2 | 5.2 |  | 16 | p | 104 | -650% | 120
6 | 35 | Form column piers and spread foundations | Normal | 4 | 5.3 | 5.3 |  | 32 | p | 168 | -525% | 200
7 | 39 | Pour column piers and foundations | Normal | 5 | 5.7 | 5.7 |  | 40 | p | 128 | -320% | 168
8 | 47 | Steel Erection | Summary | 50 | 6 | 6 |  | 328 | p | 158 | -48% | 486
9 | 49 | Erect steel columns, beams and joist - 3rd floor and roof | Normal | 10 | 6.2 | 6.2 |  | 80 | p | 56 | -70% | 136
10 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors | Normal | 10 | 6.3 | 6.3 |  | 60 | p | 102 | -170% | 162
11 | 54 | Form and Pour Concrete - Floors and Roof | Summary | 87 | 7 | 7 |  | 600.88 | p | 115.2 | -19% | 716.08
12 | 55 | Form 2nd floor including all floor openings | Normal | 5 | 7.1 | 7.1 |  | 48 | p | 115.2 | -240% | 163.2
13 | 98 | Building Finishes | Summary | 90 | 12 | 12 |  | 1200 | p | 256 | -21% | 1456
14 | 106 | Install building carpet | Normal | 20 | 12.8 | 12.8 |  | 160 | p | 168 | -105% | 328
15 | 107 | Install hardware and accessories | Normal | 15 | 12.9 | 12.9 |  | 120 | p | 88 | -73% | 208

## Baseline-Cost
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%) | Baseline Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Budget-Cost
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%) | Budget Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Actual-Cost
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%) | Actual Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Remaining-Cost
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%) | Remaining Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Total-Cost
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%) | Total Cost - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## WBS-Code
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%) | WBS Code - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## WBS-Name
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%) | WBS Name - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Baseline-WBS-Code
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%) | Baseline WBS Code - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED

## Task-Planning-Level-ID
Acumen Fuse® Forensic Analysis Report
Workbook1
Project2 - 144 Activities
Compared to: 1 Snapshot
Created on: 6/22/2026
Created by: dpolitte
Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%) | Task Planning Level ID - 0 (0%)
# | ID | Description | Activity Type | Remaining Duration | WBS Code | WBS Name | Baseline WBS Code | Project2 | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED | Project5_TAMPERED