## Project -->
The tabs that follow are setup to graph Acumen Fuse data for single projects.
The individual project charts (G1–G5) provide a tactical, time-phased diagnostic of a single project's execution health, focusing on granular details like historical throughput, schedule realism, data hygiene, and the near-term buildup of deferred work (the "bow wave"). These are deep-dive tools designed for project managers and schedulers to correct specific execution issues.

## G1_Characteristics_WorkToGo
Work-To-Go
Comparing Total # of Normal Tasks to To-Go Normal Tasks
On the Phases Ribbon, Select Charts (Line from the dropdown). From the Phase Analyzer, Select Normal Tasks and Normal Tasks (To-Go).
 | time axis 2018-01-01 to 2032-01-01
| Status Date | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Total Activities | 474 | 82 | 81 | 85 | 85 | 85 | 87 | 88 | 87 | 85 | 87 | 87 | 94 | 92 | 94 | 97 | 95 | 99 | 96 | 95 | 99 | 103 | 109 | 111 | 115 | 131 | 132 | 120 | 123 | 115 | 113 | 110 | 112 | 124 | 120 | 148 | 158 | 169 | 159 | 165 | 160 | 264 | 258 | 253 | 246 | 246 | 281 | 302 | 283 | 276 | 313 | 303 | 252 | 241 | 273 | 267 | 271 | 337 | 323 | 318 | 330 | 333 | 315 | 322 | 290 | 284 | 329 | 305 | 306 | 346 | 442 | 316 | 319 | 331 | 322 | 307 | 284 | 297 | 303 | 310 | 248 | 265 | 273 | 313 | 281 | 265 | 292 | 296 | 279 | 241 | 181 | 126 | 78 | 92 | 59 | 62 | 74 | 24 | 24 | 16 | 19 | 4 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milestones | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 2 | 4 | 9 | 0 | 3 | 2 | 30 | 8 | 1 | 2 | 5 | 8 | 13 | 10 | 8 | 6 | 10 | 6 | 3 | 8 | 3 | 2 | 7 | 9 | 10 | 12 | 24 | 16 | 27 | 9 | 12 | 45 | 17 | 9 | 17 | 107 | 7 | 12 | 10 | 15 | 14 | 11 | 15 | 11 | 24 | 7 | 7 | 12 | 24 | 17 | 18 | 30 | 35 | 51 | 33 | 26 | 16 | 5 | 9 | 3 | 6 | 15 | 0 | 3 | 1 | 5 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Normal Tasks | 8 | 1 | 0 | 1 | 1 | 1 | 3 | 4 | 3 | 1 | 3 | 3 | 4 | 4 | 5 | 8 | 6 | 8 | 5 | 4 | 6 | 10 | 12 | 13 | 15 | 29 | 29 | 20 | 22 | 14 | 10 | 9 | 11 | 19 | 17 | 35 | 43 | 43 | 39 | 47 | 43 | 82 | 94 | 95 | 90 | 83 | 96 | 109 | 100 | 94 | 125 | 120 | 86 | 76 | 100 | 101 | 102 | 148 | 126 | 122 | 123 | 117 | 115 | 111 | 103 | 94 | 113 | 118 | 125 | 146 | 157 | 132 | 130 | 144 | 128 | 117 | 101 | 107 | 112 | 106 | 73 | 84 | 86 | 112 | 94 | 83 | 101 | 122 | 97 | 89 | 69 | 45 | 24 | 33 | 21 | 23 | 32 | 11 | 7 | 5 | 4 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Summaries | 103 | 81 | 81 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 88 | 88 | 89 | 89 | 89 | 91 | 90 | 91 | 92 | 93 | 96 | 97 | 100 | 101 | 101 | 100 | 101 | 101 | 101 | 101 | 101 | 104 | 103 | 111 | 111 | 117 | 120 | 115 | 115 | 152 | 156 | 157 | 154 | 158 | 177 | 180 | 173 | 174 | 182 | 173 | 160 | 162 | 165 | 163 | 167 | 182 | 188 | 186 | 195 | 192 | 184 | 184 | 178 | 178 | 171 | 170 | 172 | 183 | 178 | 177 | 177 | 177 | 179 | 176 | 172 | 175 | 180 | 180 | 168 | 174 | 175 | 177 | 170 | 164 | 161 | 139 | 131 | 119 | 86 | 65 | 49 | 50 | 35 | 33 | 27 | 13 | 14 | 10 | 10 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hammocks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Recurring Normal Tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Tasks & Milestones | 371 | 1 | 0 | 1 | 1 | 1 | 3 | 4 | 3 | 1 | 3 | 3 | 6 | 4 | 5 | 8 | 6 | 8 | 6 | 4 | 7 | 10 | 13 | 14 | 15 | 30 | 31 | 20 | 22 | 14 | 12 | 9 | 11 | 20 | 17 | 37 | 47 | 52 | 39 | 50 | 45 | 112 | 102 | 96 | 92 | 88 | 104 | 122 | 110 | 102 | 131 | 130 | 92 | 79 | 108 | 104 | 104 | 155 | 135 | 132 | 135 | 141 | 131 | 138 | 112 | 106 | 158 | 135 | 134 | 163 | 264 | 139 | 142 | 154 | 143 | 131 | 112 | 122 | 123 | 130 | 80 | 91 | 98 | 136 | 111 | 101 | 131 | 157 | 148 | 122 | 95 | 61 | 29 | 42 | 24 | 29 | 47 | 11 | 10 | 6 | 9 | 1 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Completed Tasks & Milestones | 371 | 1 | 0 | 1 | 1 | 1 | 3 | 4 | 3 | 1 | 3 | 3 | 6 | 4 | 5 | 8 | 6 | 8 | 6 | 4 | 7 | 10 | 13 | 14 | 15 | 30 | 31 | 20 | 22 | 14 | 12 | 9 | 11 | 20 | 17 | 37 | 47 | 52 | 39 | 50 | 45 | 112 | 102 | 96 | 92 | 88 | 104 | 122 | 110 | 102 | 131 | 130 | 92 | 79 | 108 | 104 | 104 | 155 | 135 | 132 | 135 | 141 | 131 | 137 | 111 | 105 | 157 | 134 | 133 | 161 | 261 | 136 | 138 | 150 | 139 | 126 | 107 | 114 | 114 | 119 | 69 | 78 | 82 | 115 | 88 | 76 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Completed Milestones | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 2 | 4 | 9 | 0 | 3 | 2 | 30 | 8 | 1 | 2 | 5 | 8 | 13 | 10 | 8 | 6 | 10 | 6 | 3 | 8 | 3 | 2 | 7 | 9 | 10 | 12 | 24 | 16 | 27 | 9 | 12 | 45 | 17 | 9 | 17 | 107 | 7 | 12 | 10 | 15 | 14 | 11 | 15 | 11 | 24 | 7 | 7 | 12 | 24 | 17 | 18 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Completed Tasks | 8 | 1 | 0 | 1 | 1 | 1 | 3 | 4 | 3 | 1 | 3 | 3 | 4 | 4 | 5 | 8 | 6 | 8 | 5 | 4 | 6 | 10 | 12 | 13 | 15 | 29 | 29 | 20 | 22 | 14 | 10 | 9 | 11 | 19 | 17 | 35 | 43 | 43 | 39 | 47 | 43 | 82 | 94 | 95 | 90 | 83 | 96 | 109 | 100 | 94 | 125 | 120 | 86 | 76 | 100 | 101 | 102 | 148 | 126 | 122 | 123 | 117 | 115 | 110 | 102 | 93 | 112 | 117 | 124 | 144 | 154 | 129 | 126 | 140 | 124 | 112 | 96 | 99 | 103 | 95 | 62 | 71 | 70 | 91 | 71 | 58 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Activities (To-Go) - % of Total | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 56 | 56 | 57 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 59 | 59 | 59 | 59 | 60 | 60 | 60 | 60 | 60 | 61 | 61 | 61 | 61 | 64 | 64 | 65 | 68 | 68 | 69 | 69 | 69 | 70 | 75 | 77 | 81 | 84 | 86 | 93 | 97 | 99 | 107 | 110 | 114 | 116 | 125 | 130 | 139 | 145 | 150 | 192 | 296 | 279 | 241 | 181 | 126 | 78 | 92 | 59 | 62 | 74 | 24 | 24 | 16 | 19 | 4 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tasks & Milestones (To-Go) - % of Total To-Go | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 8 | 9 | 11 | 11 | 13 | 16 | 21 | 23 | 25 | 56 | 157 | 148 | 122 | 95 | 61 | 29 | 42 | 24 | 29 | 47 | 11 | 10 | 6 | 9 | 1 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Milestones (To-Go) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 35 | 51 | 33 | 26 | 16 | 5 | 9 | 3 | 6 | 15 | 0 | 3 | 1 | 5 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Normal Tasks (To-Go) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 8 | 9 | 11 | 11 | 13 | 16 | 21 | 23 | 25 | 48 | 122 | 97 | 89 | 69 | 45 | 24 | 33 | 21 | 23 | 32 | 11 | 7 | 5 | 4 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Summaries (To-Go) | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 56 | 56 | 57 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 59 | 59 | 59 | 59 | 60 | 60 | 60 | 60 | 60 | 61 | 61 | 61 | 61 | 64 | 64 | 65 | 67 | 67 | 68 | 68 | 68 | 69 | 73 | 74 | 78 | 80 | 82 | 89 | 92 | 94 | 99 | 101 | 103 | 105 | 112 | 114 | 118 | 122 | 125 | 136 | 139 | 131 | 119 | 86 | 65 | 49 | 50 | 35 | 33 | 27 | 13 | 14 | 10 | 10 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hammocks (To-Go) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Recurring Tasks (To-Go) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Longest Path (Tasks & Milestones) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13 | 22 | 26 | 10 | 9 | 5 | 18 | 12 | 13 | 25 | 7 | 6 | 1 | 4 | 1 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Longest Path (Normal Tasks) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12 | 16 | 15 | 9 | 6 | 5 | 17 | 10 | 11 | 21 | 7 | 4 | 1 | 3 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Longest Path (Milestones) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 11 | 1 | 3 | 0 | 1 | 2 | 2 | 4 | 0 | 2 | 0 | 1 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Critical Milestones (To-Go)
Critical Normal Tasks (To-Go)
| Total New Tasks & Milestones in Status Period | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total New Completed Tasks & Milestones in Status Period | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Riding Data Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Score | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Work-to-Go
To recreate this chart in Excel, choose the Publish --> To Microsoft Excel option
Chart 1
This graph illustrates all the normal tasks in the schedule (grey) vs. the work-to-go normal tasks (blue). It also shows how many work-to-go normal tasks are critical (orange).
Displaying the critical activities on this work-to-go chart helps to visualize "how much" of the the work-to-go is critical.
Milestone data can be selected instead of (or in addition to) normal activities.
Normal
Normal To-Go
Longest
In the MS Excel file, select the Phase Analysis tab.
|  | Chart 2 | [15 empty] | This is the same graph as the one above, but displays all normal tasks as "area", whereas the work-to-go normal tasks are shown as bars (blue) against the full set of normal task area (grey).
The critical tasks are still shown as a line (orange).
The benefit of this chart is that it helps the reader to visualize more directly the longest path activities (orange line) as a proportion of the work-to-go activities (blue bars).
Milestone data can be selected instead of (or in addition to) normal activities.
Completed Work vs. Work-to-Go
This chart illustrates, for normal tasks and milestones, the completed activities vs. work-to-go activities over the total work planned (grey area) . It also shows the portion of work-to-go that is critical (orange line).
Chart 3
|  | Chart 4 | [15 empty] | This chart illustrates, for normal tasks and milestones, the completed activities vs. work-to-go activities over the total work planned (grey area) . It also shows the portion of work-to-go that is critical (orange line). It is the same as the previous chart, exept that the normal tasks and milestones are represented by clustered bars, instead of stacked bars.
The benefit of this chart is that it helps the reader to visualize more directly the longest path activities (orange line) as a proportion of the work-to-go activities (blue bars).
Purpose of the Workload and Schedule Hygiene Charts The primary purpose of this suite of charts is to visualize execution capacity, identify unrealistic future planning (the "bow wave" effect), and diagnose schedule maintenance issues. By mapping historical throughput against future scheduled work and the critical path, these charts tell a story about schedule realism and team capacity.
1. Historical Throughput vs. Future Demand By showing the historical volume of tasks (gray) or completed tasks (green) alongside the "To-Go" future work (blue), the charts answer a critical feasibility question: Is the volume of work we are planning to do next month realistically aligned with the volume of work we have proven we can complete in past months?
2. The "Bow Wave" Indicator In all of these charts, there is a massive spike of blue "To-Go" work immediately following the current status date (mid-2025). This indicates a "bow wave"—where uncompleted work from the past hasn't been properly spread out, but instead simply pushed into the immediate next month. This is a classic leading indicator of an unrealistic, overly optimistic schedule.
3. Longest Path (Critical Path) Density The orange line isolates the "Longest Path" tasks relative to the total volume of work. This helps management see whether the upcoming bottleneck is due to a massive volume of parallel work (resource constraint) or a dense sequence of critical path tasks (schedule logic constraint).
The Nuance Between the Charts
Chart 1 vs. Chart 2: Work-to-Go (Normal Tasks)
Focus: These charts strip away historical completions to focus purely on the shape of the total task baseline (gray) versus what remains (blue) and what is critical (orange).
The Nuance: Chart 1 uses a solid blue line for "To-Go" work, which emphasizes the continuous trend and shape of the bow wave. Chart 2 uses blue bars, which is often preferred for discrete monthly data because it makes it much easier to see the exact concentration of individual tasks scheduled for a specific month.
Chart 3 vs. Chart 4: Completed vs. Work-to-Go Tasks
Focus: These charts add historical context, layering Completed Tasks (green) against the Total Tasks (gray area) to demonstrate the project's actual historical "burn rate" or throughput capability.
The Nuance (Schedule Hygiene): The critical difference between these two charts lies in how past data is handled leading up to the status date.
In Chart 3: The green bars perfectly match the gray background up to the current date. This means schedule hygiene is "clean"—all work scheduled in the past was either completed, or formally moved into the future (creating the huge blue spike).
In Chart 4: Look closely at the months just prior to the status date (late 2024/early 2025). The green bars (completed) fall significantly short of the gray area (total scheduled), and there are tiny slivers of blue "To-Go" tasks sitting in the past. This reveals poor schedule hygiene: there is past-due work that hasn't been statused, completed, or formally re-planned into the future. It indicates the schedule is technically out of date or "broken" prior to the current status date.
Why It’s Useful This visualization suite is used by project managers and reviewers to:
Challenge schedule realism: Spot immediate resource bottlenecks caused by deferring too much work to the near term.
Audit schedule maintenance: Identify past-due activities left lingering in the past (as seen in Chart 4).
Assess risk: See if the team is being asked to perform at a throughput rate they have never historically achieved.

## G2&G3_BowWave_2025MAR
Baseline Activities & Workoff Burden (First Look)
GRAPH 2 and GRAPH 3 metrics can be copied and pasted into the table directly from the Acumen Fuse MS Excel output to generate the charts to the right.
Add/delete columns as necessary to fit the data exported from Acumen Fuse.
| * | Yellow rows are calculated in the MS Excel sheet from the Acumen Fuse data in the rows above.
| Phase Analysis | Phase Analysis | [245 empty] | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis |  | Phase Analysis
| Primary Formula Analysis | Primary Formula Analysis | [245 empty] | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis |  | Primary Formula Analysis
[248 empty] | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line |  | Time Line | 106
GRAPH 2 |  | 2025-03-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | [150 empty] | Y-axis (max)
| Phase Analyzer | Baselined to Start | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 5 | 10 | 4 | 2 | 3 | 1 | 3 | 10 | 9 | 8 | 11 | 19 | 13 | 6 | 7 | 2 | 0 | 0 | 4 | 11 | 5 | 19 | 24 | 34 | 26 | 19 | 21 | 60 | 29 | 18 | 28 | 38 | 33 | 50 | 34 | 30 | 74 | 65 | 59 | 57 | 46 | 58 | 63 | 69 | 50 | 49 | 58 | 44 | 52 | 13 | 34 | 34 | 41 | 30 | 43 | 57 | 59 | 29 | 28 | 36 | 74 | 47 | 46 | 90 | 80 | 88 | 38 | 85 | 53 | 53 | 34 | 10 | 32 | 33 | 11 | 7 | 7 | 1 | 1 | 1 | 5 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 90
|  | Scheduled to Start | 8 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 4 | 5 | 4 | 7 | 3 | 2 | 3 | 7 | 4 | 7 | 9 | 21 | 14 | 3 | 6 | 2 | 1 | 0 | 4 | 11 | 6 | 24 | 25 | 26 | 24 | 29 | 24 | 52 | 31 | 18 | 14 | 17 | 29 | 37 | 35 | 27 | 61 | 54 | 39 | 31 | 47 | 43 | 36 | 76 | 48 | 45 | 42 | 45 | 40 | 43 | 35 | 27 | 46 | 34 | 34 | 60 | 71 | 34 | 35 | 63 | 61 | 59 | 40 | 49 | 52 | 39 | 22 | 42 | 33 | 56 | 42 | 36 | 56 | 82 | 70 | 55 | 47 | 24 | 12 | 26 | 19 | 19 | 25 | 8 | 6 | 1 | 2 | 0 | 2 | 0 | 0 | [150 empty] | 82
|  | Actual Starts | 8 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 4 | 5 | 4 | 7 | 3 | 2 | 3 | 7 | 4 | 7 | 9 | 21 | 14 | 3 | 6 | 2 | 1 | 0 | 4 | 11 | 6 | 24 | 25 | 26 | 24 | 29 | 24 | 52 | 31 | 18 | 14 | 17 | 29 | 37 | 35 | 27 | 61 | 54 | 39 | 31 | 47 | 43 | 36 | 76 | 48 | 45 | 42 | 45 | 40 | 43 | 35 | 27 | 46 | 34 | 34 | 60 | 71 | 34 | 35 | 63 | 61 | 59 | 40 | 49 | 52 | 39 | 22 | 42 | 33 | 56 | 42 | 36 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 76
|  | Baselined to Finish | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 10 | 5 | 1 | 3 | 1 | 3 | 8 | 8 | 8 | 8 | 14 | 11 | 5 | 13 | 5 | 0 | 2 | 3 | 8 | 5 | 12 | 25 | 29 | 26 | 20 | 11 | 30 | 13 | 20 | 40 | 36 | 38 | 58 | 36 | 38 | 61 | 62 | 60 | 56 | 51 | 62 | 64 | 60 | 52 | 62 | 53 | 49 | 41 | 15 | 55 | 27 | 19 | 33 | 43 | 46 | 51 | 44 | 45 | 39 | 63 | 49 | 56 | 81 | 78 | 106 | 58 | 90 | 47 | 50 | 37 | 16 | 31 | 31 | 16 | 8 | 2 | 3 | 6 | 2 | 2 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 106
|  | Scheduled to Finish | 7 | 1 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 6 | 5 | 6 | 3 | 1 | 3 | 2 | 6 | 7 | 7 | 14 | 12 | 4 | 10 | 5 | 1 | 2 | 3 | 8 | 6 | 17 | 26 | 28 | 21 | 28 | 13 | 19 | 17 | 19 | 24 | 16 | 24 | 44 | 33 | 30 | 59 | 73 | 41 | 23 | 42 | 35 | 30 | 70 | 49 | 41 | 51 | 42 | 47 | 43 | 36 | 27 | 29 | 27 | 39 | 60 | 59 | 37 | 49 | 77 | 70 | 56 | 43 | 47 | 45 | 55 | 31 | 31 | 30 | 60 | 47 | 38 | 61 | 95 | 63 | 67 | 48 | 33 | 17 | 31 | 17 | 16 | 29 | 10 | 3 | 3 | 3 | 0 | 2 | 1 | 0 | [150 empty] | 95
|  | Actual Finishes | 7 | 1 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 6 | 5 | 6 | 3 | 1 | 3 | 2 | 6 | 7 | 7 | 14 | 12 | 4 | 10 | 5 | 1 | 2 | 3 | 8 | 6 | 17 | 26 | 28 | 21 | 28 | 13 | 19 | 17 | 19 | 24 | 16 | 24 | 44 | 33 | 30 | 59 | 73 | 41 | 23 | 42 | 35 | 30 | 70 | 49 | 41 | 51 | 42 | 47 | 43 | 36 | 27 | 29 | 27 | 39 | 60 | 59 | 37 | 49 | 77 | 70 | 56 | 43 | 47 | 45 | 55 | 31 | 31 | 30 | 60 | 47 | 38 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 77
|  | Started Delayed (<=30 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 6 | 2 | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | N/A | 0 | 0 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 4 | 4 | 4 | 1 | 3 | 0 | 2 | 2 | 2 | 1 | 7 | 1 | 1 | 11 | 13 | 9 | 6 | 1 | 5 | 10 | 20 | 2 | 1 | 8 | 6 | 4 | 0 | 1 | 3 | 6 | 1 | 1 | 7 | 3 | 2 | 2 | 2 | 9 | 0 | 3 | 4 | 4 | 7 | 2 | 2 | 0 | 2 | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 20
|  | Started Delayed (Between 31 to 60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 2 | 1 | N/A | N/A | N/A | N/A | 3 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 2 | 3 | 0 | 1 | 4 | 1 | 0 | 1 | 3 | 1 | 0 | 1 | 3 | 1 | 9 | 1 | 1 | 10 | 10 | 5 | 5 | 7 | 12 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 2 | 4 | 1 | 2 | 1 | 3 | 0 | 10 | 1 | 3 | 1 | 3 | 4 | 2 | 3 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 12
|  | Started Delayed (>60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | N/A | N/A | N/A | N/A | 0 | 6 | 3 | 4 | N/A | 1 | 4 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 5 | 2 | 13 | 19 | 9 | 21 | 12 | 10 | 36 | 21 | 30 | 39 | 22 | 20 | 30 | 20 | 15 | 25 | 34 | 28 | 39 | 7 | 23 | 22 | 10 | 6 | 14 | 22 | 20 | 10 | 10 | 11 | 19 | 22 | 19 | 42 | 45 | 35 | 12 | 7 | 4 | 4 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 45
|  | Completed Delayed (<=30 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 5 | 3 | N/A | 1 | N/A | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 2 | 6 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 15 | 2 | 1 | 8 | 14 | 9 | 4 | 6 | 5 | 14 | 21 | 14 | 6 | 9 | 7 | 7 | 0 | 0 | 5 | 1 | 1 | 2 | 7 | 7 | 4 | 4 | 2 | 6 | 0 | 1 | 6 | 8 | 8 | 2 | 3 | 0 | 2 | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 21
|  | Completed Delayed (Between 31 to 60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 3 | 1 | N/A | 0 | N/A | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 1 | 3 | 1 | 1 | 7 | 1 | 2 | 2 | 4 | 4 | 1 | 1 | 3 | 5 | 2 | 1 | 5 | 5 | 8 | 2 | 1 | 7 | 16 | 8 | 7 | 4 | 1 | 1 | 0 | 0 | 6 | 3 | 4 | 3 | 8 | 4 | 0 | 0 | 3 | 6 | 8 | 3 | 4 | 1 | 2 | 4 | 1 | 3 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 16
|  | Completed Delayed (>60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 5 | 4 | 4 | 1 | 1 | 2 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 16 | 18 | 14 | 19 | 19 | 13 | 19 | 25 | 32 | 35 | 28 | 38 | 34 | 19 | 15 | 19 | 31 | 30 | 21 | 9 | 46 | 16 | 9 | 16 | 11 | 25 | 23 | 13 | 13 | 10 | 18 | 20 | 19 | 35 | 36 | 47 | 22 | 6 | 5 | 5 | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 47
GRAPH 3 |  | BEI - Starts | [80 empty] | 0.87 | 0.85 | 0.85 | 0.85 | 0.86 | 0.87 | 0.88
|  | BEI - Finishes | [80 empty] | 0.85 | 0.84 | 0.84 | 0.83 | 0.85 | 0.86 | 0.87
|  | HMI - Starts | [81 empty] | 0.02 | 0.02 | 0.04 | 0.03 | 0.08 | 0.06
|  | HMI - Finishes | [81 empty] | 0.01 | 0.04 | 0.02 | 0 | 0 | 0
|  | CEI - Starts | [81 empty] | 0.31 | 0.51 | 0.43 | 0.41 | 0.52 | 0.61
|  | CEI - Finishes | [81 empty] | 0.3 | 0.42 | 0.35 | 0.47 | 0.58 | 0.57
|  | Status Date (6-mo interval) | [80 empty] | 125 | [5 empty] | 125 | [5 empty] | 125
*Cumulative Calculations |  | Baselined to Start - Cumulative | 1 | 1 | 1 | 2 | 2 | 2 | 4 | 7 | 9 | 10 | 13 | 16 | 18 | 20 | 25 | 35 | 39 | 41 | 44 | 45 | 48 | 58 | 67 | 75 | 86 | 105 | 118 | 124 | 131 | 133 | 133 | 133 | 137 | 148 | 153 | 172 | 196 | 230 | 256 | 275 | 296 | 356 | 385 | 403 | 431 | 469 | 502 | 552 | 586 | 616 | 690 | 755 | 814 | 871 | 917 | 975 | 1038 | 1107 | 1157 | 1206 | 1264 | 1308 | 1360 | 1373 | 1407 | 1441 | 1482 | 1512 | 1555 | 1612 | 1671 | 1700 | 1728 | 1764 | 1838 | 1885 | 1931 | 2021 | 2101 | 2189 | 2227 | 2312 | 2365 | 2418 | 2452 | 2462 | 2494 | 2527 | 2538 | 2545 | 2552 | 2553 | 2554 | 2555 | 2560 | 2565 | 2566 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567
|  | Scheduled to Start - Cumulative | 8 | 8 | 8 | 9 | 9 | 9 | 11 | 14 | 16 | 17 | 20 | 23 | 25 | 27 | 31 | 36 | 40 | 47 | 50 | 52 | 55 | 62 | 66 | 73 | 82 | 103 | 117 | 120 | 126 | 128 | 129 | 129 | 133 | 144 | 150 | 174 | 199 | 225 | 249 | 278 | 302 | 354 | 385 | 403 | 417 | 434 | 463 | 500 | 535 | 562 | 623 | 677 | 716 | 747 | 794 | 837 | 873 | 949 | 997 | 1042 | 1084 | 1129 | 1169 | 1212 | 1247 | 1274 | 1320 | 1354 | 1388 | 1448 | 1519 | 1553 | 1588 | 1651 | 1712 | 1771 | 1811 | 1860 | 1912 | 1951 | 1973 | 2015 | 2048 | 2104 | 2146 | 2182 | 2238 | 2320 | 2390 | 2445 | 2492 | 2516 | 2528 | 2554 | 2573 | 2592 | 2617 | 2625 | 2631 | 2632 | 2634 | 2634 | 2636 | 2636 | 2636
|  | Actual Starts - Cumulative | 8 | 8 | 8 | 9 | 9 | 9 | 11 | 14 | 16 | 17 | 20 | 23 | 25 | 27 | 31 | 36 | 40 | 47 | 50 | 52 | 55 | 62 | 66 | 73 | 82 | 103 | 117 | 120 | 126 | 128 | 129 | 129 | 133 | 144 | 150 | 174 | 199 | 225 | 249 | 278 | 302 | 354 | 385 | 403 | 417 | 434 | 463 | 500 | 535 | 562 | 623 | 677 | 716 | 747 | 794 | 837 | 873 | 949 | 997 | 1042 | 1084 | 1129 | 1169 | 1212 | 1247 | 1274 | 1320 | 1354 | 1388 | 1448 | 1519 | 1553 | 1588 | 1651 | 1712 | 1771 | 1811 | 1860 | 1912 | 1951 | 1973 | 2015 | 2048 | 2104 | 2146 | 2182 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224 | 2224
|  | Baselined to Finish - Cumulative | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 6 | 9 | 10 | 13 | 14 | 16 | 19 | 22 | 32 | 37 | 38 | 41 | 42 | 45 | 53 | 61 | 69 | 77 | 91 | 102 | 107 | 120 | 125 | 125 | 127 | 130 | 138 | 143 | 155 | 180 | 209 | 235 | 255 | 266 | 296 | 309 | 329 | 369 | 405 | 443 | 501 | 537 | 575 | 636 | 698 | 758 | 814 | 865 | 927 | 991 | 1051 | 1103 | 1165 | 1218 | 1267 | 1308 | 1323 | 1378 | 1405 | 1424 | 1457 | 1500 | 1546 | 1597 | 1641 | 1686 | 1725 | 1788 | 1837 | 1893 | 1974 | 2052 | 2158 | 2216 | 2306 | 2353 | 2403 | 2440 | 2456 | 2487 | 2518 | 2534 | 2542 | 2544 | 2547 | 2553 | 2555 | 2557 | 2563 | 2566 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567 | 2567
|  | Scheduled to Finish - Cumulative | 7 | 8 | 8 | 8 | 8 | 8 | 10 | 13 | 16 | 17 | 20 | 21 | 23 | 26 | 28 | 34 | 39 | 45 | 48 | 49 | 52 | 54 | 60 | 67 | 74 | 88 | 100 | 104 | 114 | 119 | 120 | 122 | 125 | 133 | 139 | 156 | 182 | 210 | 231 | 259 | 272 | 291 | 308 | 327 | 351 | 367 | 391 | 435 | 468 | 498 | 557 | 630 | 671 | 694 | 736 | 771 | 801 | 871 | 920 | 961 | 1012 | 1054 | 1101 | 1144 | 1180 | 1207 | 1236 | 1263 | 1302 | 1362 | 1421 | 1458 | 1507 | 1584 | 1654 | 1710 | 1753 | 1800 | 1845 | 1900 | 1931 | 1962 | 1992 | 2052 | 2099 | 2137 | 2198 | 2293 | 2356 | 2423 | 2471 | 2504 | 2521 | 2552 | 2569 | 2585 | 2614 | 2624 | 2627 | 2630 | 2633 | 2633 | 2635 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636 | 2636
|  | Actual Finishes - Cumulative | 7 | 8 | 8 | 8 | 8 | 8 | 10 | 13 | 16 | 17 | 20 | 21 | 23 | 26 | 28 | 34 | 39 | 45 | 48 | 49 | 52 | 54 | 60 | 67 | 74 | 88 | 100 | 104 | 114 | 119 | 120 | 122 | 125 | 133 | 139 | 156 | 182 | 210 | 231 | 259 | 272 | 291 | 308 | 327 | 351 | 367 | 391 | 435 | 468 | 498 | 557 | 630 | 671 | 694 | 736 | 771 | 801 | 871 | 920 | 961 | 1012 | 1054 | 1101 | 1144 | 1180 | 1207 | 1236 | 1263 | 1302 | 1362 | 1421 | 1458 | 1507 | 1584 | 1654 | 1710 | 1753 | 1800 | 1845 | 1900 | 1931 | 1962 | 1992 | 2052 | 2099 | 2137 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190 | 2190
|  | HMI Starts - 3-mo Rolling Average | [81 empty] | 0.02 | 0.02 | 0.026667 | 0.03 | 0.05 | 0.056667 | [18 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | HMI Finishes - 3-mo Rolling Average | [81 empty] | 0.01 | 0.025 | 0.023333 | 0.02 | 0.0066667 | 0 | [18 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | CEI Starts - 3-mo Rolling Average | [81 empty] | 0.31 | 0.41 | 0.41667 | 0.45 | 0.45333 | 0.51333 | [18 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | CEI Finishes - 3-mo Rolling Average | [81 empty] | 0.3 | 0.36 | 0.35667 | 0.41333 | 0.46667 | 0.54 | [18 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
*** |  | Note: Place the max y-axis value in the columns for the status date, as well as 6 months before and after to show the 6-month intervals on the chart.
[259 empty] | Purpose of the Activity Starts Chart The primary purpose of this chart is to diagnose schedule execution health over time, rather than simply reporting dates. It provides a multi-dimensional view of schedule performance through four key lenses: | Purpose of the Cumulative Activity Starts Chart The primary purpose of this chart is to connect near-term execution performance with long-term delivery outcomes by combining monthly start behavior with cumulative progress tracking. It provides insight into overall execution flow and schedule credibility through four key lenses:
[259 empty] | 1. Plan vs. Reality Alignment By comparing the baseline plan (dark grey bars), the current schedule (orange bars), and actual execution (green bars), the chart answers a fundamental question: Are we doing what we said we would do, when we said we would do it? | 1. Link Execution to Overall Progress The cumulative lines (baseline, scheduled, actual) show how work is building over time, rather than just what is happening month to month. This big-picture view helps answer a critical question: Are we actually delivering the total scope at the pace we originally planned?
[259 empty] | 2. Timeliness of Execution The background area charts break out delayed starts by severity (<=30 days, 31-60 days, and >60 days). This highlights whether work is starting on time or slipping—and how serious those slips are. It measures schedule discipline rather than just the total volume of work. | 2. Reveal Whether Delays Are Being Recovered or Absorbed By pairing the delay distribution areas (late starts) with the cumulative curves, the chart shows the true impact of schedule slips. It makes it easy to see whether short-term delays are:
[259 empty] | 3. Leading Indicators of Schedule Performance The line graphs tracking indices like BEI (Baseline Execution Index), CEI (Current Execution Index), and HMI (Hit or Miss Index) serve as early warning metrics. Instead of waiting for downstream delays to become apparent, these trends show whether near-term commitments and start performance are moving in a healthy direction. | Being recovered later in the timeline, or
Turning into permanent, unrecoverable gaps between planned and actual progress.
4. Trend Visibility Across Status Periods Plotted over a two-year timeline with regular status markers (vertical dashed lines), the chart allows stakeholders to see whether performance is improving, degrading, or staying flat, which is critical for timely management action.
3. Assess Schedule Credibility Over the Full Timeline Comparing the cumulative baseline (light orange line) against the current schedule (yellow line) and actuals (dark blue line) helps determine the realism of the current plan. It highlights whether the schedule is:
Why It’s Useful This visualization is a vital tool for project controls, schedulers, and leadership to:
Still aligned with the original baseline expectations, or
[259 empty] | Spot systemic execution issues early (e.g., a growing wave of chronic late starts). | Drifting over time (i.e., continually rephasing and pushing work into the future instead of executing it).
Assess schedule realism vs. optimism by comparing scheduled work against historical actuals.
[259 empty] | Evaluate short-term commitment reliability using the execution indices. | 4. Evaluate Throughput vs. Backlog Buildup The chart contrasts the monthly bars (planned vs. actual starts) with the cumulative lines to reveal how unmet work is handled. It shows whether missed activities are:
Support data-driven decisions regarding corrective actions, replanning, or risk mitigation.
Catching up in subsequent months, or
Creating a growing backlog (a "bow wave" of deferred work). This gives leadership deep insight into actual execution capacity and team throughput, not just punctuality.

## G2&G3_BowWave_2024SEP
Baseline Activities & Workoff Burden (6-Month Delta Look)
Note: Running the "Bow Wave" chart again 6 months later is a crucial diagnostic technique used to test management accountability and schedule reality.
It answers a fundamental question: Did the team actually execute the deferred work, or did they simply push the problem further down the road?
If a follow-up chart shows that the massive spike of near-term "To-Go" work has simply shifted 6 months to the right (a phenomenon known as "rolling the bow wave"), it proves that the project is suffering from chronic execution failure and continuous unrealistic planning.
Conversely, if the follow-up chart shows a smoothed future curve and a higher volume of historical actuals, it validates that the team either successfully burned down their schedule debt or formally replanned the baseline to reflect a realistic throughput capacity.
| Phase Analysis | Phase Analysis | [245 empty] | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis |  | Phase Analysis
| Primary Formula Analysis | Primary Formula Analysis | [245 empty] | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis |  | Primary Formula Analysis
[248 empty] | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line |  | Time Line | 107
GRAPH 1 |  | 2024-09-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | [150 empty] | Y-axis (max)
|  | Baselined to Start | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 5 | 10 | 4 | 2 | 3 | 1 | 3 | 10 | 9 | 8 | 11 | 19 | 13 | 6 | 7 | 2 | 0 | 0 | 4 | 11 | 5 | 19 | 24 | 34 | 26 | 19 | 21 | 60 | 29 | 18 | 28 | 38 | 33 | 50 | 34 | 30 | 74 | 65 | 59 | 57 | 47 | 58 | 63 | 69 | 50 | 49 | 58 | 44 | 52 | 13 | 34 | 34 | 41 | 30 | 43 | 57 | 60 | 31 | 28 | 36 | 75 | 47 | 46 | 89 | 81 | 90 | 39 | 87 | 52 | 52 | 35 | 10 | 30 | 26 | 8 | 7 | 1 | 1 | 1 | 1 | 4 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 90
|  | Scheduled to Start | 4 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 4 | 5 | 4 | 7 | 3 | 2 | 3 | 7 | 4 | 7 | 9 | 21 | 14 | 3 | 6 | 2 | 1 | 0 | 4 | 11 | 6 | 24 | 25 | 26 | 24 | 29 | 24 | 52 | 31 | 18 | 14 | 17 | 29 | 37 | 35 | 27 | 61 | 54 | 39 | 31 | 47 | 43 | 36 | 76 | 48 | 45 | 42 | 45 | 40 | 43 | 35 | 27 | 46 | 34 | 34 | 60 | 71 | 34 | 35 | 63 | 61 | 59 | 40 | 49 | 46 | 35 | 25 | 70 | 63 | 71 | 80 | 59 | 51 | 69 | 37 | 43 | 18 | 9 | 1 | 1 | 11 | 12 | 10 | 7 | 21 | 2 | 3 | 1 | 0 | 1 | 1 | [150 empty] | 80
|  | Actual Starts | 4 | 0 | 0 | 1 | 0 | 0 | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 4 | 5 | 4 | 7 | 3 | 2 | 3 | 7 | 4 | 7 | 9 | 21 | 14 | 3 | 6 | 2 | 1 | 0 | 4 | 11 | 6 | 24 | 25 | 26 | 24 | 29 | 24 | 52 | 31 | 18 | 14 | 17 | 29 | 37 | 35 | 27 | 61 | 54 | 39 | 31 | 47 | 43 | 36 | 76 | 48 | 45 | 42 | 45 | 40 | 43 | 35 | 27 | 46 | 34 | 34 | 60 | 71 | 34 | 35 | 63 | 61 | 59 | 40 | 49 | 46 | 35 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 76
|  | Baselined to Finish | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 3 | 10 | 5 | 1 | 3 | 1 | 3 | 8 | 8 | 8 | 8 | 14 | 11 | 5 | 13 | 5 | 0 | 2 | 3 | 8 | 5 | 12 | 25 | 29 | 26 | 20 | 11 | 30 | 13 | 20 | 40 | 36 | 38 | 58 | 36 | 38 | 61 | 62 | 60 | 56 | 52 | 62 | 64 | 60 | 52 | 62 | 53 | 49 | 41 | 15 | 55 | 27 | 19 | 33 | 43 | 46 | 51 | 46 | 46 | 39 | 64 | 49 | 56 | 80 | 79 | 107 | 60 | 92 | 46 | 49 | 38 | 16 | 29 | 25 | 12 | 8 | 2 | 1 | 2 | 2 | 2 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 107
|  | Scheduled to Finish | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 6 | 5 | 6 | 3 | 1 | 3 | 2 | 6 | 7 | 7 | 14 | 12 | 4 | 10 | 5 | 1 | 2 | 3 | 8 | 6 | 17 | 26 | 28 | 21 | 28 | 13 | 19 | 17 | 19 | 24 | 16 | 24 | 44 | 33 | 30 | 59 | 73 | 41 | 23 | 42 | 35 | 30 | 70 | 49 | 41 | 51 | 42 | 47 | 43 | 36 | 27 | 29 | 27 | 39 | 60 | 59 | 37 | 49 | 77 | 70 | 56 | 43 | 47 | 42 | 50 | 31 | 69 | 63 | 79 | 89 | 59 | 55 | 70 | 49 | 45 | 22 | 11 | 2 | 1 | 10 | 9 | 13 | 8 | 19 | 3 | 3 | 2 | 0 | 1 | 2 | [150 empty] | 89
|  | Actual Finishes | 3 | 1 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 6 | 5 | 6 | 3 | 1 | 3 | 2 | 6 | 7 | 7 | 14 | 12 | 4 | 10 | 5 | 1 | 2 | 3 | 8 | 6 | 17 | 26 | 28 | 21 | 28 | 13 | 19 | 17 | 19 | 24 | 16 | 24 | 44 | 33 | 30 | 59 | 73 | 41 | 23 | 42 | 35 | 30 | 70 | 49 | 41 | 51 | 42 | 47 | 43 | 36 | 27 | 29 | 27 | 39 | 60 | 59 | 37 | 49 | 77 | 70 | 56 | 43 | 47 | 42 | 50 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [150 empty] | 77
|  | Started Delayed (<=30 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 6 | 2 | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | N/A | 0 | 0 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 4 | 4 | 4 | 1 | 3 | 0 | 2 | 2 | 2 | 1 | 7 | 1 | 1 | 11 | 13 | 9 | 6 | 1 | 5 | 10 | 20 | 2 | 1 | 8 | 6 | 4 | 0 | 1 | 3 | 6 | 1 | 1 | 7 | 3 | 2 | 2 | 2 | 9 | 0 | 3 | 4 | 3 | 7 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 20
|  | Started Delayed (Between 31 to 60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 2 | 1 | N/A | N/A | N/A | N/A | 3 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 2 | 3 | 0 | 1 | 4 | 1 | 0 | 1 | 3 | 1 | 0 | 1 | 3 | 1 | 9 | 1 | 1 | 10 | 10 | 5 | 5 | 7 | 12 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 2 | 4 | 1 | 2 | 1 | 3 | 0 | 8 | 1 | 3 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 12
|  | Started Delayed (>60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | N/A | N/A | N/A | N/A | 0 | 6 | 3 | 4 | N/A | 1 | 4 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 5 | 2 | 13 | 19 | 9 | 21 | 12 | 10 | 36 | 21 | 30 | 37 | 20 | 19 | 30 | 20 | 15 | 24 | 33 | 26 | 39 | 7 | 22 | 22 | 10 | 6 | 13 | 20 | 12 | 7 | 9 | 11 | 4 | 7 | 1 | 10 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 39
|  | Completed Delayed (<=30 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 5 | 3 | N/A | 1 | N/A | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 2 | 6 | 2 | 3 | 2 | 1 | 1 | 3 | 1 | 2 | 15 | 2 | 1 | 8 | 14 | 9 | 4 | 6 | 5 | 14 | 21 | 14 | 6 | 9 | 7 | 7 | 0 | 0 | 5 | 1 | 1 | 2 | 7 | 7 | 4 | 4 | 2 | 6 | 0 | 1 | 6 | 8 | 8 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 21
|  | Completed Delayed (Between 31 to 60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 3 | 1 | N/A | 0 | N/A | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | 1 | 3 | 1 | 1 | 7 | 1 | 2 | 2 | 4 | 4 | 1 | 1 | 3 | 5 | 2 | 1 | 5 | 5 | 8 | 2 | 1 | 7 | 16 | 8 | 7 | 4 | 1 | 1 | 0 | 0 | 6 | 3 | 4 | 3 | 8 | 4 | 0 | 0 | 3 | 6 | 7 | 3 | 3 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 16
|  | Completed Delayed (>60 days) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 5 | 4 | 4 | 1 | 1 | 2 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | N/A | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 16 | 18 | 14 | 19 | 19 | 13 | 19 | 25 | 32 | 33 | 27 | 35 | 34 | 19 | 15 | 18 | 30 | 25 | 21 | 9 | 45 | 16 | 9 | 15 | 11 | 22 | 16 | 8 | 11 | 10 | 6 | 7 | 1 | 8 | 2 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [150 empty] | 45
GRAPH 2 |  | BEI - Starts | [80 empty] | 0.87 | 0.85 | 0.85 | 0.85 | 0.86 | 0.87 | 0.88
|  | BEI - Finishes | [80 empty] | 0.85 | 0.84 | 0.84 | 0.83 | 0.85 | 0.86 | 0.87
|  | HMI - Starts | [81 empty] | 0.02 | 0.02 | 0.04
|  | HMI - Finishes | [81 empty] | 0.01 | 0.04 | 0.02
|  | CEI - Starts | [81 empty] | 0.31 | 0.51 | 0.43
|  | CEI - Finishes | [81 empty] | 0.3 | 0.42 | 0.35
*** |  | Status Date (6-mo interval) | [74 empty] | 125 | [5 empty] | 125 | [5 empty] | 125
Cumulative Calculations |  | Baselined to Start - Cumulative | 1 | 1 | 1 | 2 | 2 | 2 | 4 | 7 | 9 | 10 | 13 | 16 | 18 | 20 | 25 | 35 | 39 | 41 | 44 | 45 | 48 | 58 | 67 | 75 | 86 | 105 | 118 | 124 | 131 | 133 | 133 | 133 | 137 | 148 | 153 | 172 | 196 | 230 | 256 | 275 | 296 | 356 | 385 | 403 | 431 | 469 | 502 | 552 | 586 | 616 | 690 | 755 | 814 | 871 | 918 | 976 | 1039 | 1108 | 1158 | 1207 | 1265 | 1309 | 1361 | 1374 | 1408 | 1442 | 1483 | 1513 | 1556 | 1613 | 1673 | 1704 | 1732 | 1768 | 1843 | 1890 | 1936 | 2025 | 2106 | 2196 | 2235 | 2322 | 2374 | 2426 | 2461 | 2471 | 2501 | 2527 | 2535 | 2542 | 2543 | 2544 | 2545 | 2546 | 2550 | 2555 | 2556 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557
|  | Scheduled to Start - Cumulative | 4 | 4 | 4 | 5 | 5 | 5 | 7 | 10 | 12 | 13 | 16 | 19 | 21 | 23 | 27 | 32 | 36 | 43 | 46 | 48 | 51 | 58 | 62 | 69 | 78 | 99 | 113 | 116 | 122 | 124 | 125 | 125 | 129 | 140 | 146 | 170 | 195 | 221 | 245 | 274 | 298 | 350 | 381 | 399 | 413 | 430 | 459 | 496 | 531 | 558 | 619 | 673 | 712 | 743 | 790 | 833 | 869 | 945 | 993 | 1038 | 1080 | 1125 | 1165 | 1208 | 1243 | 1270 | 1316 | 1350 | 1384 | 1444 | 1515 | 1549 | 1584 | 1647 | 1708 | 1767 | 1807 | 1856 | 1902 | 1937 | 1962 | 2032 | 2095 | 2166 | 2246 | 2305 | 2356 | 2425 | 2462 | 2505 | 2523 | 2532 | 2533 | 2534 | 2545 | 2557 | 2567 | 2574 | 2595 | 2597 | 2600 | 2601 | 2601 | 2602 | 2603
|  | Actual Starts - Cumulative | 4 | 4 | 4 | 5 | 5 | 5 | 7 | 10 | 12 | 13 | 16 | 19 | 21 | 23 | 27 | 32 | 36 | 43 | 46 | 48 | 51 | 58 | 62 | 69 | 78 | 99 | 113 | 116 | 122 | 124 | 125 | 125 | 129 | 140 | 146 | 170 | 195 | 221 | 245 | 274 | 298 | 350 | 381 | 399 | 413 | 430 | 459 | 496 | 531 | 558 | 619 | 673 | 712 | 743 | 790 | 833 | 869 | 945 | 993 | 1038 | 1080 | 1125 | 1165 | 1208 | 1243 | 1270 | 1316 | 1350 | 1384 | 1444 | 1515 | 1549 | 1584 | 1647 | 1708 | 1767 | 1807 | 1856 | 1902 | 1937 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955 | 1955
|  | Baselined to Finish - Cumulative | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 6 | 9 | 10 | 13 | 14 | 16 | 19 | 22 | 32 | 37 | 38 | 41 | 42 | 45 | 53 | 61 | 69 | 77 | 91 | 102 | 107 | 120 | 125 | 125 | 127 | 130 | 138 | 143 | 155 | 180 | 209 | 235 | 255 | 266 | 296 | 309 | 329 | 369 | 405 | 443 | 501 | 537 | 575 | 636 | 698 | 758 | 814 | 866 | 928 | 992 | 1052 | 1104 | 1166 | 1219 | 1268 | 1309 | 1324 | 1379 | 1406 | 1425 | 1458 | 1501 | 1547 | 1598 | 1644 | 1690 | 1729 | 1793 | 1842 | 1898 | 1978 | 2057 | 2164 | 2224 | 2316 | 2362 | 2411 | 2449 | 2465 | 2494 | 2519 | 2531 | 2539 | 2541 | 2542 | 2544 | 2546 | 2548 | 2553 | 2556 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557 | 2557
|  | Scheduled to Finish - Cumulative | 3 | 4 | 4 | 4 | 4 | 4 | 6 | 9 | 12 | 13 | 16 | 17 | 19 | 22 | 24 | 30 | 35 | 41 | 44 | 45 | 48 | 50 | 56 | 63 | 70 | 84 | 96 | 100 | 110 | 115 | 116 | 118 | 121 | 129 | 135 | 152 | 178 | 206 | 227 | 255 | 268 | 287 | 304 | 323 | 347 | 363 | 387 | 431 | 464 | 494 | 553 | 626 | 667 | 690 | 732 | 767 | 797 | 867 | 916 | 957 | 1008 | 1050 | 1097 | 1140 | 1176 | 1203 | 1232 | 1259 | 1298 | 1358 | 1417 | 1454 | 1503 | 1580 | 1650 | 1706 | 1749 | 1796 | 1838 | 1888 | 1919 | 1988 | 2051 | 2130 | 2219 | 2278 | 2333 | 2403 | 2452 | 2497 | 2519 | 2530 | 2532 | 2533 | 2543 | 2552 | 2565 | 2573 | 2592 | 2595 | 2598 | 2600 | 2600 | 2601 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603 | 2603
|  | Actual Finishes - Cumulative | 3 | 4 | 4 | 4 | 4 | 4 | 6 | 9 | 12 | 13 | 16 | 17 | 19 | 22 | 24 | 30 | 35 | 41 | 44 | 45 | 48 | 50 | 56 | 63 | 70 | 84 | 96 | 100 | 110 | 115 | 116 | 118 | 121 | 129 | 135 | 152 | 178 | 206 | 227 | 255 | 268 | 287 | 304 | 323 | 347 | 363 | 387 | 431 | 464 | 494 | 553 | 626 | 667 | 690 | 732 | 767 | 797 | 867 | 916 | 957 | 1008 | 1050 | 1097 | 1140 | 1176 | 1203 | 1232 | 1259 | 1298 | 1358 | 1417 | 1454 | 1503 | 1580 | 1650 | 1706 | 1749 | 1796 | 1838 | 1888 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917 | 1917
*** |  | Note: Place the max y-axis value in the columns for the status date, as well as 6 months before and after to show the 6-month intervals on the chart.
[259 empty] | Purpose of the Activity Starts Chart The primary purpose of this chart is to diagnose schedule execution health over time, rather than simply reporting dates. It provides a multi-dimensional view of schedule performance through four key lenses: | Purpose of the Cumulative Activity Starts Chart The primary purpose of this chart is to connect near-term execution performance with long-term delivery outcomes by combining monthly start behavior with cumulative progress tracking. It provides insight into overall execution flow and schedule credibility through four key lenses:
[259 empty] | 1. Plan vs. Reality Alignment By comparing the baseline plan (dark grey bars), the current schedule (orange bars), and actual execution (green bars), the chart answers a fundamental question: Are we doing what we said we would do, when we said we would do it? | 1. Link Execution to Overall Progress The cumulative lines (baseline, scheduled, actual) show how work is building over time, rather than just what is happening month to month. This big-picture view helps answer a critical question: Are we actually delivering the total scope at the pace we originally planned?
[259 empty] | 2. Timeliness of Execution The background area charts break out delayed starts by severity (<=30 days, 31-60 days, and >60 days). This highlights whether work is starting on time or slipping—and how serious those slips are. It measures schedule discipline rather than just the total volume of work. | 2. Reveal Whether Delays Are Being Recovered or Absorbed By pairing the delay distribution areas (late starts) with the cumulative curves, the chart shows the true impact of schedule slips. It makes it easy to see whether short-term delays are:
[259 empty] | 3. Leading Indicators of Schedule Performance The line graphs tracking indices like BEI (Baseline Execution Index), CEI (Current Execution Index), and HMI (Hit or Miss Index) serve as early warning metrics. Instead of waiting for downstream delays to become apparent, these trends show whether near-term commitments and start performance are moving in a healthy direction. | Being recovered later in the timeline, or
Turning into permanent, unrecoverable gaps between planned and actual progress.
4. Trend Visibility Across Status Periods Plotted over a two-year timeline with regular status markers (vertical dashed lines), the chart allows stakeholders to see whether performance is improving, degrading, or staying flat, which is critical for timely management action.
3. Assess Schedule Credibility Over the Full Timeline Comparing the cumulative baseline (light orange line) against the current schedule (yellow line) and actuals (dark blue line) helps determine the realism of the current plan. It highlights whether the schedule is:
Why It’s Useful This visualization is a vital tool for project controls, schedulers, and leadership to:
Still aligned with the original baseline expectations, or
[259 empty] | Spot systemic execution issues early (e.g., a growing wave of chronic late starts). | Drifting over time (i.e., continually rephasing and pushing work into the future instead of executing it).
Assess schedule realism vs. optimism by comparing scheduled work against historical actuals.
[259 empty] | Evaluate short-term commitment reliability using the execution indices. | 4. Evaluate Throughput vs. Backlog Buildup The chart contrasts the monthly bars (planned vs. actual starts) with the cumulative lines to reveal how unmet work is handled. It shows whether missed activities are:
Support data-driven decisions regarding corrective actions, replanning, or risk mitigation.
Catching up in subsequent months, or
Creating a growing backlog (a "bow wave" of deferred work). This gives leadership deep insight into actual execution capacity and team throughput, not just punctuality.

## G4_Workoff Burden
Baseline Activities & Workoff Burden
Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis | Phase Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis
|  | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line | Time Line
 | time axis 2018-01-01 to 2026-08-01
Phase Analyzer | Current Baseline to Start & Started (BL Plan) | 1 | N/A | N/A | 1 | N/A | N/A | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 4 | 4 | 0 | 2 | 3 | 1 | 3 | 7 | 3 | 5 | 7 | 19 | 12 | 2 | 6 | 2 | N/A | N/A | 4 | 11 | 5 | 18 | 24 | 26 | 20 | 19 | 18 | 52 | 23 | 16 | 13 | 15 | 22 | 23 | 21 | 15 | 33 | 27 | 19 | 11 | 12 | 17 | 16 | 28 | 18 | 8 | 9 | 4 | 11 | 5 | 10 | 8 | 28 | 21 | 24 | 21 | 37 | 13 | 11 | 16 | 26 | 12 | 18 | 14 | 10 | 13 | 2 | 4 | 1 | 2 | 1 | 1 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Future Baseline to Start & Started (Early Starts) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Past Baseline to Start & Started (Workoff Burden) | 1 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 5 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | N/A | 0 | 0 | 1 | 6 | 1 | 0 | 4 | 8 | 5 | 0 | 8 | 1 | 0 | 2 | 7 | 14 | 9 | 11 | 25 | 20 | 17 | 15 | 15 | 23 | 15 | 43 | 26 | 35 | 30 | 40 | 28 | 37 | 24 | 18 | 16 | 11 | 9 | 24 | 29 | 19 | 16 | 36 | 28 | 39 | 18 | 33 | 38 | 24 | 20 | 37 | 31 | 54 | 41 | 23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Past Baseline to Start & Not Started (Workoff Burden) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18 | 67 | 59 | 50 | 42 | 42 | 17 | 11 | 6 | 22 | 16 | 5 | 3 | 0 | 1 | 0 | N/A | 0 | N/A
Phase Analyzer | Future Baseline to Start & Delayed (Workoff Burden) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 5 | 5 | 19 | 3 | 5 | 14 | 9 | 6 | 9 | 4 | 5 | 1 | 1 | N/A | 2 | N/A
Phase Analyzer | Current Baseline to Start & Not Started (Incompletes) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 15 | 9 | 7 | 11 | 24 | 31 | 18 | 66 | 45 | 47 | 32 | 9 | 29 | 26 | 8 | 7 | 1 | 1 | 1 | 1 | 4 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Phase Analyzer | Current Baseline to Finish & Finished (BL Plan) | 1 | N/A | N/A | N/A | N/A | N/A | 2 | 3 | 3 | 1 | 3 | 1 | 2 | 3 | 2 | 5 | 2 | 1 | 3 | 1 | 3 | 2 | 3 | 4 | 4 | 13 | 10 | 3 | 10 | 5 | N/A | 2 | 3 | 8 | 5 | 11 | 25 | 27 | 19 | 19 | 8 | 17 | 10 | 14 | 21 | 12 | 17 | 27 | 15 | 20 | 34 | 28 | 22 | 10 | 14 | 11 | 12 | 21 | 19 | 15 | 7 | 6 | 10 | 4 | 8 | 6 | 9 | 9 | 22 | 13 | 22 | 18 | 17 | 22 | 24 | 12 | 19 | 12 | 11 | 12 | 2 | 3 | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Future Baseline to Finish & Finished (Early Finishes) | 4 | 1 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 8 | 4 | 1 | 7 | 5 | 6 | 10 | 5 | 2 | 1 | 3 | 2 | 0 | 3 | 0 | 2 | 3 | 1 | 19 | 5 | 2 | 5 | 12 | 9 | 10 | 3 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Past Baseline to Finish & Finished (Workoff Burden) | 1 | 0 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 6 | 1 | 0 | 2 | 8 | 4 | 2 | 7 | 4 | 3 | 3 | 7 | 17 | 16 | 10 | 24 | 37 | 15 | 12 | 21 | 19 | 12 | 39 | 25 | 24 | 43 | 33 | 35 | 39 | 25 | 21 | 18 | 15 | 16 | 28 | 32 | 17 | 27 | 43 | 37 | 34 | 21 | 31 | 31 | 41 | 28 | 27 | 29 | 59 | 46 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Phase Analyzer | Past Baseline to Finish & Not Finished (Workoff Burden) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17 | 78 | 65 | 48 | 51 | 44 | 21 | 15 | 9 | 20 | 15 | 7 | 3 | 1 | 0 | 1 | N/A | 0 | 0
Phase Analyzer | Future Baseline to Finish & Delayed (Workoff Burden) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 1 | 2 | 8 | 18 | 5 | 6 | 15 | 7 | 5 | 10 | 6 | 1 | 5 | 0 | N/A | 2 | 1
Phase Analyzer | Current Baseline to Finish & Not Finished (Incompletes) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 3 | 13 | 11 | 9 | 19 | 28 | 31 | 27 | 71 | 38 | 43 | 36 | 16 | 29 | 25 | 12 | 8 | 2 | 1 | 2 | 1 | 2 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Current Baseline to Start & Not Started (Incompletes) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | -1 | 0 | 0 | -3 | -15 | -9 | -7 | -11 | -24 | -31 | -18 | -66 | -45 | -47 | -32 | -9 | -29 | -26 | -8 | -7 | -1 | -1 | -1 | -1 | -4 | -5 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0
| Current Baseline to Finish & Not Finished (Incompletes) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0 | -1 | 0 | -1 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | 0 | -1 | 0 | -1 | -3 | -13 | -11 | -9 | -19 | -28 | -31 | -27 | -71 | -38 | -43 | -36 | -16 | -29 | -25 | -12 | -8 | -2 | -1 | -2 | -1 | -2 | -5 | -3 | -1 | 0 | 0 | 0 | 0 | 0 | 0
Status Date
Purpose of the Baseline Activities & Workoff Burden Chart The primary purpose of this chart is to visualize "schedule debt." It goes beyond simply showing how much work is starting, and instead breaks down the data to reveal whether the project is executing according to its current plan, or struggling under the weight of a deferred backlog (the "workoff burden").
1. Differentiating On-Time Execution vs. Catch-Up Work The bars above the zero line represent work that is starting (or scheduled to start). By splitting these starts into "Current Baseline" (blue bars) and "Past Baseline" (orange bars), the chart reveals the team's true focus. In this specific chart, the orange bars heavily dominate the blue bars, which tells a clear story: the team is spending the vast majority of its capacity catching up on late work, rather than executing the current month's plan.
2. Visualizing Missed Commitments (The Negative Bars) The dashed bars extending below the zero line represent "Incompletes"—activities that were baselined to start in that specific month but failed to do so. This allows management to easily pinpoint exact timeframes where schedule execution broke down (for example, the massive volume of missed starts in October through December 2024).
3. Quantifying the Future "Bow Wave" of Deferred Work Looking forward from the status date (around Feb/Mar 2025), the towering yellow bars represent past baseline work that still hasn't started and has been pushed into the near future. This visually demonstrates how unmet past commitments stack up to create a highly unrealistic, near-term bottleneck of unexecuted work.
4. Tracking Early Starts (or Finishes) and Schedule Agility Though minimal in this specific dataset, the legend includes "Future Baseline to Start & Started" (green). This would indicate working ahead of schedule—a key metric for assessing if a team has the agility to pull work forward when other areas are blocked.
Why It’s Useful This visualization is highly effective for project managers, analysts, and leadership to:
Diagnose "schedule churning": Prove when a team is working hard but only making progress on past-due work.
Highlight severe baseline drift: Visually demonstrate how far the actual execution has decoupled from the original baseline plan.
Challenge future schedule realism: Point to the massive yellow "bow wave" to force a realistic replanning or re-baselining conversation.

## G5_DurationRatioS Curve_2025MAR
Duration Ratio (S-curve)
DIRECTIONS --> | In DRM Metric Library, Sort Activity Browser of "Total Activities - DRM Graph" metric by DRM from smallest to largest, then copy and paste into green columns below. | [11 empty] | Update formulas for Match and DRM to represent appropriate table/column ranges using Row Max. |  |  |  | Adjust x-axis on graph to fit the Max DRM (or as appropriate). Update the graph title for the "n" with the Task Count. Move the boxes according to the x- and y-axis calculations in columns N-Q
[13 empty] | Middle 70% - Lower End | Middle 50% - Lower End | Middle 50% - Upper End | Middle 70% - Upper End
Cum Prob | Id | Description | Baseline Duration | Actual Duration | DRM | Probability | Min DRM | Average DRM | Max DRM | Task Count | Row Max |  | 0.15 | 0.25 | 0.75 | 0.85 | ← | x-axis values for red and green boxes
0.00051414 | 1274 |  | 132 | 1 | 0.0075758 | 0.00051414 | 0.0075758 | 2.0066 | 109.5 | 1945 | 1948 | Target | 0.15 | 0.25 | 0.75 | 0.85
0.0010283 | 2645 |  | 80 | 1 | 0.0125 | 0.00051414 | [5 empty] | Match | 0.15013 | 0.24987 | 0.75013 | 0.84987 |  |  | Purpose of the Duration Ratio Probability Chart The primary purpose of this chart is to evaluate estimating accuracy and diagnose the integrity of schedule status data. By plotting the ratio of Actual Duration to Baseline Duration against its cumulative probability, the chart reveals how realistic the original estimates were and whether project actuals are being recorded honestly.
0.0015424 | 2627 |  | 60 | 1 | 0.016667 | 0.00051414 | [5 empty] | Duration Ratio | 0.75 | 1 | 1.45 | 2.5
0.0020566 | 2642 |  | 60 | 1 | 0.016667 | 0.00051414 | [6 empty] | ↑ | ↑ | ↑ | ↑ |  |  | 1. Assessing Estimating Accuracy vs. Reality The X-axis acts as a benchmark for task performance:
0.0025707 | 3636 |  | 40 | 1 | 0.025 | 0.00051414 | [6 empty] | green box y-axis low value | red box y-axis low value | red box y-axis high value | green box y-axis high value
0.0030848 | 2632 |  | 38 | 1 | 0.026316 | 0.00051414 | [12 empty] | Ratio < 1.0: Tasks finished faster than planned (about 20% of the data here).
0.003599 | 3630 |  | 30 | 1 | 0.033333 | 0.00051414 | [12 empty] | Ratio > 1.0: Tasks took longer than planned (the long tail to the right).
0.0041131 | 4341 |  | 18 | 1 | 0.055556 | 0.00051414 | [12 empty] | Ratio = 1.0: Tasks finished exactly on schedule. This distribution helps answer: Does our estimating process have an optimistic or pessimistic bias?
0.0046272 | 2447 |  | 18 | 1 | 0.055556 | 0.00051414
0.0051414 | 4243 |  | 292 | 18 | 0.061644 | 0.00051414 | [12 empty] | 2. Diagnosing Data Integrity Issues (The Vertical Spike) The most critical feature of this chart is the massive vertical spike right at the 1.0 ratio. Statistically, it is nearly impossible for project execution to be this precise. This vertical jump indicates that roughly 50% of the 1,945 tasks had actual durations that exactly matched their baselined durations. This strongly suggests poor data hygiene—specifically, that the project team is simply "auto-completing" tasks or "backing into" actuals to match the plan, rather than recording true execution times.
0.0056555 | 969 |  | 15 | 1 | 0.066667 | 0.00051414
0.0061697 | 972 |  | 15 | 1 | 0.066667 | 0.00051414 | [12 empty] | 3. Visualizing Core Data Concentration (The Boxes) The red box explicitly frames the middle 50% of the dataset (the interquartile range), while a green box would frame the middle 70%. Because the red box is almost entirely vertical and compressed at the 1.0 mark, it visually reinforces that the vast majority of "typical" tasks are subject to this exact-duration reporting phenomenon, making it a systemic issue rather than an isolated anomaly.
0.0066838 | 4332 |  | 15 | 1 | 0.066667 | 0.00051414
0.0071979 | 4345 |  | 15 | 1 | 0.066667 | 0.00051414 | [12 empty] | 4. Understanding "Tail Risk" in Execution The long, trailing curve to the right (from 1.5 up to 5.0) represents the ~30% of tasks that exceeded their planned durations. While smaller in probability, the shape of this tail shows that when tasks do run late, they can slip significantly—taking 2x, 3x, or even 5x longer than estimated. This helps quantify the severity of schedule risks when things go off-plan.
0.0077121 | 6056 |  | 15 | 1 | 0.066667 | 0.00051414
0.0082262 | 2582 |  | 15 | 1 | 0.066667 | 0.00051414 | [12 empty] | Why It’s Useful This type of statistical chart is a powerful auditing tool for project controls, risk analysts, and leadership to:
0.0087404 | 2462 |  | 15 | 1 | 0.066667 | 0.00051414
0.0092545 | 2463 |  | 15 | 1 | 0.066667 | 0.00051414 | [12 empty] | Spot "fake" actuals: Immediately identify when a team is rubber-stamping their schedule updates instead of tracking real performance.
0.0097686 | 2596 |  | 13 | 1 | 0.076923 | 0.00051414 | [12 empty] | Improve future estimating: Use the historical spread (especially the long tail) to inform more realistic duration modeling and risk contingencies.
0.010283 | 2042 |  | 23 | 2 | 0.086957 | 0.00051414 | [12 empty] | Evaluate systemic biases: Determine if the project suffers from severe optimism bias when tasks deviate from the plan.
0.010797 | 4450 |  | 10 | 1 | 0.1 | 0.00051414
0.011311 | 4009 |  | 30 | 3 | 0.1 | 0.00051414
0.011825 | 3994 |  | 10 | 1 | 0.1 | 0.00051414
0.012339 | 3995 |  | 10 | 1 | 0.1 | 0.00051414
0.012853 | 5564 |  | 10 | 1 | 0.1 | 0.00051414
0.013368 | 5885 |  | 90 | 10 | 0.11111 | 0.00051414
0.013882 | 1778 |  | 9 | 1 | 0.11111 | 0.00051414
0.014396 | 1779 |  | 9 | 1 | 0.11111 | 0.00051414
0.01491 | 5999 |  | 125 | 14 | 0.112 | 0.00051414
0.015424 | 4882 |  | 40 | 5 | 0.125 | 0.00051414
0.015938 | 4115 |  | 8 | 1 | 0.125 | 0.00051414
0.016452 | 4160 |  | 16 | 2 | 0.125 | 0.00051414
0.016967 | 4004 |  | 15 | 2 | 0.13333 | 0.00051414
0.017481 | 5530 |  | 15 | 2 | 0.13333 | 0.00051414
0.017995 | 4015 |  | 15 | 2 | 0.13333 | 0.00051414
0.018509 | 4877 |  | 37 | 5 | 0.13514 | 0.00051414
0.019023 | 2405 |  | 65 | 9 | 0.13846 | 0.00051414
0.019537 | 2410 |  | 85 | 14 | 0.16471 | 0.00051414
0.020051 | 4859 |  | 25 | 5 | 0.2 | 0.00051414
0.020566 | 4861 |  | 25 | 5 | 0.2 | 0.00051414
0.02108 | 4886 |  | 15 | 3 | 0.2 | 0.00051414
0.021594 | 4891 |  | 15 | 3 | 0.2 | 0.00051414
0.022108 | 4864 |  | 10 | 2 | 0.2 | 0.00051414
0.022622 | 5535 |  | 5 | 1 | 0.2 | 0.00051414
0.023136 | 5662 |  | 10 | 2 | 0.2 | 0.00051414
0.02365 | 3976 |  | 15 | 3 | 0.2 | 0.00051414
0.024165 | 5878 |  | 20 | 4 | 0.2 | 0.00051414
0.024679 | 6078 |  | 10 | 2 | 0.2 | 0.00051414
0.025193 | 5770 |  | 5 | 1 | 0.2 | 0.00051414
0.025707 | 5483 |  | 5 | 1 | 0.2 | 0.00051414
0.026221 | 1921 |  | 5 | 1 | 0.2 | 0.00051414
0.026735 | 1930 |  | 5 | 1 | 0.2 | 0.00051414
0.027249 | 1939 |  | 5 | 1 | 0.2 | 0.00051414
0.027763 | 1948 |  | 5 | 1 | 0.2 | 0.00051414
0.028278 | 3996 |  | 10 | 2 | 0.2 | 0.00051414
0.028792 | 4990 |  | 5 | 1 | 0.2 | 0.00051414
0.029306 | 5998 |  | 25 | 5 | 0.2 | 0.00051414
0.02982 | 1627 |  | 5 | 1 | 0.2 | 0.00051414
0.030334 | 2041 |  | 10 | 2 | 0.2 | 0.00051414
0.030848 | 2338 |  | 15 | 3 | 0.2 | 0.00051414
0.031362 | 2339 |  | 5 | 1 | 0.2 | 0.00051414
0.031877 | 6127 |  | 20 | 4 | 0.2 | 0.00051414
0.032391 | 2366 |  | 5 | 1 | 0.2 | 0.00051414
0.032905 | 2356 |  | 15 | 3 | 0.2 | 0.00051414
0.033419 | 2384 |  | 5 | 1 | 0.2 | 0.00051414
0.033933 | 7129 |  | 5 | 1 | 0.2 | 0.00051414
0.034447 | 2357 |  | 5 | 1 | 0.2 | 0.00051414
0.034961 | 2375 |  | 5 | 1 | 0.2 | 0.00051414
0.035476 | 1872 |  | 5 | 1 | 0.2 | 0.00051414
0.03599 | 2348 |  | 5 | 1 | 0.2 | 0.00051414
0.036504 | 1883 |  | 5 | 1 | 0.2 | 0.00051414
0.037018 | 2329 |  | 15 | 3 | 0.2 | 0.00051414
0.037532 | 2330 |  | 5 | 1 | 0.2 | 0.00051414
0.038046 | 4696 |  | 5 | 1 | 0.2 | 0.00051414
0.03856 | 2392 |  | 15 | 3 | 0.2 | 0.00051414
0.039075 | 2393 |  | 5 | 1 | 0.2 | 0.00051414
0.039589 | 2396 |  | 5 | 1 | 0.2 | 0.00051414
0.040103 | 2464 |  | 5 | 1 | 0.2 | 0.00051414
0.040617 | 4893 |  | 37 | 8 | 0.21622 | 0.00051414
0.041131 | 6463 |  | 555 | 124 | 0.22342 | 0.00051414
0.041645 | 3625 |  | 40 | 9 | 0.225 | 0.00051414
0.042159 | 3855 |  | 40 | 9 | 0.225 | 0.00051414
0.042674 | 4355 |  | 13 | 3 | 0.23077 | 0.00051414
0.043188 | 2460 |  | 13 | 3 | 0.23077 | 0.00051414
0.043702 | 3955 |  | 30 | 7 | 0.23333 | 0.00051414
0.044216 | 4849 |  | 40 | 10 | 0.25 | 0.00051414
0.04473 | 4850 |  | 40 | 10 | 0.25 | 0.00051414
0.045244 | 4453 |  | 16 | 4 | 0.25 | 0.00051414
0.045758 | 6518 |  | 4 | 1 | 0.25 | 0.00051414
0.046272 | 3914 |  | 20 | 5 | 0.25 | 0.00051414
0.046787 | 4084 |  | 4 | 1 | 0.25 | 0.00051414
0.047301 | 4219 |  | 4 | 1 | 0.25 | 0.00051414
0.047815 | 1772 |  | 15 | 4 | 0.26667 | 0.00051414
0.048329 | 3858 |  | 75 | 21 | 0.28 | 0.00051414
0.048843 | 3964 |  | 25 | 7 | 0.28 | 0.00051414
0.049357 | 2672 |  | 28 | 8 | 0.28571 | 0.00051414
0.049871 | 4888 |  | 37 | 11 | 0.2973 | 0.00051414
0.050386 | 4305 |  | 30 | 9 | 0.3 | 0.00051414
0.0509 | 4819 |  | 10 | 3 | 0.3 | 0.00051414
0.051414 | 524 |  | 20 | 6 | 0.3 | 0.00051414
0.051928 | 5913 |  | 20 | 6 | 0.3 | 0.00051414
0.052442 | 2644 |  | 65 | 20 | 0.30769 | 0.00051414
0.052956 | 3953 |  | 45 | 14 | 0.31111 | 0.00051414
0.05347 | 4118 |  | 16 | 5 | 0.3125 | 0.00051414
0.053985 | 2340 |  | 16 | 5 | 0.3125 | 0.00051414
0.054499 | 1873 |  | 16 | 5 | 0.3125 | 0.00051414
0.055013 | 1874 |  | 16 | 5 | 0.3125 | 0.00051414
0.055527 | 4887 |  | 37 | 12 | 0.32432 | 0.00051414
0.056041 | 4310 |  | 3 | 1 | 0.33333 | 0.00051414
0.056555 | 3756 |  | 3 | 1 | 0.33333 | 0.00051414
0.057069 | 3765 |  | 3 | 1 | 0.33333 | 0.00051414
0.057584 | 3919 |  | 30 | 10 | 0.33333 | 0.00051414
0.058098 | 4866 |  | 15 | 5 | 0.33333 | 0.00051414
0.058612 | 3787 |  | 3 | 1 | 0.33333 | 0.00051414
0.059126 | 5670 |  | 24 | 8 | 0.33333 | 0.00051414
0.05964 | 3803 |  | 3 | 1 | 0.33333 | 0.00051414
0.060154 | 5751 |  | 6 | 2 | 0.33333 | 0.00051414
0.060668 | 4103 |  | 18 | 6 | 0.33333 | 0.00051414
0.061183 | 2581 |  | 15 | 5 | 0.33333 | 0.00051414
0.061697 | 6950 |  | 3 | 1 | 0.33333 | 0.00051414
0.062211 | 2328 |  | 15 | 5 | 0.33333 | 0.00051414
0.062725 | 624 |  | 15 | 5 | 0.33333 | 0.00051414
0.063239 | 5487 |  | 88 | 30 | 0.34091 | 0.00051414
0.063753 | 2408 |  | 41 | 14 | 0.34146 | 0.00051414
0.064267 | 4892 |  | 37 | 13 | 0.35135 | 0.00051414
0.064781 | 2685 |  | 14 | 5 | 0.35714 | 0.00051414
0.065296 | 2412 |  | 38 | 14 | 0.36842 | 0.00051414
0.06581 | 4832 |  | 40 | 15 | 0.375 | 0.00051414
0.066324 | 2406 |  | 36 | 14 | 0.38889 | 0.00051414
0.066838 | 3678 |  | 5 | 2 | 0.4 | 0.00051414
0.067352 | 4860 |  | 20 | 8 | 0.4 | 0.00051414
0.067866 | 3752 |  | 5 | 2 | 0.4 | 0.00051414
0.06838 | 4896 |  | 15 | 6 | 0.4 | 0.00051414
0.068895 | 4801 |  | 10 | 4 | 0.4 | 0.00051414
0.069409 | 4802 |  | 10 | 4 | 0.4 | 0.00051414
0.069923 | 4810 |  | 10 | 4 | 0.4 | 0.00051414
0.070437 | 4803 |  | 10 | 4 | 0.4 | 0.00051414
0.070951 | 4811 |  | 10 | 4 | 0.4 | 0.00051414
0.071465 | 4814 |  | 10 | 4 | 0.4 | 0.00051414
0.071979 | 6053 |  | 15 | 6 | 0.4 | 0.00051414
0.072494 | 2753 |  | 5 | 2 | 0.4 | 0.00051414
0.073008 | 2754 |  | 5 | 2 | 0.4 | 0.00051414
0.073522 | 2755 |  | 5 | 2 | 0.4 | 0.00051414
0.074036 | 2756 |  | 5 | 2 | 0.4 | 0.00051414
0.07455 | 4008 |  | 10 | 4 | 0.4 | 0.00051414
0.075064 | 5888 |  | 5 | 2 | 0.4 | 0.00051414
0.075578 | 5534 |  | 15 | 6 | 0.4 | 0.00051414
0.076093 | 1611 |  | 5 | 2 | 0.4 | 0.00051414
0.076607 | 1612 |  | 5 | 2 | 0.4 | 0.00051414
0.077121 | 3945 |  | 20 | 8 | 0.4 | 0.00051414
0.077635 | 4012 |  | 15 | 6 | 0.4 | 0.00051414
0.078149 | 2324 |  | 20 | 8 | 0.4 | 0.00051414
0.078663 | 6858 |  | 40 | 16 | 0.4 | 0.00051414
0.079177 | 3845 |  | 23 | 10 | 0.43478 | 0.00051414
0.079692 | 2422 |  | 23 | 10 | 0.43478 | 0.00051414
0.080206 | 2407 |  | 32 | 14 | 0.4375 | 0.00051414
0.08072 | 5980 |  | 36 | 16 | 0.44444 | 0.00051414
0.081234 | 4833 |  | 40 | 18 | 0.45 | 0.00051414
0.081748 | 5717 |  | 11 | 5 | 0.45455 | 0.00051414
0.082262 | 4356 |  | 15 | 7 | 0.46667 | 0.00051414
0.082776 | 3997 |  | 15 | 7 | 0.46667 | 0.00051414
0.08329 | 6672 |  | 15 | 7 | 0.46667 | 0.00051414
0.083805 | 2614 |  | 34 | 16 | 0.47059 | 0.00051414
0.084319 | 3621 |  | 40 | 20 | 0.5 | 0.00051414
0.084833 | 3735 |  | 2 | 1 | 0.5 | 0.00051414
0.085347 | 3736 |  | 2 | 1 | 0.5 | 0.00051414
0.085861 | 3743 |  | 2 | 1 | 0.5 | 0.00051414
0.086375 | 3744 |  | 2 | 1 | 0.5 | 0.00051414
0.086889 | 5089 |  | 2 | 1 | 0.5 | 0.00051414
0.087404 | 3763 |  | 2 | 1 | 0.5 | 0.00051414
0.087918 | 2233 |  | 2 | 1 | 0.5 | 0.00051414
0.088432 | 4799 |  | 10 | 5 | 0.5 | 0.00051414
0.088946 | 4809 |  | 10 | 5 | 0.5 | 0.00051414
0.08946 | 4820 |  | 10 | 5 | 0.5 | 0.00051414
0.089974 | 4812 |  | 10 | 5 | 0.5 | 0.00051414
0.090488 | 4804 |  | 10 | 5 | 0.5 | 0.00051414
0.091003 | 4821 |  | 10 | 5 | 0.5 | 0.00051414
0.091517 | 4813 |  | 10 | 5 | 0.5 | 0.00051414
0.092031 | 4822 |  | 10 | 5 | 0.5 | 0.00051414
0.092545 | 5750 |  | 4 | 2 | 0.5 | 0.00051414
0.093059 | 3326 |  | 4 | 2 | 0.5 | 0.00051414
0.093573 | 3329 |  | 4 | 2 | 0.5 | 0.00051414
0.094087 | 3330 |  | 4 | 2 | 0.5 | 0.00051414
0.094602 | 3933 |  | 10 | 5 | 0.5 | 0.00051414
0.095116 | 6049 |  | 2 | 1 | 0.5 | 0.00051414
0.09563 | 6387 |  | 4 | 2 | 0.5 | 0.00051414
0.096144 | 5758 |  | 4 | 2 | 0.5 | 0.00051414
0.096658 | 5915 |  | 2 | 1 | 0.5 | 0.00051414
0.097172 | 1878 |  | 140 | 70 | 0.5 | 0.00051414
0.097686 | 5752 |  | 6 | 3 | 0.5 | 0.00051414
0.098201 | 6443 |  | 10 | 5 | 0.5 | 0.00051414
0.098715 | 4099 |  | 2 | 1 | 0.5 | 0.00051414
0.099229 | 4109 |  | 4 | 2 | 0.5 | 0.00051414
0.099743 | 3605 |  | 4 | 2 | 0.5 | 0.00051414
0.10026 | 5500 |  | 2 | 1 | 0.5 | 0.00051414
0.10077 | 4141 |  | 12 | 6 | 0.5 | 0.00051414
0.10129 | 6670 |  | 4 | 2 | 0.5 | 0.00051414
0.1018 | 5813 |  | 4 | 2 | 0.5 | 0.00051414
0.10231 | 4152 |  | 2 | 1 | 0.5 | 0.00051414
0.10283 | 7073 |  | 20 | 10 | 0.5 | 0.00051414
0.10334 | 6949 |  | 2 | 1 | 0.5 | 0.00051414
0.10386 | 6948 |  | 2 | 1 | 0.5 | 0.00051414
0.10437 | 6947 |  | 2 | 1 | 0.5 | 0.00051414
0.10488 | 4193 |  | 4 | 2 | 0.5 | 0.00051414
0.1054 | 6946 |  | 2 | 1 | 0.5 | 0.00051414
0.10591 | 6920 |  | 2 | 1 | 0.5 | 0.00051414
0.10643 | 5667 |  | 2 | 1 | 0.5 | 0.00051414
0.10694 | 4878 |  | 40 | 21 | 0.525 | 0.00051414
0.10746 | 4883 |  | 40 | 21 | 0.525 | 0.00051414
0.10797 | 4087 |  | 120 | 63 | 0.525 | 0.00051414
0.10848 | 4865 |  | 15 | 8 | 0.53333 | 0.00051414
0.109 | 2659 |  | 15 | 8 | 0.53333 | 0.00051414
0.10951 | 2660 |  | 15 | 8 | 0.53333 | 0.00051414
0.11003 | 5708 |  | 15 | 8 | 0.53333 | 0.00051414
0.11054 | 5671 |  | 13 | 7 | 0.53846 | 0.00051414
0.11105 | 3854 |  | 50 | 27 | 0.54 | 0.00051414
0.11157 | 4824 |  | 9 | 5 | 0.55556 | 0.00051414
0.11208 | 4112 |  | 18 | 10 | 0.55556 | 0.00051414
0.1126 | 580 |  | 60 | 34 | 0.56667 | 0.00051414
0.11311 | 3652 |  | 290 | 170 | 0.58621 | 0.00051414
0.11362 | 6505 |  | 85 | 50 | 0.58824 | 0.00051414
0.11414 | 2360 |  | 5 | 3 | 0.6 | 0.00051414
0.11465 | 4253 |  | 5 | 3 | 0.6 | 0.00051414
0.11517 | 4816 |  | 10 | 6 | 0.6 | 0.00051414
0.11568 | 3897 |  | 40 | 24 | 0.6 | 0.00051414
0.1162 | 5544 |  | 20 | 12 | 0.6 | 0.00051414
0.11671 | 4823 |  | 10 | 6 | 0.6 | 0.00051414
0.11722 | 3965 |  | 5 | 3 | 0.6 | 0.00051414
0.11774 | 3974 |  | 5 | 3 | 0.6 | 0.00051414
0.11825 | 6143 |  | 10 | 6 | 0.6 | 0.00051414
0.11877 | 1924 |  | 5 | 3 | 0.6 | 0.00051414
0.11928 | 1933 |  | 5 | 3 | 0.6 | 0.00051414
0.11979 | 1942 |  | 5 | 3 | 0.6 | 0.00051414
0.12031 | 1951 |  | 5 | 3 | 0.6 | 0.00051414
0.12082 | 4984 |  | 5 | 3 | 0.6 | 0.00051414
0.12134 | 2342 |  | 5 | 3 | 0.6 | 0.00051414
0.12185 | 6675 |  | 20 | 12 | 0.6 | 0.00051414
0.12237 | 2374 |  | 15 | 9 | 0.6 | 0.00051414
0.12288 | 2661 |  | 5 | 3 | 0.6 | 0.00051414
0.12339 | 1875 |  | 5 | 3 | 0.6 | 0.00051414
0.12391 | 2378 |  | 5 | 3 | 0.6 | 0.00051414
0.12442 | 5465 |  | 5 | 3 | 0.6 | 0.00051414
0.12494 | 2333 |  | 5 | 3 | 0.6 | 0.00051414
0.12545 | 2409 |  | 23 | 14 | 0.6087 | 0.00051414
0.12596 | 6470 |  | 162 | 100 | 0.61728 | 0.00051414
0.12648 | 6720 |  | 21 | 13 | 0.61905 | 0.00051414
0.12699 | 2423 |  | 58 | 36 | 0.62069 | 0.00051414
0.12751 | 4414 |  | 8 | 5 | 0.625 | 0.00051414
0.12802 | 4897 |  | 40 | 25 | 0.625 | 0.00051414
0.12853 | 4898 |  | 40 | 25 | 0.625 | 0.00051414
0.12905 | 5498 |  | 16 | 10 | 0.625 | 0.00051414
0.12956 | 2332 |  | 16 | 10 | 0.625 | 0.00051414
0.13008 | 4180 |  | 8 | 5 | 0.625 | 0.00051414
0.13059 | 6037 |  | 140 | 88 | 0.62857 | 0.00051414
0.13111 | 2595 |  | 14 | 9 | 0.64286 | 0.00051414
0.13162 | 2442 |  | 88 | 57 | 0.64773 | 0.00051414
0.13213 | 3747 |  | 3 | 2 | 0.66667 | 0.00051414
0.13265 | 3918 |  | 75 | 50 | 0.66667 | 0.00051414
0.13316 | 5680 |  | 3 | 2 | 0.66667 | 0.00051414
0.13368 | 5531 |  | 15 | 10 | 0.66667 | 0.00051414
0.13419 | 1970 |  | 3 | 2 | 0.66667 | 0.00051414
0.1347 | 4131 |  | 6 | 4 | 0.66667 | 0.00051414
0.13522 | 4120 |  | 6 | 4 | 0.66667 | 0.00051414
0.13573 | 2347 |  | 15 | 10 | 0.66667 | 0.00051414
0.13625 | 5705 |  | 15 | 10 | 0.66667 | 0.00051414
0.13676 | 2261 |  | 3 | 2 | 0.66667 | 0.00051414
0.13728 | 2262 |  | 3 | 2 | 0.66667 | 0.00051414
0.13779 | 2677 |  | 37 | 25 | 0.67568 | 0.00051414
0.1383 | 2678 |  | 37 | 25 | 0.67568 | 0.00051414
0.13882 | 2679 |  | 37 | 25 | 0.67568 | 0.00051414
0.13933 | 2680 |  | 37 | 25 | 0.67568 | 0.00051414
0.13985 | 2670 |  | 28 | 19 | 0.67857 | 0.00051414
0.14036 | 2671 |  | 28 | 19 | 0.67857 | 0.00051414
0.14087 | 6105 |  | 35 | 24 | 0.68571 | 0.00051414
0.14139 | 2444 |  | 87 | 60 | 0.68966 | 0.00051414
0.1419 | 4315 |  | 10 | 7 | 0.7 | 0.00051414
0.14242 | 4321 |  | 10 | 7 | 0.7 | 0.00051414
0.14293 | 3924 |  | 20 | 14 | 0.7 | 0.00051414
0.14344 | 3936 |  | 20 | 14 | 0.7 | 0.00051414
0.14396 | 5765 |  | 30 | 21 | 0.7 | 0.00051414
0.14447 | 4138 |  | 10 | 7 | 0.7 | 0.00051414
0.14499 | 6082 |  | 14 | 10 | 0.71429 | 0.00051414
0.1455 | 3923 |  | 30 | 22 | 0.73333 | 0.00051414
0.14602 | 6079 |  | 15 | 11 | 0.73333 | 0.00051414
0.14653 | 2320 |  | 15 | 11 | 0.73333 | 0.00051414
0.14704 | 6464 |  | 81 | 60 | 0.74074 | 0.00051414
0.14756 | 3853 |  | 28 | 21 | 0.75 | 0.00051414
0.14807 | 4780 |  | 36 | 27 | 0.75 | 0.00051414
0.14859 | 4782 |  | 36 | 27 | 0.75 | 0.00051414
0.1491 | 4063 |  | 4 | 3 | 0.75 | 0.00051414
0.14961 | 3874 |  | 20 | 15 | 0.75 | 0.00051414
0.15013 | 5914 |  | 20 | 15 | 0.75 | 0.00051414
0.15064 | 5814 |  | 4 | 3 | 0.75 | 0.00051414
0.15116 | 3951 |  | 30 | 23 | 0.76667 | 0.00051414
0.15167 | 4764 |  | 35 | 27 | 0.77143 | 0.00051414
0.15219 | 4766 |  | 35 | 27 | 0.77143 | 0.00051414
0.1527 | 2411 |  | 18 | 14 | 0.77778 | 0.00051414
0.15321 | 2643 |  | 18 | 14 | 0.77778 | 0.00051414
0.15373 | 6094 |  | 14 | 11 | 0.78571 | 0.00051414
0.15424 | 3648 |  | 250 | 200 | 0.8 | 0.00051414
0.15476 | 4322 |  | 5 | 4 | 0.8 | 0.00051414
0.15527 | 4858 |  | 20 | 16 | 0.8 | 0.00051414
0.15578 | 3863 |  | 5 | 4 | 0.8 | 0.00051414
0.1563 | 5682 |  | 10 | 8 | 0.8 | 0.00051414
0.15681 | 5898 |  | 5 | 4 | 0.8 | 0.00051414
0.15733 | 6041 |  | 15 | 12 | 0.8 | 0.00051414
0.15784 | 6440 |  | 10 | 8 | 0.8 | 0.00051414
0.15835 | 6412 |  | 5 | 4 | 0.8 | 0.00051414
0.15887 | 5910 |  | 5 | 4 | 0.8 | 0.00051414
0.15938 | 5911 |  | 5 | 4 | 0.8 | 0.00051414
0.1599 | 5464 |  | 15 | 12 | 0.8 | 0.00051414
0.16041 | 4178 |  | 5 | 4 | 0.8 | 0.00051414
0.16093 | 6981 |  | 5 | 4 | 0.8 | 0.00051414
0.16144 | 5674 |  | 12 | 10 | 0.83333 | 0.00051414
0.16195 | 3846 |  | 6 | 5 | 0.83333 | 0.00051414
0.16247 | 5716 |  | 12 | 10 | 0.83333 | 0.00051414
0.16298 | 3895 |  | 50 | 42 | 0.84 | 0.00051414
0.1635 | 6103 |  | 163 | 137 | 0.84049 | 0.00051414
0.16401 | 4449 |  | 20 | 17 | 0.85 | 0.00051414
0.16452 | 4851 |  | 21 | 18 | 0.85714 | 0.00051414
0.16504 | 4011 |  | 15 | 13 | 0.86667 | 0.00051414
0.16555 | 1920 |  | 15 | 13 | 0.86667 | 0.00051414
0.16607 | 1929 |  | 15 | 13 | 0.86667 | 0.00051414
0.16658 | 1938 |  | 15 | 13 | 0.86667 | 0.00051414
0.1671 | 1947 |  | 15 | 13 | 0.86667 | 0.00051414
0.16761 | 4991 |  | 15 | 13 | 0.86667 | 0.00051414
0.16812 | 2337 |  | 15 | 13 | 0.86667 | 0.00051414
0.16864 | 5947 |  | 260 | 227 | 0.87308 | 0.00051414
0.16915 | 4337 |  | 8 | 7 | 0.875 | 0.00051414
0.16967 | 3862 |  | 8 | 7 | 0.875 | 0.00051414
0.17018 | 3784 |  | 8 | 7 | 0.875 | 0.00051414
0.17069 | 3682 |  | 20 | 18 | 0.9 | 0.00051414
0.17121 | 4806 |  | 10 | 9 | 0.9 | 0.00051414
0.17172 | 3798 |  | 10 | 9 | 0.9 | 0.00051414
0.17224 | 4807 |  | 10 | 9 | 0.9 | 0.00051414
0.17275 | 4808 |  | 10 | 9 | 0.9 | 0.00051414
0.17326 | 6422 |  | 20 | 18 | 0.9 | 0.00051414
0.17378 | 3518 |  | 22 | 20 | 0.90909 | 0.00051414
0.17429 | 4796 |  | 11 | 10 | 0.90909 | 0.00051414
0.17481 | 4797 |  | 11 | 10 | 0.90909 | 0.00051414
0.17532 | 4798 |  | 11 | 10 | 0.90909 | 0.00051414
0.17584 | 3860 |  | 25 | 23 | 0.92 | 0.00051414
0.17635 | 3944 |  | 15 | 14 | 0.93333 | 0.00051414
0.17686 | 525 |  | 15 | 14 | 0.93333 | 0.00051414
0.17738 | 1919 |  | 15 | 14 | 0.93333 | 0.00051414
0.17789 | 1928 |  | 15 | 14 | 0.93333 | 0.00051414
0.17841 | 1937 |  | 15 | 14 | 0.93333 | 0.00051414
0.17892 | 1946 |  | 15 | 14 | 0.93333 | 0.00051414
0.17943 | 4989 |  | 15 | 14 | 0.93333 | 0.00051414
0.17995 | 2358 |  | 16 | 15 | 0.9375 | 0.00051414
0.18046 | 2359 |  | 16 | 15 | 0.9375 | 0.00051414
0.18098 | 1922 |  | 16 | 15 | 0.9375 | 0.00051414
0.18149 | 1923 |  | 16 | 15 | 0.9375 | 0.00051414
0.18201 | 1931 |  | 16 | 15 | 0.9375 | 0.00051414
0.18252 | 1940 |  | 16 | 15 | 0.9375 | 0.00051414
0.18303 | 1949 |  | 16 | 15 | 0.9375 | 0.00051414
0.18355 | 1932 |  | 16 | 15 | 0.9375 | 0.00051414
0.18406 | 1941 |  | 16 | 15 | 0.9375 | 0.00051414
0.18458 | 1950 |  | 16 | 15 | 0.9375 | 0.00051414
0.18509 | 4985 |  | 16 | 15 | 0.9375 | 0.00051414
0.1856 | 4986 |  | 16 | 15 | 0.9375 | 0.00051414
0.18612 | 2376 |  | 16 | 15 | 0.9375 | 0.00051414
0.18663 | 2331 |  | 16 | 15 | 0.9375 | 0.00051414
0.18715 | 2377 |  | 16 | 15 | 0.9375 | 0.00051414
0.18766 | 2394 |  | 16 | 15 | 0.9375 | 0.00051414
0.18817 | 2395 |  | 16 | 15 | 0.9375 | 0.00051414
0.18869 | 4786 |  | 36 | 34 | 0.94444 | 0.00051414
0.1892 | 2477 |  | 110 | 104 | 0.94545 | 0.00051414
0.18972 | 3634 |  | 20 | 19 | 0.95 | 0.00051414
0.19023 | 3750 |  | 20 | 19 | 0.95 | 0.00051414
0.19075 | 2521 |  | 20 | 19 | 0.95 | 0.00051414
0.19126 | 2532 |  | 20 | 19 | 0.95 | 0.00051414
0.19177 | 3655 |  | 120 | 115 | 0.95833 | 0.00051414
0.19229 | 3656 |  | 120 | 115 | 0.95833 | 0.00051414
0.1928 | 4770 |  | 35 | 34 | 0.97143 | 0.00051414
0.19332 | 4788 |  | 36 | 35 | 0.97222 | 0.00051414
0.19383 | 1915 |  | 72 | 70 | 0.97222 | 0.00051414
0.19434 | 3922 |  | 40 | 39 | 0.975 | 0.00051414
0.19486 | 5612 |  | 44 | 43 | 0.97727 | 0.00051414
0.19537 | 6106 |  | 177 | 173 | 0.9774 | 0.00051414
0.19589 | 6482 |  | 78 | 77 | 0.98718 | 0.00051414
0.1964 | 6483 |  | 81 | 80 | 0.98765 | 0.00051414
0.19692 | 6115 |  | 89 | 88 | 0.98876 | 0.00051414
0.19743 | 6471 |  | 30 | 30 | 1 | 0.00051414
0.19794 | 6847 |  | 18 | 18 | 1 | 0.00051414
0.19846 | 5445 |  | 1 | 1 | 1 | 0.00051414
0.19897 | 2088 |  | 15 | 15 | 1 | 0.00051414
0.19949 | 2089 |  | 30 | 30 | 1 | 0.00051414
0.2 | 2090 |  | 200 | 200 | 1 | 0.00051414
0.20051 | 756 |  | 4 | 4 | 1 | 0.00051414
0.20103 | 757 |  | 21 | 21 | 1 | 0.00051414
0.20154 | 774 |  | 4 | 4 | 1 | 0.00051414
0.20206 | 775 |  | 12 | 12 | 1 | 0.00051414
0.20257 | 776 |  | 4 | 4 | 1 | 0.00051414
0.20308 | 780 |  | 34 | 34 | 1 | 0.00051414
0.2036 | 936 |  | 2 | 2 | 1 | 0.00051414
0.20411 | 781 |  | 7 | 7 | 1 | 0.00051414
0.20463 | 785 |  | 22 | 22 | 1 | 0.00051414
0.20514 | 2126 |  | 1 | 1 | 1 | 0.00051414
0.20566 | 2127 |  | 230 | 230 | 1 | 0.00051414
0.20617 | 2129 |  | 121 | 121 | 1 | 0.00051414
0.20668 | 786 |  | 12 | 12 | 1 | 0.00051414
0.2072 | 2075 |  | 135 | 135 | 1 | 0.00051414
0.20771 | 787 |  | 1 | 1 | 1 | 0.00051414
0.20823 | 790 |  | 14 | 14 | 1 | 0.00051414
0.20874 | 791 |  | 5 | 5 | 1 | 0.00051414
0.20925 | 2059 |  | 3 | 3 | 1 | 0.00051414
0.20977 | 2060 |  | 20 | 20 | 1 | 0.00051414
0.21028 | 792 |  | 1 | 1 | 1 | 0.00051414
0.2108 | 2091 |  | 5 | 5 | 1 | 0.00051414
0.21131 | 795 |  | 25 | 25 | 1 | 0.00051414
0.21183 | 2092 |  | 3 | 3 | 1 | 0.00051414
0.21234 | 493 |  | 72 | 72 | 1 | 0.00051414
0.21285 | 2061 |  | 88 | 88 | 1 | 0.00051414
0.21337 | 2103 |  | 5 | 5 | 1 | 0.00051414
0.21388 | 2104 |  | 20 | 20 | 1 | 0.00051414
0.2144 | 941 |  | 21 | 21 | 1 | 0.00051414
0.21491 | 2071 |  | 15 | 15 | 1 | 0.00051414
0.21542 | 2073 |  | 10 | 10 | 1 | 0.00051414
0.21594 | 2077 |  | 10 | 10 | 1 | 0.00051414
0.21645 | 2079 |  | 10 | 10 | 1 | 0.00051414
0.21697 | 2081 |  | 10 | 10 | 1 | 0.00051414
0.21748 | 2083 |  | 10 | 10 | 1 | 0.00051414
0.21799 | 2085 |  | 81 | 81 | 1 | 0.00051414
0.21851 | 796 |  | 9 | 9 | 1 | 0.00051414
0.21902 | 2107 |  | 2 | 2 | 1 | 0.00051414
0.21954 | 943 |  | 11 | 11 | 1 | 0.00051414
0.22005 | 2074 |  | 30 | 30 | 1 | 0.00051414
0.22057 | 2078 |  | 90 | 90 | 1 | 0.00051414
0.22108 | 2080 |  | 125 | 125 | 1 | 0.00051414
0.22159 | 2082 |  | 60 | 60 | 1 | 0.00051414
0.22211 | 2084 |  | 60 | 60 | 1 | 0.00051414
0.22262 | 2108 |  | 3 | 3 | 1 | 0.00051414
0.22314 | 2109 |  | 3 | 3 | 1 | 0.00051414
0.22365 | 2072 |  | 70 | 70 | 1 | 0.00051414
0.22416 | 2110 |  | 4 | 4 | 1 | 0.00051414
0.22468 | 1977 |  | 5 | 5 | 1 | 0.00051414
0.22519 | 1982 |  | 10 | 10 | 1 | 0.00051414
0.22571 | 2111 |  | 2 | 2 | 1 | 0.00051414
0.22622 | 1978 |  | 10 | 10 | 1 | 0.00051414
0.22674 | 797 |  | 6 | 6 | 1 | 0.00051414
0.22725 | 1983 |  | 20 | 20 | 1 | 0.00051414
0.22776 | 945 |  | 10 | 10 | 1 | 0.00051414
0.22828 | 798 |  | 32 | 32 | 1 | 0.00051414
0.22879 | 799 |  | 173 | 173 | 1 | 0.00051414
0.22931 | 815 |  | 173 | 173 | 1 | 0.00051414
0.22982 | 1979 |  | 200 | 200 | 1 | 0.00051414
0.23033 | 2130 |  | 10 | 10 | 1 | 0.00051414
0.23085 | 1984 |  | 30 | 30 | 1 | 0.00051414
0.23136 | 494 |  | 197 | 197 | 1 | 0.00051414
0.23188 | 2167 |  | 2 | 2 | 1 | 0.00051414
0.23239 | 2168 |  | 3 | 3 | 1 | 0.00051414
0.2329 | 2076 |  | 79 | 79 | 1 | 0.00051414
0.23342 | 1985 |  | 3 | 3 | 1 | 0.00051414
0.23393 | 2086 |  | 20 | 20 | 1 | 0.00051414
0.23445 | 2135 |  | 3 | 3 | 1 | 0.00051414
0.23496 | 2136 |  | 3 | 3 | 1 | 0.00051414
0.23548 | 2128 |  | 10 | 10 | 1 | 0.00051414
0.23599 | 2137 |  | 75 | 75 | 1 | 0.00051414
0.2365 | 2131 |  | 2 | 2 | 1 | 0.00051414
0.23702 | 2132 |  | 15 | 15 | 1 | 0.00051414
0.23753 | 1992 |  | 3 | 3 | 1 | 0.00051414
0.23805 | 2007 |  | 4 | 4 | 1 | 0.00051414
0.23856 | 2012 |  | 3 | 3 | 1 | 0.00051414
0.23907 | 2017 |  | 3 | 3 | 1 | 0.00051414
0.23959 | 1993 |  | 10 | 10 | 1 | 0.00051414
0.2401 | 2013 |  | 45 | 45 | 1 | 0.00051414
0.24062 | 2018 |  | 30 | 30 | 1 | 0.00051414
0.24113 | 2008 |  | 10 | 10 | 1 | 0.00051414
0.24165 | 2133 |  | 1 | 1 | 1 | 0.00051414
0.24216 | 1994 |  | 85 | 85 | 1 | 0.00051414
0.24267 | 2009 |  | 125 | 125 | 1 | 0.00051414
0.24319 | 949 |  | 16 | 16 | 1 | 0.00051414
0.2437 | 2019 |  | 76 | 76 | 1 | 0.00051414
0.24422 | 800 |  | 5 | 5 | 1 | 0.00051414
0.24473 | 816 |  | 8 | 8 | 1 | 0.00051414
0.24524 | 801 |  | 3 | 3 | 1 | 0.00051414
0.24576 | 802 |  | 1 | 1 | 1 | 0.00051414
0.24627 | 804 |  | 10 | 10 | 1 | 0.00051414
0.24679 | 803 |  | 1 | 1 | 1 | 0.00051414
0.2473 | 2014 |  | 76 | 76 | 1 | 0.00051414
0.24781 | 4242 |  | 1 | 1 | 1 | 0.00051414
0.24833 | 3134 |  | 120 | 120 | 1 | 0.00051414
0.24884 | 2138 |  | 125 | 125 | 1 | 0.00051414
0.24936 | 3601 |  | 124 | 124 | 1 | 0.00051414
0.24987 | 1980 |  | 3 | 3 | 1 | 0.00051414
0.25039 | 2122 |  | 10 | 10 | 1 | 0.00051414
0.2509 | 805 |  | 1 | 1 | 1 | 0.00051414
0.25141 | 2123 |  | 2 | 2 | 1 | 0.00051414
0.25193 | 2124 |  | 1 | 1 | 1 | 0.00051414
0.25244 | 495 |  | 12 | 12 | 1 | 0.00051414
0.25296 | 509 |  | 57 | 57 | 1 | 0.00051414
0.25347 | 2062 |  | 2 | 2 | 1 | 0.00051414
0.25398 | 2063 |  | 10 | 10 | 1 | 0.00051414
0.2545 | 501 |  | 30 | 30 | 1 | 0.00051414
0.25501 | 496 |  | 3 | 3 | 1 | 0.00051414
0.25553 | 497 |  | 9 | 9 | 1 | 0.00051414
0.25604 | 2064 |  | 89 | 89 | 1 | 0.00051414
0.25656 | 1995 |  | 3 | 3 | 1 | 0.00051414
0.25707 | 806 |  | 16 | 16 | 1 | 0.00051414
0.25758 | 2002 |  | 2 | 2 | 1 | 0.00051414
0.2581 | 2003 |  | 1 | 1 | 1 | 0.00051414
0.25861 | 2004 |  | 66 | 66 | 1 | 0.00051414
0.25913 | 498 |  | 70 | 70 | 1 | 0.00051414
0.25964 | 2020 |  | 3 | 3 | 1 | 0.00051414
0.26015 | 4525 |  | 31 | 31 | 1 | 0.00051414
0.26067 | 560 |  | 1 | 1 | 1 | 0.00051414
0.26118 | 561 |  | 122 | 122 | 1 | 0.00051414
0.2617 | 502 |  | 20 | 20 | 1 | 0.00051414
0.26221 | 2015 |  | 3 | 3 | 1 | 0.00051414
0.26272 | 961 |  | 1 | 1 | 1 | 0.00051414
0.26324 | 4526 |  | 3 | 3 | 1 | 0.00051414
0.26375 | 5590 |  | 235 | 235 | 1 | 0.00051414
0.26427 | 962 |  | 5 | 5 | 1 | 0.00051414
0.26478 | 963 |  | 5 | 5 | 1 | 0.00051414
0.2653 | 4527 |  | 7 | 7 | 1 | 0.00051414
0.26581 | 3469 |  | 20 | 20 | 1 | 0.00051414
0.26632 | 4528 |  | 100 | 100 | 1 | 0.00051414
0.26684 | 2010 |  | 3 | 3 | 1 | 0.00051414
0.26735 | 503 |  | 10 | 10 | 1 | 0.00051414
0.26787 | 510 |  | 19 | 19 | 1 | 0.00051414
0.26838 | 4529 |  | 20 | 20 | 1 | 0.00051414
0.26889 | 4530 |  | 25 | 25 | 1 | 0.00051414
0.26941 | 504 |  | 15 | 15 | 1 | 0.00051414
0.26992 | 3471 |  | 12 | 12 | 1 | 0.00051414
0.27044 | 3631 |  | 60 | 60 | 1 | 0.00051414
0.27095 | 3638 |  | 83 | 83 | 1 | 0.00051414
0.27147 | 3491 |  | 15 | 15 | 1 | 0.00051414
0.27198 | 3492 |  | 14 | 14 | 1 | 0.00051414
0.27249 | 511 |  | 22 | 22 | 1 | 0.00051414
0.27301 | 505 |  | 10 | 10 | 1 | 0.00051414
0.27352 | 3468 |  | 1 | 1 | 1 | 0.00051414
0.27404 | 4256 |  | 66 | 66 | 1 | 0.00051414
0.27455 | 4257 |  | 66 | 66 | 1 | 0.00051414
0.27506 | 4258 |  | 55 | 55 | 1 | 0.00051414
0.27558 | 4259 |  | 57 | 57 | 1 | 0.00051414
0.27609 | 2005 |  | 2 | 2 | 1 | 0.00051414
0.27661 | 3478 |  | 13 | 13 | 1 | 0.00051414
0.27712 | 506 |  | 105 | 105 | 1 | 0.00051414
0.27763 | 3477 |  | 12 | 12 | 1 | 0.00051414
0.27815 | 4277 |  | 146 | 146 | 1 | 0.00051414
0.27866 | 4706 |  | 191 | 191 | 1 | 0.00051414
0.27918 | 4292 |  | 70 | 70 | 1 | 0.00051414
0.27969 | 4301 |  | 117 | 117 | 1 | 0.00051414
0.28021 | 4304 |  | 146 | 146 | 1 | 0.00051414
0.28072 | 4327 |  | 103 | 103 | 1 | 0.00051414
0.28123 | 4330 |  | 70 | 70 | 1 | 0.00051414
0.28175 | 4335 |  | 74 | 74 | 1 | 0.00051414
0.28226 | 4348 |  | 121 | 121 | 1 | 0.00051414
0.28278 | 4361 |  | 95 | 95 | 1 | 0.00051414
0.28329 | 4366 |  | 95 | 95 | 1 | 0.00051414
0.2838 | 4642 |  | 171 | 171 | 1 | 0.00051414
0.28432 | 4643 |  | 171 | 171 | 1 | 0.00051414
0.28483 | 4396 |  | 121 | 121 | 1 | 0.00051414
0.28535 | 4401 |  | 63 | 63 | 1 | 0.00051414
0.28586 | 4468 |  | 226 | 226 | 1 | 0.00051414
0.28638 | 512 |  | 30 | 30 | 1 | 0.00051414
0.28689 | 2037 |  | 1 | 1 | 1 | 0.00051414
0.2874 | 2038 |  | 81 | 81 | 1 | 0.00051414
0.28792 | 2139 |  | 124 | 124 | 1 | 0.00051414
0.28843 | 2165 |  | 1 | 1 | 1 | 0.00051414
0.28895 | 3479 |  | 3 | 3 | 1 | 0.00051414
0.28946 | 1957 |  | 7 | 7 | 1 | 0.00051414
0.28997 | 1962 |  | 7 | 7 | 1 | 0.00051414
0.29049 | 3561 |  | 1 | 1 | 1 | 0.00051414
0.291 | 1958 |  | 45 | 45 | 1 | 0.00051414
0.29152 | 1963 |  | 10 | 10 | 1 | 0.00051414
0.29203 | 4412 |  | 51 | 51 | 1 | 0.00051414
0.29254 | 3613 |  | 20 | 20 | 1 | 0.00051414
0.29306 | 3614 |  | 20 | 20 | 1 | 0.00051414
0.29357 | 3620 |  | 40 | 40 | 1 | 0.00051414
0.29409 | 3623 |  | 20 | 20 | 1 | 0.00051414
0.2946 | 3624 |  | 20 | 20 | 1 | 0.00051414
0.29512 | 5591 |  | 150 | 150 | 1 | 0.00051414
0.29563 | 1964 |  | 71 | 71 | 1 | 0.00051414
0.29614 | 2045 |  | 2 | 2 | 1 | 0.00051414
0.29666 | 3562 |  | 1 | 1 | 1 | 0.00051414
0.29717 | 2046 |  | 2 | 2 | 1 | 0.00051414
0.29769 | 2047 |  | 70 | 70 | 1 | 0.00051414
0.2982 | 4616 |  | 111 | 111 | 1 | 0.00051414
0.29871 | 513 |  | 69 | 69 | 1 | 0.00051414
0.29923 | 3615 |  | 20 | 20 | 1 | 0.00051414
0.29974 | 4459 |  | 1 | 1 | 1 | 0.00051414
0.30026 | 4466 |  | 29 | 29 | 1 | 0.00051414
0.30077 | 4493 |  | 66 | 66 | 1 | 0.00051414
0.30129 | 2618 |  | 90 | 90 | 1 | 0.00051414
0.3018 | 4251 |  | 1 | 1 | 1 | 0.00051414
0.30231 | 4254 |  | 1 | 1 | 1 | 0.00051414
0.30283 | 3563 |  | 1 | 1 | 1 | 0.00051414
0.30334 | 562 |  | 43 | 43 | 1 | 0.00051414
0.30386 | 1959 |  | 49 | 49 | 1 | 0.00051414
0.30437 | 4565 |  | 1 | 1 | 1 | 0.00051414
0.30488 | 4467 |  | 12 | 12 | 1 | 0.00051414
0.3054 | 2022 |  | 4 | 4 | 1 | 0.00051414
0.30591 | 2027 |  | 2 | 2 | 1 | 0.00051414
0.30643 | 2066 |  | 2 | 2 | 1 | 0.00051414
0.30694 | 2028 |  | 10 | 10 | 1 | 0.00051414
0.30746 | 2067 |  | 2 | 2 | 1 | 0.00051414
0.30797 | 3564 |  | 1 | 1 | 1 | 0.00051414
0.30848 | 2023 |  | 10 | 10 | 1 | 0.00051414
0.309 | 2068 |  | 2 | 2 | 1 | 0.00051414
0.30951 | 2069 |  | 117 | 117 | 1 | 0.00051414
0.31003 | 2029 |  | 86 | 86 | 1 | 0.00051414
0.31054 | 2024 |  | 142 | 142 | 1 | 0.00051414
0.31105 | 4500 |  | 15 | 15 | 1 | 0.00051414
0.31157 | 3646 |  | 45 | 45 | 1 | 0.00051414
0.31208 | 3647 |  | 45 | 45 | 1 | 0.00051414
0.3126 | 4465 |  | 29 | 29 | 1 | 0.00051414
0.31311 | 3565 |  | 1 | 1 | 1 | 0.00051414
0.31362 | 1965 |  | 2 | 2 | 1 | 0.00051414
0.31414 | 4455 |  | 79 | 79 | 1 | 0.00051414
0.31465 | 507 |  | 2 | 2 | 1 | 0.00051414
0.31517 | 2048 |  | 27 | 27 | 1 | 0.00051414
0.31568 | 4237 |  | 1 | 1 | 1 | 0.00051414
0.3162 | 4727 |  | 22 | 22 | 1 | 0.00051414
0.31671 | 4729 |  | 22 | 22 | 1 | 0.00051414
0.31722 | 4733 |  | 22 | 22 | 1 | 0.00051414
0.31774 | 4828 |  | 37 | 37 | 1 | 0.00051414
0.31825 | 4843 |  | 25 | 25 | 1 | 0.00051414
0.31877 | 4845 |  | 20 | 20 | 1 | 0.00051414
0.31928 | 4854 |  | 34 | 34 | 1 | 0.00051414
0.31979 | 4870 |  | 32 | 32 | 1 | 0.00051414
0.32031 | 4873 |  | 40 | 40 | 1 | 0.00051414
0.32082 | 3472 |  | 13 | 13 | 1 | 0.00051414
0.32134 | 563 |  | 26 | 26 | 1 | 0.00051414
0.32185 | 2149 |  | 5 | 5 | 1 | 0.00051414
0.32237 | 2151 |  | 5 | 5 | 1 | 0.00051414
0.32288 | 1960 |  | 2 | 2 | 1 | 0.00051414
0.32339 | 2150 |  | 1 | 1 | 1 | 0.00051414
0.32391 | 3566 |  | 1 | 1 | 1 | 0.00051414
0.32442 | 1987 |  | 3 | 3 | 1 | 0.00051414
0.32494 | 515 |  | 1 | 1 | 1 | 0.00051414
0.32545 | 516 |  | 68 | 68 | 1 | 0.00051414
0.32596 | 1988 |  | 10 | 10 | 1 | 0.00051414
0.32648 | 4644 |  | 50 | 50 | 1 | 0.00051414
0.32699 | 499 |  | 3 | 3 | 1 | 0.00051414
0.32751 | 3671 |  | 5 | 5 | 1 | 0.00051414
0.32802 | 3672 |  | 18 | 18 | 1 | 0.00051414
0.32853 | 3673 |  | 27 | 27 | 1 | 0.00051414
0.32905 | 4709 |  | 1 | 1 | 1 | 0.00051414
0.32956 | 4464 |  | 13 | 13 | 1 | 0.00051414
0.33008 | 4728 |  | 49 | 49 | 1 | 0.00051414
0.33059 | 4730 |  | 49 | 49 | 1 | 0.00051414
0.33111 | 4735 |  | 15 | 15 | 1 | 0.00051414
0.33162 | 4739 |  | 29 | 29 | 1 | 0.00051414
0.33213 | 4743 |  | 29 | 29 | 1 | 0.00051414
0.33265 | 4747 |  | 29 | 29 | 1 | 0.00051414
0.33316 | 3868 |  | 45 | 45 | 1 | 0.00051414
0.33368 | 3869 |  | 60 | 60 | 1 | 0.00051414
0.33419 | 4844 |  | 25 | 25 | 1 | 0.00051414
0.3347 | 3675 |  | 2 | 2 | 1 | 0.00051414
0.33522 | 4471 |  | 5 | 5 | 1 | 0.00051414
0.33573 | 1989 |  | 77 | 77 | 1 | 0.00051414
0.33625 | 2049 |  | 60 | 60 | 1 | 0.00051414
0.33676 | 564 |  | 7 | 7 | 1 | 0.00051414
0.33728 | 4871 |  | 31 | 31 | 1 | 0.00051414
0.33779 | 4855 |  | 33 | 33 | 1 | 0.00051414
0.3383 | 4928 |  | 52 | 52 | 1 | 0.00051414
0.33882 | 4829 |  | 35 | 35 | 1 | 0.00051414
0.33933 | 2152 |  | 2 | 2 | 1 | 0.00051414
0.33985 | 3567 |  | 1 | 1 | 1 | 0.00051414
0.34036 | 2166 |  | 5 | 5 | 1 | 0.00051414
0.34087 | 2619 |  | 57 | 57 | 1 | 0.00051414
0.34139 | 4479 |  | 22 | 22 | 1 | 0.00051414
0.3419 | 4481 |  | 22 | 22 | 1 | 0.00051414
0.34242 | 4486 |  | 22 | 22 | 1 | 0.00051414
0.34293 | 4847 |  | 29 | 29 | 1 | 0.00051414
0.34344 | 4736 |  | 15 | 15 | 1 | 0.00051414
0.34396 | 4740 |  | 28 | 28 | 1 | 0.00051414
0.34447 | 4744 |  | 28 | 28 | 1 | 0.00051414
0.34499 | 4748 |  | 28 | 28 | 1 | 0.00051414
0.3455 | 4429 |  | 64 | 64 | 1 | 0.00051414
0.34602 | 4979 |  | 74 | 74 | 1 | 0.00051414
0.34653 | 2032 |  | 3 | 3 | 1 | 0.00051414
0.34704 | 2140 |  | 5 | 5 | 1 | 0.00051414
0.34756 | 3568 |  | 1 | 1 | 1 | 0.00051414
0.34807 | 2033 |  | 10 | 10 | 1 | 0.00051414
0.34859 | 3677 |  | 3 | 3 | 1 | 0.00051414
0.3491 | 3679 |  | 3 | 3 | 1 | 0.00051414
0.34961 | 4914 |  | 1 | 1 | 1 | 0.00051414
0.35013 | 4872 |  | 31 | 31 | 1 | 0.00051414
0.35064 | 2191 |  | 3 | 3 | 1 | 0.00051414
0.35116 | 4737 |  | 13 | 13 | 1 | 0.00051414
0.35167 | 2034 |  | 33 | 33 | 1 | 0.00051414
0.35219 | 4856 |  | 23 | 23 | 1 | 0.00051414
0.3527 | 4249 |  | 10 | 10 | 1 | 0.00051414
0.35321 | 3717 |  | 20 | 20 | 1 | 0.00051414
0.35373 | 4830 |  | 16 | 16 | 1 | 0.00051414
0.35424 | 3870 |  | 5 | 5 | 1 | 0.00051414
0.35476 | 2030 |  | 3 | 3 | 1 | 0.00051414
0.35527 | 5552 |  | 20 | 20 | 1 | 0.00051414
0.35578 | 2158 |  | 6 | 6 | 1 | 0.00051414
0.3563 | 2159 |  | 6 | 6 | 1 | 0.00051414
0.35681 | 3569 |  | 1 | 1 | 1 | 0.00051414
0.35733 | 2155 |  | 1 | 1 | 1 | 0.00051414
0.35784 | 3651 |  | 70 | 70 | 1 | 0.00051414
0.35835 | 1997 |  | 3 | 3 | 1 | 0.00051414
0.35887 | 2479 |  | 176 | 176 | 1 | 0.00051414
0.35938 | 4741 |  | 21 | 21 | 1 | 0.00051414
0.3599 | 4745 |  | 21 | 21 | 1 | 0.00051414
0.36041 | 4749 |  | 21 | 21 | 1 | 0.00051414
0.36093 | 4848 |  | 7 | 7 | 1 | 0.00051414
0.36144 | 4875 |  | 15 | 15 | 1 | 0.00051414
0.36195 | 2160 |  | 3 | 3 | 1 | 0.00051414
0.36247 | 1998 |  | 11 | 11 | 1 | 0.00051414
0.36298 | 4915 |  | 1 | 1 | 1 | 0.00051414
0.3635 | 3686 |  | 1 | 1 | 1 | 0.00051414
0.36401 | 3687 |  | 1 | 1 | 1 | 0.00051414
0.36452 | 4880 |  | 11 | 11 | 1 | 0.00051414
0.36504 | 3487 |  | 5 | 5 | 1 | 0.00051414
0.36555 | 1999 |  | 12 | 12 | 1 | 0.00051414
0.36607 | 5558 |  | 1 | 1 | 1 | 0.00051414
0.36658 | 5557 |  | 5 | 5 | 1 | 0.00051414
0.3671 | 4876 |  | 14 | 14 | 1 | 0.00051414
0.36761 | 517 |  | 84 | 84 | 1 | 0.00051414
0.36812 | 3683 |  | 3 | 3 | 1 | 0.00051414
0.36864 | 4370 |  | 2 | 2 | 1 | 0.00051414
0.36915 | 3725 |  | 1 | 1 | 1 | 0.00051414
0.36967 | 3726 |  | 2 | 2 | 1 | 0.00051414
0.37018 | 4881 |  | 8 | 8 | 1 | 0.00051414
0.37069 | 3570 |  | 1 | 1 | 1 | 0.00051414
0.37121 | 3689 |  | 2 | 2 | 1 | 0.00051414
0.37172 | 2035 |  | 3 | 3 | 1 | 0.00051414
0.37224 | 3727 |  | 2 | 2 | 1 | 0.00051414
0.37275 | 4916 |  | 1 | 1 | 1 | 0.00051414
0.37326 | 3690 |  | 2 | 2 | 1 | 0.00051414
0.37378 | 3728 |  | 1 | 1 | 1 | 0.00051414
0.37429 | 2000 |  | 3 | 3 | 1 | 0.00051414
0.37481 | 3729 |  | 1 | 1 | 1 | 0.00051414
0.37532 | 4410 |  | 12 | 12 | 1 | 0.00051414
0.37584 | 3722 |  | 4 | 4 | 1 | 0.00051414
0.37635 | 4752 |  | 24 | 24 | 1 | 0.00051414
0.37686 | 4754 |  | 24 | 24 | 1 | 0.00051414
0.37738 | 4831 |  | 40 | 40 | 1 | 0.00051414
0.37789 | 3693 |  | 1 | 1 | 1 | 0.00051414
0.37841 | 1990 |  | 3 | 3 | 1 | 0.00051414
0.37892 | 2620 |  | 57 | 57 | 1 | 0.00051414
0.37943 | 3694 |  | 1 | 1 | 1 | 0.00051414
0.37995 | 3695 |  | 1 | 1 | 1 | 0.00051414
0.38046 | 3732 |  | 1 | 1 | 1 | 0.00051414
0.38098 | 2143 |  | 1 | 1 | 1 | 0.00051414
0.38149 | 2144 |  | 3 | 3 | 1 | 0.00051414
0.38201 | 3724 |  | 4 | 4 | 1 | 0.00051414
0.38252 | 3571 |  | 1 | 1 | 1 | 0.00051414
0.38303 | 4917 |  | 1 | 1 | 1 | 0.00051414
0.38355 | 4469 |  | 5 | 5 | 1 | 0.00051414
0.38406 | 4470 |  | 5 | 5 | 1 | 0.00051414
0.38458 | 4474 |  | 5 | 5 | 1 | 0.00051414
0.38509 | 4487 |  | 5 | 5 | 1 | 0.00051414
0.3856 | 4996 |  | 9 | 9 | 1 | 0.00051414
0.38612 | 2025 |  | 3 | 3 | 1 | 0.00051414
0.38663 | 3731 |  | 2 | 2 | 1 | 0.00051414
0.38715 | 4977 |  | 5 | 5 | 1 | 0.00051414
0.38766 | 3708 |  | 3 | 3 | 1 | 0.00051414
0.38817 | 5731 |  | 1 | 1 | 1 | 0.00051414
0.38869 | 5732 |  | 1 | 1 | 1 | 0.00051414
0.3892 | 5733 |  | 1 | 1 | 1 | 0.00051414
0.38972 | 5734 |  | 1 | 1 | 1 | 0.00051414
0.39023 | 5735 |  | 9 | 9 | 1 | 0.00051414
0.39075 | 4995 |  | 5 | 5 | 1 | 0.00051414
0.39126 | 4976 |  | 10 | 10 | 1 | 0.00051414
0.39177 | 5923 |  | 148 | 148 | 1 | 0.00051414
0.39229 | 3572 |  | 1 | 1 | 1 | 0.00051414
0.3928 | 2629 |  | 60 | 60 | 1 | 0.00051414
0.39332 | 2630 |  | 60 | 60 | 1 | 0.00051414
0.39383 | 2631 |  | 60 | 60 | 1 | 0.00051414
0.39434 | 4918 |  | 1 | 1 | 1 | 0.00051414
0.39486 | 5736 |  | 8 | 8 | 1 | 0.00051414
0.39537 | 4760 |  | 30 | 30 | 1 | 0.00051414
0.39589 | 3711 |  | 4 | 4 | 1 | 0.00051414
0.3964 | 3713 |  | 2 | 2 | 1 | 0.00051414
0.39692 | 4443 |  | 5 | 5 | 1 | 0.00051414
0.39743 | 5737 |  | 9 | 9 | 1 | 0.00051414
0.39794 | 4444 |  | 2 | 2 | 1 | 0.00051414
0.39846 | 3843 |  | 20 | 20 | 1 | 0.00051414
0.39897 | 3751 |  | 5 | 5 | 1 | 0.00051414
0.39949 | 3573 |  | 1 | 1 | 1 | 0.00051414
0.4 | 4919 |  | 1 | 1 | 1 | 0.00051414
0.40051 | 1967 |  | 3 | 3 | 1 | 0.00051414
0.40103 | 1972 |  | 3 | 3 | 1 | 0.00051414
0.40154 | 5738 |  | 9 | 9 | 1 | 0.00051414
0.40206 | 3753 |  | 3 | 3 | 1 | 0.00051414
0.40257 | 1968 |  | 10 | 10 | 1 | 0.00051414
0.40308 | 1973 |  | 10 | 10 | 1 | 0.00051414
0.4036 | 5084 |  | 4 | 4 | 1 | 0.00051414
0.40411 | 5087 |  | 3 | 3 | 1 | 0.00051414
0.40463 | 2622 |  | 18 | 18 | 1 | 0.00051414
0.40514 | 2624 |  | 11 | 11 | 1 | 0.00051414
0.40566 | 5083 |  | 1 | 1 | 1 | 0.00051414
0.40617 | 5088 |  | 5 | 5 | 1 | 0.00051414
0.40668 | 5739 |  | 9 | 9 | 1 | 0.00051414
0.4072 | 2226 |  | 1 | 1 | 1 | 0.00051414
0.40771 | 2227 |  | 1 | 1 | 1 | 0.00051414
0.40823 | 2228 |  | 2 | 2 | 1 | 0.00051414
0.40874 | 5550 |  | 1 | 1 | 1 | 0.00051414
0.40925 | 518 |  | 44 | 44 | 1 | 0.00051414
0.40977 | 3844 |  | 30 | 30 | 1 | 0.00051414
0.41028 | 1974 |  | 46 | 46 | 1 | 0.00051414
0.4108 | 5551 |  | 10 | 10 | 1 | 0.00051414
0.41131 | 5086 |  | 5 | 5 | 1 | 0.00051414
0.41183 | 3738 |  | 5 | 5 | 1 | 0.00051414
0.41234 | 4920 |  | 1 | 1 | 1 | 0.00051414
0.41285 | 5872 |  | 88 | 88 | 1 | 0.00051414
0.41337 | 2545 |  | 1 | 1 | 1 | 0.00051414
0.41388 | 3574 |  | 1 | 1 | 1 | 0.00051414
0.4144 | 2552 |  | 1 | 1 | 1 | 0.00051414
0.41491 | 5602 |  | 1 | 1 | 1 | 0.00051414
0.41542 | 5554 |  | 15 | 15 | 1 | 0.00051414
0.41594 | 2194 |  | 1 | 1 | 1 | 0.00051414
0.41645 | 2199 |  | 1 | 1 | 1 | 0.00051414
0.41697 | 2203 |  | 1 | 1 | 1 | 0.00051414
0.41748 | 5548 |  | 1 | 1 | 1 | 0.00051414
0.41799 | 5085 |  | 3 | 3 | 1 | 0.00051414
0.41851 | 5549 |  | 5 | 5 | 1 | 0.00051414
0.41902 | 4763 |  | 35 | 35 | 1 | 0.00051414
0.41954 | 4765 |  | 35 | 35 | 1 | 0.00051414
0.42005 | 3742 |  | 1 | 1 | 1 | 0.00051414
0.42057 | 4779 |  | 35 | 35 | 1 | 0.00051414
0.42108 | 4781 |  | 35 | 35 | 1 | 0.00051414
0.42159 | 5607 |  | 6 | 6 | 1 | 0.00051414
0.42211 | 5608 |  | 6 | 6 | 1 | 0.00051414
0.42262 | 5879 |  | 30 | 30 | 1 | 0.00051414
0.42314 | 2573 |  | 2 | 2 | 1 | 0.00051414
0.42365 | 3575 |  | 1 | 1 | 1 | 0.00051414
0.42416 | 5997 |  | 231 | 231 | 1 | 0.00051414
0.42468 | 5555 |  | 1 | 1 | 1 | 0.00051414
0.42519 | 4921 |  | 1 | 1 | 1 | 0.00051414
0.42571 | 521 |  | 52 | 52 | 1 | 0.00051414
0.42622 | 5718 |  | 5 | 5 | 1 | 0.00051414
0.42674 | 3746 |  | 5 | 5 | 1 | 0.00051414
0.42725 | 5672 |  | 9 | 9 | 1 | 0.00051414
0.42776 | 3881 |  | 14 | 14 | 1 | 0.00051414
0.42828 | 3576 |  | 1 | 1 | 1 | 0.00051414
0.42879 | 3755 |  | 2 | 2 | 1 | 0.00051414
0.42931 | 5676 |  | 4 | 4 | 1 | 0.00051414
0.42982 | 3489 |  | 5 | 5 | 1 | 0.00051414
0.43033 | 5578 |  | 1 | 1 | 1 | 0.00051414
0.43085 | 5579 |  | 1 | 1 | 1 | 0.00051414
0.43136 | 5091 |  | 1 | 1 | 1 | 0.00051414
0.43188 | 1975 |  | 2 | 2 | 1 | 0.00051414
0.43239 | 5092 |  | 1 | 1 | 1 | 0.00051414
0.4329 | 4006 |  | 1 | 1 | 1 | 0.00051414
0.43342 | 4922 |  | 1 | 1 | 1 | 0.00051414
0.43393 | 5576 |  | 1 | 1 | 1 | 0.00051414
0.43445 | 3758 |  | 2 | 2 | 1 | 0.00051414
0.43496 | 5094 |  | 2 | 2 | 1 | 0.00051414
0.43548 | 5095 |  | 2 | 2 | 1 | 0.00051414
0.43599 | 4772 |  | 35 | 35 | 1 | 0.00051414
0.4365 | 5096 |  | 1 | 1 | 1 | 0.00051414
0.43702 | 5097 |  | 1 | 1 | 1 | 0.00051414
0.43753 | 5582 |  | 1 | 1 | 1 | 0.00051414
0.43805 | 5904 |  | 1 | 1 | 1 | 0.00051414
0.43856 | 3864 |  | 2 | 2 | 1 | 0.00051414
0.43907 | 5615 |  | 2 | 2 | 1 | 0.00051414
0.43959 | 5917 |  | 30 | 30 | 1 | 0.00051414
0.4401 | 4663 |  | 250 | 250 | 1 | 0.00051414
0.44062 | 3577 |  | 1 | 1 | 1 | 0.00051414
0.44113 | 5919 |  | 3 | 3 | 1 | 0.00051414
0.44165 | 4923 |  | 1 | 1 | 1 | 0.00051414
0.44216 | 4817 |  | 10 | 10 | 1 | 0.00051414
0.44267 | 5920 |  | 15 | 15 | 1 | 0.00051414
0.44319 | 5741 |  | 1 | 1 | 1 | 0.00051414
0.4437 | 5742 |  | 2 | 2 | 1 | 0.00051414
0.44422 | 3930 |  | 40 | 40 | 1 | 0.00051414
0.44473 | 5743 |  | 2 | 2 | 1 | 0.00051414
0.44524 | 5556 |  | 1 | 1 | 1 | 0.00051414
0.44576 | 5614 |  | 3 | 3 | 1 | 0.00051414
0.44627 | 3766 |  | 3 | 3 | 1 | 0.00051414
0.44679 | 2147 |  | 3 | 3 | 1 | 0.00051414
0.4473 | 3490 |  | 11 | 11 | 1 | 0.00051414
0.44781 | 4623 |  | 11 | 11 | 1 | 0.00051414
0.44833 | 2200 |  | 3 | 3 | 1 | 0.00051414
0.44884 | 2204 |  | 3 | 3 | 1 | 0.00051414
0.44936 | 5744 |  | 2 | 2 | 1 | 0.00051414
0.44987 | 4818 |  | 10 | 10 | 1 | 0.00051414
0.45039 | 3762 |  | 2 | 2 | 1 | 0.00051414
0.4509 | 5619 |  | 2 | 2 | 1 | 0.00051414
0.45141 | 5745 |  | 2 | 2 | 1 | 0.00051414
0.45193 | 5746 |  | 3 | 3 | 1 | 0.00051414
0.45244 | 3906 |  | 25 | 25 | 1 | 0.00051414
0.45296 | 3799 |  | 4 | 4 | 1 | 0.00051414
0.45347 | 3810 |  | 2 | 2 | 1 | 0.00051414
0.45398 | 5678 |  | 2 | 2 | 1 | 0.00051414
0.4545 | 5679 |  | 5 | 5 | 1 | 0.00051414
0.45501 | 2229 |  | 1 | 1 | 1 | 0.00051414
0.45553 | 2230 |  | 1 | 1 | 1 | 0.00051414
0.45604 | 5747 |  | 4 | 4 | 1 | 0.00051414
0.45656 | 3578 |  | 1 | 1 | 1 | 0.00051414
0.45707 | 3797 |  | 5 | 5 | 1 | 0.00051414
0.45758 | 3970 |  | 10 | 10 | 1 | 0.00051414
0.4581 | 2231 |  | 2 | 2 | 1 | 0.00051414
0.45861 | 4924 |  | 1 | 1 | 1 | 0.00051414
0.45913 | 2232 |  | 2 | 2 | 1 | 0.00051414
0.45964 | 4624 |  | 2 | 2 | 1 | 0.00051414
0.46015 | 522 |  | 21 | 21 | 1 | 0.00051414
0.46067 | 2234 |  | 1 | 1 | 1 | 0.00051414
0.46118 | 1911 |  | 54 | 54 | 1 | 0.00051414
0.4617 | 2192 |  | 2 | 2 | 1 | 0.00051414
0.46221 | 2201 |  | 1 | 1 | 1 | 0.00051414
0.46272 | 3973 |  | 15 | 15 | 1 | 0.00051414
0.46324 | 2162 |  | 10 | 10 | 1 | 0.00051414
0.46375 | 3579 |  | 1 | 1 | 1 | 0.00051414
0.46427 | 4925 |  | 1 | 1 | 1 | 0.00051414
0.46478 | 4507 |  | 10 | 10 | 1 | 0.00051414
0.4653 | 2163 |  | 1 | 1 | 1 | 0.00051414
0.46581 | 6003 |  | 4 | 4 | 1 | 0.00051414
0.46632 | 5646 |  | 2 | 2 | 1 | 0.00051414
0.46684 | 4794 |  | 5 | 5 | 1 | 0.00051414
0.46735 | 4835 |  | 5 | 5 | 1 | 0.00051414
0.46787 | 5099 |  | 5 | 5 | 1 | 0.00051414
0.46838 | 4900 |  | 5 | 5 | 1 | 0.00051414
0.46889 | 3896 |  | 20 | 20 | 1 | 0.00051414
0.46941 | 5529 |  | 1 | 1 | 1 | 0.00051414
0.46992 | 5647 |  | 2 | 2 | 1 | 0.00051414
0.47044 | 2096 |  | 5 | 5 | 1 | 0.00051414
0.47095 | 5648 |  | 2 | 2 | 1 | 0.00051414
0.47147 | 3580 |  | 1 | 1 | 1 | 0.00051414
0.47198 | 5991 |  | 3 | 3 | 1 | 0.00051414
0.47249 | 2205 |  | 1 | 1 | 1 | 0.00051414
0.47301 | 4926 |  | 1 | 1 | 1 | 0.00051414
0.47352 | 5649 |  | 1 | 1 | 1 | 0.00051414
0.47404 | 3811 |  | 2 | 2 | 1 | 0.00051414
0.47455 | 5650 |  | 1 | 1 | 1 | 0.00051414
0.47506 | 5651 |  | 2 | 2 | 1 | 0.00051414
0.47558 | 3887 |  | 10 | 10 | 1 | 0.00051414
0.47609 | 3581 |  | 1 | 1 | 1 | 0.00051414
0.47661 | 5628 |  | 1 | 1 | 1 | 0.00051414
0.47712 | 6001 |  | 2 | 2 | 1 | 0.00051414
0.47763 | 5629 |  | 1 | 1 | 1 | 0.00051414
0.47815 | 5656 |  | 1 | 1 | 1 | 0.00051414
0.47866 | 5630 |  | 1 | 1 | 1 | 0.00051414
0.47918 | 6000 |  | 8 | 8 | 1 | 0.00051414
0.47969 | 4927 |  | 1 | 1 | 1 | 0.00051414
0.48021 | 6027 |  | 2 | 2 | 1 | 0.00051414
0.48072 | 6028 |  | 1 | 1 | 1 | 0.00051414
0.48123 | 5631 |  | 1 | 1 | 1 | 0.00051414
0.48175 | 5622 |  | 1 | 1 | 1 | 0.00051414
0.48226 | 5632 |  | 84 | 84 | 1 | 0.00051414
0.48278 | 5623 |  | 9 | 9 | 1 | 0.00051414
0.48329 | 5625 |  | 21 | 21 | 1 | 0.00051414
0.4838 | 5633 |  | 1 | 1 | 1 | 0.00051414
0.48432 | 1912 |  | 67 | 67 | 1 | 0.00051414
0.48483 | 6035 |  | 5 | 5 | 1 | 0.00051414
0.48535 | 5624 |  | 2 | 2 | 1 | 0.00051414
0.48586 | 6043 |  | 15 | 15 | 1 | 0.00051414
0.48638 | 6008 |  | 22 | 22 | 1 | 0.00051414
0.48689 | 4064 |  | 4 | 4 | 1 | 0.00051414
0.4874 | 4085 |  | 4 | 4 | 1 | 0.00051414
0.48792 | 6052 |  | 1 | 1 | 1 | 0.00051414
0.48843 | 6047 |  | 6 | 6 | 1 | 0.00051414
0.48895 | 6114 |  | 68 | 68 | 1 | 0.00051414
0.48946 | 2484 |  | 3 | 3 | 1 | 0.00051414
0.48997 | 3582 |  | 1 | 1 | 1 | 0.00051414
0.49049 | 5634 |  | 1 | 1 | 1 | 0.00051414
0.491 | 2097 |  | 5 | 5 | 1 | 0.00051414
0.49152 | 3325 |  | 3 | 3 | 1 | 0.00051414
0.49203 | 3786 |  | 2 | 2 | 1 | 0.00051414
0.49254 | 3785 |  | 3 | 3 | 1 | 0.00051414
0.49306 | 6074 |  | 7 | 7 | 1 | 0.00051414
0.49357 | 2811 |  | 1 | 1 | 1 | 0.00051414
0.49409 | 2812 |  | 1 | 1 | 1 | 0.00051414
0.4946 | 2813 |  | 1 | 1 | 1 | 0.00051414
0.49512 | 2814 |  | 1 | 1 | 1 | 0.00051414
0.49563 | 4007 |  | 1 | 1 | 1 | 0.00051414
0.49614 | 3583 |  | 1 | 1 | 1 | 0.00051414
0.49666 | 4083 |  | 4 | 4 | 1 | 0.00051414
0.49717 | 2173 |  | 2 | 2 | 1 | 0.00051414
0.49769 | 6048 |  | 24 | 24 | 1 | 0.00051414
0.4982 | 6096 |  | 5 | 5 | 1 | 0.00051414
0.49871 | 6057 |  | 6 | 6 | 1 | 0.00051414
0.49923 | 6099 |  | 6 | 6 | 1 | 0.00051414
0.49974 | 6100 |  | 7 | 7 | 1 | 0.00051414
0.50026 | 6545 |  | 210 | 210 | 1 | 0.00051414
0.50077 | 3584 |  | 1 | 1 | 1 | 0.00051414
0.50129 | 6097 |  | 6 | 6 | 1 | 0.00051414
0.5018 | 3459 |  | 26 | 26 | 1 | 0.00051414
0.50231 | 5927 |  | 69 | 69 | 1 | 0.00051414
0.50283 | 2195 |  | 3 | 3 | 1 | 0.00051414
0.50334 | 2196 |  | 1 | 1 | 1 | 0.00051414
0.50386 | 5754 |  | 1 | 1 | 1 | 0.00051414
0.50437 | 1914 |  | 58 | 58 | 1 | 0.00051414
0.50488 | 5755 |  | 1 | 1 | 1 | 0.00051414
0.5054 | 5756 |  | 1 | 1 | 1 | 0.00051414
0.50591 | 6109 |  | 7 | 7 | 1 | 0.00051414
0.50643 | 3585 |  | 1 | 1 | 1 | 0.00051414
0.50694 | 6452 |  | 13 | 13 | 1 | 0.00051414
0.50746 | 6453 |  | 13 | 13 | 1 | 0.00051414
0.50797 | 3806 |  | 2 | 2 | 1 | 0.00051414
0.50848 | 6130 |  | 6 | 6 | 1 | 0.00051414
0.509 | 6497 |  | 100 | 100 | 1 | 0.00051414
0.50951 | 638 |  | 1 | 1 | 1 | 0.00051414
0.51003 | 6077 |  | 1 | 1 | 1 | 0.00051414
0.51054 | 6110 |  | 7 | 7 | 1 | 0.00051414
0.51105 | 6480 |  | 75 | 75 | 1 | 0.00051414
0.51157 | 5925 |  | 42 | 42 | 1 | 0.00051414
0.51208 | 6112 |  | 2 | 2 | 1 | 0.00051414
0.5126 | 6455 |  | 41 | 41 | 1 | 0.00051414
0.51311 | 6132 |  | 10 | 10 | 1 | 0.00051414
0.51362 | 6456 |  | 18 | 18 | 1 | 0.00051414
0.51414 | 6392 |  | 1 | 1 | 1 | 0.00051414
0.51465 | 3586 |  | 1 | 1 | 1 | 0.00051414
0.51517 | 6536 |  | 45 | 45 | 1 | 0.00051414
0.51568 | 6549 |  | 146 | 146 | 1 | 0.00051414
0.5162 | 6550 |  | 104 | 104 | 1 | 0.00051414
0.51671 | 6457 |  | 23 | 23 | 1 | 0.00051414
0.51722 | 6458 |  | 32 | 32 | 1 | 0.00051414
0.51774 | 6459 |  | 21 | 21 | 1 | 0.00051414
0.51825 | 6460 |  | 28 | 28 | 1 | 0.00051414
0.51877 | 3802 |  | 3 | 3 | 1 | 0.00051414
0.51928 | 6461 |  | 57 | 57 | 1 | 0.00051414
0.51979 | 2169 |  | 3 | 3 | 1 | 0.00051414
0.52031 | 6546 |  | 155 | 155 | 1 | 0.00051414
0.52082 | 6465 |  | 34 | 34 | 1 | 0.00051414
0.52134 | 6479 |  | 50 | 50 | 1 | 0.00051414
0.52185 | 5921 |  | 6 | 6 | 1 | 0.00051414
0.52237 | 3956 |  | 3 | 3 | 1 | 0.00051414
0.52288 | 2170 |  | 3 | 3 | 1 | 0.00051414
0.52339 | 6468 |  | 27 | 27 | 1 | 0.00051414
0.52391 | 6134 |  | 22 | 22 | 1 | 0.00051414
0.52442 | 5922 |  | 12 | 12 | 1 | 0.00051414
0.52494 | 6116 |  | 20 | 20 | 1 | 0.00051414
0.52545 | 6469 |  | 3 | 3 | 1 | 0.00051414
0.52596 | 6537 |  | 53 | 53 | 1 | 0.00051414
0.52648 | 6075 |  | 1 | 1 | 1 | 0.00051414
0.52699 | 6030 |  | 2 | 2 | 1 | 0.00051414
0.52751 | 6544 |  | 37 | 37 | 1 | 0.00051414
0.52802 | 3587 |  | 1 | 1 | 1 | 0.00051414
0.52853 | 6113 |  | 1 | 1 | 1 | 0.00051414
0.52905 | 6473 |  | 3 | 3 | 1 | 0.00051414
0.52956 | 5484 |  | 5 | 5 | 1 | 0.00051414
0.53008 | 6391 |  | 1 | 1 | 1 | 0.00051414
0.53059 | 6547 |  | 81 | 81 | 1 | 0.00051414
0.53111 | 6573 |  | 1 | 1 | 1 | 0.00051414
0.53162 | 6520 |  | 4 | 4 | 1 | 0.00051414
0.53213 | 6538 |  | 71 | 71 | 1 | 0.00051414
0.53265 | 6474 |  | 4 | 4 | 1 | 0.00051414
0.53316 | 6574 |  | 3 | 3 | 1 | 0.00051414
0.53368 | 6080 |  | 15 | 15 | 1 | 0.00051414
0.53419 | 6539 |  | 89 | 89 | 1 | 0.00051414
0.5347 | 3910 |  | 5 | 5 | 1 | 0.00051414
0.53522 | 6493 |  | 51 | 51 | 1 | 0.00051414
0.53573 | 2052 |  | 2 | 2 | 1 | 0.00051414
0.53625 | 6475 |  | 6 | 6 | 1 | 0.00051414
0.53676 | 1918 |  | 1 | 1 | 1 | 0.00051414
0.53728 | 1927 |  | 1 | 1 | 1 | 0.00051414
0.53779 | 1936 |  | 1 | 1 | 1 | 0.00051414
0.5383 | 1945 |  | 1 | 1 | 1 | 0.00051414
0.53882 | 4988 |  | 1 | 1 | 1 | 0.00051414
0.53933 | 5983 |  | 10 | 10 | 1 | 0.00051414
0.53985 | 3588 |  | 1 | 1 | 1 | 0.00051414
0.54036 | 4093 |  | 4 | 4 | 1 | 0.00051414
0.54087 | 6477 |  | 18 | 18 | 1 | 0.00051414
0.54139 | 6478 |  | 19 | 19 | 1 | 0.00051414
0.5419 | 6444 |  | 4 | 4 | 1 | 0.00051414
0.54242 | 6521 |  | 19 | 19 | 1 | 0.00051414
0.54293 | 6522 |  | 21 | 21 | 1 | 0.00051414
0.54344 | 6523 |  | 21 | 21 | 1 | 0.00051414
0.54396 | 4016 |  | 15 | 15 | 1 | 0.00051414
0.54447 | 6541 |  | 14 | 14 | 1 | 0.00051414
0.54499 | 5761 |  | 4 | 4 | 1 | 0.00051414
0.5455 | 6575 |  | 1 | 1 | 1 | 0.00051414
0.54602 | 6576 |  | 7 | 7 | 1 | 0.00051414
0.54653 | 6540 |  | 70 | 70 | 1 | 0.00051414
0.54704 | 6577 |  | 1 | 1 | 1 | 0.00051414
0.54756 | 3589 |  | 1 | 1 | 1 | 0.00051414
0.54807 | 6578 |  | 3 | 3 | 1 | 0.00051414
0.54859 | 6513 |  | 5 | 5 | 1 | 0.00051414
0.5491 | 5691 |  | 1 | 1 | 1 | 0.00051414
0.54961 | 6042 |  | 5 | 5 | 1 | 0.00051414
0.55013 | 2579 |  | 1 | 1 | 1 | 0.00051414
0.55064 | 6487 |  | 30 | 30 | 1 | 0.00051414
0.55116 | 6488 |  | 35 | 35 | 1 | 0.00051414
0.55167 | 6489 |  | 35 | 35 | 1 | 0.00051414
0.55219 | 6490 |  | 54 | 54 | 1 | 0.00051414
0.5527 | 6491 |  | 30 | 30 | 1 | 0.00051414
0.55321 | 6492 |  | 30 | 30 | 1 | 0.00051414
0.55373 | 6494 |  | 55 | 55 | 1 | 0.00051414
0.55424 | 6495 |  | 25 | 25 | 1 | 0.00051414
0.55476 | 6500 |  | 25 | 25 | 1 | 0.00051414
0.55527 | 6503 |  | 50 | 50 | 1 | 0.00051414
0.55578 | 6507 |  | 16 | 16 | 1 | 0.00051414
0.5563 | 6508 |  | 60 | 60 | 1 | 0.00051414
0.55681 | 6509 |  | 65 | 65 | 1 | 0.00051414
0.55733 | 6580 |  | 1 | 1 | 1 | 0.00051414
0.55784 | 4078 |  | 4 | 4 | 1 | 0.00051414
0.55835 | 4082 |  | 4 | 4 | 1 | 0.00051414
0.55887 | 6496 |  | 20 | 20 | 1 | 0.00051414
0.55938 | 6524 |  | 16 | 16 | 1 | 0.00051414
0.5599 | 6622 |  | 6 | 6 | 1 | 0.00051414
0.56041 | 6498 |  | 50 | 50 | 1 | 0.00051414
0.56093 | 6499 |  | 30 | 30 | 1 | 0.00051414
0.56144 | 6501 |  | 60 | 60 | 1 | 0.00051414
0.56195 | 6502 |  | 40 | 40 | 1 | 0.00051414
0.56247 | 6506 |  | 25 | 25 | 1 | 0.00051414
0.56298 | 6826 |  | 5 | 5 | 1 | 0.00051414
0.5635 | 6073 |  | 2 | 2 | 1 | 0.00051414
0.56401 | 6554 |  | 12 | 12 | 1 | 0.00051414
0.56452 | 3590 |  | 1 | 1 | 1 | 0.00051414
0.56504 | 2646 |  | 4 | 4 | 1 | 0.00051414
0.56555 | 6623 |  | 3 | 3 | 1 | 0.00051414
0.56607 | 6591 |  | 1 | 1 | 1 | 0.00051414
0.56658 | 6565 |  | 8 | 8 | 1 | 0.00051414
0.5671 | 6527 |  | 8 | 8 | 1 | 0.00051414
0.56761 | 6825 |  | 14 | 14 | 1 | 0.00051414
0.56812 | 6543 |  | 71 | 71 | 1 | 0.00051414
0.56864 | 6528 |  | 3 | 3 | 1 | 0.00051414
0.56915 | 6555 |  | 6 | 6 | 1 | 0.00051414
0.56967 | 2469 |  | 21 | 21 | 1 | 0.00051414
0.57018 | 2470 |  | 21 | 21 | 1 | 0.00051414
0.57069 | 4700 |  | 1 | 1 | 1 | 0.00051414
0.57121 | 3591 |  | 1 | 1 | 1 | 0.00051414
0.57172 | 5482 |  | 1 | 1 | 1 | 0.00051414
0.57224 | 6557 |  | 5 | 5 | 1 | 0.00051414
0.57275 | 6566 |  | 11 | 11 | 1 | 0.00051414
0.57326 | 6525 |  | 11 | 11 | 1 | 0.00051414
0.57378 | 6526 |  | 17 | 17 | 1 | 0.00051414
0.57429 | 6441 |  | 2 | 2 | 1 | 0.00051414
0.57481 | 6548 |  | 45 | 45 | 1 | 0.00051414
0.57532 | 6556 |  | 15 | 15 | 1 | 0.00051414
0.57584 | 3947 |  | 15 | 15 | 1 | 0.00051414
0.57635 | 2485 |  | 2 | 2 | 1 | 0.00051414
0.57686 | 2651 |  | 18 | 18 | 1 | 0.00051414
0.57738 | 6792 |  | 2 | 2 | 1 | 0.00051414
0.57789 | 2486 |  | 2 | 2 | 1 | 0.00051414
0.57841 | 4065 |  | 4 | 4 | 1 | 0.00051414
0.57892 | 4073 |  | 4 | 4 | 1 | 0.00051414
0.57943 | 4074 |  | 4 | 4 | 1 | 0.00051414
0.57995 | 5664 |  | 4 | 4 | 1 | 0.00051414
0.58046 | 3592 |  | 1 | 1 | 1 | 0.00051414
0.58098 | 2487 |  | 1 | 1 | 1 | 0.00051414
0.58149 | 2488 |  | 3 | 3 | 1 | 0.00051414
0.58201 | 4096 |  | 1 | 1 | 1 | 0.00051414
0.58252 | 4097 |  | 2 | 2 | 1 | 0.00051414
0.58303 | 5895 |  | 1 | 1 | 1 | 0.00051414
0.58355 | 6542 |  | 30 | 30 | 1 | 0.00051414
0.58406 | 4100 |  | 8 | 8 | 1 | 0.00051414
0.58458 | 4067 |  | 4 | 4 | 1 | 0.00051414
0.58509 | 6530 |  | 2 | 2 | 1 | 0.00051414
0.5856 | 6799 |  | 4 | 4 | 1 | 0.00051414
0.58612 | 6910 |  | 17 | 17 | 1 | 0.00051414
0.58663 | 6798 |  | 1 | 1 | 1 | 0.00051414
0.58715 | 2490 |  | 4 | 4 | 1 | 0.00051414
0.58766 | 6659 |  | 2 | 2 | 1 | 0.00051414
0.58817 | 2491 |  | 4 | 4 | 1 | 0.00051414
0.58869 | 6860 |  | 20 | 20 | 1 | 0.00051414
0.5892 | 3832 |  | 3 | 3 | 1 | 0.00051414
0.58972 | 3833 |  | 3 | 3 | 1 | 0.00051414
0.59023 | 6929 |  | 91 | 91 | 1 | 0.00051414
0.59075 | 7020 |  | 2 | 2 | 1 | 0.00051414
0.59126 | 6594 |  | 12 | 12 | 1 | 0.00051414
0.59177 | 6595 |  | 12 | 12 | 1 | 0.00051414
0.59229 | 6596 |  | 27 | 27 | 1 | 0.00051414
0.5928 | 6793 |  | 3 | 3 | 1 | 0.00051414
0.59332 | 6794 |  | 2 | 2 | 1 | 0.00051414
0.59383 | 3593 |  | 1 | 1 | 1 | 0.00051414
0.59434 | 5693 |  | 2 | 2 | 1 | 0.00051414
0.59486 | 7021 |  | 3 | 3 | 1 | 0.00051414
0.59537 | 529 |  | 1 | 1 | 1 | 0.00051414
0.59589 | 535 |  | 1 | 1 | 1 | 0.00051414
0.5964 | 590 |  | 1 | 1 | 1 | 0.00051414
0.59692 | 621 |  | 1 | 1 | 1 | 0.00051414
0.59743 | 6558 |  | 25 | 25 | 1 | 0.00051414
0.59794 | 6801 |  | 1 | 1 | 1 | 0.00051414
0.59846 | 3966 |  | 5 | 5 | 1 | 0.00051414
0.59897 | 6911 |  | 1 | 1 | 1 | 0.00051414
0.59949 | 4104 |  | 1 | 1 | 1 | 0.00051414
0.6 | 3831 |  | 3 | 3 | 1 | 0.00051414
0.60051 | 6912 |  | 5 | 5 | 1 | 0.00051414
0.60103 | 6931 |  | 2 | 2 | 1 | 0.00051414
0.60154 | 3835 |  | 2 | 2 | 1 | 0.00051414
0.60206 | 4077 |  | 4 | 4 | 1 | 0.00051414
0.60257 | 4079 |  | 4 | 4 | 1 | 0.00051414
0.60308 | 4080 |  | 4 | 4 | 1 | 0.00051414
0.6036 | 5665 |  | 4 | 4 | 1 | 0.00051414
0.60411 | 6915 |  | 135 | 135 | 1 | 0.00051414
0.60463 | 4106 |  | 2 | 2 | 1 | 0.00051414
0.60514 | 4108 |  | 8 | 8 | 1 | 0.00051414
0.60566 | 4186 |  | 8 | 8 | 1 | 0.00051414
0.60617 | 585 |  | 1 | 1 | 1 | 0.00051414
0.60668 | 541 |  | 1 | 1 | 1 | 0.00051414
0.6072 | 547 |  | 1 | 1 | 1 | 0.00051414
0.60771 | 553 |  | 1 | 1 | 1 | 0.00051414
0.60823 | 596 |  | 1 | 1 | 1 | 0.00051414
0.60874 | 602 |  | 1 | 1 | 1 | 0.00051414
0.60925 | 608 |  | 1 | 1 | 1 | 0.00051414
0.60977 | 5493 |  | 4 | 4 | 1 | 0.00051414
0.61028 | 5663 |  | 4 | 4 | 1 | 0.00051414
0.6108 | 6597 |  | 4 | 4 | 1 | 0.00051414
0.61131 | 6599 |  | 4 | 4 | 1 | 0.00051414
0.61183 | 6600 |  | 5 | 5 | 1 | 0.00051414
0.61234 | 3594 |  | 1 | 1 | 1 | 0.00051414
0.61285 | 6930 |  | 6 | 6 | 1 | 0.00051414
0.61337 | 7006 |  | 10 | 10 | 1 | 0.00051414
0.61388 | 6603 |  | 9 | 9 | 1 | 0.00051414
0.6144 | 6083 |  | 10 | 10 | 1 | 0.00051414
0.61491 | 6800 |  | 4 | 4 | 1 | 0.00051414
0.61542 | 3813 |  | 1 | 1 | 1 | 0.00051414
0.61594 | 3816 |  | 3 | 3 | 1 | 0.00051414
0.61645 | 7007 |  | 24 | 24 | 1 | 0.00051414
0.61697 | 6605 |  | 8 | 8 | 1 | 0.00051414
0.61748 | 4113 |  | 2 | 2 | 1 | 0.00051414
0.61799 | 4066 |  | 4 | 4 | 1 | 0.00051414
0.61851 | 4111 |  | 2 | 2 | 1 | 0.00051414
0.61902 | 6601 |  | 3 | 3 | 1 | 0.00051414
0.61954 | 7008 |  | 2 | 2 | 1 | 0.00051414
0.62005 | 6863 |  | 3 | 3 | 1 | 0.00051414
0.62057 | 6861 |  | 5 | 5 | 1 | 0.00051414
0.62108 | 7028 |  | 4 | 4 | 1 | 0.00051414
0.62159 | 7019 |  | 13 | 13 | 1 | 0.00051414
0.62211 | 4068 |  | 4 | 4 | 1 | 0.00051414
0.62262 | 6608 |  | 2 | 2 | 1 | 0.00051414
0.62314 | 6865 |  | 5 | 5 | 1 | 0.00051414
0.62365 | 3595 |  | 1 | 1 | 1 | 0.00051414
0.62416 | 6559 |  | 1 | 1 | 1 | 0.00051414
0.62468 | 6914 |  | 4 | 4 | 1 | 0.00051414
0.62519 | 7032 |  | 5 | 5 | 1 | 0.00051414
0.62571 | 6932 |  | 14 | 14 | 1 | 0.00051414
0.62622 | 7034 |  | 2 | 2 | 1 | 0.00051414
0.62674 | 6864 |  | 5 | 5 | 1 | 0.00051414
0.62725 | 6862 |  | 2 | 2 | 1 | 0.00051414
0.62776 | 1880 |  | 1 | 1 | 1 | 0.00051414
0.62828 | 6606 |  | 1 | 1 | 1 | 0.00051414
0.62879 | 4070 |  | 4 | 4 | 1 | 0.00051414
0.62931 | 4075 |  | 4 | 4 | 1 | 0.00051414
0.62982 | 6789 |  | 1 | 1 | 1 | 0.00051414
0.63033 | 7030 |  | 9 | 9 | 1 | 0.00051414
0.63085 | 2580 |  | 14 | 14 | 1 | 0.00051414
0.63136 | 6712 |  | 1 | 1 | 1 | 0.00051414
0.63188 | 6610 |  | 1 | 1 | 1 | 0.00051414
0.63239 | 6531 |  | 6 | 6 | 1 | 0.00051414
0.6329 | 6713 |  | 1 | 1 | 1 | 0.00051414
0.63342 | 6705 |  | 2 | 2 | 1 | 0.00051414
0.63393 | 3596 |  | 1 | 1 | 1 | 0.00051414
0.63445 | 4130 |  | 3 | 3 | 1 | 0.00051414
0.63496 | 4101 |  | 6 | 6 | 1 | 0.00051414
0.63548 | 2428 |  | 1 | 1 | 1 | 0.00051414
0.63599 | 4071 |  | 4 | 4 | 1 | 0.00051414
0.6365 | 7084 |  | 4 | 4 | 1 | 0.00051414
0.63702 | 2429 |  | 1 | 1 | 1 | 0.00051414
0.63753 | 6135 |  | 2 | 2 | 1 | 0.00051414
0.63805 | 6136 |  | 3 | 3 | 1 | 0.00051414
0.63856 | 6137 |  | 2 | 2 | 1 | 0.00051414
0.63907 | 6138 |  | 3 | 3 | 1 | 0.00051414
0.63959 | 6802 |  | 4 | 4 | 1 | 0.00051414
0.6401 | 7117 |  | 25 | 25 | 1 | 0.00051414
0.64062 | 2116 |  | 1 | 1 | 1 | 0.00051414
0.64113 | 2583 |  | 15 | 15 | 1 | 0.00051414
0.64165 | 3597 |  | 1 | 1 | 1 | 0.00051414
0.64216 | 2117 |  | 1 | 1 | 1 | 0.00051414
0.64267 | 2118 |  | 3 | 3 | 1 | 0.00051414
0.64319 | 7023 |  | 4 | 4 | 1 | 0.00051414
0.6437 | 4119 |  | 2 | 2 | 1 | 0.00051414
0.64422 | 2684 |  | 1 | 1 | 1 | 0.00051414
0.64473 | 6560 |  | 5 | 5 | 1 | 0.00051414
0.64524 | 6778 |  | 9 | 9 | 1 | 0.00051414
0.64576 | 2593 |  | 1 | 1 | 1 | 0.00051414
0.64627 | 2603 |  | 1 | 1 | 1 | 0.00051414
0.64679 | 4666 |  | 4 | 4 | 1 | 0.00051414
0.6473 | 4126 |  | 2 | 2 | 1 | 0.00051414
0.64781 | 4127 |  | 2 | 2 | 1 | 0.00051414
0.64833 | 1766 |  | 13 | 13 | 1 | 0.00051414
0.64884 | 1767 |  | 13 | 13 | 1 | 0.00051414
0.64936 | 2656 |  | 14 | 14 | 1 | 0.00051414
0.64987 | 2372 |  | 1 | 1 | 1 | 0.00051414
0.65039 | 5816 |  | 7 | 7 | 1 | 0.00051414
0.6509 | 3598 |  | 1 | 1 | 1 | 0.00051414
0.65141 | 1869 |  | 1 | 1 | 1 | 0.00051414
0.65193 | 2319 |  | 5 | 5 | 1 | 0.00051414
0.65244 | 4121 |  | 2 | 2 | 1 | 0.00051414
0.65296 | 579 |  | 1 | 1 | 1 | 0.00051414
0.65347 | 2322 |  | 5 | 5 | 1 | 0.00051414
0.65398 | 6791 |  | 4 | 4 | 1 | 0.00051414
0.6545 | 6666 |  | 2 | 2 | 1 | 0.00051414
0.65501 | 6667 |  | 2 | 2 | 1 | 0.00051414
0.65553 | 6668 |  | 2 | 2 | 1 | 0.00051414
0.65604 | 6669 |  | 2 | 2 | 1 | 0.00051414
0.65656 | 6671 |  | 2 | 2 | 1 | 0.00051414
0.65707 | 2363 |  | 1 | 1 | 1 | 0.00051414
0.65758 | 2381 |  | 1 | 1 | 1 | 0.00051414
0.6581 | 7126 |  | 1 | 1 | 1 | 0.00051414
0.65861 | 4148 |  | 2 | 2 | 1 | 0.00051414
0.65913 | 3599 |  | 1 | 1 | 1 | 0.00051414
0.65964 | 7164 |  | 8 | 8 | 1 | 0.00051414
0.66015 | 5522 |  | 1 | 1 | 1 | 0.00051414
0.66067 | 2599 |  | 15 | 15 | 1 | 0.00051414
0.66118 | 4076 |  | 4 | 4 | 1 | 0.00051414
0.6617 | 3600 |  | 1 | 1 | 1 | 0.00051414
0.66221 | 4161 |  | 1 | 1 | 1 | 0.00051414
0.66272 | 4162 |  | 2 | 2 | 1 | 0.00051414
0.66324 | 2600 |  | 3 | 3 | 1 | 0.00051414
0.66375 | 4163 |  | 2 | 2 | 1 | 0.00051414
0.66427 | 5703 |  | 1 | 1 | 1 | 0.00051414
0.66478 | 5459 |  | 1 | 1 | 1 | 0.00051414
0.6653 | 7183 |  | 3 | 3 | 1 | 0.00051414
0.66581 | 1771 |  | 15 | 15 | 1 | 0.00051414
0.66632 | 2458 |  | 1 | 1 | 1 | 0.00051414
0.66684 | 2345 |  | 1 | 1 | 1 | 0.00051414
0.66735 | 2354 |  | 1 | 1 | 1 | 0.00051414
0.66787 | 2390 |  | 1 | 1 | 1 | 0.00051414
0.66838 | 4151 |  | 10 | 10 | 1 | 0.00051414
0.66889 | 5792 |  | 3 | 3 | 1 | 0.00051414
0.66941 | 1774 |  | 1 | 1 | 1 | 0.00051414
0.66992 | 5569 |  | 10 | 10 | 1 | 0.00051414
0.67044 | 7181 |  | 1 | 1 | 1 | 0.00051414
0.67095 | 2658 |  | 1 | 1 | 1 | 0.00051414
0.67147 | 2437 |  | 4 | 4 | 1 | 0.00051414
0.67198 | 5796 |  | 1 | 1 | 1 | 0.00051414
0.67249 | 5797 |  | 1 | 1 | 1 | 0.00051414
0.67301 | 2439 |  | 7 | 7 | 1 | 0.00051414
0.67352 | 2182 |  | 3 | 3 | 1 | 0.00051414
0.67404 | 5462 |  | 1 | 1 | 1 | 0.00051414
0.67455 | 4199 |  | 8 | 8 | 1 | 0.00051414
0.67506 | 2258 |  | 1 | 1 | 1 | 0.00051414
0.67558 | 2259 |  | 1 | 1 | 1 | 0.00051414
0.67609 | 2327 |  | 1 | 1 | 1 | 0.00051414
0.67661 | 7182 |  | 2 | 2 | 1 | 0.00051414
0.67712 | 2260 |  | 1 | 1 | 1 | 0.00051414
0.67763 | 2608 |  | 15 | 15 | 1 | 0.00051414
0.67815 | 2689 |  | 15 | 15 | 1 | 0.00051414
0.67866 | 4200 |  | 5 | 5 | 1 | 0.00051414
0.67918 | 2178 |  | 3 | 3 | 1 | 0.00051414
0.67969 | 2315 |  | 10 | 10 | 1 | 0.00051414
0.68021 | 5706 |  | 1 | 1 | 1 | 0.00051414
0.68072 | 6979 |  | 5 | 5 | 1 | 0.00051414
0.68123 | 5824 |  | 2 | 2 | 1 | 0.00051414
0.68175 | 2316 |  | 15 | 15 | 1 | 0.00051414
0.68226 | 6724 |  | 3 | 3 | 1 | 0.00051414
0.68278 | 4177 |  | 3 | 3 | 1 | 0.00051414
0.68329 | 6567 |  | 1 | 1 | 1 | 0.00051414
0.6838 | 6568 |  | 14 | 14 | 1 | 0.00051414
0.68432 | 4703 |  | 5 | 5 | 1 | 0.00051414
0.68483 | 4172 |  | 2 | 2 | 1 | 0.00051414
0.68535 | 5709 |  | 3 | 3 | 1 | 0.00051414
0.68586 | 5710 |  | 3 | 3 | 1 | 0.00051414
0.68638 | 5830 |  | 1 | 1 | 1 | 0.00051414
0.68689 | 5827 |  | 1 | 1 | 1 | 0.00051414
0.6874 | 6956 |  | 1 | 1 | 1 | 0.00051414
0.68792 | 5694 |  | 1 | 1 | 1 | 0.00051414
0.68843 | 5697 |  | 1 | 1 | 1 | 0.00051414
0.68895 | 5815 |  | 9 | 9 | 1 | 0.00051414
0.68946 | 6954 |  | 1 | 1 | 1 | 0.00051414
0.68997 | 6961 |  | 2 | 2 | 1 | 0.00051414
0.69049 | 1776 |  | 13 | 13 | 1 | 0.00051414
0.691 | 2610 |  | 3 | 3 | 1 | 0.00051414
0.69152 | 6985 |  | 6 | 6 | 1 | 0.00051414
0.69203 | 2691 |  | 3 | 3 | 1 | 0.00051414
0.69254 | 6993 |  | 3 | 3 | 1 | 0.00051414
0.69306 | 5831 |  | 1 | 1 | 1 | 0.00051414
0.69357 | 5517 |  | 1 | 1 | 1 | 0.00051414
0.69409 | 6965 |  | 3 | 3 | 1 | 0.00051414
0.6946 | 1777 |  | 1 | 1 | 1 | 0.00051414
0.69512 | 6517 |  | 2 | 2 | 1 | 0.00051414
0.69563 | 1780 |  | 1 | 1 | 1 | 0.00051414
0.69614 | 2461 |  | 1 | 1 | 1 | 0.00051414
0.69666 | 5996 |  | 190 | 195 | 1.0263 | 0.00051414
0.69717 | 4784 |  | 36 | 37 | 1.0278 | 0.00051414
0.69769 | 5995 |  | 190 | 196 | 1.0316 | 0.00051414
0.6982 | 6386 |  | 135 | 141 | 1.0444 | 0.00051414
0.69871 | 5547 |  | 317 | 334 | 1.0536 | 0.00051414
0.69923 | 4768 |  | 35 | 37 | 1.0571 | 0.00051414
0.69974 | 2364 |  | 15 | 16 | 1.0667 | 0.00051414
0.70026 | 4351 |  | 108 | 116 | 1.0741 | 0.00051414
0.70077 | 6512 |  | 27 | 29 | 1.0741 | 0.00051414
0.70129 | 4295 |  | 157 | 170 | 1.0828 | 0.00051414
0.7018 | 4980 |  | 154 | 167 | 1.0844 | 0.00051414
0.70231 | 3697 |  | 20 | 22 | 1.1 | 0.00051414
0.70283 | 3857 |  | 40 | 44 | 1.1 | 0.00051414
0.70334 | 4373 |  | 135 | 150 | 1.1111 | 0.00051414
0.70386 | 4374 |  | 135 | 150 | 1.1111 | 0.00051414
0.70437 | 4375 |  | 135 | 150 | 1.1111 | 0.00051414
0.70488 | 4376 |  | 135 | 150 | 1.1111 | 0.00051414
0.7054 | 4377 |  | 135 | 150 | 1.1111 | 0.00051414
0.70591 | 4378 |  | 135 | 150 | 1.1111 | 0.00051414
0.70643 | 4320 |  | 121 | 136 | 1.124 | 0.00051414
0.70694 | 5690 |  | 8 | 9 | 1.125 | 0.00051414
0.70746 | 4129 |  | 8 | 9 | 1.125 | 0.00051414
0.70797 | 4314 |  | 120 | 136 | 1.1333 | 0.00051414
0.70848 | 2598 |  | 15 | 17 | 1.1333 | 0.00051414
0.709 | 519 |  | 20 | 23 | 1.15 | 0.00051414
0.70951 | 3941 |  | 60 | 70 | 1.1667 | 0.00051414
0.71003 | 5912 |  | 30 | 35 | 1.1667 | 0.00051414
0.71054 | 6033 |  | 77 | 90 | 1.1688 | 0.00051414
0.71105 | 7022 |  | 132 | 156 | 1.1818 | 0.00051414
0.71157 | 4154 |  | 11 | 13 | 1.1818 | 0.00051414
0.71208 | 4354 |  | 103 | 122 | 1.1845 | 0.00051414
0.7126 | 6451 |  | 103 | 122 | 1.1845 | 0.00051414
0.71311 | 5965 |  | 65 | 77 | 1.1846 | 0.00051414
0.71362 | 2478 |  | 65 | 77 | 1.1846 | 0.00051414
0.71414 | 6485 |  | 16 | 19 | 1.1875 | 0.00051414
0.71465 | 1884 |  | 16 | 19 | 1.1875 | 0.00051414
0.71517 | 6466 |  | 81 | 97 | 1.1975 | 0.00051414
0.71568 | 3842 |  | 60 | 72 | 1.2 | 0.00051414
0.7162 | 6036 |  | 110 | 132 | 1.2 | 0.00051414
0.71671 | 3891 |  | 50 | 60 | 1.2 | 0.00051414
0.71722 | 4622 |  | 15 | 18 | 1.2 | 0.00051414
0.71774 | 3830 |  | 5 | 6 | 1.2 | 0.00051414
0.71825 | 4362 |  | 177 | 213 | 1.2034 | 0.00051414
0.71877 | 5951 |  | 130 | 157 | 1.2077 | 0.00051414
0.71928 | 6454 |  | 105 | 127 | 1.2095 | 0.00051414
0.71979 | 4758 |  | 33 | 40 | 1.2121 | 0.00051414
0.72031 | 4759 |  | 33 | 40 | 1.2121 | 0.00051414
0.72082 | 2605 |  | 14 | 17 | 1.2143 | 0.00051414
0.72134 | 3982 |  | 60 | 73 | 1.2167 | 0.00051414
0.72185 | 5090 |  | 101 | 125 | 1.2376 | 0.00051414
0.72237 | 3972 |  | 50 | 62 | 1.24 | 0.00051414
0.72288 | 6481 |  | 115 | 143 | 1.2435 | 0.00051414
0.72339 | 5882 |  | 41 | 51 | 1.2439 | 0.00051414
0.72391 | 5949 |  | 125 | 156 | 1.248 | 0.00051414
0.72442 | 4755 |  | 40 | 50 | 1.25 | 0.00051414
0.72494 | 5760 |  | 4 | 5 | 1.25 | 0.00051414
0.72545 | 3915 |  | 4 | 5 | 1.25 | 0.00051414
0.72596 | 4069 |  | 4 | 5 | 1.25 | 0.00051414
0.72648 | 6723 |  | 4 | 5 | 1.25 | 0.00051414
0.72699 | 5692 |  | 59 | 74 | 1.2542 | 0.00051414
0.72751 | 4767 |  | 35 | 44 | 1.2571 | 0.00051414
0.72802 | 4783 |  | 35 | 44 | 1.2571 | 0.00051414
0.72853 | 2382 |  | 15 | 19 | 1.2667 | 0.00051414
0.72905 | 3824 |  | 80 | 102 | 1.275 | 0.00051414
0.72956 | 3983 |  | 25 | 32 | 1.28 | 0.00051414
0.73008 | 3709 |  | 7 | 9 | 1.2857 | 0.00051414
0.73059 | 3710 |  | 7 | 9 | 1.2857 | 0.00051414
0.73111 | 3883 |  | 75 | 97 | 1.2933 | 0.00051414
0.73162 | 4553 |  | 85 | 110 | 1.2941 | 0.00051414
0.73213 | 4800 |  | 10 | 13 | 1.3 | 0.00051414
0.73265 | 5657 |  | 10 | 13 | 1.3 | 0.00051414
0.73316 | 3998 |  | 10 | 13 | 1.3 | 0.00051414
0.73368 | 4198 |  | 20 | 26 | 1.3 | 0.00051414
0.73419 | 4285 |  | 152 | 199 | 1.3092 | 0.00051414
0.7347 | 5609 |  | 159 | 209 | 1.3145 | 0.00051414
0.73522 | 4340 |  | 99 | 132 | 1.3333 | 0.00051414
0.73573 | 3700 |  | 3 | 4 | 1.3333 | 0.00051414
0.73625 | 4836 |  | 3 | 4 | 1.3333 | 0.00051414
0.73676 | 5620 |  | 3 | 4 | 1.3333 | 0.00051414
0.73728 | 3834 |  | 3 | 4 | 1.3333 | 0.00051414
0.73779 | 4092 |  | 6 | 8 | 1.3333 | 0.00051414
0.7383 | 6081 |  | 15 | 20 | 1.3333 | 0.00051414
0.73882 | 4480 |  | 43 | 58 | 1.3488 | 0.00051414
0.73933 | 4482 |  | 43 | 58 | 1.3488 | 0.00051414
0.73985 | 4483 |  | 43 | 58 | 1.3488 | 0.00051414
0.74036 | 632 |  | 80 | 109 | 1.3625 | 0.00051414
0.74087 | 3657 |  | 120 | 164 | 1.3667 | 0.00051414
0.74139 | 2341 |  | 16 | 22 | 1.375 | 0.00051414
0.7419 | 5984 |  | 31 | 43 | 1.3871 | 0.00051414
0.74242 | 3950 |  | 80 | 111 | 1.3875 | 0.00051414
0.74293 | 3961 |  | 80 | 111 | 1.3875 | 0.00051414
0.74344 | 3904 |  | 10 | 14 | 1.4 | 0.00051414
0.74396 | 2365 |  | 15 | 21 | 1.4 | 0.00051414
0.74447 | 2355 |  | 15 | 21 | 1.4 | 0.00051414
0.74499 | 6050 |  | 170 | 240 | 1.4118 | 0.00051414
0.7455 | 3467 |  | 24 | 34 | 1.4167 | 0.00051414
0.74602 | 6472 |  | 55 | 78 | 1.4182 | 0.00051414
0.74653 | 3611 |  | 40 | 57 | 1.425 | 0.00051414
0.74704 | 5523 |  | 14 | 20 | 1.4286 | 0.00051414
0.74756 | 3871 |  | 30 | 43 | 1.4333 | 0.00051414
0.74807 | 3859 |  | 30 | 43 | 1.4333 | 0.00051414
0.74859 | 2416 |  | 45 | 65 | 1.4444 | 0.00051414
0.7491 | 2417 |  | 45 | 65 | 1.4444 | 0.00051414
0.74961 | 3641 |  | 20 | 29 | 1.45 | 0.00051414
0.75013 | 3962 |  | 80 | 116 | 1.45 | 0.00051414
0.75064 | 4769 |  | 35 | 51 | 1.4571 | 0.00051414
0.75116 | 4785 |  | 35 | 51 | 1.4571 | 0.00051414
0.75167 | 5463 |  | 15 | 22 | 1.4667 | 0.00051414
0.75219 | 4790 |  | 36 | 53 | 1.4722 | 0.00051414
0.7527 | 5764 |  | 206 | 304 | 1.4757 | 0.00051414
0.75321 | 5763 |  | 206 | 305 | 1.4806 | 0.00051414
0.75373 | 3719 |  | 2 | 3 | 1.5 | 0.00051414
0.75424 | 3721 |  | 2 | 3 | 1.5 | 0.00051414
0.75476 | 4627 |  | 2 | 3 | 1.5 | 0.00051414
0.75527 | 3745 |  | 2 | 3 | 1.5 | 0.00051414
0.75578 | 3748 |  | 2 | 3 | 1.5 | 0.00051414
0.7563 | 3861 |  | 6 | 9 | 1.5 | 0.00051414
0.75681 | 5577 |  | 2 | 3 | 1.5 | 0.00051414
0.75733 | 5613 |  | 2 | 3 | 1.5 | 0.00051414
0.75784 | 5093 |  | 2 | 3 | 1.5 | 0.00051414
0.75835 | 5894 |  | 90 | 135 | 1.5 | 0.00051414
0.75887 | 4889 |  | 12 | 18 | 1.5 | 0.00051414
0.75938 | 4894 |  | 12 | 18 | 1.5 | 0.00051414
0.7599 | 3978 |  | 80 | 120 | 1.5 | 0.00051414
0.76041 | 5653 |  | 2 | 3 | 1.5 | 0.00051414
0.76093 | 5759 |  | 4 | 6 | 1.5 | 0.00051414
0.76144 | 4110 |  | 6 | 9 | 1.5 | 0.00051414
0.76195 | 4187 |  | 4 | 6 | 1.5 | 0.00051414
0.76247 | 4142 |  | 4 | 6 | 1.5 | 0.00051414
0.76298 | 2448 |  | 18 | 27 | 1.5 | 0.00051414
0.7635 | 4147 |  | 12 | 18 | 1.5 | 0.00051414
0.76401 | 7169 |  | 6 | 9 | 1.5 | 0.00051414
0.76452 | 4156 |  | 6 | 9 | 1.5 | 0.00051414
0.76504 | 5793 |  | 2 | 3 | 1.5 | 0.00051414
0.76555 | 5794 |  | 2 | 3 | 1.5 | 0.00051414
0.76607 | 5826 |  | 2 | 3 | 1.5 | 0.00051414
0.76658 | 4344 |  | 89 | 134 | 1.5056 | 0.00051414
0.7671 | 3980 |  | 80 | 122 | 1.525 | 0.00051414
0.76761 | 4382 |  | 135 | 206 | 1.5259 | 0.00051414
0.76812 | 2346 |  | 15 | 23 | 1.5333 | 0.00051414
0.76864 | 4771 |  | 35 | 54 | 1.5429 | 0.00051414
0.76915 | 4787 |  | 35 | 54 | 1.5429 | 0.00051414
0.76967 | 6476 |  | 31 | 48 | 1.5484 | 0.00051414
0.77018 | 3635 |  | 20 | 31 | 1.55 | 0.00051414
0.77069 | 4834 |  | 40 | 62 | 1.55 | 0.00051414
0.77121 | 5950 |  | 20 | 31 | 1.55 | 0.00051414
0.77172 | 4776 |  | 29 | 45 | 1.5517 | 0.00051414
0.77224 | 4774 |  | 34 | 53 | 1.5588 | 0.00051414
0.77275 | 3893 |  | 30 | 47 | 1.5667 | 0.00051414
0.77326 | 6484 |  | 21 | 33 | 1.5714 | 0.00051414
0.77378 | 3640 |  | 40 | 63 | 1.575 | 0.00051414
0.77429 | 5567 |  | 80 | 126 | 1.575 | 0.00051414
0.77481 | 4420 |  | 5 | 8 | 1.6 | 0.00051414
0.77532 | 4421 |  | 5 | 8 | 1.6 | 0.00051414
0.77584 | 4422 |  | 5 | 8 | 1.6 | 0.00051414
0.77635 | 4895 |  | 25 | 40 | 1.6 | 0.00051414
0.77686 | 5677 |  | 5 | 8 | 1.6 | 0.00051414
0.77738 | 3957 |  | 10 | 16 | 1.6 | 0.00051414
0.77789 | 1626 |  | 5 | 8 | 1.6 | 0.00051414
0.77841 | 4308 |  | 131 | 210 | 1.6031 | 0.00051414
0.77892 | 1902 |  | 80 | 129 | 1.6125 | 0.00051414
0.77943 | 1904 |  | 80 | 129 | 1.6125 | 0.00051414
0.77995 | 3892 |  | 50 | 81 | 1.62 | 0.00051414
0.78046 | 2443 |  | 31 | 51 | 1.6452 | 0.00051414
0.78098 | 3644 |  | 44 | 73 | 1.6591 | 0.00051414
0.78149 | 4428 |  | 30 | 50 | 1.6667 | 0.00051414
0.78201 | 5581 |  | 3 | 5 | 1.6667 | 0.00051414
0.78252 | 4756 |  | 3 | 5 | 1.6667 | 0.00051414
0.78303 | 6054 |  | 15 | 25 | 1.6667 | 0.00051414
0.78355 | 3913 |  | 30 | 50 | 1.6667 | 0.00051414
0.78406 | 1770 |  | 9 | 15 | 1.6667 | 0.00051414
0.78458 | 6952 |  | 3 | 5 | 1.6667 | 0.00051414
0.78509 | 5584 |  | 30 | 51 | 1.7 | 0.00051414
0.7856 | 3890 |  | 50 | 85 | 1.7 | 0.00051414
0.78612 | 1866 |  | 10 | 17 | 1.7 | 0.00051414
0.78663 | 6107 |  | 41 | 71 | 1.7317 | 0.00051414
0.78715 | 6108 |  | 41 | 71 | 1.7317 | 0.00051414
0.78766 | 6787 |  | 38 | 66 | 1.7368 | 0.00051414
0.78817 | 4365 |  | 121 | 211 | 1.7438 | 0.00051414
0.78869 | 5952 |  | 20 | 35 | 1.75 | 0.00051414
0.7892 | 6486 |  | 25 | 44 | 1.76 | 0.00051414
0.78972 | 4791 |  | 34 | 60 | 1.7647 | 0.00051414
0.79023 | 3975 |  | 90 | 160 | 1.7778 | 0.00051414
0.79075 | 5489 |  | 27 | 48 | 1.7778 | 0.00051414
0.79126 | 4522 |  | 172 | 308 | 1.7907 | 0.00051414
0.79177 | 3629 |  | 30 | 54 | 1.8 | 0.00051414
0.79229 | 4252 |  | 5 | 9 | 1.8 | 0.00051414
0.7928 | 4773 |  | 35 | 63 | 1.8 | 0.00051414
0.79332 | 4789 |  | 35 | 63 | 1.8 | 0.00051414
0.79383 | 4899 |  | 10 | 18 | 1.8 | 0.00051414
0.79434 | 3934 |  | 40 | 72 | 1.8 | 0.00051414
0.79486 | 6128 |  | 5 | 9 | 1.8 | 0.00051414
0.79537 | 6129 |  | 5 | 9 | 1.8 | 0.00051414
0.79589 | 3645 |  | 20 | 36 | 1.8 | 0.00051414
0.7964 | 7128 |  | 15 | 27 | 1.8 | 0.00051414
0.79692 | 5460 |  | 15 | 27 | 1.8 | 0.00051414
0.79743 | 4792 |  | 33 | 60 | 1.8182 | 0.00051414
0.79794 | 4442 |  | 30 | 55 | 1.8333 | 0.00051414
0.79846 | 3885 |  | 30 | 55 | 1.8333 | 0.00051414
0.79897 | 3654 |  | 120 | 221 | 1.8417 | 0.00051414
0.79949 | 6119 |  | 39 | 72 | 1.8462 | 0.00051414
0.8 | 6125 |  | 39 | 72 | 1.8462 | 0.00051414
0.80051 | 6859 |  | 20 | 37 | 1.85 | 0.00051414
0.80103 | 3836 |  | 14 | 26 | 1.8571 | 0.00051414
0.80154 | 2675 |  | 37 | 69 | 1.8649 | 0.00051414
0.80206 | 4403 |  | 40 | 75 | 1.875 | 0.00051414
0.80257 | 3908 |  | 75 | 142 | 1.8933 | 0.00051414
0.80308 | 2606 |  | 13 | 25 | 1.9231 | 0.00051414
0.8036 | 2687 |  | 13 | 25 | 1.9231 | 0.00051414
0.80411 | 4385 |  | 103 | 199 | 1.932 | 0.00051414
0.80463 | 6446 |  | 15 | 29 | 1.9333 | 0.00051414
0.80514 | 4290 |  | 92 | 179 | 1.9457 | 0.00051414
0.80566 | 3612 |  | 20 | 39 | 1.95 | 0.00051414
0.80617 | 3660 |  | 80 | 156 | 1.95 | 0.00051414
0.80668 | 3718 |  | 2 | 4 | 2 | 0.00051414
0.8072 | 3698 |  | 1 | 2 | 2 | 0.00051414
0.80771 | 3720 |  | 2 | 4 | 2 | 0.00051414
0.80823 | 3703 |  | 5 | 10 | 2 | 0.00051414
0.80874 | 4862 |  | 20 | 40 | 2 | 0.00051414
0.80925 | 3704 |  | 5 | 10 | 2 | 0.00051414
0.80977 | 3666 |  | 80 | 160 | 2 | 0.00051414
0.81028 | 3714 |  | 2 | 4 | 2 | 0.00051414
0.8108 | 3737 |  | 2 | 4 | 2 | 0.00051414
0.81131 | 3740 |  | 1 | 2 | 2 | 0.00051414
0.81183 | 3741 |  | 2 | 4 | 2 | 0.00051414
0.81234 | 3764 |  | 5 | 10 | 2 | 0.00051414
0.81285 | 5627 |  | 1 | 2 | 2 | 0.00051414
0.81337 | 5654 |  | 3 | 6 | 2 | 0.00051414
0.81388 | 3900 |  | 15 | 30 | 2 | 0.00051414
0.8144 | 3902 |  | 25 | 50 | 2 | 0.00051414
0.81491 | 5892 |  | 2 | 4 | 2 | 0.00051414
0.81542 | 2489 |  | 3 | 6 | 2 | 0.00051414
0.81594 | 6785 |  | 1 | 2 | 2 | 0.00051414
0.81645 | 5891 |  | 1 | 2 | 2 | 0.00051414
0.81697 | 4114 |  | 1 | 2 | 2 | 0.00051414
0.81748 | 4125 |  | 2 | 4 | 2 | 0.00051414
0.81799 | 4122 |  | 2 | 4 | 2 | 0.00051414
0.81851 | 4202 |  | 5 | 10 | 2 | 0.00051414
0.81902 | 2760 |  | 2 | 4 | 2 | 0.00051414
0.81954 | 5795 |  | 1 | 2 | 2 | 0.00051414
0.82005 | 2609 |  | 15 | 30 | 2 | 0.00051414
0.82057 | 5825 |  | 3 | 6 | 2 | 0.00051414
0.82108 | 4175 |  | 2 | 4 | 2 | 0.00051414
0.82159 | 5829 |  | 1 | 2 | 2 | 0.00051414
0.82211 | 6945 |  | 1 | 2 | 2 | 0.00051414
0.82262 | 3639 |  | 20 | 41 | 2.05 | 0.00051414
0.82314 | 2311 |  | 15 | 31 | 2.0667 | 0.00051414
0.82365 | 4447 |  | 29 | 60 | 2.069 | 0.00051414
0.82416 | 6084 |  | 104 | 217 | 2.0865 | 0.00051414
0.82468 | 3637 |  | 20 | 42 | 2.1 | 0.00051414
0.82519 | 4890 |  | 20 | 42 | 2.1 | 0.00051414
0.82571 | 6442 |  | 10 | 21 | 2.1 | 0.00051414
0.82622 | 523 |  | 19 | 40 | 2.1053 | 0.00051414
0.82674 | 4369 |  | 94 | 198 | 2.1064 | 0.00051414
0.82725 | 3662 |  | 60 | 127 | 2.1167 | 0.00051414
0.82776 | 4149 |  | 8 | 17 | 2.125 | 0.00051414
0.82828 | 3872 |  | 30 | 64 | 2.1333 | 0.00051414
0.82879 | 1870 |  | 15 | 32 | 2.1333 | 0.00051414
0.82931 | 7127 |  | 15 | 32 | 2.1333 | 0.00051414
0.82982 | 4390 |  | 93 | 199 | 2.1398 | 0.00051414
0.83033 | 6385 |  | 7 | 15 | 2.1429 | 0.00051414
0.83085 | 4153 |  | 7 | 15 | 2.1429 | 0.00051414
0.83136 | 5966 |  | 13 | 28 | 2.1538 | 0.00051414
0.83188 | 4775 |  | 29 | 63 | 2.1724 | 0.00051414
0.83239 | 4626 |  | 23 | 50 | 2.1739 | 0.00051414
0.8329 | 5707 |  | 5 | 11 | 2.2 | 0.00051414
0.83342 | 2690 |  | 15 | 33 | 2.2 | 0.00051414
0.83393 | 4793 |  | 18 | 40 | 2.2222 | 0.00051414
0.83445 | 5889 |  | 60 | 135 | 2.25 | 0.00051414
0.83496 | 5704 |  | 15 | 34 | 2.2667 | 0.00051414
0.83548 | 3942 |  | 35 | 80 | 2.2857 | 0.00051414
0.83599 | 2615 |  | 40 | 92 | 2.3 | 0.00051414
0.8365 | 2040 |  | 23 | 53 | 2.3043 | 0.00051414
0.83702 | 2674 |  | 37 | 86 | 2.3243 | 0.00051414
0.83753 | 6515 |  | 3 | 7 | 2.3333 | 0.00051414
0.83805 | 1903 |  | 55 | 129 | 2.3455 | 0.00051414
0.83856 | 3626 |  | 40 | 96 | 2.4 | 0.00051414
0.83907 | 3931 |  | 30 | 72 | 2.4 | 0.00051414
0.83959 | 3901 |  | 25 | 60 | 2.4 | 0.00051414
0.8401 | 3937 |  | 30 | 72 | 2.4 | 0.00051414
0.84062 | 6126 |  | 36 | 87 | 2.4167 | 0.00051414
0.84113 | 4189 |  | 12 | 29 | 2.4167 | 0.00051414
0.84165 | 5933 |  | 130 | 317 | 2.4385 | 0.00051414
0.84216 | 3826 |  | 27 | 66 | 2.4444 | 0.00051414
0.84267 | 3960 |  | 40 | 98 | 2.45 | 0.00051414
0.84319 | 5893 |  | 60 | 147 | 2.45 | 0.00051414
0.8437 | 3938 |  | 15 | 37 | 2.4667 | 0.00051414
0.84422 | 3688 |  | 4 | 10 | 2.5 | 0.00051414
0.84473 | 4387 |  | 8 | 20 | 2.5 | 0.00051414
0.84524 | 3692 |  | 4 | 10 | 2.5 | 0.00051414
0.84576 | 3723 |  | 4 | 10 | 2.5 | 0.00051414
0.84627 | 3730 |  | 4 | 10 | 2.5 | 0.00051414
0.84679 | 3712 |  | 4 | 10 | 2.5 | 0.00051414
0.8473 | 3733 |  | 2 | 5 | 2.5 | 0.00051414
0.84781 | 4863 |  | 2 | 5 | 2.5 | 0.00051414
0.84833 | 3757 |  | 4 | 10 | 2.5 | 0.00051414
0.84884 | 5884 |  | 60 | 150 | 2.5 | 0.00051414
0.84936 | 3932 |  | 10 | 25 | 2.5 | 0.00051414
0.84987 | 6141 |  | 2 | 5 | 2.5 | 0.00051414
0.85039 | 4081 |  | 4 | 10 | 2.5 | 0.00051414
0.8509 | 4140 |  | 2 | 5 | 2.5 | 0.00051414
0.85141 | 2459 |  | 14 | 35 | 2.5 | 0.00051414
0.85193 | 4174 |  | 4 | 10 | 2.5 | 0.00051414
0.85244 | 2475 |  | 97 | 244 | 2.5155 | 0.00051414
0.85296 | 2476 |  | 97 | 244 | 2.5155 | 0.00051414
0.85347 | 5603 |  | 75 | 190 | 2.5333 | 0.00051414
0.85398 | 2657 |  | 13 | 33 | 2.5385 | 0.00051414
0.8545 | 6131 |  | 11 | 28 | 2.5455 | 0.00051414
0.85501 | 631 |  | 80 | 207 | 2.5875 | 0.00051414
0.85553 | 3952 |  | 40 | 104 | 2.6 | 0.00051414
0.85604 | 5916 |  | 10 | 26 | 2.6 | 0.00051414
0.85656 | 4145 |  | 5 | 13 | 2.6 | 0.00051414
0.85707 | 7120 |  | 5 | 13 | 2.6 | 0.00051414
0.85758 | 4137 |  | 8 | 21 | 2.625 | 0.00051414
0.8581 | 6822 |  | 14 | 37 | 2.6429 | 0.00051414
0.85861 | 3840 |  | 90 | 238 | 2.6444 | 0.00051414
0.85913 | 4423 |  | 3 | 8 | 2.6667 | 0.00051414
0.85964 | 4424 |  | 3 | 8 | 2.6667 | 0.00051414
0.86015 | 4415 |  | 3 | 8 | 2.6667 | 0.00051414
0.86067 | 4777 |  | 15 | 40 | 2.6667 | 0.00051414
0.86118 | 2383 |  | 15 | 40 | 2.6667 | 0.00051414
0.8617 | 3619 |  | 45 | 121 | 2.6889 | 0.00051414
0.86221 | 3603 |  | 36 | 97 | 2.6944 | 0.00051414
0.86272 | 3827 |  | 27 | 73 | 2.7037 | 0.00051414
0.86324 | 3610 |  | 45 | 122 | 2.7111 | 0.00051414
0.86375 | 6384 |  | 11 | 30 | 2.7273 | 0.00051414
0.86427 | 1881 |  | 15 | 41 | 2.7333 | 0.00051414
0.86478 | 3935 |  | 20 | 55 | 2.75 | 0.00051414
0.8653 | 4102 |  | 4 | 11 | 2.75 | 0.00051414
0.86581 | 3894 |  | 50 | 139 | 2.78 | 0.00051414
0.86632 | 4030 |  | 45 | 126 | 2.8 | 0.00051414
0.86684 | 4036 |  | 45 | 126 | 2.8 | 0.00051414
0.86735 | 2434 |  | 21 | 59 | 2.8095 | 0.00051414
0.86787 | 1969 |  | 61 | 172 | 2.8197 | 0.00051414
0.86838 | 3616 |  | 35 | 99 | 2.8286 | 0.00051414
0.86889 | 3943 |  | 35 | 99 | 2.8286 | 0.00051414
0.86941 | 4885 |  | 20 | 57 | 2.85 | 0.00051414
0.86992 | 6034 |  | 20 | 57 | 2.85 | 0.00051414
0.87044 | 5562 |  | 27 | 77 | 2.8519 | 0.00051414
0.87095 | 3898 |  | 35 | 100 | 2.8571 | 0.00051414
0.87147 | 4028 |  | 45 | 129 | 2.8667 | 0.00051414
0.87198 | 5994 |  | 14 | 41 | 2.9286 | 0.00051414
0.87249 | 3911 |  | 15 | 44 | 2.9333 | 0.00051414
0.87301 | 3909 |  | 70 | 208 | 2.9714 | 0.00051414
0.87352 | 4316 |  | 6 | 18 | 3 | 0.00051414
0.87404 | 3633 |  | 20 | 60 | 3 | 0.00051414
0.87455 | 4416 |  | 5 | 15 | 3 | 0.00051414
0.87506 | 3321 |  | 2 | 6 | 3 | 0.00051414
0.87558 | 3899 |  | 15 | 45 | 3 | 0.00051414
0.87609 | 5532 |  | 1 | 3 | 3 | 0.00051414
0.87661 | 5938 |  | 20 | 60 | 3 | 0.00051414
0.87712 | 3981 |  | 10 | 30 | 3 | 0.00051414
0.87763 | 6411 |  | 2 | 6 | 3 | 0.00051414
0.87815 | 6448 |  | 2 | 6 | 3 | 0.00051414
0.87866 | 4039 |  | 45 | 135 | 3 | 0.00051414
0.87918 | 4043 |  | 45 | 135 | 3 | 0.00051414
0.87969 | 4045 |  | 45 | 135 | 3 | 0.00051414
0.88021 | 4047 |  | 45 | 135 | 3 | 0.00051414
0.88072 | 4048 |  | 45 | 135 | 3 | 0.00051414
0.88123 | 4049 |  | 45 | 135 | 3 | 0.00051414
0.88175 | 4052 |  | 45 | 135 | 3 | 0.00051414
0.88226 | 4040 |  | 45 | 135 | 3 | 0.00051414
0.88278 | 4041 |  | 45 | 135 | 3 | 0.00051414
0.88329 | 5490 |  | 45 | 135 | 3 | 0.00051414
0.8838 | 4025 |  | 45 | 135 | 3 | 0.00051414
0.88432 | 4044 |  | 45 | 135 | 3 | 0.00051414
0.88483 | 5497 |  | 8 | 24 | 3 | 0.00051414
0.88535 | 7068 |  | 8 | 24 | 3 | 0.00051414
0.88586 | 4139 |  | 1 | 3 | 3 | 0.00051414
0.88638 | 1769 |  | 9 | 27 | 3 | 0.00051414
0.88689 | 6976 |  | 11 | 33 | 3 | 0.00051414
0.8874 | 7119 |  | 5 | 15 | 3 | 0.00051414
0.88792 | 4201 |  | 4 | 12 | 3 | 0.00051414
0.88843 | 5488 |  | 33 | 100 | 3.0303 | 0.00051414
0.88895 | 6117 |  | 30 | 91 | 3.0333 | 0.00051414
0.88946 | 6420 |  | 60 | 182 | 3.0333 | 0.00051414
0.88997 | 4753 |  | 24 | 73 | 3.0417 | 0.00051414
0.89049 | 3926 |  | 40 | 122 | 3.05 | 0.00051414
0.891 | 4331 |  | 19 | 58 | 3.0526 | 0.00051414
0.89152 | 2472 |  | 35 | 108 | 3.0857 | 0.00051414
0.89203 | 3825 |  | 27 | 84 | 3.1111 | 0.00051414
0.89254 | 3632 |  | 60 | 192 | 3.2 | 0.00051414
0.89306 | 4023 |  | 45 | 144 | 3.2 | 0.00051414
0.89357 | 2452 |  | 14 | 45 | 3.2143 | 0.00051414
0.89409 | 4434 |  | 9 | 29 | 3.2222 | 0.00051414
0.8946 | 7179 |  | 8 | 26 | 3.25 | 0.00051414
0.89512 | 3829 |  | 19 | 62 | 3.2632 | 0.00051414
0.89563 | 4022 |  | 45 | 147 | 3.2667 | 0.00051414
0.89614 | 6090 |  | 15 | 49 | 3.2667 | 0.00051414
0.89666 | 3927 |  | 40 | 131 | 3.275 | 0.00051414
0.89717 | 3987 |  | 50 | 164 | 3.28 | 0.00051414
0.89769 | 3873 |  | 55 | 181 | 3.2909 | 0.00051414
0.8982 | 6390 |  | 19 | 63 | 3.3158 | 0.00051414
0.89871 | 3680 |  | 3 | 10 | 3.3333 | 0.00051414
0.89923 | 3701 |  | 3 | 10 | 3.3333 | 0.00051414
0.89974 | 3702 |  | 3 | 10 | 3.3333 | 0.00051414
0.90026 | 3761 |  | 3 | 10 | 3.3333 | 0.00051414
0.90077 | 4132 |  | 6 | 20 | 3.3333 | 0.00051414
0.90129 | 1871 |  | 15 | 50 | 3.3333 | 0.00051414
0.9018 | 5560 |  | 32 | 108 | 3.375 | 0.00051414
0.90231 | 4336 |  | 15 | 51 | 3.4 | 0.00051414
0.90283 | 3865 |  | 5 | 17 | 3.4 | 0.00051414
0.90334 | 4391 |  | 7 | 24 | 3.4286 | 0.00051414
0.90386 | 4033 |  | 45 | 156 | 3.4667 | 0.00051414
0.90437 | 4698 |  | 15 | 52 | 3.4667 | 0.00051414
0.90488 | 4116 |  | 4 | 14 | 3.5 | 0.00051414
0.9054 | 5485 |  | 15 | 53 | 3.5333 | 0.00051414
0.90591 | 4032 |  | 45 | 159 | 3.5333 | 0.00051414
0.90643 | 3792 |  | 11 | 39 | 3.5455 | 0.00051414
0.90694 | 2647 |  | 8 | 29 | 3.625 | 0.00051414
0.90746 | 5572 |  | 40 | 145 | 3.625 | 0.00051414
0.90797 | 3984 |  | 45 | 164 | 3.6444 | 0.00051414
0.90848 | 3828 |  | 17 | 62 | 3.6471 | 0.00051414
0.909 | 3661 |  | 80 | 292 | 3.65 | 0.00051414
0.90951 | 3642 |  | 50 | 183 | 3.66 | 0.00051414
0.91003 | 4879 |  | 15 | 55 | 3.6667 | 0.00051414
0.91054 | 4884 |  | 15 | 55 | 3.6667 | 0.00051414
0.91105 | 3946 |  | 15 | 55 | 3.6667 | 0.00051414
0.91157 | 4026 |  | 45 | 165 | 3.6667 | 0.00051414
0.91208 | 4035 |  | 45 | 165 | 3.6667 | 0.00051414
0.9126 | 4042 |  | 45 | 165 | 3.6667 | 0.00051414
0.91311 | 4046 |  | 45 | 165 | 3.6667 | 0.00051414
0.91362 | 4050 |  | 45 | 165 | 3.6667 | 0.00051414
0.91414 | 4176 |  | 3 | 11 | 3.6667 | 0.00051414
0.91465 | 3622 |  | 40 | 147 | 3.675 | 0.00051414
0.91517 | 4034 |  | 45 | 168 | 3.7333 | 0.00051414
0.91568 | 2391 |  | 15 | 56 | 3.7333 | 0.00051414
0.9162 | 6111 |  | 6 | 23 | 3.8333 | 0.00051414
0.91671 | 3875 |  | 20 | 77 | 3.85 | 0.00051414
0.91722 | 4166 |  | 8 | 31 | 3.875 | 0.00051414
0.91774 | 6118 |  | 20 | 78 | 3.9 | 0.00051414
0.91825 | 3685 |  | 3 | 12 | 4 | 0.00051414
0.91877 | 4426 |  | 2 | 8 | 4 | 0.00051414
0.91928 | 4436 |  | 2 | 8 | 4 | 0.00051414
0.91979 | 4437 |  | 2 | 8 | 4 | 0.00051414
0.92031 | 3667 |  | 40 | 160 | 4 | 0.00051414
0.92082 | 3668 |  | 40 | 160 | 4 | 0.00051414
0.92134 | 3734 |  | 1 | 4 | 4 | 0.00051414
0.92185 | 3739 |  | 1 | 4 | 4 | 0.00051414
0.92237 | 2473 |  | 35 | 140 | 4 | 0.00051414
0.92288 | 530 |  | 15 | 60 | 4 | 0.00051414
0.92339 | 536 |  | 15 | 60 | 4 | 0.00051414
0.92391 | 591 |  | 15 | 60 | 4 | 0.00051414
0.92442 | 2099 |  | 2 | 8 | 4 | 0.00051414
0.92494 | 2799 |  | 1 | 4 | 4 | 0.00051414
0.92545 | 2800 |  | 1 | 4 | 4 | 0.00051414
0.92596 | 4992 |  | 1 | 4 | 4 | 0.00051414
0.92648 | 6939 |  | 1 | 4 | 4 | 0.00051414
0.92699 | 4117 |  | 1 | 4 | 4 | 0.00051414
0.92751 | 2787 |  | 1 | 4 | 4 | 0.00051414
0.92802 | 2795 |  | 1 | 4 | 4 | 0.00051414
0.92853 | 4418 |  | 10 | 41 | 4.1 | 0.00051414
0.92905 | 5905 |  | 10 | 41 | 4.1 | 0.00051414
0.92956 | 3886 |  | 20 | 82 | 4.1 | 0.00051414
0.93008 | 5565 |  | 20 | 82 | 4.1 | 0.00051414
0.93059 | 7116 |  | 10 | 41 | 4.1 | 0.00051414
0.93111 | 1910 |  | 20 | 83 | 4.15 | 0.00051414
0.93162 | 4027 |  | 45 | 189 | 4.2 | 0.00051414
0.93213 | 2418 |  | 45 | 194 | 4.3111 | 0.00051414
0.93265 | 3754 |  | 3 | 13 | 4.3333 | 0.00051414
0.93316 | 3804 |  | 3 | 13 | 4.3333 | 0.00051414
0.93368 | 2098 |  | 3 | 13 | 4.3333 | 0.00051414
0.93419 | 2433 |  | 23 | 100 | 4.3478 | 0.00051414
0.9347 | 5948 |  | 20 | 88 | 4.4 | 0.00051414
0.93522 | 965 |  | 9 | 40 | 4.4444 | 0.00051414
0.93573 | 4205 |  | 15 | 67 | 4.4667 | 0.00051414
0.93625 | 3684 |  | 2 | 9 | 4.5 | 0.00051414
0.93676 | 6121 |  | 20 | 90 | 4.5 | 0.00051414
0.93728 | 4031 |  | 45 | 204 | 4.5333 | 0.00051414
0.93779 | 1864 |  | 32 | 147 | 4.5938 | 0.00051414
0.9383 | 2681 |  | 21 | 98 | 4.6667 | 0.00051414
0.93882 | 6649 |  | 3 | 14 | 4.6667 | 0.00051414
0.93933 | 6828 |  | 3 | 14 | 4.6667 | 0.00051414
0.93985 | 4386 |  | 5 | 24 | 4.8 | 0.00051414
0.94036 | 4407 |  | 5 | 24 | 4.8 | 0.00051414
0.94087 | 4408 |  | 5 | 24 | 4.8 | 0.00051414
0.94139 | 6002 |  | 5 | 24 | 4.8 | 0.00051414
0.9419 | 6790 |  | 5 | 24 | 4.8 | 0.00051414
0.94242 | 3985 |  | 33 | 164 | 4.9697 | 0.00051414
0.94293 | 4413 |  | 1 | 5 | 5 | 0.00051414
0.94344 | 3759 |  | 1 | 5 | 5 | 0.00051414
0.94396 | 6514 |  | 2 | 10 | 5 | 0.00051414
0.94447 | 6120 |  | 18 | 90 | 5 | 0.00051414
0.94499 | 2607 |  | 1 | 5 | 5 | 0.00051414
0.9455 | 2688 |  | 1 | 5 | 5 | 0.00051414
0.94602 | 4911 |  | 22 | 111 | 5.0455 | 0.00051414
0.94653 | 542 |  | 15 | 76 | 5.0667 | 0.00051414
0.94704 | 2373 |  | 15 | 77 | 5.1333 | 0.00051414
0.94756 | 4404 |  | 5 | 26 | 5.2 | 0.00051414
0.94807 | 4051 |  | 45 | 237 | 5.2667 | 0.00051414
0.94859 | 4405 |  | 5 | 27 | 5.4 | 0.00051414
0.9491 | 3989 |  | 30 | 164 | 5.4667 | 0.00051414
0.94961 | 4406 |  | 5 | 28 | 5.6 | 0.00051414
0.95013 | 623 |  | 14 | 80 | 5.7143 | 0.00051414
0.95064 | 4419 |  | 5 | 29 | 5.8 | 0.00051414
0.95116 | 2290 |  | 5 | 29 | 5.8 | 0.00051414
0.95167 | 3664 |  | 60 | 349 | 5.8167 | 0.00051414
0.95219 | 3669 |  | 80 | 480 | 6 | 0.00051414
0.9527 | 5940 |  | 20 | 120 | 6 | 0.00051414
0.95321 | 6142 |  | 1 | 6 | 6 | 0.00051414
0.95373 | 6784 |  | 1 | 6 | 6 | 0.00051414
0.95424 | 5494 |  | 4 | 24 | 6 | 0.00051414
0.95476 | 5495 |  | 4 | 24 | 6 | 0.00051414
0.95527 | 6660 |  | 3 | 18 | 6 | 0.00051414
0.95578 | 6718 |  | 2 | 12 | 6 | 0.00051414
0.9563 | 3988 |  | 33 | 200 | 6.0606 | 0.00051414
0.95681 | 4435 |  | 5 | 31 | 6.2 | 0.00051414
0.95733 | 1775 |  | 9 | 56 | 6.2222 | 0.00051414
0.95784 | 1882 |  | 15 | 94 | 6.2667 | 0.00051414
0.95835 | 3658 |  | 60 | 380 | 6.3333 | 0.00051414
0.95887 | 5524 |  | 13 | 84 | 6.4615 | 0.00051414
0.95938 | 3979 |  | 10 | 66 | 6.6 | 0.00051414
0.9599 | 6031 |  | 10 | 67 | 6.7 | 0.00051414
0.96041 | 4286 |  | 10 | 68 | 6.8 | 0.00051414
0.96093 | 2425 |  | 27 | 187 | 6.9259 | 0.00051414
0.96144 | 4682 |  | 10 | 71 | 7.1 | 0.00051414
0.96195 | 5934 |  | 20 | 144 | 7.2 | 0.00051414
0.96247 | 2652 |  | 12 | 88 | 7.3333 | 0.00051414
0.96298 | 3986 |  | 20 | 147 | 7.35 | 0.00051414
0.9635 | 5936 |  | 20 | 152 | 7.6 | 0.00051414
0.96401 | 6450 |  | 16 | 123 | 7.6875 | 0.00051414
0.96452 | 3643 |  | 20 | 158 | 7.9 | 0.00051414
0.96504 | 4902 |  | 15 | 123 | 8.2 | 0.00051414
0.96555 | 4105 |  | 6 | 50 | 8.3333 | 0.00051414
0.96607 | 4398 |  | 4 | 34 | 8.5 | 0.00051414
0.96658 | 6627 |  | 3 | 26 | 8.6667 | 0.00051414
0.9671 | 5967 |  | 10 | 87 | 8.7 | 0.00051414
0.96761 | 5580 |  | 1 | 9 | 9 | 0.00051414
0.96812 | 4146 |  | 2 | 18 | 9 | 0.00051414
0.96864 | 973 |  | 10 | 91 | 9.1 | 0.00051414
0.96915 | 622 |  | 15 | 137 | 9.1333 | 0.00051414
0.96967 | 4379 |  | 5 | 46 | 9.2 | 0.00051414
0.97018 | 4439 |  | 4 | 37 | 9.25 | 0.00051414
0.97069 | 3676 |  | 3 | 28 | 9.3333 | 0.00051414
0.97121 | 2100 |  | 3 | 28 | 9.3333 | 0.00051414
0.97172 | 2237 |  | 3 | 28 | 9.3333 | 0.00051414
0.97224 | 7036 |  | 20 | 189 | 9.45 | 0.00051414
0.97275 | 4188 |  | 2 | 19 | 9.5 | 0.00051414
0.97326 | 4181 |  | 2 | 19 | 9.5 | 0.00051414
0.97378 | 3659 |  | 60 | 574 | 9.5667 | 0.00051414
0.97429 | 4014 |  | 15 | 144 | 9.6 | 0.00051414
0.97481 | 4425 |  | 3 | 29 | 9.6667 | 0.00051414
0.97532 | 2053 |  | 20 | 194 | 9.7 | 0.00051414
0.97584 | 4430 |  | 5 | 50 | 10 | 0.00051414
0.97635 | 4451 |  | 1 | 10 | 10 | 0.00051414
0.97686 | 3877 |  | 3 | 30 | 10 | 0.00051414
0.97738 | 2115 |  | 1 | 10 | 10 | 0.00051414
0.97789 | 6609 |  | 2 | 20 | 10 | 0.00051414
0.97841 | 597 |  | 15 | 151 | 10.0667 | 0.00051414
0.97892 | 4440 |  | 4 | 41 | 10.25 | 0.00051414
0.97943 | 2597 |  | 1 | 11 | 11 | 0.00051414
0.97995 | 5659 |  | 10 | 114 | 11.4 | 0.00051414
0.98046 | 4903 |  | 11 | 127 | 11.5455 | 0.00051414
0.98098 | 2336 |  | 1 | 12 | 12 | 0.00051414
0.98149 | 4699 |  | 15 | 185 | 12.3333 | 0.00051414
0.98201 | 6133 |  | 7 | 87 | 12.4286 | 0.00051414
0.98252 | 5749 |  | 2 | 25 | 12.5 | 0.00051414
0.98303 | 970 |  | 10 | 133 | 13.3 | 0.00051414
0.98355 | 2585 |  | 2 | 27 | 13.5 | 0.00051414
0.98406 | 2589 |  | 2 | 27 | 13.5 | 0.00051414
0.98458 | 4452 |  | 1 | 14 | 14 | 0.00051414
0.98509 | 4438 |  | 2 | 29 | 14.5 | 0.00051414
0.9856 | 4309 |  | 5 | 73 | 14.6 | 0.00051414
0.98612 | 4901 |  | 7 | 108 | 15.4286 | 0.00051414
0.98663 | 4135 |  | 2 | 34 | 17 | 0.00051414
0.98715 | 4136 |  | 2 | 34 | 17 | 0.00051414
0.98766 | 4431 |  | 4 | 69 | 17.25 | 0.00051414
0.98817 | 2240 |  | 1 | 18 | 18 | 0.00051414
0.98869 | 2243 |  | 1 | 18 | 18 | 0.00051414
0.9892 | 4013 |  | 15 | 287 | 19.1333 | 0.00051414
0.98972 | 5977 |  | 3 | 58 | 19.3333 | 0.00051414
0.99023 | 4248 |  | 1 | 20 | 20 | 0.00051414
0.99075 | 4167 |  | 4 | 87 | 21.75 | 0.00051414
0.99126 | 3791 |  | 1 | 22 | 22 | 0.00051414
0.99177 | 2185 |  | 2 | 48 | 24 | 0.00051414
0.99229 | 4150 |  | 2 | 48 | 24 | 0.00051414
0.9928 | 4397 |  | 3 | 78 | 26 | 0.00051414
0.99332 | 2586 |  | 1 | 27 | 27 | 0.00051414
0.99383 | 2587 |  | 1 | 27 | 27 | 0.00051414
0.99434 | 2588 |  | 1 | 27 | 27 | 0.00051414
0.99486 | 7066 |  | 4 | 118 | 29.5 | 0.00051414
0.99537 | 2181 |  | 10 | 356 | 35.6 | 0.00051414
0.99589 | 4432 |  | 2 | 72 | 36 | 0.00051414
0.9964 | 2174 |  | 10 | 362 | 36.2 | 0.00051414
0.99692 | 2177 |  | 10 | 364 | 36.4 | 0.00051414
0.99743 | 2430 |  | 2 | 74 | 37 | 0.00051414
0.99794 | 2188 |  | 1 | 46 | 46 | 0.00051414
0.99846 | 4512 |  | 2 | 117 | 58.5 | 0.00051414
0.99897 | 2186 |  | 2 | 142 | 71 | 0.00051414
0.99949 | 2655 |  | 1 | 80 | 80 | 0.00051414
1 | 1914 |  | 2 | 219 | 109.5 | 0.00051414
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Portfolio -->
The tabs that follow are setup to graph Acumen Fuse data for multiple projects as a "portfolio" view.
The multiple-project charts (G3, G6, G7) serve as strategic, portfolio-level benchmarks designed for PMO leadership and executives. By stripping away timeline details and plotting standard execution indices (like CEI, HMI, and BEI) on scatter plots, these charts allow leadership to quickly triage systemic risks, spot severe outliers, and compare overall schedule predictability and discipline across an entire portfolio at a single glance.

## G3_Quad_HMI&CEI
Quad Chart - HMI vs. CEI
Manual Entry - Data from Acumen Fuse
| HMI | CEI
Project 1 | 0.55 | 0.6
Project 2 | 0.63 | 0.7
Project 3 | 0.1 | 0.3 | Purpose of the HMI vs. CEI Scatter Plot The primary purpose of this chart is to evaluate and compare schedule execution discipline and predictability across a portfolio of projects. By plotting two distinct leading indicators—Current Execution Index (CEI) against the Hit or Miss Index (HMI)—the chart reveals not just how much work is getting done, but whether teams are working on the right things.
Project 4 | 0.95 | 1
Project 5 | 0.9 | 0.95 | 1. Measuring Throughput vs. Precision The axes represent two different angles of execution health:
Project 6 | 0.15 | 0.8
Project 7 | 0.7 | 0.5 | CEI (Y-Axis): Measures throughput against the plan. It answers: Did we finish the work we promised to finish this period?
Project 8 | 0.1 | 0.2 | HMI (X-Axis): Measures precision and focus. It answers: Of the work we actually did finish, how much of it was actually scheduled for this period?
Project 9 | 0.35 | 0.5
Project 10 | 0.2 | 0.4 | 2. Portfolio-Level Benchmarking By plotting multiple projects (represented by different colored dots) on a single 0-to-1 scale, this chart provides leadership with an immediate, high-level view of portfolio health. It quickly separates top performers from those struggling with schedule control or resource allocation.
Project 11 | 0.3 | 0.8
Project 12 | 0.9 | 1 | 3. Identifying the "Gold Standard" (Top-Right Quadrant) Projects clustered in the upper right (like Projects 4, 5, and 12) are the most predictable and disciplined. Scores close to 1.0 on both axes mean these teams accurately plan their near-term work, execute exactly what they planned, and avoid getting distracted by unplanned or out-of-sequence tasks.
4. Diagnosing Problematic Execution Profiles The chart visually categorizes different types of schedule dysfunction:
The "Danger Zone" (Bottom-Left): Projects like 3 and 8 have low scores in both metrics. This indicates high chaos—they aren't finishing their scheduled work, and the work they are doing wasn't part of the near-term plan.
The "Distracted Achievers" (Top-Left): Projects like 6 and 11 have high CEI but low HMI. This means they are finishing a high volume of work, but they are likely working out-of-sequence, cherry-picking easier tasks, or grabbing future work to stay busy while critical near-term tasks slip.
Why It’s Useful This visualization is a vital tool for PMO (Project Management Office) leadership and executives to:
Assess portfolio predictability at a single glance.
Target interventions by distinguishing between projects that need help with throughput (low CEI) versus those that need help with focus and schedule discipline (low HMI).
Spot "fake" progress by revealing when a team is simply churning through out-of-sequence tasks rather than executing the actual plan.
Color-coded quadrants will need to be manually added.
Quadrants:
Top Right (Green), HMI>0.8, CEI>0.6: Work is getting done according to the baseline plan and the schedule forecast plan.
Top Left (Yellow), HMI<0.8, CEI>0.6: Work is getting done according to the schedule forecast plan but not the baseline plan.
Bottom Right (Yellow), HMI>0.8, CEI<0.6: Work is getting done according to the baseline plan, but not the forecast plan. These scenarios are much less likely but would indicate that there is a disconnect between current planning and baseline expectations.
Bottom Left (Red), HMI<0.8, CEI<0.6: Work is neither getting done according to the baseline plan nor the forecast plan. The project is having difficulty meeting schedule and replanning and/or risk mitigation should be considered.
Hit or Miss Index (HMI) – compares how many tasks in a given month were completed that were baselined to be completed in that month, hence the phrase "hit or miss."
HMI helps answer the question:
•Did we accomplish the tasks we said we would accomplish according to the baseline this month?
•Is work getting done in according to the baseline plan?
Current Execution Index (CEI) – calculates how many tasks in a given month were completed that were planned/forecast to complete in that month per prior month’s schedule update.
CEI helps answer the question:
•Did we accomplish this month what we said we would accomplish when we updated the schedule forecast last month?
•Is work getting done in the forecasted time frame?

## G6_Quad_S-ratioVsF-ratio
Quad Chart - To-Go-Starts vs. To-Go-Finishes
Purpose of the Starts vs. Finishes (To-Go vs. Baseline) Chart The primary purpose of this scatter plot is to evaluate schedule slippage, scope growth, and the buildup of deferred work across a portfolio of projects. By comparing the volume of remaining work in the current schedule against the remaining work expected in the original baseline, this chart quickly identifies projects that are drowning in delayed activities.
1. Measuring Schedule Growth and Delays The axes represent ratios of current remaining work ("To-Go") versus what was originally planned ("Baseline"):
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis |  |  |  | X-Axis (Starts Ratio): A ratio of current tasks left to start divided by baseline tasks left to start.
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis |  |  |  | Y-Axis (Finishes Ratio): A ratio of current tasks left to finish divided by baseline tasks left to finish. A ratio of exactly 1.0 means the project has the exact amount of work remaining as originally planned for this point in time.
|  | Baselined to Start | Scheduled to Start | Baselined to Finish | Scheduled to Finish |  | To-Go Starts vs. Baseline Starts | To-Go Finishes vs. Baseline Finishes | 2. Identifying "In Control" Projects (The 1.0 Cluster) Projects tightly clustered around the 1.0 / 1.0 mark in the bottom-left corner (like Projects 2, 3, 7, and 8) represent healthy or "in-control" schedules. These teams are tracking closely to their original baseline expectations—they have not pushed a massive volume of unmet past work into the future, nor have they suffered from massive scope creep.
Ribbons | Project 1 | 124 | 505 | 128 | 539 | Project 1 | 4.0726 | 4.2109
Ribbons | Project 2 | 379 | 412 | 413 | 446 | Project 2 | 1.0871 | 1.0799 | 3. Spotting Severe Outliers and "Bow Waves" (The Upper Right) The chart’s most powerful feature is its ability to highlight extreme outliers. Projects located far up the diagonal (like Projects 1 and 9) are in severe distress. A ratio of 4.0 or 6.0 indicates that these projects have 4 to 6 times more work left to start and finish than the original baseline dictated. This massive accumulation of future work usually points to a severe "bow wave" of deferred tasks, chronic execution delays, or massive unbaselined scope additions.
Ribbons | Project 3 | 37 | 46 | 39 | 49 | Project 3 | 1.2432 | 1.2564
Ribbons | Project 4 | 14 | 14 | 26 | 26 | Project 4 | 1 | 1 | 4. The Start/Finish Correlation The fact that the projects plot along a neat 45-degree diagonal line reinforces a core scheduling reality: start delays dictate finish delays. If a project has four times as much work left to start as planned, it naturally has four times as much work left to finish.
Ribbons | Project 5 | 0 | 31 | 0 | 31 | Project 5 | 0 | 0
Ribbons | Project 6 | 454 | 454 | 477 | 477 | Project 6 | 1 | 1 | Why It’s Useful This visualization is highly effective for PMO leadership and executives to:
Ribbons | Project 7 | 10 | 14 | 10 | 14 | Project 7 | 1.4 | 1.4
Ribbons | Project 8 | 1 | 1 | 4 | 4 | Project 8 | 1 | 1 | Triage portfolio risk: Instantly identify which specific projects (the outliers) require immediate executive intervention.
Ribbons | Project 9 | 55 | 293 | 59 | 346 | Project 9 | 5.3273 | 5.8644 | Quantify the "Bow Wave": Show exactly how bloated a project's remaining schedule has become compared to the original plan.
Trigger re-baselining conversations: Visually prove when a project's current reality has decoupled so far from its original baseline (e.g., 6x the remaining work) that the current plan is no longer viable or realistic to execute.
Color-coded quadrants will need to be manually added.
To-Go Start Ratio vs. To-Go Finish Ratio
To-Go Start Ratio – To-Go Starts / To-Go Baseline Starts
To-Go Finish Ration – To-Go Finishes / To-Go Baseline Finishes
Quadrants:
•Top Right (Orange, Red), x>1, y>1: Planning to start and finish more tasks than baselined – possibly catch-up or resequencing of work.
•Top Left (Yellow), x<1, y>1: Finishing more tasks than starting — may be closing out backlog, but not initiating new work as planned.
•Bottom Right (Yellow), x>1, y<1: Planning to start more tasks than the baseline, but not finishing as many — risk of work buildup or overload.
•Bottom Left (Green), x≤1, y≤1: Assuming all activities have assigned baseline starts and baseline finishes, then less work remains than what was baselined as “to go” work from time now — both fewer starts and fewer finishes are planned than baselined.
•*Note: There is flexibility on whether the quadrant bounds should be set at 1 or +5-10% to allow for some late starts and finishes.
Line of Equality:
•Above the line: More to-go finishes vs. baseline plan than to-go starts vs. baseline plan. Planning to finish more work relative to the baseline than start work. This could indicate that work is taking longer to finish (i.e., growing activity durations).
•Below the line: There should not be more to-go starts than to-go finishes. This would indicate an error in the schedule.

## G7_Quad_BEIvsCP%
Quad Chart - BEI vs Critical Path %
Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis | Ribbon Analysis
Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis | Primary Formula Analysis |  | Purpose of the % of Critical Activities vs. Baseline Execution Chart The primary purpose of this scatter plot is to evaluate how historical schedule execution impacts future schedule risk. By plotting Baseline Execution Index (BEI) against the density of the critical path, the chart reveals whether poor past performance is causing future work to lose its flexibility (float) and stack up into a brittle, high-risk schedule.
Calculated
|  | BEI - Value Tasks | Tasks & Milestones (To-Go) - % of Total To-Go | Critical Path To-Go | % Critical Path To-Go Activities | 1. Balancing Past Throughput with Future Flexibility The axes represent two distinct but deeply connected scheduling concepts:
Ribbons | Project 1 | 0.86 | 793 | 30 | 0.037831
Ribbons | Project 2 | 0.5 | 668 | 163 | 0.24401 | X-Axis (BEI - Value Tasks): Measures historical execution against the baseline. A score near 1.0 means the team is completing work exactly at the pace originally planned. A low score means they are falling behind.
Ribbons | Project 3 | 0.35 | 68 | 33 | 0.48529 | Y-Axis (% Critical Path To-Go Activities): Measures the proportion of remaining work that is on the critical path (possessing zero float). A low percentage means the schedule has healthy flexibility. A high percentage means the schedule is highly constrained and "brittle"—meaning any slip in any task will delay the whole project.
Ribbons | Project 4 | 0.7 | 37 | 2 | 0.054054
Ribbons | Project 5 | 0 | 47 | 0 | 0 | 2. The "Healthy" Zone (Bottom-Right) Projects clustered in the lower right (like Projects 1, 4, and 6) represent healthy, well-managed schedules. They have a high BEI (meaning they are executing their baseline plan efficiently) and a low percentage of critical remaining work (meaning their future schedule still contains plenty of float and flexibility to absorb unexpected issues).
Ribbons | Project 6 | 0.9 | 584 | 34 | 0.058219
Ribbons | Project 7 | 0.25 | 16 | 2 | 0.125 | 3. The "Danger" Zone (Top-Left) Projects moving toward the upper left (like Project 3) are flashing warning signs. They have a low execution index (falling behind baseline) and a high percentage of critical remaining work (nearly 50% of everything left to do is critical).
4. Diagnosing "Float Erosion" This chart visually demonstrates the concept of "float erosion." When teams fail to execute their plan (low BEI), delayed non-critical tasks consume their available float. Eventually, those delayed tasks become critical. A schedule where 40-50% of all remaining tasks are on the critical path is often a sign that parallel paths have collapsed, and the project is at extreme risk for day-for-day slips.
Activity Starts – show how quickly work is being initiated.
| Activity Finishes – show how quickly work is actually being completed. |  |  |  |  | Why It’s Useful This visualization is highly effective for PMO leadership and risk managers to:
If starts are on track, but finishes are lagging, there will likely be a buildup of in-progress work or execution issues (bow wave).
| A delay in starts compared to the baseline may indicate upstream schedule slippage. |  |  |  |  | Assess project fragility: Quickly identify projects that have lost their schedule flexibility and cannot absorb any more delays (high Y-axis).
| A delay in finishes, even if starts are on time, may signal downstream inefficiencies or underestimated durations. |  |  |  |  | Connect cause and effect: Show project managers how failing to meet near-term commitments (low X-axis) directly increases the overall risk profile of the remaining project.
| Comparing both helps isolate where in the schedule the delays are occurring—early (planning/start delays) or late (execution/finish delays). |  |  |  |  | Target schedule reviews: Identify schedules that may need a logic deep-dive (e.g., if a project has terrible execution but zero critical tasks, the schedule logic might be broken or missing).
If actual starts and finishes closely match the baselined and planned counts, the schedule is likely under control.
Significant variance between planned vs. actual starts and finishes may indicate a need for replanning or risk mitigation.
| Showing late activities in the background also gives insight into how many activities started or finished on plan vs. not on plan. |  |  |  |  | Color-coded quadrants will need to be manually added.
Overlaying BEI, HMI, and CEI gives you a sense of how well those starts aligned with the schedule expectations.
Critical Path % Typical Range: In a well-developed schedule, 5% to 15% of the total activities are usually on the critical path.
Warning Flags:
<5% Critical: May indicate excessive float and lack of clarity about what’s truly driving the project's end date. (e.g., missing logic - predecessor or successor links, overuse of leads and lags)
>15–20% Critical: Could signal poor logic (e.g., overuse of constraints, lack of float, or too many links between activities – “hotspots”).
The ideal percentage depends on:
•Project Type & Complexity: Infrastructure projects may have different profiles than software or design-heavy projects.
•Level of Detail: More detailed schedules (e.g., with many low-level tasks) may naturally have a lower percentage of critical activities.
•Use of Constraints: Excessive use of constraints can artificially inflate the number of critical activities.
•Schedule Quality: A high-quality schedule has well-defined logic and reasonable float, regardless of the critical percentage.