## Sheet1
Excluded | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Percent Complete | Total Float
Unchecked |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File | 0 | 0 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Planned | 0% | C | 6
Unchecked |  | 388 | Service Delivery Planning COMPLETE | Hard_File | 0 | 1 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0% | C | 54
Unchecked |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File | 0 | 1 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0% | C | 50
Unchecked |  | 404 | Customer Service Program Development COMPLETE | Hard_File | 0 | 1 | 0 | 0 | 2026-10-08 | 2026-10-08 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0% | C | 20
Unchecked |  | 406 | Training/Readiness Development COMPLETE | Hard_File | 0 | 1 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0% | C | 14
Unchecked |  | 407 | Resource Readiness Training COMPLETE | Hard_File | 0 | 1 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0% | C | 10
Unchecked |  | 155 | Customer Service Program Development COMPLETE | Hard_File | 0 | 1 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0% | C | 0