## Sheet1
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Percent Complete | Total Float
Unchecked |  | 91 | Initial Assessment | Hard_File_updated | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 94% | C | 3
Unchecked |  | 92 | Perform Product Review | Hard_File_updated | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 94% | C | 3
Unchecked |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100% | C | 0
Unchecked |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100% | C | 0
Unchecked |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100% | C | 0
Unchecked |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100% | C | 0
Unchecked |  | 373 | Build Customer Service Program | Hard_File_updated | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 32% | C | 14
Unchecked |  | 392 | Customer Service Program Development | Hard_File_updated | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 74% | C | 22
Unchecked |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100% | C | 0
Unchecked |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100% | C | 0
Unchecked |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100% | C | 0
Unchecked |  | 322 | Service Planning | Hard_File_updated | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 43% | C | 11
Unchecked |  | 125 | Design Support Services | Hard_File_updated | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 45% | C | 11
Unchecked |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 53% | C | 11
Unchecked |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60% | C | 0
Unchecked |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0% | C | 2
Unchecked |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0% | C | 3
Unchecked |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0% | C | 0
Unchecked |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0% | C | 0
Unchecked |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0% | C | 0
Unchecked |  | 383 | Business Performance Planning | Hard_File_updated | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 0% | C | 53
Unchecked |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0% | C | 53
Unchecked |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0% | C | 3
Unchecked |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0% | C | 0
Unchecked |  | 129 | Training & Readiness | Hard_File_updated | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0% | C | 0
Unchecked |  | 212 | Training Needs Assessment | Hard_File_updated | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0% | C | 0
Unchecked |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0% | C | 3
Unchecked |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 0% | C | 11
Unchecked |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0% | C | 13
Unchecked |  | 100 | Resources Requirements | Hard_File_updated | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0% | C | 0
Unchecked |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0% | C | 0
Unchecked |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0% | C | 53
Unchecked |  | 318 | Technology Infrastructure | Hard_File_updated | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 0% | C | 37
Unchecked |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0% | C | 37
Unchecked |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0% | C | 12
Unchecked |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0% | C | 0
Unchecked |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0% | C | 11
Unchecked |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0% | C | 0
Unchecked |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0% | C | 37
Unchecked |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0% | C | 11
Unchecked |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0% | C | 11
Unchecked |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0% | C | 11
Unchecked |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0% | C | 0
Unchecked |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0% | C | 0
Unchecked |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0% | C | 22
Unchecked |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0% | C | 0
Unchecked |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0% | C | 54
Unchecked |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0% | C | 37
Unchecked |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0% | C | 54
Unchecked |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0% | C | 0
Unchecked |  | 235 | Training Planning | Hard_File_updated | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0% | C | 0
Unchecked |  | 299 | Content Development Planning | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0% | C | 0
Unchecked |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0% | C | 0
Unchecked |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0% | C | 22
Unchecked |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0% | C | 54
Unchecked |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0% | C | 0
Unchecked |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0% | C | 0
Unchecked |  | 372 | Build Technology Infrastructure | Hard_File_updated | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 0% | C | 38
Unchecked |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0% | C | 38
Unchecked |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0% | C | 0
Unchecked |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0% | C | 1
Unchecked |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0% | C | 0
Unchecked |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0% | C | 39
Unchecked |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0% | C | 1
Unchecked |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0% | C | 0
Unchecked |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0% | C | 0
Unchecked |  | 237 | Training Delivery Planning | Hard_File_updated | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0% | C | 0
Unchecked |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0% | C | 0
Unchecked |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0% | C | 0
Unchecked |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0% | C | 50
Unchecked |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0% | C | 0
Unchecked |  | 391 | Program Deployment | Hard_File_updated | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 0% | C | 8
Unchecked |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0% | C | 38
Unchecked |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0% | C | 0
Unchecked |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0% | C | 0
Unchecked |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0% | C | 0
Unchecked |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0% | C | 0
Unchecked |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0% | C | 0
Unchecked |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0% | C | 0
Unchecked |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0% | C | 0
Unchecked |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0% | C | 0
Unchecked |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0% | C | 0
Unchecked |  | 283 | Training Delivery Logistics | Hard_File_updated | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0% | C | 0
Unchecked |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0% | C | 0
Unchecked |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0% | C | 0
Unchecked |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0% | C | 0
Unchecked |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0% | C | 0
Unchecked |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0% | C | 0
Unchecked |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0% | C | 0
Unchecked |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0% | C | 0
Unchecked |  | 306 | Finalize Training Planning | Hard_File_updated | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0% | C | 0
Unchecked |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0% | C | 0
Unchecked |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0% | C | 0
Unchecked |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0% | C | 0
Unchecked |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0% | C | 0
Unchecked |  | 375 | Training/Readiness Development | Hard_File_updated | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0% | C | 0
Unchecked |  | 219 | Training Content Development | Hard_File_updated | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0% | C | 0
Unchecked |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0% | C | 0
Unchecked |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0% | C | 0
Unchecked |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0% | C | 0
Unchecked |  | 221 | Build Training Content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0% | C | 0
Unchecked |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0% | C | 0
Unchecked |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0% | C | 0
Unchecked |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0% | C | 0
Unchecked |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0% | C | 0
Unchecked |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0% | C | 0
Unchecked |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0% | C | 0
Unchecked |  | 175 | Develop Training Delivery Engine | Hard_File_updated | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0% | C | 0
Unchecked |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0% | C | 0
Unchecked |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0% | C | 0
Unchecked |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0% | C | 0
Unchecked |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0% | C | 22
Unchecked |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0% | C | 0
Unchecked |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0% | C | 0
Unchecked |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0% | C | 0
Unchecked |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0% | C | 0
Unchecked |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0% | C | 0
Unchecked |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0% | C | 0
Unchecked |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0% | C | 14
Unchecked |  | 393 | Resource Readiness | Hard_File_updated | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0% | C | 0
Unchecked |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0% | C | 0
Unchecked |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0% | C | 0
Unchecked |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0% | C | 0
Unchecked |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0% | C | 10
Unchecked |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0% | C | 0
Unchecked |  | 37 | Post Launch | Hard_File_updated | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0% | C | 0
Unchecked |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0% | C | 0
Unchecked |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0% | C | 0
Unchecked |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0% | C | 0
Unchecked |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0% | C | 0
Unchecked |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0% | C | 0
Unchecked |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0% | C | 0
Unchecked |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0% | C | 0
Unchecked |  | 143 | Monitoring | Hard_File_updated | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0% | C | 0
Unchecked |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0% | C | 0
Unchecked |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0% | C | 0
Unchecked |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0% | C | 0
Unchecked |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0% | C | 0
Unchecked |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0% | C | 0
Unchecked |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0% | C | 0
Unchecked |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0% | C | 0