## Program-Summary
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program Summary
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
NASA_Quick Library
|  | Quick Add Metrics | Schedule Errors | Schedule Warnings | Critical Path | BEI - Incomplete Activities Analysis | Control Milestone Dates | Margin Date | Margin Duration | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7)
Ribbons | Hard_File | 100 | 47 | 85 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 60 | 0 | 100 | 100 | 100
Ribbons | Hard_File_updated | 100 | 48 | 88 | 1 | 100 | 100 | 100 | 100 | 100 | 99 | 55 | 0 | 100 | 100 | 100
NASA Metrics
|  | Status & Quality | Performance | Schedule Errors | Schedule Warnings | Critical Path
Ribbons | Hard_File | 58.8571 | 68.0714 | 47 | 85 | 0
Ribbons | Hard_File_updated | 59.4286 | 67.6786 | 48 | 88 | 1
Advanced
Baseline Compliance
Ribbons | Hard_File | 0
Ribbons | Hard_File_updated | 1
Industry Standards
|  | Schedule Execution Metrics (SEM) | Half Step Delay Analysis
Ribbons | Hard_File | 60 | 0
Ribbons | Hard_File_updated | 50 | 0

## Program-Summary-2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program Summary 2
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
|  | NASA_Quick Library | [14 empty] | NASA Metrics |  |  | Status & Quality | [7 empty] | Performance | [26 empty] | Baseline Execution Index (BEI) |  | Hit or Miss Index (HMI) |  | Current Execution Index (CEI) |  | Advanced | [20 empty] | Industry Standards
|  | Quick Add Metrics | Schedule Errors | Schedule Warnings | Critical Path | BEI - Incomplete Activities Analysis | Control Milestone Dates | Margin Date | Margin Duration | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7) | Schedule Errors | Schedule Warnings | Critical Path | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Duration | Quality - Constraints | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors | Performance - Completed | Performance - In-Progress | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Float | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | DRM | Tracking Dates | Margin Duration | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path | BEI - Tasks | BEI - Milestones | HMI - Tasks | HMI - Milestones | CEI - Tasks | CEI - Milestones | Baseline Compliance | [20 empty] | Schedule Execution Metrics (SEM) | Half Step Delay Analysis
Ribbons | Hard_File | 100 | 47 | 85 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 60 | 0 | 100 | 100 | 100 | 47 | 85 | 0 | 100 | N/A | 100 | 0 | 22 | 73 | 22 | 95 | 0 | 0 | 0 | 100 | 86 | 0 | 100 | 100 | 100 | 60 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 60 | N/A | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | [20 empty] | 60 | 0
Ribbons | Hard_File_updated | 100 | 48 | 88 | 1 | 100 | 100 | 100 | 100 | 100 | 99 | 55 | 0 | 100 | 100 | 100 | 48 | 88 | 1 | 100 | N/A | 100 | 0 | 27 | 67 | 28 | 94 | 0 | 0 | 0 | 100 | 88 | 0 | 99 | 99 | 99 | 55 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 55 | N/A | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1 | [20 empty] | 50 | 0
|  | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | DRM | DRM | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis
|  | Status Date | Specific Task Start | Specific Task Finish | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 44d | Zero Days Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | High Float 10% | Negative Float | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | CP Logic Density™ | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Status Date | Milestone #1 - 100 | Float Milestone #1 - 100 | Milestone #2 - 101 | Float to Milestone #2 - 101 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 104 | New Activities Since Previous Status Date | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Critical Milestones (To-Go) | Critical Normal Tasks (To-Go) | Riding Data Date | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Duration Ratio Metric (DRM) | DRM Graph | Baselined to Start | Scheduled to Start | Baselined to Finish | Scheduled to Finish | BEI - Value Activities | Tasks & Milestones (To-Go) - % of Total To-Go | Critical Path To-Go | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | Longest Path (Normal Tasks) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Riding Data Date | Status Date | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Summary-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Manual Tasks (To-Go) | Critical Tasks and Milestones (To-Go) | Wrong Status (To-Go) | Invalid Forecast Dates | Missing WBS (To-Go) | All Activities (To Go) | Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Baselined to Start | Scheduled to Start | Actual Starts | Current Baselined to Start & Started | Past Baselined to Start & Started | Future Baseline to Start & Started | Baselined to Finish | Scheduled to Finish | Actual Finishes | Current Baselined to Finish & Finished | Past Baselined to Finish & Finished | Future Baselined to Finish & Finished | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Baselined to Start - To Time Now | Scheduled to Start - To Time Now | Started | Started Late | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | BEI - Value Task Starts | Baselined to Finish - To Time Now | Scheduled to Finish - To Time Now | Finished | Finished Late | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Finishes | Started - Future | Not Baselined to Start | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Started | Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Not Started (Incomplete) | Baselined to Start - Check | Future Baseline to Start & Started (Early Starts) | Past Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Not Finished - Check | Baselined to Finish - Check | Future Baseline to Finish & Finished - Check | Workoff Burden (Snapshot_Phase) (SEM01) | Workoff Burden - Starts To-Go (Total) (SEM07) | Past Baseline to Start & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) (SEM07) | Workoff Burden - Finishes To-Go (Total) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Baselined to Start | Scheduled to Start | Started - Scheduled | Started - Baseline Comparison | BEI - Value Task Starts | HMI - Value Task Starts | CEI - Value Task Starts | Baselined to Finish | Scheduled to Finish | Finished | BEI - Value Task Finishes | HMI - Value Task Finishes | CEI - Value Task Finishes | Status Date | Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Baseline Comparison | Started Late (from Baseline) | Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished Late | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Baselined Tasks | Baselined to Start - TOTAL | Complete Task Starts - Cumulative | Incomplete Task Starts - Cumulative (in work) | Old Incomplete Task Starts in Status Period | Baselined to Finish | Complete Task Finishes - Cumulative (in work) | Incomplete Task Finishes - Cumulative | Old Incomplete Task Finishes in Status Period | Old Completed Task Finishes in Status Period | BEI - Value Tasks | BEI - Total Tasks | BEI - Incomplete Tasks | HMI - Value Tasks | HMI - Total Tasks | HMI - Incomplete Tasks | CEI - Value Tasks | CEI - Total Tasks | CEI - Incomplete Tasks | BEI - Complete Milestones | HMI - Complete Tasks | CEI - Complete Tasks | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Incomplete Milestones | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | BEI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | BEI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | Status Date | Total Activities - DRM | Total Activities - DRM Graph | Status Date | Milestone #1 - 5158 | Float Milestone #1 - 5158 | Milestone #2 - 4786 | Float to Milestone #2 - 4786 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 105 | New Activities Since Previous Status Date | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | BEI - Value Tasks | HMI - Value Tasks | CEI - Value Tasks | BEI - Value Milestones | HMI - Value Milestones | CEI - Value Milestones | BEI - Value Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - CP Tasks - Planned Cumulative | BEI - CP Value Tasks | HMI - Value Tasks | HMI - Complete Tasks | HMI - Incomplete Tasks | HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Value Tasks | CEI - Value Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Value Tasks | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Completed Activities (1) | Workoff Burden (SEM01) | BRI Current (SEM02) | BRI Cumulative (SEM03) | BPI Current (SEM04) | BEI Current (SEM05) | BEI Cumulative (SEM06) | TC-BEI (SEM07) | FRI Current (SEM08) | Delta (BEI vs TC-BEI) (SEM09) | Time Now (HSD01) | Label (HSD02) | Forecast to be Started but not Started yet (HSD03) | Started Late (HSD04) | Forecast to be Finished but not Finished yet (HSD05) | Finished Late (HSD06) | Total days delay in the half step (Days) (HSD06) | Total days delay in the full update (Days) (HSD07) | Total days ahead in the half step (Days) (HSD08) | Total days ahead in the full update (Days) (HSD09) | Cumulative Finish Impact (Days) (HSD10) | Net Finish Impact (Days) (HSD10) | Project Finish (HSD20)
|  | 2026-08-11 | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 6 | 74 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 17 | 0 | 103 | 24 | 79 | 1 | 33 | 6 | 27 | 0 | 1:05 | 0 | 74 | 81 | 2.12 | N/A | N/A | N/A | 0 | 1 | 0.27 | 11 | 3 | 8 | 2026-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2026-08-11 | N/A | 2026-08-20 | 2026-08-26 | N/A | N/A | N/A | N/A | 2026-08-11 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | 2026-08-11 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 7 | 1 | 6 | 134 | 103 | 24 | 79 | 31 | 0 | 0 | 33 | 27 | 6 | 6 | 27 | 0 | 85 | 85 | 7 | 85 | 85 | 6 | N/A | N/A | N/A | 1 | 0 | 0 | 0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 7 | N/A | 0 | 78 | 6 | 0 | 0 | 79 | 8 | 70 | 8 | 71 | 6 | 6 | 79 | 79 | 79 | 79 | 0.29 | 103 | 33 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 17 | 6 | 74 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 27 | 33 | 1:05 | 6 | 6 | 85 | 79 | 27 | 0 | 74 | 0 | 2.12 | 0 | 1 | 2026-08-11 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 7 | 1 | 6 | 134 | 103 | 24 | 79 | 31 | 0 | 0 | 33 | 27 | 6 | 0 | 2026-08-11 | 134 | 103 | 1:03 | 1:03 | 1:05 | 0 | 33 | 0 | 0 | 0 | 103 | 103 | 65 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 27 | 1 | 1 | 0 | 0 | 0 | 79 | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 0 | 100 | 99 | 2.08 | 1.05 | 1.03 | 0 | 102 | 0 | 0 | 0 | 102 | 96 | 0 | 0 | 0 | 96 | 8 | 1 | 7 | 0 | 0 | 1.06 | 102 | 108 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | 0 | 0 | 0 | 1.03 | 96 | 7 | 106 | 0 | N/A | N/A | 0 | N/A | N/A | 1 | N/A | N/A | 0 | 0 | 0 | 7 | 3 | 3 | 1 | 21 | 5 | -8 | 6 | 3 | 2 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 102 | 3 | 84 | 15 | 0 | 0 | 78 | 2 | 66 | 10 | 10 | 24 | 1 | 18 | 5 | 5 | 110 | 103 | 103 | 8 | 7 | 0 | 100% | 0 | 100% | N/A | 0 | 0.8 | 110 | 103 | 103 | 33 | 6 | 27 | 0 | 1:05 | 17 | 6 | 74 | 0 | 33 | 6 | 27 | 0 | 1:03 | 1:05 | 2.05 | 2.12 | 1 | 0 | 74 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | 1 | 85 | 85 | 7 | 85 | 85 | 6 | N/A | N/A | N/A | 1 | 0 | 0 | 85 | 85 | 7 | 7 | 0 | 0 | 85 | 85 | 6 | 6 | 0 | 0 | N/A | N/A | N/A | 1 | 0 | 0 | 12 | 12 | 4 | N/A | N/A | N/A | N/A | 0.33 | 11 | 11 | 3 | 1 | 1 | 0 | 0 | 0.27 | 3 | 0 | 0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 0 | 7 | 0 | 0 | 78 | 85 | N/A | 0 | 6 | 0 | 0 | 79 | 85 | 0 | 0 | 78 | 8 | 70 | 79 | 8 | 71 | 7 | N/A | 0 | 78 | 6 | 0 | 0 | 79 | 8 | 70 | 8 | 71 | 12 | 12 | 4 | 4 | 0.33 | 0.27 | 0.27 | 11 | 11 | 3 | 0.27 | 0.27 | 0.27 | 2026-08-11 | 7 | 7 | N/A | 6 | 6 | 1 | 3 | 1 | 2 | 0 | -57 | 63 | 5 | 21 | 5 | -10 | 6 | 2 | 0 | 6 | 0 | 0 | 3 | 2 | 1 | 3 | 1 | 2 | 0 | -57 | 63 | 5 | 21 | 5 | -10 | 6 | 2 | 0 | 6 | 0 | 0 | 3 | 2 | 1 | 85 | 85 | 4 | 8 | N/A | 85 | 3 | 8 | N/A | N/A | 0.27 | 11 | 8 | 0.27 | 11 | 8 | 0.27 | 11 | 8 | 1 | 3 | 3 | 0.33 | 3 | 1 | 2 | 0.33 | 3 | 1 | 2 | 0.33 | 3 | 1 | 2 | 0.55 | 0.55 | 0.55 | 0.33 | 0.33 | 0.33 | 2026-08-11 | 6 | 6 | 2026-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2026-08-11 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | 2026-08-11 | N/A | 2026-08-20 | 2026-08-26 | N/A | N/A | N/A | N/A | 0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 0.27 | 0.27 | 0.27 | 0.33 | 0.33 | 0.33 | 0.27 | 3 | 8 | 0 | N/A | 0.27 | 3 | 8 | 0 | N/A | 0.27 | 3 | 8 | 0 | N/A | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2026-08-11 | 0.27 | 11 | 3 | N/A | 8 | 0.55 | 6 | 3 | 0.33 | 3 | 1 | N/A | 2 | 0.33 | 1 | 3 | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 0.33 | 3 | 1 | 2 | 0.33 | 1 | 0 | 2026-08-11 | 2026-08-11 | 11 | 2 | 1 | 8 | 18% | 12 | 4 | 0 | 8 | 33% | 6 | 0 | 0.11 | 0.27 | 0.11 | 0.11 | 0.27 | 1.11 | 0.11 | -0.67 | 2026-08-11 | N/A | 8 | 0 | 8 | 1 | N/A | 190 | N/A | 73 | -117 | 0 | 2026-11-05
[5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 6% | 72% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 17% | 0% | 94% | 23% | 77% | 1% | 32% | 18% | 82% | 0% |  | 0% | 72% | 79% |  |  | 27% | 73% | 0% | 1% |  |  | 27% | 73% | [21 empty] | N/A | 100% | N/A | N/A | N/A | N/A | N/A |  |  | 18% | 60% | 22% | 0% | 0% | 78% | 6% | 4% | 7% | 95% | 77% | 18% | 59% | 23% | 0% | 0% | 83% | 68% | 15% | 18% | 82% | 0% | [6 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0% | [33 empty] | 77% | 32% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 17% | 6% | 72% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 68% | 83% | 0.22 | 25% | 15% | 60% | 59% | 34% | 0% | 72% | 0% |  | 0% | 1% |  |  | 18% | 60% | 22% | 0% | 0% | 78% | 6% | 4% | 7% | 95% | 77% | 18% | 59% | 23% | 0% | 0% | 83% | 68% | 15% | 0% |  | 95% | 77% | 0.39 | 0.3 | 0.22 | 0% | 32% | 0% | 0% | 0% | 100% | 77% | 82% | 0% | 1% |  |  | 0% | 0% | 1% | 34% |  |  | 0% | 0% | 0% | 93% | 3% | 2% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 6% | 0% | 97% | 96% |  |  |  | 0% | 100% | 0% | 0% | 0% | 99% | 93% | 0% | 0% | 0% | 93% | 8% | 1% | 7% | 0% | 0% |  | 100% |  | 0% | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 1% | ( N/A ) | ( N/A ) | 0% | 0% | 0% |  | 100% | 7% |  | 0% |  |  | 0% |  |  | 1% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 6% | 43% | 43% | 14% |  |  |  | 7% | 50% | 33% | 17% | 0% | 0% | 2% | 4% | 0% | 100% | 0% | 1% | 0% | 100% | 0% | 100% |  |  |  | 0% | 0% | 93% | 3% | 82% | 15% | 0% | 0% | 92% | 3% | 85% | 13% | 13% | 96% | 4% | 75% | 21% | 21% | 100% |  |  |  |  | 0% |  | 0% |  | ( N/A ) | 0% |  | 100% | 94% | 94% | 32% | 25% | 34% | 0% | 0.22 | 17% | 6% | 72% | 0% | 32% | 25% | 34% | 0% | 0.3 | 0.22 |  |  | 8% | 0% | 72% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 27% | 73% | 0% | 1% | [6 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0% | [12 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0% | 14% | 14% |  |  | ( N/A ) | ( N/A ) | ( N/A ) |  | 13% | 13% |  |  | 100% | 0% | 0% |  |  | 0% | [28 empty] | 0% | [19 empty] | 100% | 33% | 33% | [10 empty] | 8% | 8% | N/A | 7% | 7% |  | 50% | 17% | 33% | 0% | -954% | 1044% | 90% |  |  |  | 5% | 29% | 0% | 7% | 0% | 0% | 27% | 33% | 17% | 50% | 17% | 33% | 0% | -954% | 1044% | 90% |  |  |  | 5% | 29% | 0% | 7% | 0% | 0% | 27% | 33% | 17% |  |  | 33% | 67% |  |  | 27% | 27% |  |  |  |  | 73% |  |  | 73% |  |  | 73% | 33% | 27% | 27% |  |  | 33% | 67% |  |  | 33% | 67% |  |  | 33% | 67% | [58 empty] | 27% | 73% |  |  |  | 27% | 73% |  |  |  | 27% | 73% |  |  |  |  | 27% | 73% |  | 55% |  |  |  |  | 33% | 67% |  | 33% |  |  |  |  | 27% | 0% | 73% |  | 55% |  |  |  | 33% | 0% | 67% |  | 33% |  |  |  | 27% | 73% |  | 55% |  |  |  |  | 33% | 67% |  | 33% |  |  |  | 13% | 18% | 9% | 73% |  | 14% | 33% | 0% | 67% |  |  | 0% | [10 empty] | 9% | 0% | 9% | 9%

## NASA_Quick-Library
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick Library
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
NASA_Quick Library
|  | Quick Add Metrics | Schedule Errors | Schedule Warnings | Critical Path | BEI - Incomplete Activities Analysis | Control Milestone Dates | Margin Date | Margin Duration | Status - Characteristics (GRAPH 1) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - BEI vs CP% (GRAPH 7)
Ribbons | Hard_File | 100 | 47 | 85 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 60 | 0 | 100 | 100 | 100
Ribbons | Hard_File_updated | 100 | 48 | 88 | 1 | 100 | 100 | 100 | 100 | 100 | 99 | 55 | 0 | 100 | 100 | 100
|  | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
|  | Status Date | Specific Task Start | Specific Task Finish | Score
Ribbons | Hard_File | 2026-07-07 | N/A | N/A | 100
Ribbons
Ribbons | Hard_File_updated | 2026-08-11 | N/A | N/A | 100
Ribbons
|  | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
|  | Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
Ribbons | Hard_File | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 68 | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-07 | 47
Ribbons |  | ( N/A ) | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 1% | 80% | 6% | 1% | 5% | ( N/A ) | 0% | 0% | 0% | 0% | 0% | 0%
Ribbons | Hard_File_updated | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 48
Ribbons |  | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
|  | High Float 44d | Zero Days Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | High Float 10% | Negative Float | Score
Ribbons | Hard_File | 2 | 78 | 0 | 0 | 0 | N/A | 1 | N/A | 0 | 0 | 20 | 0 | 85
Ribbons |  | 2% | 71% | 0% | 0% | 0% | ( N/A ) | 1% | ( N/A ) | 0% | 0% | 18% | 0%
Ribbons | Hard_File_updated | 6 | 74 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 17 | 0 | 88
Ribbons |  | 6% | 72% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 17% | 0%
|  | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
|  | Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | CP Logic Density™ | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
Ribbons | Hard_File | 110 | 25 | 85 | 0 | 34 | 7 | 27 | 0 | 1:04 | 0 | 78 | 90 | 2.21 | N/A | N/A | N/A | 0 | 0 | 0
Ribbons |  | 100% | 23% | 77% | 0% | 31% | 21% | 79% | 0% |  | 0% | 71% | 82% |  |  | N/A | N/A | 0% | 0%
Ribbons | Hard_File_updated | 103 | 24 | 79 | 1 | 33 | 6 | 27 | 0 | 1:05 | 0 | 74 | 81 | 2.12 | N/A | N/A | N/A | 0 | 1 | 1
Ribbons |  | 94% | 23% | 77% | 1% | 32% | 18% | 82% | 0% |  | 0% | 72% | 79% |  |  | 27% | 73% | 0% | 1%
|  | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis
|  | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A
Ribbons | Hard_File_updated | 0.27 | 11 | 3 | 8 | 100
Ribbons |  |  |  | 27% | 73%
|  | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates
|  | Status Date | Milestone #1 - 100 | Float Milestone #1 - 100 | Milestone #2 - 101 | Float to Milestone #2 - 101 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 104 | New Activities Since Previous Status Date | Score
Ribbons | Hard_File | 2026-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 100
Ribbons
Ribbons | Hard_File_updated | 2026-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 100
Ribbons
|  | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Hard_File | 2026-07-07 | N/A | 2026-08-20 | 2026-08-26 | 2026-08-18 | N/A | N/A | N/A | 100
Ribbons
Ribbons | Hard_File_updated | 2026-08-11 | N/A | 2026-08-20 | 2026-08-26 | N/A | N/A | N/A | N/A | 100
Ribbons
|  | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Hard_File | 2026-07-07 | N/A | 1 | 0 | 1 | N/A | N/A | N/A | 100
Ribbons |  |  | N/A | 100% | N/A | 100% | N/A | N/A | N/A
Ribbons | Hard_File_updated | 2026-08-11 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | 100
Ribbons |  |  | N/A | 100% | N/A | N/A | N/A | N/A | N/A
|  | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1)
|  | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Critical Milestones (To-Go) | Critical Normal Tasks (To-Go) | Riding Data Date | Score
Ribbons | Hard_File | 2026-07-07 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 0 | 0 | 0 | 141 | 110 | 25 | 85 | 31 | 0 | 0 | 34 | 27 | 7 | 7 | 27 | 0 | 100
Ribbons |  |  |  | 18% | 60% | 22% | 0% | 0% | 78% | 0% | 0% | 0% | 100% | 78% | 18% | 60% | 22% | 0% | 0% | 79% | 63% | 16% | 21% | 79% | 0%
Ribbons | Hard_File_updated | 2026-08-11 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 7 | 1 | 6 | 134 | 103 | 24 | 79 | 31 | 0 | 0 | 33 | 27 | 6 | 6 | 27 | 0 | 100
Ribbons |  |  |  | 18% | 60% | 22% | 0% | 0% | 78% | 6% | 4% | 7% | 95% | 77% | 18% | 59% | 23% | 0% | 0% | 83% | 68% | 15% | 18% | 82% | 0%
|  | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project)
|  | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
Ribbons | Hard_File | 85 | 85 | 0 | 85 | 85 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons | [7 empty] | N/A | ( N/A ) | ( N/A ) | N/A | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated | 85 | 85 | 7 | 85 | 85 | 6 | N/A | N/A | N/A | 1 | 0 | 0 | 99
Ribbons | [7 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0%
|  | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon)
|  | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 | 85 | 85 | 85 | 1 | 60
Ribbons
Ribbons | Hard_File_updated | 0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 55
Ribbons
|  | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4)
|  | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
Ribbons | Hard_File | N/A | N/A | N/A | 85 | N/A | N/A | N/A | 85 | 0 | 85 | 0 | 85 | 0
Ribbons
Ribbons | Hard_File_updated | 7 | N/A | 0 | 78 | 6 | 0 | 0 | 79 | 8 | 70 | 8 | 71 | 0
Ribbons
|  | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project)
|  | Duration Ratio Metric (DRM) | DRM Graph | Score
Ribbons | Hard_File | 0 | 0 | 100
Ribbons
Ribbons | Hard_File_updated | 6 | 6 | 100
Ribbons
|  | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6)
|  | Baselined to Start | Scheduled to Start | Baselined to Finish | Scheduled to Finish | Score
Ribbons | Hard_File | 85 | 85 | 85 | 85 | 100
Ribbons
Ribbons | Hard_File_updated | 79 | 79 | 79 | 79 | 100
Ribbons
|  | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7)
|  | BEI - Value Activities | Tasks & Milestones (To-Go) - % of Total To-Go | Critical Path To-Go | Score
Ribbons | Hard_File | N/A | 110 | 34 | 100
Ribbons |  |  | 78% | 31%
Ribbons | Hard_File_updated | 0.29 | 103 | 33 | 100
Ribbons |  |  | 77% | 32%

## NASA_Quick-Library-Quick-Add-M
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Quick Add Metrics | Quick Add Metrics | Quick Add Metrics | Quick Add Metrics
Status Date | Specific Task Start | Specific Task Finish | Score
2026-08-11 | N/A | N/A | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Project Time Now Date) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Specific Task Start | Specific Task Start | N/A |  | N/A
Provides the start date of a specific task.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Specific Task Finish | Specific Task Finish | N/A |  | N/A
Provides the finish date of a specific task.

## NASA_Quick-Library-Schedule-Er
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
Wrong Status - Actual Starts | Wrong Status - Actual Finishes | Invalid Forecast Dates | Expected Finish But Still In-Progress | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 48
0% | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Wrong Status - Actual Starts | Wrong Status - Actual Starts | 0 | 0% | 0
Number of activity starts that have been statused into the future.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Wrong Status - Actual Finishes | Wrong Status - Actual Finishes | 0 | 0% | 0
Number of activity finishes that have been statused into the future.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Invalid Forecast Dates | Invalid Forecast Dates | 0 | 0% | 0 | 0%
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Expected Finish But Still In-Progress | Expected Finish But Still In-Progress | 0 | 0% | 0
In-progress activities that are 100% complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing WBS | Missing WBS | 0 | 0% | 0 | 0%
Number of activities that are missing WBS values.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones with Duration>0 | Milestones with Duration>0 | 0 | 0% | 0 | 0%
Milestones with a duration greater than 0 days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities with Duration=0 | Activities with Duration=0 | 1 | 1% | 1 | 1%
Activities that have an original duration of 0 days.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | 0 | 0 | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Estimated Duration | Estimated Duration | 65 | 82% | 68 | 80%
Tasks with estimated duration in Microsoft Project.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | 0 | 2 | Planned
FALSE |  |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | 0 | 3 | Planned
FALSE |  |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | 0 | 0 | Planned
FALSE |  |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | 0 | 53 | Planned
FALSE |  |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | 0 | 3 | Planned
FALSE |  |  | 180 | Online support | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | 0 | 13 | Planned
FALSE |  |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | 0 | 0 | Planned
FALSE |  |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | 0 | 53 | Planned
FALSE |  |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | 0 | 37 | Planned
FALSE |  |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | 0 | 12 | Planned
FALSE |  |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | 0 | 11 | Planned
FALSE |  |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | 0 | 0 | Planned
FALSE |  |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | 0 | 37 | Planned
FALSE |  |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | 0 | 11 | Planned
FALSE |  |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | 0 | 0 | Planned
FALSE |  |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | 0 | 22 | Planned
FALSE |  |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | 0 | 0 | Planned
FALSE |  |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | 0 | 54 | Planned
FALSE |  |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | 0 | 0 | Planned
FALSE |  |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | 0 | 0 | Planned
FALSE |  |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | 0 | 0 | Planned
FALSE |  |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | 0 | 38 | Planned
FALSE |  |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | 0 | 0 | Planned
FALSE |  |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | 0 | 1 | Planned
FALSE |  |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | 0 | 0 | Planned
FALSE |  |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | 0 | 39 | Planned
FALSE |  |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | 0 | 1 | Planned
FALSE |  |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | 0 | 0 | Planned
FALSE |  |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | 0 | 0 | Planned
FALSE |  |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | 0 | 0 | Planned
FALSE |  |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | 0 | 38 | Planned
FALSE |  |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | 0 | 0 | Planned
FALSE |  |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | 0 | 0 | Planned
FALSE |  |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | 0 | 0 | Planned
FALSE |  |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | 0 | 0 | Planned
FALSE |  |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | 0 | 0 | Planned
FALSE |  |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | 0 | 0 | Planned
FALSE |  |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | 0 | 0 | Planned
FALSE |  |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | 0 | 0 | Planned
FALSE |  |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | 0 | 0 | Planned
FALSE |  |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | 0 | 0 | Planned
FALSE |  |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | 0 | 0 | Planned
FALSE |  |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | 0 | 0 | Planned
FALSE |  |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | 0 | 0 | Planned
FALSE |  |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | 0 | 0 | Planned
FALSE |  |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | 0 | 0 | Planned
FALSE |  |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | 0 | 0 | Planned
FALSE |  |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | 0 | 0 | Planned
FALSE |  |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | 0 | 0 | Planned
FALSE |  |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | 0 | 0 | Planned
FALSE |  |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | 0 | 0 | Planned
FALSE |  |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | 0 | 0 | Planned
FALSE |  |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | 0 | 0 | Planned
FALSE |  |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | 0 | 0 | Planned
FALSE |  |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | 0 | 0 | Planned
FALSE |  |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | 0 | 0 | Planned
FALSE |  |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | 0 | 0 | Planned
FALSE |  |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | 0 | 0 | Planned
FALSE |  |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | 0 | 0 | Planned
FALSE |  |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | 0 | 0 | Planned
FALSE |  |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | 0 | 0 | Planned
FALSE |  |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | 0 | 0 | Planned
FALSE |  |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | 0 | 0 | Planned
FALSE |  |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | 0 | 0 | Planned
FALSE |  |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | 0 | 0 | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Logic | Missing Logic | 8 | 8% | 7 | 6%
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Percent Complete | Total Float | Status
FALSE |  | FALSE | None | 0 | 1 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | 60 | 0 | InProgress
FALSE |  | FALSE | None | 1 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | 0 | 54 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | 0 | 54 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | 0 | 50 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | 0 | 22 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | 0 | 14 | Planned
FALSE |  | FALSE | None | 1 | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | 0 | 10 | Planned
FALSE |  | TRUE | Deadline | 1 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | 0 | 0 | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Predecessors | Missing Predecessors | 0 | 0% | 1 | 1%
Number of activities that are missing a predecessor.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Successors | Missing Successors | 7 | 7% | 6 | 5%
Number of normal activities that are missing a successor.
Excluded | Created | Critical | Primary Constraint | Number of Predecessors | Number of Successors | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | FALSE | None | 1 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | FALSE | None | 1 | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | FALSE | None | 1 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | FALSE | None | 1 | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | FALSE | None | 1 | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | FALSE | None | 1 | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | TRUE | Deadline | 1 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Start | Open Start | 0 | 0% | 0
Activities where only the predecessor(s) are either Finish-to-Finish or Start-to-Finish resulting in an open start to the activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Finish | Open Finish | 0 | 0% | 0 | 0%
Activities where the only successors(s) are either Start-to-Finish or Start-to-Start resulting in an open finish to the activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Unsatisfied Constraints | Unsatisfied Constraints | 0 | 0% | 0 | 0%
Activities where the constraint date cannot be met
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summary Links | Summary Links | 0 | 0% | 0 | 0%
Number of summary activities that have logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hard Constraints | Hard Constraints | 0 | 0% | 0 | 0%
Number of activities with hard or two-way constraints.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/Hidden Duration | Critical w/Hidden Duration | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA_Quick-Library-Schedule-Wa
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
High Float 44d | Zero Days Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | High Float 10% | Negative Float | Score
6 | 74 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 17 | 0 | 88
6% | 72% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0% | 17% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Float 44d | High Float 44d | 6 | 6% | 2 | 2%
Number of activities with total float greater than 2 months. This number should not exceed 10%.
Excluded | Critical | Project Remaining Duration | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 62 | 53 | 20 | 33 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE | FALSE | 62 | 53 | 20 | 33 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0
FALSE | FALSE | 62 | 54 | 20 | 34 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE | FALSE | 62 | 54 | 54 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE | FALSE | 62 | 54 | 20 | 34 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0
FALSE | FALSE | 62 | 50 | 50 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Zero Days Float | Zero Days Float | 74 | 72% | 78 | 71%
Total number of activities with 0 days float. This number should not exceed 15%.
Excluded | Critical | Total Float | Previous_TotalFloat | TotalFloatDelta | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | FALSE | 0 | 0 | 0 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60
FALSE | FALSE | 0 | 0 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE | FALSE | 0 | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE | TRUE | 0 | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hidden Duration (Planned) | Hidden Duration (Planned) | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of their original durations.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 0 | 0%
Number of critical activities with a high number of predecessors as well as a high number of successors (>2).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Merge Hotspot | Critical Merge Hotspot | 0 | 0% | 0 | 0%
The total number of activities with a high number of predecessor links (>2) that are also critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags | N/A |  | N/A
Number of activities with a high number of predecessor links and lags on the predecessor relationships.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Diverge Hotspot | Critical Diverge Hotspot | 0 | 0% | 1 | 1%
Number of activities with a high number of successor links (>2) that are also critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags | N/A |  | N/A
Number of activities with a high number of successor links and critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Deadlines | Deadlines | 0 | 0% | 0 | 0%
A Deadline is entered as a target finish date for a task (activity), but it functions more like a monitoring tool than a constraint.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Float 10% | High Float 10% | 17 | 17% | 20 | 18%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.

## NASA_Quick-Library-Critical-Pa
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
Tasks & Milestones (To Go) | Milestones (To-Go) | Normal Tasks (To-Go) | Normal Tasks (To-Go, In Progress) | Critical Path (Tasks & Milestones) | Critical Path (Milestones) | Critical Path (Normal Tasks) | Critical Path (Normal In Progress) | Critical Milestone-to-Task Ratio (To-Go) | Negative Float | Zero Days Float | Near-Critical (<10 Days Float) | CP Logic Density™ | Critical CEI - Value Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
103 | 24 | 79 | 1 | 33 | 6 | 27 | 0 | 1:05 | 0 | 74 | 81 | 2.12 | N/A | N/A | N/A | 0 | 1 | 1
94% | 23% | 77% | 1% | 32% | 18% | 82% | 0% |  | 0% | 72% | 79% |  |  | 27% | 73% | 0% | 1%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Tasks & Milestones (To Go) | Tasks & Milestones (To Go) | 103 | 94% | 110 | 100%
Remaining tasks and milestones in the schedule.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 0 | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress
FALSE |  | FALSE | 2 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned
FALSE |  | FALSE | 3 | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 53 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 3 | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned
FALSE |  | FALSE | 3 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned
FALSE |  | FALSE | 53 | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned
FALSE |  | FALSE | 12 | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned
FALSE |  | FALSE | 11 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned
FALSE |  | FALSE | 22 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned
FALSE |  | FALSE | 54 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned
FALSE |  | FALSE | 54 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned
FALSE |  | FALSE | 22 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned
FALSE |  | FALSE | 54 | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 39 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 50 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 22 | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned
FALSE |  | FALSE | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned
FALSE |  | FALSE | 14 | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned
FALSE |  | FALSE | 10 | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones (To-Go) | Milestones (To-Go) | 24 | 23% | 25 | 23%
Number of milestones to-go. Includes % of to-go activities that are milestones (vs. normal activities).
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | FALSE | 3 |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0
FALSE |  | FALSE | 11 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | FALSE | 37 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | FALSE | 54 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | FALSE | 54 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | FALSE | 50 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | FALSE | 22 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | FALSE | 14 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | FALSE | 10 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 79 | 77% | 85 | 77%
Number of normal activities to-go. Includes % of to-go activities that are normal activities (vs. milestones).
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 0 | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress
FALSE |  | FALSE | 2 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned
FALSE |  | FALSE | 3 | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 53 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 3 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned
FALSE |  | FALSE | 53 | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned
FALSE |  | FALSE | 12 | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned
FALSE |  | FALSE | 22 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned
FALSE |  | FALSE | 54 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned
FALSE |  | FALSE | 22 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 39 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks (To-Go, In Progress) | Normal Tasks (To-Go, In Progress) | 1 | 1% | 0 | 0%
Number of normal, in-progress to-go activities. Includes % of to-go activities that are normal, in-progress activities.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | FALSE | 0 | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress
FALSE |  | FALSE | 2 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned
FALSE |  | FALSE | 3 | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 53 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned
FALSE |  | FALSE | 3 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned
FALSE |  | FALSE | 13 | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned
FALSE |  | FALSE | 53 | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned
FALSE |  | FALSE | 12 | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned
FALSE |  | FALSE | 37 | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned
FALSE |  | FALSE | 11 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned
FALSE |  | FALSE | 22 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned
FALSE |  | FALSE | 54 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned
FALSE |  | FALSE | 22 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned
FALSE |  | FALSE | 39 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 1 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned
FALSE |  | FALSE | 38 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned
FALSE |  | FALSE | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Path (Tasks & Milestones) | Critical Path (Tasks & Milestones) | 33 | 32% | 34 | 31%
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Path (Milestones) | Critical Path (Milestones) | 6 | 18% | 7 | 21%
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Path (Normal Tasks) | Critical Path (Normal Tasks) | 27 | 82% | 27 | 79%
Activities that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Path (Normal In Progress) | Critical Path (Normal In Progress) | 0 | 0% | 0 | 0%
Number of critical, in-progress activities.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | 1:05 |  | 1:04
Ratio of the number of milestones to the number of normal activities. Ideally, milestones should make up 5% to 10% of the activities in the schedule.
Excluded | Created | Critical | Total Float | Type | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Status | Percent Complete
FALSE |  | TRUE | 0 | Normal |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Planned | 0
FALSE |  | TRUE | 0 | Normal |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Planned | 0
FALSE |  | TRUE | 0 | Milestone |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Zero Days Float | Zero Days Float | 74 | 72% | 78 | 71%
Total number of activities with 0 days float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 0 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60
FALSE |  | FALSE | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Near-Critical (<10 Days Float) | Near-Critical (<10 Days Float) | 81 | 79% | 90 | 82%
Total number of activities with less than 10 days of float.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | FALSE | 0 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60
FALSE |  | FALSE | 2 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0
FALSE |  | FALSE | 3 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | FALSE | 3 |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0
FALSE |  | FALSE | 3 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | FALSE | 1 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | FALSE | 10 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | TRUE | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CP Logic Density™ | CP Logic Density™ | 2.12 |  | 2.21
The average number of logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical CEI - Value Tasks | Critical CEI - Value Tasks | N/A |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical CEI - Complete Tasks | Critical CEI - Complete Tasks | N/A | 27% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical CEI - Incomplete Tasks | Critical CEI - Incomplete Tasks | N/A | 73% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Newly Critical Activities | Newly Critical Activities | 0 | 0% | 0 | 0%
Number of remaining activities that were added to the critical path this period (i.e., not critical in the last period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities No Longer Critical | Activities No Longer Critical | 1 | 1% | 0 | 0%
Number of activities that were previously critical but are no longer on the critical path this period.
Excluded | Created | Critical | Total Float | Previous_Critical | Id | Description | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Project
FALSE |  | FALSE | 3 | TRUE | 147 | Product Review COMPLETE | 0 | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | Hard_File_updated

## NASA_Quick-Library-BEI---Incom
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis | BEI - Incomplete Activities Analysis
BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | Score
0.27 | 11 | 3 | 8 | 100
|  | 27% | 73%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Total Tasks | BEI - Total Tasks | 11 |  | 0
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Tasks | BEI - Complete Tasks | 3 | 27% | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 8 | 73% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11

## NASA_Quick-Library-Control-Mil
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates | Control Milestone Dates
Status Date | Milestone #1 - 100 | Float Milestone #1 - 100 | Milestone #2 - 101 | Float to Milestone #2 - 101 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 104 | New Activities Since Previous Status Date | Score
2026-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #1 - 100 | Milestone #1 - 100 | N/A |  | N/A
Tracks the milestone start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float Milestone #1 - 100 | Float Milestone #1 - 100 | N/A |  | N/A
Tracks the milestone's total float across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #2 - 101 | Milestone #2 - 101 | N/A |  | N/A
Tracks the milestone start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #2 - 101 | Float to Milestone #2 - 101 | N/A |  | N/A
Tracks the milestone's total float across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #3 - 102 | Milestone #3 - 102 | N/A |  | N/A
Tracks the milestone start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #3 - 102 | Float to Milestone #3 - 102 | N/A |  | N/A
Tracks the milestone's total float across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #4 - 103 | Milestone #4 - 103 | N/A |  | N/A
Tracks the milestone start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #4 - 103 | Float to Milestone #4 - 103 | N/A |  | N/A
Tracks the milestone's total float across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #5 - 104 | Milestone #5 - 104 | N/A |  | N/A
Tracks the milestone start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #5 - 104 | Float to Milestone #5 - 104 | N/A |  | N/A
Tracks the milestone's total float across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
New Activities Since Previous Status Date | New Activities Since Previous Status Date | 0 |  | 0

## NASA_Quick-Library-Margin-Date
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-11 | N/A | 2026-08-20 | 2026-08-26 | N/A | N/A | N/A | N/A | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | 2026-08-20 |  | 2026-08-20
Tracks the margin activity start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | 2026-08-26 |  | 2026-08-26
Tracks the margin activity start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | 2026-08-18
Tracks the margin activity start date across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A
Tracks the margin activity start date across multiple schedule status updates.

## NASA_Quick-Library-Margin-Dura
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-11 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | 100
| N/A | 100% | N/A | N/A | N/A | N/A | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | 1 | 100% | 1 | 100%
Tracks the margin activity's remaining duration across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | 0 |  | 0
Tracks the margin activity's remaining duration across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | 1 | 100%
Tracks the margin activity's remaining duration across multiple schedule status updates.
Excluded | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A
Tracks the margin activity's remaining duration across multiple schedule status updates.

## NASA_Quick-Library-Status---Ch
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1) | Status - Characteristics (GRAPH 1)
Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Critical Milestones (To-Go) | Critical Normal Tasks (To-Go) | Riding Data Date | Score
2026-08-11 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 7 | 1 | 6 | 134 | 103 | 24 | 79 | 31 | 0 | 0 | 33 | 27 | 6 | 6 | 27 | 0 | 100
|  | 18% | 60% | 22% | 0% | 0% | 78% | 6% | 4% | 7% | 95% | 77% | 18% | 59% | 23% | 0% | 0% | 83% | 68% | 15% | 18% | 82% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Activities | Total Activities | 141 |  | 141
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones | Milestones | 25 | 18% | 25 | 18%
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks | Normal Tasks | 85 | 60% | 85 | 60%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summaries | Summaries | 31 | 22% | 31 | 22%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hammocks | Hammocks | 0 | 0% | 0 | 0%
Number of hammocks within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Recurring Normal Tasks | Recurring Normal Tasks | 0 | 0% | 0 | 0%
Tasks marked as recurring.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Tasks & Milestones | Total Tasks & Milestones | 110 | 78% | 110 | 78%
Total number of regular tasks and milestones in the project schedule.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Tasks & Milestones | Completed Tasks & Milestones | 7 | 6% | 0 | 0%
Total number of completed tasks and milestones
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 1 | 1 |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 0 | 0 |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE | 1.35 | 20 | 27 |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE | 1.6 | 5 | 8 |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Milestones | Completed Milestones | 1 | 4% | 0 | 0%
Total number of completed milestones.
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 0 |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Tasks | Completed Tasks | 6 | 7% | 0 | 0%
Total number of completed tasks
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 1 | 1 |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE | 1.35 | 20 | 27 |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE | 1.6 | 5 | 8 |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Activities (To-Go) - % of Total | Total Activities (To-Go) - % of Total | 134 | 95% | 141 | 100%
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 103 | 77% | 110 | 78%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones (To-Go) | Milestones (To-Go) | 24 | 18% | 25 | 18%
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 79 | 59% | 85 | 60%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summaries (To-Go) | Summaries (To-Go) | 31 | 23% | 31 | 22%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hammocks (To-Go) | Hammocks (To-Go) | 0 | 0% | 0 | 0%
Number of level of effort (hammocks) within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Recurring Tasks (To-Go) | Recurring Tasks (To-Go) | 0 | 0% | 0 | 0%
Tasks marked recurring that are in progress or planned (future).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Tasks & Milestones) | Longest Path (Tasks & Milestones) | 33 | 83% | 34 | 79%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Normal Tasks) | Longest Path (Normal Tasks) | 27 | 68% | 27 | 63%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Milestones) | Longest Path (Milestones) | 6 | 15% | 7 | 16%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 6 | 18% | 7 | 21%
Number of critical milestones to-go.
Excluded | Created | Total Float | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | 0 | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Normal Tasks (To-Go) | Critical Normal Tasks (To-Go) | 27 | 82% | 27 | 79%
Number of critical activities to-go.
Excluded | Created | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | TRUE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | TRUE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)

## NASA_Quick-Library-Performance
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project) | Performance - Baseline_Bow Wave (GRAPH 2, Project)
Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
85 | 85 | 7 | 85 | 85 | 6 | N/A | N/A | N/A | 1 | 0 | 0 | 99
[6 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start | Baselined to Start | 85 |  | 85
Number of activities that are baselined to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start | Scheduled to Start | 85 |  | 85
Number of activities that are scheduled/planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actual Starts | Actual Starts | 7 |  | 0
Number of activities that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish | Baselined to Finish | 85 |  | 85
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Finish | Scheduled to Finish | 85 |  | 85
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actual Finishes | Actual Finishes | 6 |  | 0
Number of activities that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | N/A |  | N/A
Number of activities that finished up to 30 days after their baselined finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 1 | 100% | N/A
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.

## NASA_Quick-Library-Performance2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 3, Snapshot_Ribbon)
BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 55
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Starts - Cumulative | BEI - Value Task Starts - Cumulative | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Finishes - Cumulative | BEI - Value Task Finishes - Cumulative | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Starts - by Status Dates | HMI - Value Task Starts - by Status Dates | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for task starts. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Finishes - by Status Dates | HMI - Value Task Finishes - by Status Dates | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for task finishes. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Starts - by Status Dates | CEI - Value Task Starts - by Status Dates | 0.33 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Finishes - by Status Dates | CEI - Value Task Finishes - by Status Dates | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FEI - Value Task Starts - Cumulative | FEI - Value Task Starts - Cumulative | 1.11 |  | 1
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FEI - Value Task Finish - Cumulative | FEI - Value Task Finish - Cumulative | 1.11 |  | 1
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Finishes - Cumulative | To Go - BEI - Value Task Finishes - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - Planned Task Starts - Count | To Go - Planned Task Starts - Count | 78 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Task Finishes - Count | To Go - BEI - Task Finishes - Count | 79 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - Baselined Task Starts - Count | To Go - Baselined Task Starts - Count | 78 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned

## NASA_Quick-Library-Performance3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH 4)
Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
7 | N/A | 0 | 78 | 6 | 0 | 0 | 79 | 8 | 70 | 8 | 71 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Started (BL Plan) | Current Baseline to Start & Started (BL Plan) | 7 |  | N/A
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Start & Started (Early Starts) | Future Baseline to Start & Started (Early Starts) | N/A |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Start & Started (Workoff Burden) | Past Baseline to Start & Started (Workoff Burden) | 0 |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Start & Not Started (Incompletes) | 78 |  | 85
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Finished (BL Plan) | Current Baseline to Finish & Finished (BL Plan) | 6 |  | N/A
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Finish & Finished (Early Finishes) | Future Baseline to Finish & Finished (Early Finishes) | 0 |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Finish & Finished (Workoff Burden) | Past Baseline to Finish & Finished (Workoff Burden) | 0 |  | N/A
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Not Finished (Incompletes) | Current Baseline to Finish & Not Finished (Incompletes) | 79 |  | 85
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Start & Not Started (Workoff Burden) | Past Baseline to Start & Not Started (Workoff Burden) | 8 |  | 0
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Start & Already Delayed (Workoff Burden) | Future Baseline to Start & Already Delayed (Workoff Burden) | 70 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Finish & Not Finished (Workoff Burden) | Past Baseline to Finish & Not Finished (Workoff Burden) | 8 |  | 0
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Finish & Already Delayed (Workoff Burden) | Future Baseline to Finish & Already Delayed (Workoff Burden) | 71 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | 2026-08-05 | 2026-08-05 | 2026-08-05 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned

## NASA_Quick-Library-Performance4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project) | Performance - Duration Ratio (GRAPH 5, Project)
Duration Ratio Metric (DRM) | DRM Graph | Score
6 | 6 | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Duration Ratio Metric (DRM) | Duration Ratio Metric (DRM) | 6 |  | 0
Duration Ratio Metric compares the actual time a task or project phase took (Actual Duration) to the time it was originally planned or expected to take (Baseline Duration). The result is a ratio that quantifies schedule performance. Duration Ratio = ActualDuration/BaselineDuration
Excluded | Notes | Id | Description | Baseline Duration | Actual Duration | DRM | Project | Original Duration | Remaining Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | 1 | 1 | 1 | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | 1 | 1 | 1 | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | 20 | 27 | 1.35 | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | 1 | 1 | 1 | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | 5 | 5 | 1 | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | 5 | 8 | 1.6 | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
DRM Graph | DRM Graph | 6 |  | 0
The total number of activities within a grouping.
Id | Description | Baseline Duration | Actual Duration | DRM
97 | Identify typical product usage scenarios | 1 | 1 | 1
96 | Identify typical customer types | 1 | 1 | 1
95 | Identify anticipated product problem points | 20 | 27 | 1.35
400 | Build customer service programs | 1 | 1 | 1
399 | Perform subject matter expert review | 5 | 5 | 1
401 | Perform user acceptance testing with customers | 5 | 8 | 1.6

## NASA_Quick-Library-Performance5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6) | Performance - Baseline_To-Go Activities (GRAPH 6)
Baselined to Start | Scheduled to Start | Baselined to Finish | Scheduled to Finish | Score
79 | 79 | 79 | 79 | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start | Baselined to Start | 79 |  | 85
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start | Scheduled to Start | 79 |  | 85
Number of activities that are planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish | Baselined to Finish | 79 |  | 85
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Finish | Scheduled to Finish | 79 |  | 85
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0

## NASA_Quick-Library-Performance6
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA_Quick-Library -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7) | Performance - BEI vs CP% (GRAPH 7)
BEI - Value Activities | Tasks & Milestones (To-Go) - % of Total To-Go | Critical Path To-Go | Score
0.29 | 103 | 33 | 100
| 77% | 32%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Activities | BEI - Value Activities | 0.29 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 103 | 77% | 110 | 78%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Path To-Go | Critical Path To-Go | 33 | 32% | 34 | 31%
Normal activities and milestones that together form the longest path through to project completion.
Excluded | Created | Critical | Total Float | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status
FALSE |  | TRUE | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned
FALSE |  | TRUE | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned
FALSE |  | TRUE | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned

## NASA-Metrics
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA Metrics
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
NASA Metrics
|  | Status & Quality | Performance | Schedule Errors | Schedule Warnings | Critical Path
Ribbons | Hard_File | 58.8571 | 68.0714 | 47 | 85 | 0
Ribbons | Hard_File_updated | 59.4286 | 67.6786 | 48 | 88 | 1
Status & Quality
|  | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Duration | Quality - Constraints | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors
Ribbons | Hard_File | 100 | N/A | 100 | 0 | 22 | 73 | 22 | 95
Ribbons | Hard_File_updated | 100 | N/A | 100 | 0 | 27 | 67 | 28 | 94
Performance
|  | Performance - Completed | Performance - In-Progress | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Float | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | Baseline Execution Index (BEI) | Hit or Miss Index (HMI) | Current Execution Index (CEI) | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | DRM | Tracking Dates | Margin Duration | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path
Ribbons | Hard_File | 0 | 0 | 0 | 100 | 86 | 0 | 100 | 100 | 100 | 60 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 60 | N/A | 100
Ribbons | Hard_File_updated | 0 | 0 | 0 | 100 | 88 | 0 | 99 | 99 | 99 | 55 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 55 | N/A | 100
|  | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
|  | Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
Ribbons | Hard_File | 0 | 0 | 0 | 0 | 0 | 1 | 68 | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-07 | 47
Ribbons |  | ( N/A ) | 0% | 0% | 0% | 0% | 1% | 80% | 6% | 1% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ribbons | Hard_File_updated | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 48
Ribbons |  | 0% | 0% | 0% | 0% | 0% | 1% | 82% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
|  | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | Score
Ribbons | Hard_File | 20 | 2 | 78 | 0 | 0 | 0 | 0 | N/A | 1 | N/A | 0 | 0 | 85
Ribbons |  | 18% | 2% | 71% | 0% | 0% | 0% | 0% | ( N/A ) | 1% | ( N/A ) | 0% | 0%
Ribbons | Hard_File_updated | 17 | 6 | 74 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 88
Ribbons |  | 17% | 6% | 72% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0%
|  | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
|  | Longest Path (Normal Tasks) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
Ribbons | Hard_File | 27 | 34 | 1:04 | 7 | 7 | 85 | 85 | 27 | 0 | 78 | 0 | 2.21 | 0 | 0 | 0
Ribbons |  | 63% | 79% | 0.26 | 28% | 16% | 60% | 60% | 32% | 0% | 71% | 0% |  | 0% | 0%
Ribbons | Hard_File_updated | 27 | 33 | 1:05 | 6 | 6 | 85 | 79 | 27 | 0 | 74 | 0 | 2.12 | 0 | 1 | 1
Ribbons |  | 68% | 83% | 0.22 | 25% | 15% | 60% | 59% | 34% | 0% | 72% | 0% |  | 0% | 1%

## NASA-Metrics-Status---Quality
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA Metrics Status & Quality
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Status & Quality
|  | Status - Characteristics | Status - New Activities (Snapshot) | Quality - Construction | Quality - Duration | Quality - Constraints | Quality - Logic | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Successors
Ribbons | Hard_File | 100 | N/A | 100 | 0 | 22 | 73 | 22 | 95
Ribbons | Hard_File_updated | 100 | N/A | 100 | 0 | 27 | 67 | 28 | 94
|  | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics
|  | Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Riding Data Date | Score
Ribbons | Hard_File | 2026-07-07 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 0 | 0 | 0 | 141 | 110 | 25 | 85 | 31 | 0 | 0 | 34 | 27 | 7 | 0 | 100
Ribbons |  |  |  | 18% | 60% | 22% | 0% | 0% | 78% | 0% | 0% | 0% | 100% | 78% | 18% | 60% | 22% | 0% | 0% | 79% | 63% | 16% | 0%
Ribbons | Hard_File_updated | 2026-08-11 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 7 | 1 | 6 | 134 | 103 | 24 | 79 | 31 | 0 | 0 | 33 | 27 | 6 | 0 | 100
Ribbons |  |  |  | 18% | 60% | 22% | 0% | 0% | 78% | 6% | 4% | 7% | 95% | 77% | 18% | 59% | 23% | 0% | 0% | 83% | 68% | 15% | 0%
|  | Status - New Activities (Snapshot) | Status - New Activities (Snapshot)
|  | Status Date | Score
Ribbons | Hard_File | 2026-07-07 | N/A
Ribbons
Ribbons | Hard_File_updated | 2026-08-11 | N/A
Ribbons
|  | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction
|  | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Summary-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Manual Tasks (To-Go) | Critical Tasks and Milestones (To-Go) | Wrong Status (To-Go) | Invalid Forecast Dates | Missing WBS (To-Go) | All Activities (To Go) | Score
Ribbons | Hard_File | 141 | 110 | 1:03 | 1:03 | 1:04 | 0 | 34 | 0 | 0 | 0 | 110 | 100
Ribbons |  | 100% | 78% | 0.36 | 0.29 | 0.26 | 0% | 31% | ( N/A ) | 0% | 0% | 100%
Ribbons | Hard_File_updated | 134 | 103 | 1:03 | 1:03 | 1:05 | 0 | 33 | 0 | 0 | 0 | 103 | 100
Ribbons |  | 95% | 77% | 0.39 | 0.3 | 0.22 | 0% | 32% | 0% | 0% | 0% | 100%
|  | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration
|  | Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Score
Ribbons | Hard_File | 110 | 68 | 0 | 1 | 2 | 2 | 0 | 0 | 2 | 27 | 1 | 1 | 0 | 0 | 0 | 85 | 0
Ribbons |  | 78% | 80% | 0% | 1% |  |  | 0% | 0% | 2% | 32% |  |  | 0% | 0% | 0% | 100%
Ribbons | Hard_File_updated | 103 | 65 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 27 | 1 | 1 | 0 | 0 | 0 | 79 | 0
Ribbons |  | 77% | 82% | 0% | 1% |  |  | 0% | 0% | 1% | 34% |  |  | 0% | 0% | 0% | 93%
|  | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints
|  | Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Score
Ribbons | Hard_File | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 0 | 108 | 107 | 22
Ribbons |  | 2% | 1% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 5% | 0% | 98% | 97%
Ribbons | Hard_File_updated | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 0 | 100 | 99 | 27
Ribbons |  | 3% | 2% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 6% | 0% | 97% | 96%
|  | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic
|  | Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Score
Ribbons | Hard_File | 2.07 | 1.04 | 1.04 | 0 | 109 | 0 | 0 | 0 | 109 | 104 | 0 | 0 | 0 | 104 | 7 | 1 | 6 | 0 | 0 | 73
Ribbons |  |  |  |  | 0% | 99% | 0% | 0% | 0% | 99% | 95% | 0% | 0% | 0% | 95% | 6% | 1% | 5% | 0% | 0%
Ribbons | Hard_File_updated | 2.08 | 1.05 | 1.03 | 0 | 102 | 0 | 0 | 0 | 102 | 96 | 0 | 0 | 0 | 96 | 8 | 1 | 7 | 0 | 0 | 67
Ribbons |  |  |  |  | 0% | 100% | 0% | 0% | 0% | 99% | 93% | 0% | 0% | 0% | 93% | 8% | 1% | 7% | 0% | 0%
|  | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors
|  | Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
Ribbons | Hard_File | 1.04 | 109 | 114 | 1 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | 0 | 0 | 0 | 22
Ribbons |  |  | 100% |  | 1% | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 1% | ( N/A ) | ( N/A ) | 0% | 0% | 0%
Ribbons | Hard_File_updated | 1.06 | 102 | 108 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | 0 | 0 | 0 | 28
Ribbons |  |  | 100% |  | 0% | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 1% | ( N/A ) | ( N/A ) | 0% | 0% | 0%
|  | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors
|  | Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
Ribbons | Hard_File | 1.04 | 104 | 6 | 114 | 0 | N/A | N/A | 0 | N/A | N/A | 1 | N/A | N/A | 1 | 0 | 0 | 95
Ribbons |  |  | 100% | 5% |  | 0% |  |  | 0% |  |  | 1% | ( N/A ) | ( N/A ) | 1% | 0% | 0%
Ribbons | Hard_File_updated | 1.03 | 96 | 7 | 106 | 0 | N/A | N/A | 0 | N/A | N/A | 1 | N/A | N/A | 0 | 0 | 0 | 94
Ribbons |  |  | 100% | 7% |  | 0% |  |  | 0% |  |  | 1% | ( N/A ) | ( N/A ) | 0% | 0% | 0%

## NASA-Metrics-Status---Quality-
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics | Status - Characteristics
Status Date | Total Activities | Milestones | Normal Tasks | Summaries | Hammocks | Recurring Normal Tasks | Total Tasks & Milestones | Completed Tasks & Milestones | Completed Milestones | Completed Tasks | Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Milestones (To-Go) | Normal Tasks (To-Go) | Summaries (To-Go) | Hammocks (To-Go) | Recurring Tasks (To-Go) | Longest Path (Tasks & Milestones) | Longest Path (Normal Tasks) | Longest Path (Milestones) | Riding Data Date | Score
2026-08-11 | 141 | 25 | 85 | 31 | 0 | 0 | 110 | 7 | 1 | 6 | 134 | 103 | 24 | 79 | 31 | 0 | 0 | 33 | 27 | 6 | 0 | 100
|  | 18% | 60% | 22% | 0% | 0% | 78% | 6% | 4% | 7% | 95% | 77% | 18% | 59% | 23% | 0% | 0% | 83% | 68% | 15% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Activities | Total Activities | 141 |  | 141
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones | Milestones | 25 | 18% | 25 | 18%
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks | Normal Tasks | 85 | 60% | 85 | 60%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summaries | Summaries | 31 | 22% | 31 | 22%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hammocks | Hammocks | 0 | 0% | 0 | 0%
Number of hammocks within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Recurring Normal Tasks | Recurring Normal Tasks | 0 | 0% | 0 | 0%
Tasks marked as recurring.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Tasks & Milestones | Total Tasks & Milestones | 110 | 78% | 110 | 78%
Total number of regular tasks and milestones in the project schedule.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Tasks & Milestones | Completed Tasks & Milestones | 7 | 6% | 0 | 0%
Total number of completed tasks and milestones
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 1 | 1 |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 0 | 0 |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE | 1.35 | 20 | 27 |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE | 1.6 | 5 | 8 |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Milestones | Completed Milestones | 1 | 4% | 0 | 0%
Total number of completed milestones.
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 0 |  | 100 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | Standard | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Tasks | Completed Tasks | 6 | 7% | 0 | 0%
Total number of completed tasks
Excluded | DRM | Baseline Duration | Actual Duration | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 1 | 1 |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE | 1.35 | 20 | 27 |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE | 1 | 1 | 1 |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE | 1 | 5 | 5 |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE | 1.6 | 5 | 8 |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Activities (To-Go) - % of Total | Total Activities (To-Go) - % of Total | 134 | 95% | 141 | 100%
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 103 | 77% | 110 | 78%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones (To-Go) | Milestones (To-Go) | 24 | 18% | 25 | 18%
Number of milestones within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 79 | 59% | 85 | 60%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summaries (To-Go) | Summaries (To-Go) | 31 | 23% | 31 | 22%
Number of summary activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hammocks (To-Go) | Hammocks (To-Go) | 0 | 0% | 0 | 0%
Number of hammocks within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Recurring Tasks (To-Go) | Recurring Tasks (To-Go) | 0 | 0% | 0 | 0%
Tasks marked recurring that are in progress or planned (future).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Tasks & Milestones) | Longest Path (Tasks & Milestones) | 33 | 83% | 34 | 79%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Normal Tasks) | Longest Path (Normal Tasks) | 27 | 68% | 27 | 63%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Milestones) | Longest Path (Milestones) | 6 | 15% | 7 | 16%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)

## NASA-Metrics-Status---Quality-2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Status - New Activities (Snapshot) | Status - New Activities (Snapshot)
Status Date | Score
2026-08-11 | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Status---Quality-3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction | Quality - Construction
Total Activities (To-Go) - % of Total | Tasks & Milestones (To-Go) - % of Total To-Go | Summary-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Manual Tasks (To-Go) | Critical Tasks and Milestones (To-Go) | Wrong Status (To-Go) | Invalid Forecast Dates | Missing WBS (To-Go) | All Activities (To Go) | Score
134 | 103 | 1:03 | 1:03 | 1:05 | 0 | 33 | 0 | 0 | 0 | 103 | 100
95% | 77% | 0.39 | 0.3 | 0.22 | 0% | 32% | 0% | 0% | 0% | 100%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Activities (To-Go) - % of Total | Total Activities (To-Go) - % of Total | 134 | 95% | 141 | 100%
The total number of activities within a grouping. Percentage shows total total to-go (planned and in-progress) activities (normal, milestone, summary and LOE) out of total to-go and completed activities.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 94 |  | 91 | Initial Assessment | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 94 |  | 92 | Perform Product Review | Hard_File_updated | Standard | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 3
FALSE |  | 32 |  | 373 | Build Customer Service Program | Hard_File_updated | Standard | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 14
FALSE |  | 74 |  | 392 | Customer Service Program Development | Hard_File_updated | Standard | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 22
FALSE |  | 43 |  | 322 | Service Planning | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 11
FALSE |  | 45 |  | 125 | Design Support Services | Hard_File_updated | Standard | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 53 |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | Standard | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 11
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 383 | Business Performance Planning | Hard_File_updated | Standard | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 53
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 129 | Training & Readiness | Hard_File_updated | Standard | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 212 | Training Needs Assessment | Hard_File_updated | Standard | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | Standard | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 11
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 100 | Resources Requirements | Hard_File_updated | Standard | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 318 | Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 37
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 235 | Training Planning | Hard_File_updated | Standard | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 299 | Content Development Planning | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 372 | Build Technology Infrastructure | Hard_File_updated | Standard | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 38
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 237 | Training Delivery Planning | Hard_File_updated | Standard | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0
FALSE |  | 0 |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | Standard | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 391 | Program Deployment | Hard_File_updated | Standard | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 8
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | Standard | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 283 | Training Delivery Logistics | Hard_File_updated | Standard | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 306 | Finalize Training Planning | Hard_File_updated | Standard | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 375 | Training/Readiness Development | Hard_File_updated | Standard | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 219 | Training Content Development | Hard_File_updated | Standard | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 221 | Build Training Content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 175 | Develop Training Delivery Engine | Hard_File_updated | Standard | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 393 | Resource Readiness | Hard_File_updated | Standard | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 37 | Post Launch | Hard_File_updated | Standard | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | Standard | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 143 | Monitoring | Hard_File_updated | Standard | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 103 | 77% | 110 | 78%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summary-to-Task Ratio (To-Go) | Summary-to-Task Ratio (To-Go) | 1:03 | 0.39 | 1:03 | 0.36
Ratio of the number of summary to the number of normal activities. Should not be less than 1:20.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | 1:03 | 0.3 | 1:03 | 0.29
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | 1:05 | 0.22 | 1:04 | 0.26
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Manual Tasks (To-Go) | Manual Tasks (To-Go) | 0 | 0% | 0 | 0%
Tasks marked for manual calculation in Microsoft Project 2010 and higher
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Tasks and Milestones (To-Go) | Critical Tasks and Milestones (To-Go) | 33 | 32% | 34 | 31%
Number of critical activities to-go.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Wrong Status (To-Go) | Wrong Status (To-Go) | 0 | 0% | 0
Number of activities that have been statused into the future.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Invalid Forecast Dates | Invalid Forecast Dates | 0 | 0% | 0 | 0%
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing WBS (To-Go) | Missing WBS (To-Go) | 0 | 0% | 0 | 0%
Number of activities that are missing WBS values.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
All Activities (To Go) | All Activities (To Go) | 103 | 100% | 110 | 100%
The total number of activities within a grouping that have predecessors.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0

## NASA-Metrics-Status---Quality-4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration | Quality - Duration
Tasks & Milestones (To-Go) - % of Total To-Go | Estimated Duration | Milestones with Duration>0 | Activities with Duration=0 | Avg. Original Duration | Avg. Remaining Duration | High Baseline Duration (44d) | High Planned Duration (44d) | Insufficient Detail™ | Critical Activities (To-Go) | Avg. Critical Original Duration | Avg. Critical Remaining Duration | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical w/Insufficient Detail™ | Activities (To-Go) | Score
103 | 65 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 27 | 1 | 1 | 0 | 0 | 0 | 79 | 0
77% | 82% | 0% | 1% |  |  | 0% | 0% | 1% | 34% |  |  | 0% | 0% | 0% | 93%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Tasks & Milestones (To-Go) - % of Total To-Go | Tasks & Milestones (To-Go) - % of Total To-Go | 103 | 77% | 110 | 78%
The total number of activities within a grouping. Percentage shows total to-go (planned and in-progress) tasks and milestones out of all activities (normal, milestone, summary, and LOE).
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Estimated Duration | Estimated Duration | 65 | 82% | 68 | 80%
Tasks with estimated duration in Microsoft Project. This condition occurs when an original duration has not been entered by the user.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  |  | 180 | Online support | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones with Duration>0 | Milestones with Duration>0 | 0 | 0% | 0 | 0%
Milestones with a duration greater than 0 days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities with Duration=0 | Activities with Duration=0 | 1 | 1% | 1 | 1%
Activities that have an original duration of 0 days.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg. Original Duration | Avg. Original Duration | 1 |  | 2
Average planned or original duration of all normal activities and milestones within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg. Remaining Duration | Avg. Remaining Duration | 1 |  | 2
Average remaining duration of all normal activities and milestones within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Baseline Duration (44d) | High Baseline Duration (44d) | 0 | 0% | 0 | 0%
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Planned Duration (44d) | High Planned Duration (44d) | 0 | 0% | 0 | 0%
Total number of activities that have a duration longer than 2 months. This number should not exceed 5%.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Insufficient Detail™ | Insufficient Detail™ | 1 | 1% | 2 | 2%
Number of activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Activities (To-Go) | Critical Activities (To-Go) | 27 | 34% | 27 | 32%
Number of critical activities
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg. Critical Original Duration | Avg. Critical Original Duration | 1 |  | 1
Average planned or original duration of all critical activities within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg. Critical Remaining Duration | Avg. Critical Remaining Duration | 1 |  | 1
Average remaining duration of all normal activities and milestones within a grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/High Baseline Duration (44d) | Critical w/High Baseline Duration (44d) | 0 | 0% | 0 | 0%
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 91 | Initial Assessment | Hard_File_updated | 18 | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 94 | 3
FALSE |  |  | 92 | Perform Product Review | Hard_File_updated | 18 | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 94 | 3
FALSE |  |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  |  | 95 | Identify anticipated product problem points | Hard_File_updated | 20 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  |  | 373 | Build Customer Service Program | Hard_File_updated | 42 | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 32 | 14
FALSE |  |  | 392 | Customer Service Program Development | Hard_File_updated | 37 | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 74 | 22
FALSE |  |  | 400 | Build customer service programs | Hard_File_updated | 1 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 5 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  |  | 322 | Service Planning | Hard_File_updated | 11 | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 43 | 11
FALSE |  |  | 125 | Design Support Services | Hard_File_updated | 10 | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 45 | 11
FALSE |  |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | 9 | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 53 | 11
FALSE |  |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  |  | 383 | Business Performance Planning | Hard_File_updated | 2 | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 0 | 53
FALSE |  |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | 42 | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE |  |  | 129 | Training & Readiness | Hard_File_updated | 42 | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE |  |  | 212 | Training Needs Assessment | Hard_File_updated | 14 | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0 | 0
FALSE |  |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | 1 | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 0 | 11
FALSE |  |  | 180 | Online support | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  |  | 100 | Resources Requirements | Hard_File_updated | 2 | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0 | 0
FALSE |  |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  |  | 318 | Technology Infrastructure | Hard_File_updated | 3 | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 0 | 37
FALSE |  |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  |  | 235 | Training Planning | Hard_File_updated | 27 | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE |  |  | 299 | Content Development Planning | Hard_File_updated | 4 | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0 | 0
FALSE |  |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  |  | 372 | Build Technology Infrastructure | Hard_File_updated | 3 | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 0 | 38
FALSE |  |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  |  | 237 | Training Delivery Planning | Hard_File_updated | 21 | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0 | 0
FALSE |  |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | 12 | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0 | 0
FALSE |  |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  |  | 391 | Program Deployment | Hard_File_updated | 40 | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 0 | 8
FALSE |  |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | 10 | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0 | 0
FALSE |  |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  |  | 283 | Training Delivery Logistics | Hard_File_updated | 8 | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0 | 0
FALSE |  |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  |  | 306 | Finalize Training Planning | Hard_File_updated | 3 | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE |  |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  |  | 375 | Training/Readiness Development | Hard_File_updated | 12 | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0 | 0
FALSE |  |  | 219 | Training Content Development | Hard_File_updated | 4 | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0 | 0
FALSE |  |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 221 | Build Training Content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0 | 0
FALSE |  |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  |  | 175 | Develop Training Delivery Engine | Hard_File_updated | 8 | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0 | 0
FALSE |  |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  |  | 393 | Resource Readiness | Hard_File_updated | 5 | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0 | 0
FALSE |  |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  |  | 37 | Post Launch | Hard_File_updated | 8 | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0 | 0
FALSE |  |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | 4 | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0 | 0
FALSE |  |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  |  | 143 | Monitoring | Hard_File_updated | 4 | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0 | 0
FALSE |  |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/High Planned Duration (44d) | Critical w/High Planned Duration (44d) | 0 | 0% | 0 | 0%
Number of critical activities with a duration longer than 44 days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/Insufficient Detail™ | Critical w/Insufficient Detail™ | 0 | 0% | 0 | 0%
Number of critical activities that have a duration longer than 10% of the total duration of the project. This number should not exceed 5%.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities (To-Go) | Activities (To-Go) | 79 | 93% | 85 | 100%
The total number of activities within a grouping.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  |  | 95 | Identify anticipated product problem points | Hard_File_updated | 20 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  |  | 400 | Build customer service programs | Hard_File_updated | 1 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 5 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  |  | 180 | Online support | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0

## NASA-Metrics-Status---Quality-5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints | Quality - Constraints
Total Constraints | Start No Earlier Than | Start No Later Than | Finish No Earlier Than | Finish No Later Than | Hard Constraints | Must Start On | Must Finish On | As Late As Possible | Deadlines | Mandatory Start | Mandatory Finish | Open Ends with Constraints | Open Ends w/o Constraints | Unsatisfied Constraints | No Constraints | No Constraints | Score
3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 0 | 100 | 99 | 27
3% | 2% | 0% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 6% | 0% | 97% | 96%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Constraints | Total Constraints | 3 | 3% | 2 | 2%
Number of activities with certain constraint types.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | StartOnOrAfter | 2026-08-12 | None |  | FALSE | 2 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0
FALSE |  | FinishOnOrAfter | 2026-07-31 | None |  | FALSE | 3 |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0
FALSE |  | StartOnOrAfter | 2026-07-31 | None |  | FALSE | 11 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Start No Earlier Than | Start No Earlier Than | 2 | 2% | 1 | 1%
Number of activities with a soft (one-way) constraint that forces the activity to start on or after a given date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Start No Later Than | Start No Later Than | 0 | 0% | 0 | 0%
Number of activities with a soft (one-way) constraint that forces the activity to start on or before a given date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finish No Earlier Than | Finish No Earlier Than | 1 | 1% | 1 | 1%
Number of activities with a soft (one-way) constraint that forces the activity to finish on or after a specific date
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finish No Later Than | Finish No Later Than | 0 | 0% | 0 | 0%
Number of activities with a soft (one-way) constraint that forces the activity to finish on or before a specific date
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hard Constraints | Hard Constraints | 0 | 0% | 0 | 0%
Number of activities with hard or two-way constraints.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Must Start On | Must Start On | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to start on a specific date but does not override CPM Calculations.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Must Finish On | Must Finish On | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date but does not override CPM Calculations.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
As Late As Possible | As Late As Possible | 0 | 0% | 0 | 0%
Number of activities with a soft (one-way) constraint that forces the activity to start as late as possible without impacting the Early or Late dates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Deadlines | Deadlines | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date, overriding CPM calculations.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Mandatory Start | Mandatory Start | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to start on a specific date, overriding CPM calculations.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Mandatory Finish | Mandatory Finish | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date, overriding CPM calculations.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Ends with Constraints | Open Ends with Constraints | 1 | 1% | 1 | 1%
Activities where missing logic is accounted for through the use of a constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Ends w/o Constraints | Open Ends w/o Constraints | 7 | 6% | 6 | 5%
Activities that are missing logic without any type of supporting constraint.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Unsatisfied Constraints | Unsatisfied Constraints | 0 | 0% | 0 | 0%
Activities where the constraint date cannot be met
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
No Constraints | No Constraints | 100 | 97% | 108 | 98%
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 0 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60
FALSE |  | None |  | None |  | FALSE | 3 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 53 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 3 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 13 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 53 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 37 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 12 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 11 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 37 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 11 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 11 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 22 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 54 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 37 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 54 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 22 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 54 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 1 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 39 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 1 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 50 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 22 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 14 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 10 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | Deadline | 2026-11-05 | None |  | TRUE | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
No Constraints | No Constraints | 99 | 96% | 107 | 97%
Number of activities with no constraints.
Excluded | Created | Primary Constraint | Primary Constraint Date | Secondary Constraint | Secondary Constraint Date | Critical | Total Float | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE |  | None |  | None |  | FALSE | 0 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60
FALSE |  | None |  | None |  | FALSE | 3 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 53 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 3 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 13 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 53 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 37 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 12 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 11 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 37 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 11 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 11 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 22 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 54 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 37 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 54 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 22 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 54 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 1 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 39 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 1 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 50 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 38 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 22 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | None |  | None |  | FALSE | 14 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | None |  | None |  | FALSE | 10 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | None |  | None |  | TRUE | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0

## NASA-Metrics-Status---Quality-6
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic | Quality - Logic
Logic Density™ | Logic Density™ - Predecessors | Logic Density™ - Successors | Summary Links | All Activities w/Predecessors | SS Predecessors | SF Predecessors | FF Predecessors | FS Predecessors | All Activities w/Successors | SS Successors | FF Successors | SF Successors | FS Successors | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Score
2.08 | 1.05 | 1.03 | 0 | 102 | 0 | 0 | 0 | 102 | 96 | 0 | 0 | 0 | 96 | 8 | 1 | 7 | 0 | 0 | 67
|  |  | 0% | 100% | 0% | 0% | 0% | 99% | 93% | 0% | 0% | 0% | 93% | 8% | 1% | 7% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Density™ | Logic Density™ | 2.08 |  | 2.07
The average number of logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Density™ - Predecessors | Logic Density™ - Predecessors | 1.05 |  | 1.04
The average number of predecessor logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Density™ - Successors | Logic Density™ - Successors | 1.03 |  | 1.04
The average number of successor logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summary Links | Summary Links | 0 | 0% | 0 | 0%
Number of summary activities that have logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
All Activities w/Predecessors | All Activities w/Predecessors | 102 | 100% | 109 | 99%
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Predecessors | Number of Leads | Number of Lags | Maximum Lag | Minimum Lag | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE | 3 | 0 | 0 | 0 | 0 |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE | 2 | 0 | 0 | 0 | 0 |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 | 0 | 0 |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
SS Predecessors | SS Predecessors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Start (SS) logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
SF Predecessors | SF Predecessors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Finish (SF) logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FF Predecessors | FF Predecessors | 0 | 0% | 0 | 0%
Number of activities with Finish-to-Finish (FF) logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FS Predecessors | FS Predecessors | 102 | 99% | 109 | 99%
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Number of FS Predecessors | Number Of FS Predecessor Lags | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 1 | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 1 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 1 | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE | 1 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 1 | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 1 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 1 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 1 | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE | 1 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 1 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 1 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 3 | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE | 1 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 1 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 2 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 1 | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE | 1 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | 1 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 1 | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | 1 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 1 | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 1 | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 1 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 1 | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | 1 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 1 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 2 | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | 1 | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE | 2 | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE | 2 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | 1 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
All Activities w/Successors | All Activities w/Successors | 96 | 93% | 104 | 95%
The total number of activities within a grouping. Includes normal activities and milestones that are planned or in-progress.
Excluded | Number of Successors | Number of Successor Leads | Number of Successor Lags | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE | 1 | 0 | 0 |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE | 1 | 0 | 0 |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE | 1 | 0 | 0 |  | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE | 2 | 0 | 0 |  | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE | 2 | 0 | 0 |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE | 4 | 0 | 0 |  | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE | 1 | 0 | 0 |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE | 1 | 0 | 0 |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE | 1 | 0 | 0 |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE | 1 | 0 | 0 |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE | 1 | 0 | 0 |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE | 1 | 0 | 0 |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE | 1 | 0 | 0 |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE | 1 | 0 | 0 |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE | 1 | 0 | 0 |  | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE | 1 | 0 | 0 |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE | 1 | 0 | 0 |  | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE | 1 | 0 | 0 |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE | 2 | 0 | 0 |  | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE | 1 | 0 | 0 |  | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE | 1 | 0 | 0 |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE | 1 | 0 | 0 |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE | 1 | 0 | 0 |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE | 2 | 0 | 0 |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE | 1 | 0 | 0 |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE | 1 | 0 | 0 |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE | 1 | 0 | 0 |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE | 2 | 0 | 0 |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE | 2 | 0 | 0 |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE | 2 | 0 | 0 |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE | 1 | 0 | 0 |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
SS Successors | SS Successors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Start (SS) logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FF Successors | FF Successors | 0 | 0% | 0 | 0%
Number of activities with Finish-to-Finish (FF) logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
SF Successors | SF Successors | 0 | 0% | 0 | 0%
Number of activities with Start-to-Finish (SF) logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FS Successors | FS Successors | 96 | 93% | 104 | 95%
Number of activities with Finish-to-Start (FS) logic links. Should be at least 90%.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Logic | Missing Logic | 8 | 8% | 7 | 6%
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 0 | 1 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Predecessors | Missing Predecessors | 1 | 1% | 1 | 1%
Number of activities that are missing a predecessor.
Excluded | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 | 1 |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Successors | Missing Successors | 7 | 7% | 6 | 5%
Number of normal activities that are missing a successor.
Excluded | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | 1 | 0 |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | 1 | 0 |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | 1 | 0 |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | 1 | 0 |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE | 1 | 0 |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE | 1 | 0 |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Start | Open Start | 0 | 0% | 0 | 0%
Activities where only the predecessor(s) are either Finish-to-Finish or Start-to-Finish resulting in an open start to the activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Finish | Open Finish | 0 | 0% | 0 | 0%
Activities where the only successors(s) are either Start-to-Finish or Start-to-Start resulting in an open finish to the activity.

## NASA-Metrics-Status---Quality-7
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors | Quality - Logic Hotspots - Predecessors
Logic Density™ - Predecessors | All Activities w/Predecessors | Total # Predecessors | Activities Missing Predecessors | Activities w/Leads on Predecessor | Total # Predecessor Leads | Max # Predecessor Leads on an Activity | Activities w/Lags on Predecessor | Total # Predecessor Lags | Max # of Predecessor Lags on an Activity | Min Predecessor Lag (days) | Max Predecessor Lag (days) | Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | Merge Hotspot (Predecessors >2) | Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags & Low Total Float | Critical Merge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
1.06 | 102 | 108 | 0 | 0 | N/A | N/A | 0 | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | 0 | 0 | 0 | 28
| 100% |  | 0% | 0% |  |  | 0% |  |  |  |  | 0% | 0% | 1% | ( N/A ) | ( N/A ) | 0% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Density™ - Predecessors | Logic Density™ - Predecessors | 1.06 |  | 1.04
The average number of predecessor logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
All Activities w/Predecessors | All Activities w/Predecessors | 102 | 100% | 109 | 100%
The total number of activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total # Predecessors | Total # Predecessors | 108 |  | 114
The total number of successors on all activities within a grouping that have predecessors. Includes normal activities and milestones that are planned.
Excluded | Created | Percent Complete | Number of Predecessors | Number of Leads | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 3 | 0 | 0 | 0 | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 54
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 54
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 50
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 14
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 10
FALSE |  | 0 | 2 | 0 | 0 | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities Missing Predecessors | Activities Missing Predecessors | 0 | 0% | 1 | 1%
Number of activities that are missing a predecessor.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities w/Leads on Predecessor | Activities w/Leads on Predecessor | 0 | 0% | 0 | 0%
Total number of activities carrying a lead (negative lag) on the link to their predecessor activity. This number should not exceed 5%.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total # Predecessor Leads | Total # Predecessor Leads | N/A |  | N/A
Total number of predecessor relationships with leads (negative lag) in the schedule
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Max # Predecessor Leads on an Activity | Max # Predecessor Leads on an Activity | N/A |  | N/A
The max number of predecessor leads (negative lag) on an activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities w/Lags on Predecessor | Activities w/Lags on Predecessor | 0 | 0% | 0 | 0%
Total number of activities carrying a lag on the link to their predecessor activity. This number should not exceed 5%.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total # Predecessor Lags | Total # Predecessor Lags | N/A |  | N/A
Total number of predecessor relationships with lags in the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Max # of Predecessor Lags on an Activity | Max # of Predecessor Lags on an Activity | N/A |  | N/A
The max number of predecessor lags on an activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Min Predecessor Lag (days) | Min Predecessor Lag (days) | 0 |  | 0
The smallest predecessor lag value for the selected activity grouping.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Max Predecessor Lag (days) | Max Predecessor Lag (days) | 0 |  | 0
The largest predecessor lag value for the selected activity grouping.
Excluded | Number of Predecessors | Number of Lags | Minimum Lag | Maximum Lag | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 0 | 0 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 1 | 0 | 0 | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 1 | 0 | 0 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 1 | 0 | 0 | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE | 1 | 0 | 0 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 1 | 0 | 0 | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 1 | 0 | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 1 | 0 | 0 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 1 | 0 | 0 | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE | 1 | 0 | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 1 | 0 | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 1 | 0 | 0 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 3 | 0 | 0 | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE | 1 | 0 | 0 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 1 | 0 | 0 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 2 | 0 | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 1 | 0 | 0 | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE | 1 | 0 | 0 | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | 1 | 0 | 0 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 1 | 0 | 0 | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | 1 | 0 | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 1 | 0 | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 1 | 0 | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 1 | 0 | 0 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 1 | 0 | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | 1 | 0 | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 1 | 0 | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 2 | 0 | 0 | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | 1 | 0 | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE | 2 | 0 | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE | 2 | 0 | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | 1 | 0 | 0 | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hidden Duration (Planned) | Hidden Duration (Planned) | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/Hidden Duration (Planned) | Critical w/Hidden Duration (Planned) | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Merge Hotspot (Predecessors >2) | Merge Hotspot (Predecessors >2) | 1 | 1% | 1 | 1%
The total number of activities with a high number of predecessor links.
Excluded | Number of Predecessors | Number of Successors | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 3 | 1 | FALSE | 11 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags | N/A |  | N/A
Number of activities with a high number of predecessor links with lags on the predecessor relationships.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Merge Hotspot w/Predecessor Lags & Low Total Float | Merge Hotspot w/Predecessor Lags & Low Total Float | N/A |  | N/A
Number of activities with a high number of predecessor links with lags on the predecessor relationships and low total float.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Merge Hotspot | Critical Merge Hotspot | 0 | 0% | 0 | 0%
The total number of activities with a high number of predecessor links that are also critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Hotspot™ | Logic Hotspot™ | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessors as well as a high number of successors.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessors as well as a high number of successors.

## NASA-Metrics-Status---Quality-8
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Status---Quality -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors | Quality - Logic Hotspots - Successors
Logic Density™ - Successors | All Activities w/Successors | Activities Missing Successors | Total # Successors | Activities w/Leads on Successor | Total# of Successor Leads | Max # of Successor Leads on Activity | Activities w/Lags on Successor | Total# of Successor Lags | Max # of Successor Lags on Activity | Diverge Hotspot (Successors >2) | Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags & Low Total Float | Critical Diverge Hotspot | Logic Hotspot™ | Critical Logic Hotspot™ | Score
1.03 | 96 | 7 | 106 | 0 | N/A | N/A | 0 | N/A | N/A | 1 | N/A | N/A | 0 | 0 | 0 | 94
| 100% | 7% |  | 0% |  |  | 0% |  |  | 1% | ( N/A ) | ( N/A ) | 0% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Density™ - Successors | Logic Density™ - Successors | 1.03 |  | 1.04
The average number of successor logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
All Activities w/Successors | All Activities w/Successors | 96 | 100% | 104 | 100%
The total number of activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 | 1 | 0 | 0 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 | 1 | 0 | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 | 4 | 0 | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 | 1 | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 | 1 | 0 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 | 1 | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 | 2 | 0 | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 | 1 | 0 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities Missing Successors | Activities Missing Successors | 7 | 7% | 6 | 5%
Number of activities that are missing a successor.
Excluded | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | 0 |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | 0 |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | 0 |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | 0 |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE | 0 |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE | 0 |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total # Successors | Total # Successors | 106 |  | 114
The total number of successors on all activities within a grouping.
Excluded | Created | Percent Complete | Number of Successors | Number of Successor Leads | Number of Successor Lags | Notes | Id | Description | Project | Calendar | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 | 1 | 0 | 0 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 | 1 | 0 | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 | 4 | 0 | 0 |  | 147 | Product Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 | 1 | 0 | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 | 1 | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 | 1 | 0 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 | 1 | 0 | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 | 1 | 0 | 0 |  | 149 | Resource Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 | 2 | 0 | 0 |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 37
FALSE |  | 0 | 1 | 0 | 0 |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 | 1 | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 | 1 | 0 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 | 1 | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 | 1 | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 305 | Training Delivery Planning Complete | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 256 | Training Planning COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 | 2 | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 | 1 | 0 | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities w/Leads on Successor | Activities w/Leads on Successor | 0 | 0% | 0 | 0%
Total number of activities carrying a lead (negative lag) on the link to their successor activity. This number should not exceed 5%.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total# of Successor Leads | Total# of Successor Leads | N/A |  | N/A
Total number of successor relationships with leads in the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Max # of Successor Leads on Activity | Max # of Successor Leads on Activity | N/A |  | N/A
The max number of successor leads (negative lag) on an activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities w/Lags on Successor | Activities w/Lags on Successor | 0 | 0% | 0 | 0%
Total number of activities carrying a lag on the link to their successor activity. This number should not exceed 5%.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total# of Successor Lags | Total# of Successor Lags | N/A |  | N/A
Total number of successor relationships with lags in the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Max # of Successor Lags on Activity | Max # of Successor Lags on Activity | N/A |  | N/A
The max number of successor lags on an activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Diverge Hotspot (Successors >2) | Diverge Hotspot (Successors >2) | 1 | 1% | 1 | 1%
Number of activities with a high number of successor links.
Excluded | Number of Predecessors | Number of Successors | Number of Lags | Maximum Lag | Critical | Total Float | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete
FALSE | 1 | 4 | 0 | 0 | FALSE | 3 |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags | N/A |  | N/A
Number of activities with a high number of successor links and critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Diverge Hotspot w/Successor Lags & Low Total Float | Diverge Hotspot w/Successor Lags & Low Total Float | N/A |  | N/A
Number of activities with a high number of successor links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Diverge Hotspot | Critical Diverge Hotspot | 0 | 0% | 1 | 1%
Number of activities with a high number of successor links that are also critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Hotspot™ | Logic Hotspot™ | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessors as well as a high number of successors.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessors as well as a high number of successors.

## NASA-Metrics-Performance
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA Metrics Performance
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Performance
|  | Performance - Completed | Performance - In-Progress | Performance - Planned/Future | Performance - Baseline Compliance | Performance - Float | Performance - Critical Path | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline_Additional Metrics | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Incomplete - Old & New | Baseline Execution Index (BEI) | Hit or Miss Index (HMI) | Current Execution Index (CEI) | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Values Adjusted | DRM | Tracking Dates | Margin Duration | Margin Date | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | BEI, HMI, CEI - Values | BEI, HMI, CEI - Critical Path
Ribbons | Hard_File | 0 | 0 | 0 | 100 | 86 | 0 | 100 | 100 | 100 | 60 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 60 | N/A | 100
Ribbons | Hard_File_updated | 0 | 0 | 0 | 100 | 88 | 0 | 99 | 99 | 99 | 55 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | N/A | 100 | 100 | 100 | 100 | 55 | N/A | 100
|  | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed
|  | Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Score
Ribbons | Hard_File | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ribbons |  | 0% | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | ( N/A ) | 0% | 0% | 0% | 0% | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated | 7 | 3 | 3 | 1 | 21 | 5 | -8 | 6 | 3 | 2 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0
Ribbons |  | 6% | 43% | 43% | 14% |  |  |  | 7% | 50% | 33% | 17% | 0% | 0% | 2% | 4% | 0% | 100% | 0%
|  | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress
|  | Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Score
Ribbons | Hard_File | 0 | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | 0
Ribbons |  | 0% | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | 0%
Ribbons | Hard_File_updated | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Ribbons |  | 1% | 0% | 100% | 0% | 100% |  |  |  | 0% | 0%
|  | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future
|  | Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Score
Ribbons | Hard_File | 110 | 0 | 110 | 0 | 0 | 0 | 85 | 0 | 85 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0
Ribbons |  | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 100% | 0% | 100% | 0% | 0%
Ribbons | Hard_File_updated | 102 | 3 | 84 | 15 | 0 | 0 | 78 | 2 | 66 | 10 | 10 | 24 | 1 | 18 | 5 | 5 | 0
Ribbons |  | 93% | 3% | 82% | 15% | 0% | 0% | 92% | 3% | 85% | 13% | 13% | 96% | 4% | 75% | 21% | 21%
|  | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance
|  | Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Score
Ribbons | Hard_File | 110 | 110 | 110 | 0 | 0 | 0 | 100% | 0 | 100% | N/A | N/A | N/A | 110 | 110 | 110 | 100
Ribbons |  | 100% |  |  |  |  | 0% |  | 0% |  | ( N/A ) | ( N/A ) |  | 100% | 100% | 100%
Ribbons | Hard_File_updated | 110 | 103 | 103 | 8 | 7 | 0 | 100% | 0 | 100% | N/A | 0 | 0.8 | 110 | 103 | 103 | 100
Ribbons |  | 100% |  |  |  |  | 0% |  | 0% |  | ( N/A ) | 0% |  | 100% | 94% | 94%
|  | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float
|  | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Score
Ribbons | Hard_File | 34 | 7 | 27 | 0 | 1:04 | 20 | 2 | 78 | 0 | 86
Ribbons |  | 31% | 28% | 32% | 0% | 0.26 | 18% | 2% | 71% | 0%
Ribbons | Hard_File_updated | 33 | 6 | 27 | 0 | 1:05 | 17 | 6 | 74 | 0 | 88
Ribbons |  | 32% | 25% | 34% | 0% | 0.22 | 17% | 6% | 72% | 0%
|  | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path
|  | Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
Ribbons | Hard_File | 34 | 7 | 27 | 0 | 1:03 | 1:04 | 2.07 | 2.21 | 1 | 0 | 78 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | 0 | 0
Ribbons |  | 31% | 28% | 32% | 0% | 0.29 | 0.26 |  |  | 6% | 0% | 71% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | N/A | N/A | 0% | 0%
Ribbons | Hard_File_updated | 33 | 6 | 27 | 0 | 1:03 | 1:05 | 2.05 | 2.12 | 1 | 0 | 74 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | 1 | 0
Ribbons |  | 32% | 25% | 34% | 0% | 0.3 | 0.22 |  |  | 8% | 0% | 72% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 27% | 73% | 0% | 1%
|  | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH)
|  | Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
Ribbons | Hard_File | 85 | 85 | 0 | 85 | 85 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons | [7 empty] | N/A | ( N/A ) | ( N/A ) | N/A | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated | 85 | 85 | 7 | 85 | 85 | 6 | N/A | N/A | N/A | 1 | 0 | 0 | 99
Ribbons | [7 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0%
|  | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics)
|  | Baselined to Start | Scheduled to Start | Actual Starts | Current Baselined to Start & Started | Past Baselined to Start & Started | Future Baseline to Start & Started | Baselined to Finish | Scheduled to Finish | Actual Finishes | Current Baselined to Finish & Finished | Past Baselined to Finish & Finished | Future Baselined to Finish & Finished | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
Ribbons | Hard_File | 85 | 85 | 0 | N/A | N/A | N/A | 85 | 85 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons | [13 empty] | N/A | ( N/A ) | ( N/A ) | N/A | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated | 85 | 85 | 7 | 7 | 0 | 0 | 85 | 85 | 6 | 6 | 0 | 0 | N/A | N/A | N/A | 1 | 0 | 0 | 99
Ribbons | [13 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0%
|  | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now
|  | Baselined to Start - To Time Now | Scheduled to Start - To Time Now | Started | Started Late | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | BEI - Value Task Starts | Baselined to Finish - To Time Now | Scheduled to Finish - To Time Now | Finished | Finished Late | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Finishes | Started - Future | Not Baselined to Start | Score
Ribbons | Hard_File | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 100
Ribbons |  | 0% | 0% |  |  | ( N/A ) | ( N/A ) | ( N/A ) |  | 0% | 0% |  |  | ( N/A ) | ( N/A ) | ( N/A ) |  |  | 0%
Ribbons | Hard_File_updated | 12 | 12 | 4 | N/A | N/A | N/A | N/A | 0.33 | 11 | 11 | 3 | 1 | 1 | 0 | 0 | 0.27 | 3 | 0 | 99
Ribbons |  | 14% | 14% |  |  | ( N/A ) | ( N/A ) | ( N/A ) |  | 13% | 13% |  |  | 100% | 0% | 0% |  |  | 0%
|  | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH)
|  | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 | 85 | 85 | 85 | 1 | 60
Ribbons
Ribbons | Hard_File_updated | 0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 55
Ribbons
|  | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics)
|  | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Started | Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Not Started (Incomplete) | Baselined to Start - Check | Future Baseline to Start & Started (Early Starts) | Past Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Not Finished - Check | Baselined to Finish - Check | Future Baseline to Finish & Finished - Check | Workoff Burden (Snapshot_Phase) (SEM01) | Workoff Burden - Starts To-Go (Total) (SEM07) | Past Baseline to Start & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) (SEM07) | Workoff Burden - Finishes To-Go (Total) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | 85 | 85 | N/A | N/A | N/A | N/A | N/A | 85 | 85 | N/A | N/A | 85 | 0 | 85 | 85 | 0 | 85 | 0
Ribbons | [15 empty] | N/A
Ribbons | Hard_File_updated | 0 | 7 | 0 | 0 | 78 | 85 | N/A | 0 | 6 | 0 | 0 | 79 | 85 | 0 | 0 | 78 | 8 | 70 | 79 | 8 | 71 | 0
Ribbons | [15 empty] | 0%
|  | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH)
|  | Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
Ribbons | Hard_File | N/A | N/A | N/A | 85 | N/A | N/A | N/A | 85 | 0 | 85 | 0 | 85 | 0
Ribbons
Ribbons | Hard_File_updated | 7 | N/A | 0 | 78 | 6 | 0 | 0 | 79 | 8 | 70 | 8 | 71 | 0
Ribbons
|  | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now
|  | Baselined to Start | Scheduled to Start | Started - Scheduled | Started - Baseline Comparison | BEI - Value Task Starts | HMI - Value Task Starts | CEI - Value Task Starts | Baselined to Finish | Scheduled to Finish | Finished | BEI - Value Task Finishes | HMI - Value Task Finishes | CEI - Value Task Finishes | Status Date | Score
Ribbons | Hard_File | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | N/A | N/A | N/A | 2026-07-07 | 100
Ribbons |  |  | ( N/A ) | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated | 12 | 12 | 4 | 4 | 0.33 | 0.27 | 0.27 | 11 | 11 | 3 | 0.27 | 0.27 | 0.27 | 2026-08-11 | 100
Ribbons |  |  | 100% | 33% | 33%
|  | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics
|  | Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Baseline Comparison | Started Late (from Baseline) | Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished Late | Score
Ribbons | Hard_File | 0 | 0 | N/A | 0 | 0 | N/A | 100
Ribbons |  | 0% | 0% | N/A | 0% | 0%
Ribbons | Hard_File_updated | 7 | 7 | N/A | 6 | 6 | 1 | 100
Ribbons |  | 8% | 8% | N/A | 7% | 7%
|  | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST
|  | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
Ribbons | Hard_File | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | N/A | 0 | 0 | 0
Ribbons |  | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | N/A | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated | 3 | 1 | 2 | 0 | -57 | 63 | 5 | 21 | 5 | -10 | 6 | 2 | 0 | 6 | 0 | 0 | 3 | 2 | 1 | 0
Ribbons |  | 50% | 17% | 33% | 0% | -954% | 1044% | 90% |  |  |  | 5% | 29% | 0% | 7% | 0% | 0% | 27% | 33% | 17%
|  | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST
|  | Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
Ribbons | Hard_File | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | 0 | 0 | 0 | N/A | 0 | 0 | 0
Ribbons |  | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) | ( N/A ) |  |  |  | 0% | ( N/A ) | ( N/A ) | 0% | 0% | 0% | N/A | ( N/A ) | ( N/A )
Ribbons | Hard_File_updated | 3 | 1 | 2 | 0 | -57 | 63 | 5 | 21 | 5 | -10 | 6 | 2 | 0 | 6 | 0 | 0 | 3 | 2 | 1 | 0
Ribbons |  | 50% | 17% | 33% | 0% | -954% | 1044% | 90% |  |  |  | 5% | 29% | 0% | 7% | 0% | 0% | 27% | 33% | 17%
|  | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New
|  | Baselined Tasks | Baselined to Start - TOTAL | Complete Task Starts - Cumulative | Incomplete Task Starts - Cumulative (in work) | Old Incomplete Task Starts in Status Period | Baselined to Finish | Complete Task Finishes - Cumulative (in work) | Incomplete Task Finishes - Cumulative | Old Incomplete Task Finishes in Status Period | Old Completed Task Finishes in Status Period | Score
Ribbons | Hard_File | 85 | 85 | 0 | N/A | N/A | 85 | 0 | N/A | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A |  |  | N/A | N/A
Ribbons | Hard_File_updated | 85 | 85 | 4 | 8 | N/A | 85 | 3 | 8 | N/A | N/A | 100
Ribbons |  |  |  | 33% | 67% |  |  | 27% | 27%
Baseline Execution Index (BEI)
|  | BEI - Tasks | BEI - Milestones
Ribbons | Hard_File | 100 | 100
Ribbons | Hard_File_updated | 100 | 100
Hit or Miss Index (HMI)
|  | HMI - Tasks | HMI - Milestones
Ribbons | Hard_File | 100 | 100
Ribbons | Hard_File_updated | 100 | 100
Current Execution Index (CEI)
|  | CEI - Tasks | CEI - Milestones
Ribbons | Hard_File | 100 | 100
Ribbons | Hard_File_updated | 100 | 100
|  | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks
|  | BEI - Value Tasks | BEI - Total Tasks | BEI - Incomplete Tasks | HMI - Value Tasks | HMI - Total Tasks | HMI - Incomplete Tasks | CEI - Value Tasks | CEI - Total Tasks | CEI - Incomplete Tasks | BEI - Complete Milestones | HMI - Complete Tasks | CEI - Complete Tasks | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | 0 | N/A | N/A | 0 | N/A | N/A | N/A | N/A | 100
Ribbons |  |  |  | N/A |  |  | N/A |  |  | N/A | N/A | N/A | N/A
Ribbons | Hard_File_updated | 0.27 | 11 | 8 | 0.27 | 11 | 8 | 0.27 | 11 | 8 | 1 | 3 | 3 | 100
Ribbons |  |  |  | 73% |  |  | 73% |  |  | 73% | 33% | 27% | 27%
|  | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones
|  | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Incomplete Milestones | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A |  |  | N/A | N/A |  |  | N/A | N/A
Ribbons | Hard_File_updated | 0.33 | 3 | 1 | 2 | 0.33 | 3 | 1 | 2 | 0.33 | 3 | 1 | 2 | 100
Ribbons |  |  |  | 33% | 67% |  |  | 33% | 67% |  |  | 33% | 67%
|  | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted
|  | BEI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | BEI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | Status Date | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | N/A
Ribbons
Ribbons | Hard_File_updated | 0.55 | 0.55 | 0.55 | 0.33 | 0.33 | 0.33 | 2026-08-11 | N/A
Ribbons
|  | DRM | DRM | DRM
|  | Total Activities - DRM | Total Activities - DRM Graph | Score
Ribbons | Hard_File | 0 | 0 | 100
Ribbons
Ribbons | Hard_File_updated | 6 | 6 | 100
Ribbons
|  | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates
|  | Status Date | Milestone #1 - 5158 | Float Milestone #1 - 5158 | Milestone #2 - 4786 | Float to Milestone #2 - 4786 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 105 | New Activities Since Previous Status Date | Score
Ribbons | Hard_File | 2026-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 100
Ribbons
Ribbons | Hard_File_updated | 2026-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 100
Ribbons
|  | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Hard_File | 2026-07-07 | N/A | 1 | 0 | 1 | N/A | N/A | N/A | 100
Ribbons
Ribbons | Hard_File_updated | 2026-08-11 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | 100
Ribbons
|  | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
|  | Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
Ribbons | Hard_File | 2026-07-07 | N/A | 2026-08-20 | 2026-08-26 | 2026-08-18 | N/A | N/A | N/A | 100
Ribbons
Ribbons | Hard_File_updated | 2026-08-11 | N/A | 2026-08-20 | 2026-08-26 | N/A | N/A | N/A | N/A | 100
Ribbons
|  | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon)
|  | BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 | 85 | 85 | 85 | 1 | 60
Ribbons
Ribbons | Hard_File_updated | 0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 55
Ribbons
|  | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values
|  | BEI - Value Tasks | HMI - Value Tasks | CEI - Value Tasks | BEI - Value Milestones | HMI - Value Milestones | CEI - Value Milestones | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ribbons
Ribbons | Hard_File_updated | 0.27 | 0.27 | 0.27 | 0.33 | 0.33 | 0.33 | N/A
Ribbons
|  | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path
|  | BEI - Value Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - CP Tasks - Planned Cumulative | BEI - CP Value Tasks | HMI - Value Tasks | HMI - Complete Tasks | HMI - Incomplete Tasks | HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Value Tasks | CEI - Value Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Value Tasks | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  | N/A | N/A |  |  |  | N/A | N/A |  |  |  | N/A | N/A
Ribbons | Hard_File_updated | 0.27 | 3 | 8 | 0 | N/A | 0.27 | 3 | 8 | 0 | N/A | 0.27 | 3 | 8 | 0 | N/A | 100
Ribbons |  |  | 27% | 73% |  |  |  | 27% | 73% |  |  |  | 27% | 73%

## NASA-Metrics-Performance-Perfo
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed | Performance - Completed
Actually Finished - Tasks & Milestones | Completed Ahead - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | Completed Delayed - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | Actually Finished - Tasks | Completed Ahead - Tasks | Completed On-Schedule - Tasks | Completed Delayed - Tasks | Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Late - Tasks | Extended Durations - Tasks | Actually Finished - Milestones | Completed Ahead - Milestones | Completed On-Schedule - Milestones | Completed Delayed - Milestones | Score
7 | 3 | 3 | 1 | 21 | 5 | -8 | 6 | 3 | 2 | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0
6% | 43% | 43% | 14% |  |  |  | 7% | 50% | 33% | 17% | 0% | 0% | 2% | 4% | 0% | 100% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actually Finished - Tasks & Milestones | Actually Finished - Tasks & Milestones | 7 | 6% | 0 | 0%
Number of activities and miletones that have finished.
Excluded | DRM | Actual Finish | % | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-07-08 | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 2026-07-08 | 1 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE | 1 | 2026-07-09 | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 | 2026-07-28 | 1 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-29 | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-31 | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 | 2026-08-06 | 1 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Ahead - Tasks & Milestones | Completed Ahead - Tasks & Milestones | 3 | 43% | 0
Number of activities and milestones that finished before their planned finish date
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-07-29 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-31 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 | 2026-08-06 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed On-Schedule - Tasks & Milestones | Completed On-Schedule - Tasks & Milestones | 3 | 43% | 0
Number of activities and milestones that completed on time.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-07-08 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 2026-07-08 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE | 1 | 2026-07-09 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed - Tasks & Milestones | Completed Delayed - Tasks & Milestones | 1 | 14% | 0
Number of activities and milestones that finished after their planned finish date.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.35 | 2026-07-28 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Finished Early - Tasks & Milestones | Avg Days Finished Early - Tasks & Milestones | 21 |  | 0
Average number of days that all activities within a grouping finished early (before the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Finished Late - Tasks & Milestones | Avg Days Finished Late - Tasks & Milestones | 5 |  | 0
Average number of days that all activities within a grouping finished late (after the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Finish Variance - Tasks & Milestones | Avg Finish Variance - Tasks & Milestones | -8 |  | 0
Average variance (in days) between activities that finished early and those that finished late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actually Finished - Tasks | Actually Finished - Tasks | 6 | 7% | 0 | 0%
Number of normal activities that have finished.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-07-08 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-09 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 | 2026-07-28 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-29 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-31 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 | 2026-08-06 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Ahead - Tasks | Completed Ahead - Tasks | 3 | 50% | 0
Number of activities that finished before their planned finish date
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-07-29 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-31 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 | 2026-08-06 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed On-Schedule - Tasks | Completed On-Schedule - Tasks | 2 | 33% | 0
Number of activities that completed on time.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 | 2026-07-08 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 | 2026-07-09 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed - Tasks | Completed Delayed - Tasks | 1 | 17% | 0
Number of activities that finished after their planned finish date.
Excluded | DRM | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.35 | 2026-07-28 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Accelerated Durations Early/On-Schedule - Tasks | Accelerated Durations Early/On-Schedule - Tasks | 0 | 0% | 0 | 0%
Number of activities that started after their planned start date but finished before or on their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Accelerated Durations Late - Tasks | Accelerated Durations Late - Tasks | 0 | 0% | 0 | 0%
Number of activities that started after their planned start date and reduced their durations, but still finished late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Extended Durations - Tasks | Extended Durations - Tasks | 2 | 2% | 0 | 0%
Number of activities with actual durations greater than their baseline durations.
Excluded | DRM | Baseline Duration | Actual Duration | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Actual Start | Actual Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.35 | 20 | 27 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | 2026-07-09 | 2026-07-28 | Normal | Complete | 100 | 0
FALSE | 1.6 | 5 | 8 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | 2026-07-31 | 2026-08-06 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actually Finished - Milestones | Actually Finished - Milestones | 1 | 4% | 0 | 0%
Number of milestones that have finished.
Excluded | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-07-08 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Ahead - Milestones | Completed Ahead - Milestones | 0 | 0% | 0
Number of milestones that finished before their planned finish date
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed On-Schedule - Milestones | Completed On-Schedule - Milestones | 1 | 100% | 0
Number of milestones that completed on time.
Excluded | Actual Finish | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-07-08 |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed - Milestones | Completed Delayed - Milestones | 0 | 0% | 0
Number of milestones that finished after their planned finish date.

## NASA-Metrics-Performance-Perfo2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress | Performance - In-Progress
Actually Started - Tasks | In-Progress Started Ahead - Tasks | In-Progress Started On-Schedule - Tasks | In-Progress Started Delayed - Tasks | In-Progress Delayed Finish - Tasks | Avg Days Started Early | Avg Days Started Late | Avg Start Variance | Expected Finish | In-Progress Schedule Overrun - Tasks & Milestones | Score
1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1% | 0% | 100% | 0% | 100% |  |  |  | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actually Started - Tasks | Actually Started - Tasks | 1 | 1% | 0 | 0%
Total number of activities that have started.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-08-05 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
In-Progress Started Ahead - Tasks | In-Progress Started Ahead - Tasks | 0 | 0% | 0
Number of activities that started before their planned start date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
In-Progress Started On-Schedule - Tasks | In-Progress Started On-Schedule - Tasks | 1 | 100% | 0
Number of activities that are currently underway and started on time.
Excluded | Actual Start | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 2026-08-05 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
In-Progress Started Delayed - Tasks | In-Progress Started Delayed - Tasks | 0 | 0% | 0
Number of activities that started after their planned start date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
In-Progress Delayed Finish - Tasks | In-Progress Delayed Finish - Tasks | 1 | 100% | 0
Number of in-progress activities that have slipped from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Started Early | Avg Days Started Early | 0 |  | N/A
Average number of days that all activities within a grouping started early (before the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Started Late | Avg Days Started Late | 0 |  | N/A
Average number of days that all activities within a grouping started late (after the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Start Variance | Avg Start Variance | 0 |  | 0
A calculation of the average variance between total days started early and total days started late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Expected Finish | Expected Finish | 0 | 0% | 0 | 0%
In-progress activities that are 100% complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
In-Progress Schedule Overrun - Tasks & Milestones | In-Progress Schedule Overrun - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of activities where the remaining duration is greater than the original duration

## NASA-Metrics-Performance-Perfo3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future | Performance - Planned/Future
Scheduled to Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | Riding Data Date - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | Scheduled to Start - Tasks | Planned Ahead Start - Tasks | Planned On Schedule Start - Tasks | Planned Delayed Start - Tasks | Planned Delayed Finish - Tasks | Scheduled to Start - Milestones | Planned Ahead Start - Milestones | Planned On Schedule Start - Milestones | Planned Delayed Start - Milestones | Planned Delayed Finish - Milestones | Score
102 | 3 | 84 | 15 | 0 | 0 | 78 | 2 | 66 | 10 | 10 | 24 | 1 | 18 | 5 | 5 | 0
93% | 3% | 82% | 15% | 0% | 0% | 92% | 3% | 85% | 13% | 13% | 96% | 4% | 75% | 21% | 21%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start - Tasks & Milestones | Scheduled to Start - Tasks & Milestones | 102 | 93% | 110 | 100%
Number of activities and milestones that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Ahead Start - Tasks & Milestones | Planned Ahead Start - Tasks & Milestones | 3 | 3% | 0 | 0%
Number of activities and milestines that are currently planned to start before their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned On Schedule Start - Tasks & Milestones | Planned On Schedule Start - Tasks & Milestones | 84 | 82% | 110 | 100%
Number of activities and milestones that are planned to start on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Delayed Start - Tasks & Milestones | Planned Delayed Start - Tasks & Milestones | 15 | 15% | 0 | 0%
Number of activities and milestones that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Riding Data Date - Tasks & Milestones | Riding Data Date - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Schedule Overrun - Tasks & Milestones | Planned Schedule Overrun - Tasks & Milestones | 0 | 0% | 0 | 0%
Number of activities where the remaining duration is greater than the original duration
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start - Tasks | Scheduled to Start - Tasks | 78 | 92% | 85 | 100%
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Ahead Start - Tasks | Planned Ahead Start - Tasks | 2 | 3% | 0 | 0%
Number of activities that are currently planned to start before their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned On Schedule Start - Tasks | Planned On Schedule Start - Tasks | 66 | 85% | 85 | 100%
Number of activities that are planned to start on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Delayed Start - Tasks | Planned Delayed Start - Tasks | 10 | 13% | 0 | 0%
Number of activities that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Delayed Finish - Tasks | Planned Delayed Finish - Tasks | 10 | 13% | 0 | 0%
Number of planned/future activities that are schedule to slip from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start - Milestones | Scheduled to Start - Milestones | 24 | 96% | 25 | 100%
Number of milestones that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Ahead Start - Milestones | Planned Ahead Start - Milestones | 1 | 4% | 0 | 0%
Number of milestones that are currently planned to start before their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned On Schedule Start - Milestones | Planned On Schedule Start - Milestones | 18 | 75% | 25 | 100%
Number of milestones that are planned to start on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Delayed Start - Milestones | Planned Delayed Start - Milestones | 5 | 21% | 0 | 0%
Number of milestones that are currently planned to start after their baseline start date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Planned Delayed Finish - Milestones | Planned Delayed Finish - Milestones | 5 | 21% | 0 | 0%
Number of planned/future activities that are schedule to slip from their baseline dates
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54

## NASA-Metrics-Performance-Perfo4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance | Performance - Baseline Compliance
Schedule Baseline Activities | Scheduled/Baselined to Start | Scheduled/Baselined to Finish | Start/ed | Finish/ed | Start Variance (Phase) | Start Compliance™ (Phase) | Finish Variance (Phase) | Finish Compliance™ (Phase) | Started Delayed (>30 days) | Completed Delayed (>30 days) | SPI(t) | Scheduled Activities | Scheduled to Start | Scheduled to Finish | Score
110 | 103 | 103 | 8 | 7 | 0 | 100% | 0 | 100% | N/A | 0 | 0.8 | 110 | 103 | 103 | 100
100% |  |  |  |  | 0% |  | 0% |  | ( N/A ) | 0% |  | 100% | 94% | 94%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Schedule Baseline Activities | Schedule Baseline Activities | 110 | 100% | 110 | 100%
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled/Baselined to Start | Scheduled/Baselined to Start | 103 |  | 110
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled/Baselined to Finish | Scheduled/Baselined to Finish | 103 |  | 110
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Start/ed | Start/ed | 8 |  | 0
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finish/ed | Finish/ed | 7 |  | 0
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Start Variance (Phase) | Start Variance (Phase) | 0 | 0% | 0 | 0%
Number of activities starting or that have started outside of the expected baselined period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Start Compliance™ (Phase) | Start Compliance™ (Phase) | 100% |  | 100%
A calculation of activity start date compliance with baselined start dates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finish Variance (Phase) | Finish Variance (Phase) | 0 | 0% | 0 | 0%
Number of activities finishing or that have finished outside the expected baselined period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finish Compliance™ (Phase) | Finish Compliance™ (Phase) | 100% |  | 100%
A calculation of activity finish date compliance with baselined finish dates.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (>30 days) | Started Delayed (>30 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (>30 days) | Completed Delayed (>30 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
SPI(t) | SPI(t) | 0.8 |  | N/A
Ratio showing the performance of the activity relative to the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled Activities | Scheduled Activities | 110 | 100% | 110 | 100%
Number of tasks in the schedule that have baseline dates assigned.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start | Scheduled to Start | 103 | 94% | 110 | 100%
Number of activities that are scheduled to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Finish | Scheduled to Finish | 103 | 94% | 110 | 100%
Number of activities that are scheduled to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0

## NASA-Metrics-Performance-Perfo5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float | Performance - Float
Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Critical Milestone-to-Task Ratio (To-Go) | High Float 10% | High Float 44d | Zero Days Float | Negative Float | Score
33 | 6 | 27 | 0 | 1:05 | 17 | 6 | 74 | 0 | 88
32% | 25% | 34% | 0% | 0.22 | 17% | 6% | 72% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path - Critical Activities and Milestones | Longest Path - Critical Activities and Milestones | 33 | 32% | 34 | 31%
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 6 | 25% | 7 | 28%
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Tasks (To-Go) | Critical Tasks (To-Go) | 27 | 34% | 27 | 32%
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Tasks (In Progress) | Critical Tasks (In Progress) | 0 | 0% | 0 | 0%
Number of critical activities to-go.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | 1:05 | 0.22 | 1:04 | 0.26
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Float 10% | High Float 10% | 17 | 17% | 20 | 18%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Float 44d | High Float 44d | 6 | 6% | 2 | 2%
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Zero Days Float | Zero Days Float | 74 | 72% | 78 | 71%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.

## NASA-Metrics-Performance-Perfo6
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path | Performance - Critical Path
Longest Path - Critical Activities and Milestones | Critical Milestones (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | Logic Density™ | CP Logic Density™ | Critical w/Missing Logic | Critical w/Hard Constraints | Zero Days Float | Negative Float | Critical LOE | Critical w/High Baseline Duration (44d) | Critical w/High Planned Duration (44d) | Critical with Predecessor Lag | Critical with Successor Lag | Critical with Hard Constraints | Negative Float with Predecessor Lag | Negative Float with Successor Lag | Critical CEI - Value Tasks | Critical CEI - Total Tasks | Critical CEI - Complete Tasks | Critical CEI - Incomplete Tasks | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
33 | 6 | 27 | 0 | 1:03 | 1:05 | 2.05 | 2.12 | 1 | 0 | 74 | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | 0 | 1 | 0
32% | 25% | 34% | 0% | 0.3 | 0.22 |  |  | 8% | 0% | 72% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 27% | 73% | 0% | 1%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path - Critical Activities and Milestones | Longest Path - Critical Activities and Milestones | 33 | 32% | 34 | 31%
Activities that together form the longest path through to project completion. (Number of critical activities.)
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 6 | 25% | 7 | 28%
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Tasks (To-Go) | Critical Tasks (To-Go) | 27 | 34% | 27 | 32%
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Tasks (In Progress) | Critical Tasks (In Progress) | 0 | 0% | 0 | 0%
Number of critical activities to-go.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone-to-Task Ratio (To-Go) | Milestone-to-Task Ratio (To-Go) | 1:03 | 0.3 | 1:03 | 0.29
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | 1:05 | 0.22 | 1:04 | 0.26
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Logic Density™ | Logic Density™ | 2.05 |  | 2.07
The average number of logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CP Logic Density™ | CP Logic Density™ | 2.12 |  | 2.21
The average number of logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/Missing Logic | Critical w/Missing Logic | 1 | 8% | 1 | 6%
Total number of critical activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Number of Predecessors | Number of Successors | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 1 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/Hard Constraints | Critical w/Hard Constraints | 0 | 0% | 0 | 0%
Number of critical activities with hard or two-way constraints.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Zero Days Float | Zero Days Float | 74 | 72% | 78 | 71%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical LOE | Critical LOE | N/A | 0% | N/A | 0%
Critical Level Of Effort or Hammock Tasks
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/High Baseline Duration (44d) | Critical w/High Baseline Duration (44d) | 0 | 0% | 0 | 0%
Total number of critical activities that have a duration longer than 2 months. This number should not exceed 5%.
Excluded | Critical | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  |  | 91 | Initial Assessment | Hard_File_updated | 18 | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 94 | 3
FALSE | FALSE |  |  | 92 | Perform Product Review | Hard_File_updated | 18 | 29 | 2 | 2026-07-08 | 2026-08-17 | 2026-07-08 | 2026-07-31 | Summary | InProgress | 94 | 3
FALSE | FALSE |  |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE | FALSE |  |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 95 | Identify anticipated product problem points | Hard_File_updated | 20 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 373 | Build Customer Service Program | Hard_File_updated | 42 | 57 | 39 | 2026-07-28 | 2026-10-15 | 2026-08-18 | 2026-10-15 | Summary | InProgress | 32 | 14
FALSE | FALSE |  |  | 392 | Customer Service Program Development | Hard_File_updated | 37 | 49 | 13 | 2026-07-28 | 2026-10-06 | 2026-08-18 | 2026-10-08 | Summary | InProgress | 74 | 22
FALSE | FALSE |  |  | 400 | Build customer service programs | Hard_File_updated | 1 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 5 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | FALSE |  |  | 322 | Service Planning | Hard_File_updated | 11 | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-17 | Summary | InProgress | 43 | 11
FALSE | FALSE |  |  | 125 | Design Support Services | Hard_File_updated | 10 | 12 | 7 | 2026-08-05 | 2026-08-20 | 2026-07-31 | 2026-08-14 | Summary | InProgress | 45 | 11
FALSE | FALSE |  |  | 4 | Develop Levels of Customer Service (Free and Paid) | Hard_File_updated | 9 | 12 | 6 | 2026-08-05 | 2026-08-20 | 2026-08-04 | 2026-08-14 | Summary | InProgress | 53 | 11
FALSE | FALSE |  |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | FALSE |  |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | FALSE |  |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | FALSE |  |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 383 | Business Performance Planning | Hard_File_updated | 2 | 5 | 5 | 2026-08-17 | 2026-08-21 | 2026-08-17 | 2026-08-18 | Summary | Planned | 0 | 53
FALSE | FALSE |  |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | FALSE |  |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE | FALSE |  |  | 315 | Service Delivery Infrastructure Planning | Hard_File_updated | 42 | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 129 | Training & Readiness | Hard_File_updated | 42 | 31 | 31 | 2026-08-17 | 2026-09-29 | 2026-07-31 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 212 | Training Needs Assessment | Hard_File_updated | 14 | 4 | 4 | 2026-08-17 | 2026-08-21 | 2026-07-31 | 2026-08-21 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | FALSE |  |  | 45 | Design Customer Service Contact Scenarios | Hard_File_updated | 1 | 2 | 2 | 2026-08-17 | 2026-08-19 | 2026-07-31 | 2026-08-04 | Summary | Planned | 0 | 11
FALSE | FALSE |  |  | 180 | Online support | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | FALSE |  |  | 100 | Resources Requirements | Hard_File_updated | 2 | 2 | 2 | 2026-08-18 | 2026-08-20 | 2026-08-18 | 2026-08-20 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | FALSE |  |  | 318 | Technology Infrastructure | Hard_File_updated | 3 | 3 | 3 | 2026-08-18 | 2026-08-21 | 2026-08-18 | 2026-08-21 | Summary | Planned | 0 | 37
FALSE | FALSE |  |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | FALSE |  |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE | FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | FALSE |  |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | FALSE |  |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | FALSE |  |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
FALSE | FALSE |  |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | FALSE |  |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | FALSE |  |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | FALSE |  |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE | FALSE |  |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | FALSE |  |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 235 | Training Planning | Hard_File_updated | 27 | 27 | 27 | 2026-08-21 | 2026-09-29 | 2026-08-21 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 299 | Content Development Planning | Hard_File_updated | 4 | 4 | 4 | 2026-08-21 | 2026-08-26 | 2026-08-21 | 2026-08-26 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | FALSE |  |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | TRUE |  |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 372 | Build Technology Infrastructure | Hard_File_updated | 3 | 3 | 3 | 2026-08-24 | 2026-08-27 | 2026-08-24 | 2026-08-27 | Summary | Planned | 0 | 38
FALSE | FALSE |  |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | FALSE |  |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | FALSE |  |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | FALSE |  |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | FALSE |  |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 237 | Training Delivery Planning | Hard_File_updated | 21 | 21 | 21 | 2026-08-27 | 2026-09-24 | 2026-08-27 | 2026-09-24 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 293 | Assess Trainer Needs & Options | Hard_File_updated | 12 | 12 | 12 | 2026-08-27 | 2026-09-11 | 2026-08-27 | 2026-09-11 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | FALSE |  |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 391 | Program Deployment | Hard_File_updated | 40 | 40 | 40 | 2026-08-28 | 2026-10-23 | 2026-08-28 | 2026-10-23 | Summary | Planned | 0 | 8
FALSE | FALSE |  |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | FALSE |  |  | 285 | Review Outsourcing Options - Training Delivery | Hard_File_updated | 10 | 10 | 10 | 2026-08-31 | 2026-09-11 | 2026-08-31 | 2026-09-11 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 283 | Training Delivery Logistics | Hard_File_updated | 8 | 8 | 8 | 2026-09-14 | 2026-09-23 | 2026-09-14 | 2026-09-23 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 306 | Finalize Training Planning | Hard_File_updated | 3 | 3 | 3 | 2026-09-24 | 2026-09-29 | 2026-09-24 | 2026-09-29 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 375 | Training/Readiness Development | Hard_File_updated | 12 | 12 | 12 | 2026-09-29 | 2026-10-15 | 2026-09-29 | 2026-10-15 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 219 | Training Content Development | Hard_File_updated | 4 | 4 | 4 | 2026-09-29 | 2026-10-05 | 2026-09-29 | 2026-10-05 | Summary | Planned | 0 | 0
FALSE | FALSE |  |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 221 | Build Training Content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-05 | 2026-10-02 | 2026-10-05 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 175 | Develop Training Delivery Engine | Hard_File_updated | 8 | 8 | 8 | 2026-10-05 | 2026-10-15 | 2026-10-05 | 2026-10-15 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | FALSE |  |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | FALSE |  |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE | TRUE |  |  | 393 | Resource Readiness | Hard_File_updated | 5 | 5 | 5 | 2026-10-16 | 2026-10-22 | 2026-10-16 | 2026-10-22 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE | TRUE |  |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 37 | Post Launch | Hard_File_updated | 8 | 8 | 8 | 2026-10-23 | 2026-11-05 | 2026-10-23 | 2026-11-05 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 142 | Engage in Post Launch Preparation Activities | Hard_File_updated | 4 | 4 | 4 | 2026-10-23 | 2026-10-30 | 2026-10-23 | 2026-10-30 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  |  | 143 | Monitoring | Hard_File_updated | 4 | 4 | 4 | 2026-10-30 | 2026-11-05 | 2026-10-30 | 2026-11-05 | Summary | Planned | 0 | 0
FALSE | TRUE |  |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/High Planned Duration (44d) | Critical w/High Planned Duration (44d) | 0 | 0% | 0 | 0%
Number of critical activities with a duration longer than 44 days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical with Predecessor Lag | Critical with Predecessor Lag | 0 | 0% | 0 | 0%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical with Successor Lag | Critical with Successor Lag | 0 | 0% | 0 | 0%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical with Hard Constraints | Critical with Hard Constraints | 0 | 0% | 0 | 0%
Number of activities with hard or two-way constraints.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float with Predecessor Lag | Negative Float with Predecessor Lag | 0 | 0% | 0 | 0%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float with Successor Lag | Negative Float with Successor Lag | 0 | 0% | 0 | 0%
Number of critical activities and milestones with lags.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical CEI - Value Tasks | Critical CEI - Value Tasks | N/A |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical CEI - Total Tasks | Critical CEI - Total Tasks | 0 |  | 0
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical CEI - Complete Tasks | Critical CEI - Complete Tasks | N/A | 27% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical CEI - Incomplete Tasks | Critical CEI - Incomplete Tasks | N/A | 73% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Newly Critical Activities | Newly Critical Activities | 0 | 0% | 0 | 0%
How many remaining activities were added to the critical path this period
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities No Longer Critical | Activities No Longer Critical | 1 | 1% | 0 | 0%
How many remaining activities are no longer on the critical path this period.
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
147 | Product Review COMPLETE | FALSE | TRUE | 0 | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 3 | Hard_File_updated

## NASA-Metrics-Performance-Perfo7
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH) | Performance - Baseline_Bow Wave (GRAPH)
Baselined to Start | Scheduled to Start | Actual Starts | Baselined to Finish | Scheduled to Finish | Actual Finishes | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
85 | 85 | 7 | 85 | 85 | 6 | N/A | N/A | N/A | 1 | 0 | 0 | 99
[6 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start | Baselined to Start | 85 |  | 85
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start | Scheduled to Start | 85 |  | 85
Number of activities that are planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actual Starts | Actual Starts | 7 |  | 0
Number of activities that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish | Baselined to Finish | 85 |  | 85
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Finish | Scheduled to Finish | 85 |  | 85
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actual Finishes | Actual Finishes | 6 |  | 0
Number of activities that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 1 | 100% | N/A
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.

## NASA-Metrics-Performance-Perfo8
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics) | Performance - Baseline_Bow Wave (Project_Phase, All Metrics)
Baselined to Start | Scheduled to Start | Actual Starts | Current Baselined to Start & Started | Past Baselined to Start & Started | Future Baseline to Start & Started | Baselined to Finish | Scheduled to Finish | Actual Finishes | Current Baselined to Finish & Finished | Past Baselined to Finish & Finished | Future Baselined to Finish & Finished | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | Score
85 | 85 | 7 | 7 | 0 | 0 | 85 | 85 | 6 | 6 | 0 | 0 | N/A | N/A | N/A | 1 | 0 | 0 | 99
[12 empty] | N/A | ( N/A ) | ( N/A ) | 100% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start | Baselined to Start | 85 |  | 85
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start | Scheduled to Start | 85 |  | 85
Number of activities that are planned to start.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actual Starts | Actual Starts | 7 |  | 0
Number of activities that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baselined to Start & Started | Current Baselined to Start & Started | 7 |  | N/A
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baselined to Start & Started | Past Baselined to Start & Started | 0 |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Start & Started | Future Baseline to Start & Started | 0 |  | N/A
Number of activities that have started in the current period no matter their baseline start date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish | Baselined to Finish | 85 |  | 85
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Finish | Scheduled to Finish | 85 |  | 85
Number of activities within that are planned to finish.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actual Finishes | Actual Finishes | 6 |  | 0
Number of activities that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baselined to Finish & Finished | Current Baselined to Finish & Finished | 6 |  | N/A
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baselined to Finish & Finished | Past Baselined to Finish & Finished | 0 |  | N/A
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baselined to Finish & Finished | Future Baselined to Finish & Finished | 0 |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 1 | 100% | N/A
Number of activities that finished after their planned finish date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.

## NASA-Metrics-Performance-Perfo9
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now | Performance - Baseline_Bow Wave_To Time Now
Baselined to Start - To Time Now | Scheduled to Start - To Time Now | Started | Started Late | Started Delayed (<=30 days) | Started Delayed (Between 31 to 60 days) | Started Delayed (>60 days) | BEI - Value Task Starts | Baselined to Finish - To Time Now | Scheduled to Finish - To Time Now | Finished | Finished Late | Completed Delayed (<=30 days) | Completed Delayed (Between 31 to 60 days) | Completed Delayed (>60 days) | BEI - Value Task Finishes | Started - Future | Not Baselined to Start | Score
12 | 12 | 4 | N/A | N/A | N/A | N/A | 0.33 | 11 | 11 | 3 | 1 | 1 | 0 | 0 | 0.27 | 3 | 0 | 99
14% | 14% |  |  | ( N/A ) | ( N/A ) | ( N/A ) |  | 13% | 13% |  |  | 100% | 0% | 0% |  |  | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start - To Time Now | Baselined to Start - To Time Now | 12 | 14% | 0 | 0%
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start - To Time Now | Scheduled to Start - To Time Now | 12 | 14% | 0 | 0%
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started | Started | 4 |  | 0
Number of activities starting or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Late | Started Late | N/A |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (<=30 days) | Started Delayed (<=30 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (Between 31 to 60 days) | Started Delayed (Between 31 to 60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Delayed (>60 days) | Started Delayed (>60 days) | N/A |  | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Starts | BEI - Value Task Starts | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish - To Time Now | Baselined to Finish - To Time Now | 11 | 13% | 0 | 0%
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Finish - To Time Now | Scheduled to Finish - To Time Now | 11 | 13% | 0 | 0%
Number of activities within that are planned to finish.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finished | Finished | 3 |  | 0
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finished Late | Finished Late | 1 |  | N/A
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (<=30 days) | Completed Delayed (<=30 days) | 1 | 100% | N/A
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (Between 31 to 60 days) | Completed Delayed (Between 31 to 60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed (>60 days) | Completed Delayed (>60 days) | 0 | 0% | N/A
Number of activities that finished after their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Finishes | BEI - Value Task Finishes | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started - Future | Started - Future | 3 |  | 0
Number of activities starting or that were baselined to start in the future, but have alread started
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Not Baselined to Start | Not Baselined to Start | 0 | 0% | 0 | 0%
Number of activities that are scheduled/baselined to start or that have started in the current period.

## NASA-Metrics-Performance-Perf10
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (Snapshot_Ribbon, GRAPH)
BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 55
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Starts - Cumulative | BEI - Value Task Starts - Cumulative | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Finishes - Cumulative | BEI - Value Task Finishes - Cumulative | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Starts - by Status Dates | HMI - Value Task Starts - by Status Dates | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for task starts. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Finishes - by Status Dates | HMI - Value Task Finishes - by Status Dates | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for task finishes. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Starts - by Status Dates | CEI - Value Task Starts - by Status Dates | 0.33 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Finishes - by Status Dates | CEI - Value Task Finishes - by Status Dates | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FEI - Value Task Starts - Cumulative | FEI - Value Task Starts - Cumulative | 1.11 |  | 1
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FEI - Value Task Finish - Cumulative | FEI - Value Task Finish - Cumulative | 1.11 |  | 1
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Finishes - Cumulative | To Go - BEI - Value Task Finishes - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - Planned Task Starts - Count | To Go - Planned Task Starts - Count | 78 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Task Finishes - Count | To Go - BEI - Task Finishes - Count | 79 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - Baselined Task Starts - Count | To Go - Baselined Task Starts - Count | 78 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned

## NASA-Metrics-Performance-Perf11
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics) | Performance - Baseline_Bow Wave_Workoff Burden (All Metrics)
Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Started | Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Not Started (Incomplete) | Baselined to Start - Check | Future Baseline to Start & Started (Early Starts) | Past Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Not Finished - Check | Baselined to Finish - Check | Future Baseline to Finish & Finished - Check | Workoff Burden (Snapshot_Phase) (SEM01) | Workoff Burden - Starts To-Go (Total) (SEM07) | Past Baseline to Start & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) (SEM07) | Workoff Burden - Finishes To-Go (Total) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
0 | 7 | 0 | 0 | 78 | 85 | N/A | 0 | 6 | 0 | 0 | 79 | 85 | 0 | 0 | 78 | 8 | 70 | 79 | 8 | 71 | 0
0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Start & Started (Workoff Burden) | Past Baseline to Start & Started (Workoff Burden) | 0 |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Started | Current Baseline to Start & Started | 7 |  | N/A
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Started Past (Early Starts) | Current Baseline to Start & Started Past (Early Starts) | 0 |  | N/A
Number of activities that have started in the current period no matter their baseline start date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Started Future (Late Starts) | Current Baseline to Start & Started Future (Late Starts) | 0 |  | N/A
Number of activities that have started in the current period no matter their baseline start date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Not Started (Incomplete) | Current Baseline to Start & Not Started (Incomplete) | 78 |  | 85
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start - Check | Baselined to Start - Check | 85 |  | 85
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Start & Started (Early Starts) | Future Baseline to Start & Started (Early Starts) | N/A |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Finish & Finished - Check | Past Baseline to Finish & Finished - Check | 0 |  | N/A
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Finished - Check | Current Baseline to Finish & Finished - Check | 6 |  | N/A
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Finished Past - Check | Current Baseline to Finish & Finished Past - Check | 0 |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Finished Future - Check | Current Baseline to Finish & Finished Future - Check | 0 |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Not Finished - Check | Current Baseline to Finish & Not Finished - Check | 79 |  | 85
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish - Check | Baselined to Finish - Check | 85 |  | 85
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Finish & Finished - Check | Future Baseline to Finish & Finished - Check | 0 |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Workoff Burden (Snapshot_Phase) | Workoff Burden (Snapshot_Phase) | 0 | 0% | N/A
Workoff 30 Day Window
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Workoff Burden - Starts To-Go (Total) | Workoff Burden - Starts To-Go (Total) | 78 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Start & Not Finished (Workoff Burden) | Past Baseline to Start & Not Finished (Workoff Burden) | 8 |  | 0
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Start & AlreadyDelayed (Workoff Burden) | Future Baseline to Start & AlreadyDelayed (Workoff Burden) | 70 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Workoff Burden - Finishes To-Go (Total) | Workoff Burden - Finishes To-Go (Total) | 79 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | 2026-08-05 | 2026-08-05 | 2026-08-05 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Finish & Not Finished (Workoff Burden) | Past Baseline to Finish & Not Finished (Workoff Burden) | 8 |  | 0
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Finish & Already Delayed (Workoff Burden) | Future Baseline to Finish & Already Delayed (Workoff Burden) | 71 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | 2026-08-05 | 2026-08-05 | 2026-08-05 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned

## NASA-Metrics-Performance-Perf12
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH) | Performance - Baseline_Bow Wave_Workoff Burden (GRAPH)
Current Baseline to Start & Started (BL Plan) | Future Baseline to Start & Started (Early Starts) | Past Baseline to Start & Started (Workoff Burden) | Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Finish & Finished (BL Plan) | Future Baseline to Finish & Finished (Early Finishes) | Past Baseline to Finish & Finished (Workoff Burden) | Current Baseline to Finish & Not Finished (Incompletes) | Past Baseline to Start & Not Started (Workoff Burden) (SEM07) | Future Baseline to Start & Already Delayed (Workoff Burden) (SEM07) | Past Baseline to Finish & Not Finished (Workoff Burden) (SEM07) | Future Baseline to Finish & Already Delayed (Workoff Burden) (SEM07) | Score
7 | N/A | 0 | 78 | 6 | 0 | 0 | 79 | 8 | 70 | 8 | 71 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Started (BL Plan) | Current Baseline to Start & Started (BL Plan) | 7 |  | N/A
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Start & Started (Early Starts) | Future Baseline to Start & Started (Early Starts) | N/A |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Start & Started (Workoff Burden) | Past Baseline to Start & Started (Workoff Burden) | 0 |  | N/A
Number of activities that have started in the current period with baseline start dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Start & Not Started (Incompletes) | Current Baseline to Start & Not Started (Incompletes) | 78 |  | 85
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Finished (BL Plan) | Current Baseline to Finish & Finished (BL Plan) | 6 |  | N/A
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Finish & Finished (Early Finishes) | Future Baseline to Finish & Finished (Early Finishes) | 0 |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Finish & Finished (Workoff Burden) | Past Baseline to Finish & Finished (Workoff Burden) | 0 |  | N/A
Number of that have finished in the current period with baseline finish dates in the past (before current period).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Current Baseline to Finish & Not Finished (Incompletes) | Current Baseline to Finish & Not Finished (Incompletes) | 79 |  | 85
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Start & Not Started (Workoff Burden) | Past Baseline to Start & Not Started (Workoff Burden) | 8 |  | 0
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Start & Already Delayed (Workoff Burden) | Future Baseline to Start & Already Delayed (Workoff Burden) | 70 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Past Baseline to Finish & Not Finished (Workoff Burden) | Past Baseline to Finish & Not Finished (Workoff Burden) | 8 |  | 0
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Future Baseline to Finish & Already Delayed (Workoff Burden) | Future Baseline to Finish & Already Delayed (Workoff Burden) | 71 |  | 85
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | 2026-08-05 | 2026-08-05 | 2026-08-05 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned

## NASA-Metrics-Performance-Perf13
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now | Performance - Baseline Bow Wave_BEI, HMI, CEI_To Time Now
Baselined to Start | Scheduled to Start | Started - Scheduled | Started - Baseline Comparison | BEI - Value Task Starts | HMI - Value Task Starts | CEI - Value Task Starts | Baselined to Finish | Scheduled to Finish | Finished | BEI - Value Task Finishes | HMI - Value Task Finishes | CEI - Value Task Finishes | Status Date | Score
12 | 12 | 4 | 4 | 0.33 | 0.27 | 0.27 | 11 | 11 | 3 | 0.27 | 0.27 | 0.27 | 2026-08-11 | 100
| 100% | 33% | 33%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start | Baselined to Start | 12 |  | 0
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Start | Scheduled to Start | 12 | 100% | 0
Number of activities that are planned to start.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started - Scheduled | Started - Scheduled | 4 | 33% | 0
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started - Baseline Comparison | Started - Baseline Comparison | 4 | 33% | 0
Number of activities baselined in the current period that have started (at any time).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Starts | BEI - Value Task Starts | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Starts | HMI - Value Task Starts | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Starts | CEI - Value Task Starts | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish | Baselined to Finish | 11 |  | 0
Number of activities that are scheduled/baselined to finish or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Scheduled to Finish | Scheduled to Finish | 11 |  | 0
Number of activities within that are planned to finish.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finished | Finished | 3 |  | 0
Number of activities finishing or that have finished in the current period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Finishes | BEI - Value Task Finishes | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Finishes | HMI - Value Task Finishes | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Finishes | CEI - Value Task Finishes | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Perf14
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics | Performance - Baseline_Additional Metrics
Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Baseline Comparison | Started Late (from Baseline) | Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished Late | Score
7 | 7 | N/A | 6 | 6 | 1 | 100
8% | 8% | N/A | 7% | 7%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started (incl. Future Baseline Starts) - Scheduled | Started (incl. Future Baseline Starts) - Scheduled | 7 | 8% | 0 | 0%
Number of activities that have started in the current period no matter their baseline start date.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started (incl. Future Baseline Starts) - Baseline Comparison | Started (incl. Future Baseline Starts) - Baseline Comparison | 7 | 8% | 0 | 0%
Number of activities baselined in the current period that have started (at any time).
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Late (from Baseline) | Started Late (from Baseline) | N/A |  | N/A
Number of activities finishing or that have finished in the current period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finished (incl. Future Baseline Finishes) - Scheduled | Finished (incl. Future Baseline Finishes) - Scheduled | 6 | 7% | 0 | 0%
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finished (incl. Future Baseline Finishes) - Baseline Comparison | Finished (incl. Future Baseline Finishes) - Baseline Comparison | 6 | 7% | 0 | 0%
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finished Late | Finished Late | 1 |  | N/A
Number of activities finishing or that have finished in the current period.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perf15
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST | Performance - Completions & Duration Variances - TEST
Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
3 | 1 | 2 | 0 | -57 | 63 | 5 | 21 | 5 | -10 | 6 | 2 | 0 | 6 | 0 | 0 | 3 | 2 | 1 | 0
50% | 17% | 33% | 0% | -954% | 1044% | 90% |  |  |  | 5% | 29% | 0% | 7% | 0% | 0% | 27% | 33% | 17%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Ahead | Completed Ahead | 3 | 50% | 0
Number of activities that finished before their planned finish date
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed | Completed Delayed | 1 | 17% | 0
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed On-Schedule | Completed On-Schedule | 2 | 33% | 0
Number of activities that completed on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Accelerated | Accelerated | 0 | 0% | 0
Number of activities that started after their planned start date but finished before or on their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Days Variance | Days Variance | -57 | -954% | 0
Total variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Days Early | Days Early | 63 | 1044% | 0
A calculation of the total number of days saved by activities that finished early.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Days Late | Days Late | 5 | 90% | 0
A calculation of the total number of days lost by activities that started late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Early | Avg Days Early | 21 |  | 0
Average number of days that all activities within a grouping finished early (before the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Late | Avg Days Late | 5 |  | 0
Average number of days that all activities within a grouping finished late (after the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Variance | Avg Variance | -10 |  | 0
Average variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actually Finished | Actually Finished | 6 | 5% | 0 | 0%
Number of activities that have finished.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Took Longer than Planned | Took Longer than Planned | 2 | 29% | N/A
Number of activities that took longer than forecasted.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Took Less Than Planned | Took Less Than Planned | 0 | 0% | N/A
Number of activities that took less than forecasted.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed (w/Baseline Duration) | Completed (w/Baseline Duration) | 6 | 7% | 0 | 0%
Total number of completed activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed (w/o Baseline Duration) | Completed (w/o Baseline Duration) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed (w/Baseline Dur=0) | Completed (w/Baseline Dur=0) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baseline-to-Date Completed Tasks | Baseline-to-Date Completed Tasks | 3 | 27% | N/A
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missed Durations | Missed Durations | 2 | 33% | 0
Number of activities that have slipped from their baseline duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missed Durations & Late Actual Finish | Missed Durations & Late Actual Finish | 1 | 17% | 0
Number of activities that have slipped from their baseline duration and finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perf16
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST | Performance - Completions & Duration Variance w/Duration Ratio - TEST
Completed Ahead | Completed Delayed | Completed On-Schedule | Accelerated | Days Variance | Days Early | Days Late | Avg Days Early | Avg Days Late | Avg Variance | Actually Finished | Took Longer than Planned | Took Less Than Planned | Completed (w/Baseline Duration) | Completed (w/o Baseline Duration) | Completed (w/Baseline Dur=0) | Baseline-to-Date Completed Tasks | Missed Durations | Missed Durations & Late Actual Finish | Score
3 | 1 | 2 | 0 | -57 | 63 | 5 | 21 | 5 | -10 | 6 | 2 | 0 | 6 | 0 | 0 | 3 | 2 | 1 | 0
50% | 17% | 33% | 0% | -954% | 1044% | 90% |  |  |  | 5% | 29% | 0% | 7% | 0% | 0% | 27% | 33% | 17%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Ahead | Completed Ahead | 3 | 50% | 0
Number of activities that finished before their planned finish date
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Delayed | Completed Delayed | 1 | 17% | 0
Number of activities that finished after their planned finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed On-Schedule | Completed On-Schedule | 2 | 33% | 0
Number of activities that completed on time.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Accelerated | Accelerated | 0 | 0% | 0
Number of activities that started after their planned start date but finished before or on their planned finish date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Days Variance | Days Variance | -57 | -954% | 0
Total variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Days Early | Days Early | 63 | 1044% | 0
A calculation of the total number of days saved by activities that finished early.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Days Late | Days Late | 5 | 90% | 0
A calculation of the total number of days lost by activities that started late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Early | Avg Days Early | 21 |  | 0
Average number of days that all activities within a grouping finished early (before the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Days Late | Avg Days Late | 5 |  | 0
Average number of days that all activities within a grouping finished late (after the baseline start date).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Avg Variance | Avg Variance | -10 |  | 0
Average variance (in days) between activities that started early and those that started late.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Actually Finished | Actually Finished | 6 | 5% | 0 | 0%
Number of activities that have finished.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Took Longer than Planned | Took Longer than Planned | 2 | 29% | N/A
Number of activities that took longer than forecasted.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Took Less Than Planned | Took Less Than Planned | 0 | 0% | N/A
Number of activities that took less than forecasted.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed (w/Baseline Duration) | Completed (w/Baseline Duration) | 6 | 7% | 0 | 0%
Total number of completed activities.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed (w/o Baseline Duration) | Completed (w/o Baseline Duration) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed (w/Baseline Dur=0) | Completed (w/Baseline Dur=0) | 0 | 0% | 0 | 0%
Total number of completed activities.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baseline-to-Date Completed Tasks | Baseline-to-Date Completed Tasks | 3 | 27% | N/A
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missed Durations | Missed Durations | 2 | 33% | 0
Number of activities that have slipped from their baseline duration.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missed Durations & Late Actual Finish | Missed Durations & Late Actual Finish | 1 | 17% | 0
Number of activities that have slipped from their baseline duration and finish date.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Perf17
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New | Performance - Incomplete - Old & New
Baselined Tasks | Baselined to Start - TOTAL | Complete Task Starts - Cumulative | Incomplete Task Starts - Cumulative (in work) | Old Incomplete Task Starts in Status Period | Baselined to Finish | Complete Task Finishes - Cumulative (in work) | Incomplete Task Finishes - Cumulative | Old Incomplete Task Finishes in Status Period | Old Completed Task Finishes in Status Period | Score
85 | 85 | 4 | 8 | N/A | 85 | 3 | 8 | N/A | N/A | 100
|  | 33% | 67% |  |  | 27% | 27%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined Tasks | Baselined Tasks | 85 |  | 85
The total number of baselined tasks.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Actual Duration | Start | Finish | Actual Start | Baseline Start | Baseline Finish | Actual Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-09 | 2026-07-23 | 2026-07-28 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-08-18 | 2026-08-19 | 2026-07-29 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-08-19 | 2026-08-21 | 2026-07-31 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-21 | 2026-08-27 | 2026-08-06 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 9 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-05 | 2026-08-14 |  | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 0 | 2026-08-12 | 2026-08-12 |  | 2026-07-23 | 2026-07-23 |  | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-17 | 2026-08-17 |  | 2026-07-23 | 2026-07-24 |  | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-17 | 2026-08-17 |  | 2026-08-17 | 2026-08-17 |  | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-17 | 2026-08-17 |  | 2026-08-17 | 2026-08-17 |  | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-17 | 2026-08-18 |  | 2026-07-31 | 2026-08-01 |  | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-17 | 2026-08-18 |  | 2026-07-31 | 2026-08-03 |  | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-18 | 2026-08-18 |  | 2026-08-18 | 2026-08-18 |  | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-18 | 2026-08-18 |  | 2026-08-17 | 2026-08-18 |  | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-18 | 2026-08-19 |  | 2026-08-18 | 2026-08-19 |  | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-18 | 2026-08-19 |  | 2026-08-03 | 2026-08-03 |  | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 |  | 2026-08-19 | 2026-08-19 |  | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-19 | 2026-08-19 |  | 2026-08-03 | 2026-08-04 |  | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-19 | 2026-08-20 |  | 2026-08-19 | 2026-08-20 |  | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-19 | 2026-08-21 |  | 2026-08-19 | 2026-08-21 |  | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-19 | 2026-08-20 |  | 2026-08-04 | 2026-08-04 |  | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-20 | 2026-08-20 |  | 2026-08-04 | 2026-08-05 |  | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-20 | 2026-08-20 |  | 2026-08-20 | 2026-08-20 |  | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-20 | 2026-08-21 |  | 2026-08-27 | 2026-08-27 |  | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-20 | 2026-08-21 |  | 2026-08-20 | 2026-08-21 |  | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-21 | 2026-08-21 |  | 2026-08-18 | 2026-08-18 |  | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 0 | 2026-08-21 | 2026-08-22 |  | 2026-08-21 | 2026-08-22 |  | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 0 | 2026-08-21 | 2026-10-06 |  | 2026-09-22 | 2026-10-08 |  | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-22 | 2026-08-22 |  | 2026-08-22 | 2026-08-22 |  | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-24 | 2026-08-24 |  | 2026-08-24 | 2026-08-24 |  | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-24 | 2026-08-25 |  | 2026-08-24 | 2026-08-25 |  | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-24 | 2026-08-25 |  | 2026-08-24 | 2026-08-25 |  | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 |  | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-25 | 2026-08-25 |  | 2026-08-25 | 2026-08-25 |  | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 0 | 2026-08-25 | 2026-08-27 |  | 2026-08-25 | 2026-08-27 |  | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-26 | 2026-08-26 |  | 2026-08-26 | 2026-08-26 |  | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-26 | 2026-08-26 |  | 2026-08-26 | 2026-08-26 |  | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-27 | 2026-08-27 |  | 2026-08-27 | 2026-08-27 |  | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-28 | 2026-08-28 |  | 2026-08-28 | 2026-08-28 |  | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-08-28 | 2026-08-31 |  | 2026-08-28 | 2026-08-31 |  | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 0 | 2026-08-31 | 2026-09-04 |  | 2026-08-31 | 2026-09-04 |  | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-07 | 2026-09-07 |  | 2026-09-07 | 2026-09-07 |  | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-08 | 2026-09-08 |  | 2026-09-08 | 2026-09-08 |  | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-09 | 2026-09-09 |  | 2026-09-09 | 2026-09-09 |  | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-10 | 2026-09-10 |  | 2026-09-10 | 2026-09-10 |  | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-11 | 2026-09-11 |  | 2026-09-11 | 2026-09-11 |  | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-14 | 2026-09-14 |  | 2026-09-14 | 2026-09-14 |  | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-15 | 2026-09-15 |  | 2026-09-15 | 2026-09-15 |  | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-16 | 2026-09-16 |  | 2026-09-16 | 2026-09-16 |  | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 0 | 2026-09-17 | 2026-09-22 |  | 2026-09-17 | 2026-09-22 |  | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-22 | 2026-09-23 |  | 2026-09-22 | 2026-09-23 |  | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-23 | 2026-09-24 |  | 2026-09-23 | 2026-09-24 |  | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-24 | 2026-09-25 |  | 2026-09-24 | 2026-09-25 |  | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-25 | 2026-09-28 |  | 2026-09-25 | 2026-09-28 |  | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-28 | 2026-09-29 |  | 2026-09-28 | 2026-09-29 |  | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-29 | 2026-09-30 |  | 2026-09-29 | 2026-09-30 |  | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-09-30 | 2026-10-01 |  | 2026-09-30 | 2026-10-01 |  | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-01 | 2026-10-02 |  | 2026-10-01 | 2026-10-02 |  | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-02 | 2026-10-02 |  | 2026-10-02 | 2026-10-02 |  | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-02 | 2026-10-03 |  | 2026-10-02 | 2026-10-03 |  | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-03 | 2026-10-03 |  | 2026-10-03 | 2026-10-03 |  | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-03 | 2026-10-03 |  | 2026-10-03 | 2026-10-03 |  | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-03 | 2026-10-04 |  | 2026-10-03 | 2026-10-04 |  | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-05 | 2026-10-05 |  | 2026-10-05 | 2026-10-05 |  | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-05 | 2026-10-06 |  | 2026-10-05 | 2026-10-06 |  | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 0 | 2026-10-06 | 2026-10-07 |  | 2026-10-06 | 2026-10-07 |  | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-07 | 2026-10-08 |  | 2026-10-07 | 2026-10-08 |  | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-08 | 2026-10-09 |  | 2026-10-08 | 2026-10-09 |  | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 0 | 2026-10-09 | 2026-10-13 |  | 2026-10-09 | 2026-10-13 |  | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-14 | 2026-10-14 |  | 2026-10-14 | 2026-10-14 |  | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-15 | 2026-10-15 |  | 2026-10-15 | 2026-10-15 |  | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-16 | 2026-10-16 |  | 2026-10-16 | 2026-10-16 |  | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-19 | 2026-10-19 |  | 2026-10-19 | 2026-10-19 |  | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 0 | 2026-10-20 | 2026-10-22 |  | 2026-10-20 | 2026-10-22 |  | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-23 | 2026-10-23 |  | 2026-10-23 | 2026-10-23 |  | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-23 | 2026-10-26 |  | 2026-10-23 | 2026-10-26 |  | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-26 | 2026-10-26 |  | 2026-10-26 | 2026-10-26 |  | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 0 | 2026-10-26 | 2026-10-29 |  | 2026-10-26 | 2026-10-29 |  | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-29 | 2026-10-30 |  | 2026-10-29 | 2026-10-30 |  | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-30 | 2026-10-30 |  | 2026-10-30 | 2026-10-30 |  | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-10-30 | 2026-11-02 |  | 2026-10-30 | 2026-11-02 |  | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-11-02 | 2026-11-02 |  | 2026-11-02 | 2026-11-02 |  | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 0 | 2026-11-02 | 2026-11-03 |  | 2026-11-02 | 2026-11-03 |  | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 0 | 2026-11-03 | 2026-11-05 |  | 2026-11-03 | 2026-11-05 |  | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Start - TOTAL | Baselined to Start - TOTAL | 85 |  | 85
Number of activities that are scheduled/baselined to start or that have started in the current period.
Excluded | Created | Actual Start | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 2026-07-08 | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 2026-07-08 | 100 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 2026-07-09 | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 2026-07-28 | 100 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 2026-07-29 | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 2026-07-31 | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 2026-08-05 | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  |  | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  |  | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  |  | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  |  | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  |  | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  |  | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  |  | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  |  | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  |  | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  |  | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  |  | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  |  | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  |  | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  |  | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Complete Task Starts - Cumulative | Complete Task Starts - Cumulative | 4 | 33% | 0
The total number (cumulative) of tasks that were baselined to start and started.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Start | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Incomplete Task Starts - Cumulative (in work) | Incomplete Task Starts - Cumulative (in work) | 8 | 67% | N/A
The total number (cumulative) of tasks that were baselined to start but did not start.
Excluded | Created | Actual Start | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  |  | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  |  | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  |  | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  |  | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Old Incomplete Task Starts in Status Period | Old Incomplete Task Starts in Status Period | N/A |  | N/A
The total number (cumulative) of tasks were created prior to the current status period and baselined to start but did not start.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baselined to Finish | Baselined to Finish | 85 |  | 85
Number of activities that are baselined to finish or that have finished in the current period.
Excluded | Created | Percent Complete | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 1 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 | 1 |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 5 | 2026-07-29 | 2026-07-31 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 | 1.6 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 8 | 2026-07-31 | 2026-08-06 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Complete Task Finishes - Cumulative (in work) | Complete Task Finishes - Cumulative (in work) | 3 | 27% | 0
The total number (cumulative) of tasks that were baselined to finish and finshed.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Incomplete Task Finishes - Cumulative | Incomplete Task Finishes - Cumulative | 8 | 27% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Old Incomplete Task Finishes in Status Period | Old Incomplete Task Finishes in Status Period | N/A |  | N/A
The total number (cumulative) of tasks that were created prior to the current status period and baselined to complete but did not complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Old Completed Task Finishes in Status Period | Old Completed Task Finishes in Status Period | N/A |  | N/A
The total number (cumulative) of tasks that were were created prior to the current status period and baselined to complete and completed.

## NASA-Metrics-Performance-Basel
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA Metrics Performance Baseline Execution Index (BEI)
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Baseline Execution Index (BEI)
|  | BEI - Tasks | BEI - Milestones
Ribbons | Hard_File | 100 | 100
Ribbons | Hard_File_updated | 100 | 100
|  | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks
|  | BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2026-07-07 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A
Ribbons | Hard_File_updated | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 100
Ribbons |  |  |  | 27% | 73% |  | 55%
|  | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones
|  | BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 2026-07-07 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A
Ribbons | Hard_File_updated | 0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2026-08-11 | 100
Ribbons |  |  |  | 33% | 67% |  | 33%

## NASA-Metrics-Performance-Basel2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance-Basel -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks | BEI - Tasks
BEI - Value Tasks | BEI - Total Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - Value Tasks (adjusted) | BEI - Complete Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | Status Date | Score
0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 100
|  | 27% | 73% |  | 55%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Total Tasks | BEI - Total Tasks | 11 |  | 0
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Tasks | BEI - Complete Tasks | 3 | 27% | N/A
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 8 | 73% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Tasks (adjusted) | BEI - Value Tasks (adjusted) | 0.55 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline. Takes credit for future-baselined activities that are complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Tasks (adjusted) | BEI - Complete Tasks (adjusted) | 6 | 55% | 0
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Future Tasks (adjusted) | BEI - Complete Future Tasks (adjusted) | 3 |  | N/A
The total number tasks that are baselined to complete in the future and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined activities that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Basel3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance-Basel -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones | BEI - Milestones
BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | BEI - Value Milestones (adjusted) | BEI - Complete Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | Status Date | Score
0.33 | 3 | 1 | 2 | 0.33 | 1 | N/A | 2026-08-11 | 100
|  | 33% | 67% |  | 33%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Milestones | BEI - Value Milestones | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Total Milestones | BEI - Total Milestones | 3 |  | 0
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Milestones | BEI - Complete Milestones | 1 | 33% | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Incomplete Milestones | BEI - Incomplete Milestones | 2 | 67% | N/A
The total number (cumulative) of milestones that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Milestones (adjusted) | BEI - Value Milestones (adjusted) | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline. Takes credit for future-baselined milestones that are complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Milestones (adjusted) | BEI - Complete Milestones (adjusted) | 1 | 33% | 0
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Future Milestones (adjusted) | BEI - Complete Future Milestones (adjusted) | N/A |  | N/A
The total number of milestones that are baselined to complete in the future and actually completed on or before time now (i.e., IMS status date). Takes credit for future-baselined milestones that are complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Hit-o
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA Metrics Performance Hit or Miss Index (HMI)
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hit or Miss Index (HMI)
|  | HMI - Tasks | HMI - Milestones
Ribbons | Hard_File | 100 | 100
Ribbons | Hard_File_updated | 100 | 100
|  | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks
|  | HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A | N/A |  | N/A
Ribbons | Hard_File_updated | 0.27 | 11 | 3 | N/A | 8 | 0.55 | 6 | 3 | 100
Ribbons |  |  |  | 27% | 0% | 73% |  | 55%
|  | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones
|  | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | 100
Ribbons |  |  |  | N/A | N/A | N/A |  | N/A
Ribbons | Hard_File_updated | 0.33 | 3 | 1 | N/A | 2 | 0.33 | 1 | 3 | 100
Ribbons |  |  |  | 33% | 0% | 67% |  | 33%

## NASA-Metrics-Performance-Hit-o2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance-Hit-o -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks | HMI - Tasks
HMI - Value Tasks | HMI - Total Tasks | HMI - Complete Tasks | HMI - Completed Early Tasks | HMI - Incomplete Tasks | HMI - Value Tasks (adjusted) | HMI - Complete Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | Score
0.27 | 11 | 3 | N/A | 8 | 0.55 | 6 | 3 | 100
|  | 27% | 0% | 73% |  | 55%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Total Tasks | HMI - Total Tasks | 11 |  | 0
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Tasks | HMI - Complete Tasks | 3 | 27% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Completed Early Tasks | HMI - Completed Early Tasks | N/A | 0% | N/A
The total number of tasks that were baselined to complete within the current status period and actually completed before the current status period (i.e., from previous IMS status date to current IMS status date). Calculates tasks that are missing from the HMI Value calculation because they were completed early.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Incomplete Tasks | HMI - Incomplete Tasks | 8 | 73% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | 0.55 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month). Gives credit for tasks baselined in the future that completed during the given status period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Tasks (adjusted) | HMI - Complete Tasks (adjusted) | 6 | 55% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for tasks baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Future Tasks (adjusted) | HMI - Complete Future Tasks (adjusted) | 3 |  | N/A
The total number of tasks that were baselined to complete in the future and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for tasks baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Hit-o3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance-Hit-o -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones | HMI - Milestones
HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Completed Early Milestones | HMI - Incomplete Milestones | HMI - Value Milestones (adjusted) | HMI - Complete Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | Score
0.33 | 3 | 1 | N/A | 2 | 0.33 | 1 | 3 | 100
|  | 33% | 0% | 67% |  | 33%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Milestones | HMI - Value Milestones | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for milestones. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Total Milestones | HMI - Total Milestones | 3 |  | 0
The total number of milestones baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Milestones | HMI - Complete Milestones | 1 | 33% | N/A
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Completed Early Milestones | HMI - Completed Early Milestones | N/A | 0% | N/A
The total number of milestones that were baselined to complete within the current status period and actually completed before the current status period (i.e., from previous IMS status date to current IMS status date). Calculates milestones that are missing from the HMI Value calculation because they were completed early.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Incomplete Milestones | HMI - Incomplete Milestones | 2 | 67% | N/A
The total number of milestones that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month). Gives credit for milestones baselined in the future that completed during the given status period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Milestones (adjusted) | HMI - Complete Milestones (adjusted) | 1 | 33% | N/A
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for milestones baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Future Milestones (adjusted) | HMI - Complete Future Milestones (adjusted) | 3 |  | N/A
The total number of milestones that were baselined to complete in the future and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date). Gives credit for milestones baselined in the future that completed during the given status period.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-Curre
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA Metrics Performance Current Execution Index (CEI)
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Current Execution Index (CEI)
|  | CEI - Tasks | CEI - Milestones
Ribbons | Hard_File | 100 | 100
Ribbons | Hard_File_updated | 100 | 100
|  | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks
|  | CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A
Ribbons | Hard_File_updated | 0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 100
Ribbons |  |  |  | 27% | 73% |  | 55%
|  | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones
|  | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Score
Ribbons | Hard_File | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | 100
Ribbons |  |  |  | N/A | N/A |  | N/A
Ribbons | Hard_File_updated | 0.33 | 3 | 1 | 2 | 0.33 | 1 | 0 | 2026-08-11 | 100
Ribbons |  |  |  | 33% | 67% |  | 33%

## NASA-Metrics-Performance-Curre2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance-Curre -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks | CEI - Tasks
CEI - Value Tasks | CEI - Total Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - Value Tasks (adjusted) | CEI - Complete Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | Status Date | Score
0.27 | 11 | 3 | 8 | 0.55 | 6 | 3 | 2026-08-11 | 100
|  | 27% | 73% |  | 55%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Total Tasks | CEI - Total Tasks | 11 |  | 0
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 1 | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 1.35 | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 0 | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 0 | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 0 | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 0 | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 0 | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 0 | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 0 | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 0 | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Tasks | CEI - Complete Tasks | 3 | 27% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 1 | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 1.35 | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Incomplete Tasks | CEI - Incomplete Tasks | 8 | 73% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | 0.55 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast. Takes credit for future-planned activities that were completed within the measured timeframe.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Tasks (adjusted) | CEI - Complete Tasks (adjusted) | 6 | 55% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned activities that were completed within the measured timeframe.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Future Tasks (adjusted) | CEI - Complete Future Tasks (adjusted) | 3 |  | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the future per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned activities that were completed within the measured timeframe.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-Curre3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance-Curre -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones | CEI - Milestones
CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | CEI - Value Milestones (adjusted) | CEI - Complete Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | Status Date | Score
0.33 | 3 | 1 | 2 | 0.33 | 1 | 0 | 2026-08-11 | 100
|  | 33% | 67% |  | 33%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Milestones | CEI - Value Milestones | 0.33 |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Total Milestones | CEI - Total Milestones | 3 |  | 0
The number of milestones forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Milestones | CEI - Complete Milestones | 1 | 33% | N/A
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Incomplete Milestones | CEI - Incomplete Milestones | 2 | 67% | N/A
The number of milestones that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | 0.33 |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast. Takes credit for future-planned milestones that were completed within the measured timeframe.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Milestones (adjusted) | CEI - Complete Milestones (adjusted) | 1 | 33% | N/A
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned milestones that were completed within the measured timeframe.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Future Milestones (adjusted) | CEI - Complete Future Milestones (adjusted) | 0 |  | N/A
The number of milestones completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the future per the previous month's schedule forecast (based on the prior schedule's status date). Takes credit for future-planned milestones that were completed within the measured timeframe.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-BEI--
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks | BEI, HMI, CEI - Tasks
BEI - Value Tasks | BEI - Total Tasks | BEI - Incomplete Tasks | HMI - Value Tasks | HMI - Total Tasks | HMI - Incomplete Tasks | CEI - Value Tasks | CEI - Total Tasks | CEI - Incomplete Tasks | BEI - Complete Milestones | HMI - Complete Tasks | CEI - Complete Tasks | Score
0.27 | 11 | 8 | 0.27 | 11 | 8 | 0.27 | 11 | 8 | 1 | 3 | 3 | 100
|  | 73% |  |  | 73% |  |  | 73% | 33% | 27% | 27%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Total Tasks | BEI - Total Tasks | 11 |  | 0
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 8 | 73% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Total Tasks | HMI - Total Tasks | 11 |  | 0
The total number of tasks baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Incomplete Tasks | HMI - Incomplete Tasks | 8 | 73% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Total Tasks | CEI - Total Tasks | 11 |  | 0
The number of tasks forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Incomplete Tasks | CEI - Incomplete Tasks | 8 | 73% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Milestones | BEI - Complete Milestones | 1 | 33% | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Tasks | HMI - Complete Tasks | 3 | 27% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Tasks | CEI - Complete Tasks | 3 | 27% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 1 | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 1 | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 1.35 | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0

## NASA-Metrics-Performance-BEI--2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones | BEI, HMI, CEI - Milestones
BEI - Value Milestones | BEI - Total Milestones | BEI - Complete Milestones | BEI - Incomplete Milestones | HMI - Value Milestones | HMI - Total Milestones | HMI - Complete Milestones | HMI - Incomplete Milestones | CEI - Value Milestones | CEI - Total Milestones | CEI - Complete Milestones | CEI - Incomplete Milestones | Score
0.33 | 3 | 1 | 2 | 0.33 | 3 | 1 | 2 | 0.33 | 3 | 1 | 2 | 100
|  | 33% | 67% |  |  | 33% | 67% |  |  | 33% | 67%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Milestones | BEI - Value Milestones | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Total Milestones | BEI - Total Milestones | 3 |  | 0
The total number (cumulative) of tasks baselined to be completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Milestones | BEI - Complete Milestones | 1 | 33% | N/A
The total number (cumulative) milestones that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Incomplete Milestones | BEI - Incomplete Milestones | 2 | 67% | N/A
The total number (cumulative) of milestones that were baselined to complete but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Milestones | HMI - Value Milestones | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for milestones. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Total Milestones | HMI - Total Milestones | 3 |  | 0
The total number of milestones baselined to be completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Milestones | HMI - Complete Milestones | 1 | 33% | N/A
The total number of milestones that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Incomplete Milestones | HMI - Incomplete Milestones | 2 | 67% | N/A
The total number of milestones that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Milestones | CEI - Value Milestones | 0.33 |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Total Milestones | CEI - Total Milestones | 3 |  | 0
The number of milestones forecasted in the previous month's schedule (based on the prior schedule's status date) to be completed in the current month (time between prior schedule's satus date and current schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Milestones | CEI - Complete Milestones | 1 | 33% | N/A
The number of activities completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Incomplete Milestones | CEI - Incomplete Milestones | 2 | 67% | N/A
The number of milestones that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-07-31 | 2026-07-31 | Milestone | Planned | 0 | 3
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-04 | 2026-08-04 | Milestone | Planned | 0 | 11

## NASA-Metrics-Performance-BEI--3
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted | BEI, HMI, CEI - Values Adjusted
BEI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | BEI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | Status Date | Score
0.55 | 0.55 | 0.55 | 0.33 | 0.33 | 0.33 | 2026-08-11 | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Tasks (adjusted) | BEI - Value Tasks (adjusted) | 0.55 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline. Takes credit for future-baselined activities that are complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Tasks (adjusted) | HMI - Value Tasks (adjusted) | 0.55 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month). Gives credit for tasks baselined in the future that completed during the given status period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Tasks (adjusted) | CEI - Value Tasks (adjusted) | 0.55 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast. Takes credit for future-planned activities that were completed within the measured timeframe.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Milestones (adjusted) | BEI - Value Milestones (adjusted) | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline. Takes credit for future-baselined milestones that are complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Milestones (adjusted) | HMI - Value Milestones (adjusted) | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month). Gives credit for milestones baselined in the future that completed during the given status period.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Milestones (adjusted) | CEI - Value Milestones (adjusted) | 0.33 |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast. Takes credit for future-planned milestones that were completed within the measured timeframe.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Performance-DRM
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
DRM | DRM | DRM
Total Activities - DRM | Total Activities - DRM Graph | Score
6 | 6 | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Activities - DRM | Total Activities - DRM | 6 |  | 0
The total number of activities within a grouping.
Excluded | Notes | Id | Description | Baseline Duration | Actual Duration | DRM | Project | Actual Start | Actual Finish | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | 1 | 1 | 1 | Hard_File_updated | 2026-07-08 | 2026-07-08 | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | 1 | 1 | 1 | Hard_File_updated | 2026-07-08 | 2026-07-09 | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | 20 | 27 | 1.35 | Hard_File_updated | 2026-07-09 | 2026-07-28 | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 400 | Build customer service programs | 1 | 1 | 1 | Hard_File_updated | 2026-07-28 | 2026-07-29 | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
FALSE |  | 399 | Perform subject matter expert review | 5 | 5 | 1 | Hard_File_updated | 2026-07-29 | 2026-07-31 | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 100 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | 5 | 8 | 1.6 | Hard_File_updated | 2026-07-31 | 2026-08-06 | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total Activities - DRM Graph | Total Activities - DRM Graph | 6 |  | 0
The total number of activities within a grouping.
Id | Description | Baseline Duration | Actual Duration | DRM
97 | Identify typical product usage scenarios | 1 | 1 | 1
96 | Identify typical customer types | 1 | 1 | 1
95 | Identify anticipated product problem points | 20 | 27 | 1.35
400 | Build customer service programs | 1 | 1 | 1
399 | Perform subject matter expert review | 5 | 5 | 1
401 | Perform user acceptance testing with customers | 5 | 8 | 1.6

## NASA-Metrics-Performance-Track
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates | Tracking Dates
Status Date | Milestone #1 - 5158 | Float Milestone #1 - 5158 | Milestone #2 - 4786 | Float to Milestone #2 - 4786 | Milestone #3 - 102 | Float to Milestone #3 - 102 | Milestone #4 - 103 | Float to Milestone #4 - 103 | Milestone #5 - 104 | Float to Milestone #5 - 105 | New Activities Since Previous Status Date | Score
2026-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #1 - 5158 | Milestone #1 - 5158 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float Milestone #1 - 5158 | Float Milestone #1 - 5158 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #2 - 4786 | Milestone #2 - 4786 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #2 - 4786 | Float to Milestone #2 - 4786 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #3 - 102 | Milestone #3 - 102 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #3 - 102 | Float to Milestone #3 - 102 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #4 - 103 | Milestone #4 - 103 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #4 - 103 | Float to Milestone #4 - 103 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestone #5 - 104 | Milestone #5 - 104 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Float to Milestone #5 - 105 | Float to Milestone #5 - 105 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
New Activities Since Previous Status Date | New Activities Since Previous Status Date | 0 |  | 0

## NASA-Metrics-Performance-Margi
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration | Margin Duration
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-11 | N/A | 1 | 0 | N/A | N/A | N/A | N/A | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | 1 |  | 1
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | 0 |  | 0
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | 1
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A

## NASA-Metrics-Performance-Margi2
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date | Margin Date
Status Date | Margin - Margin Task Name #1 | Margin - Margin Task Name #2 | Margin - Margin Task Name #3 | Margin - Margin Task Name #4 | Margin - Margin Task Name #5 | Margin - Margin Task Name #6 | Margin - Margin Task Name #7 | Score
2026-08-11 | N/A | 2026-08-20 | 2026-08-26 | N/A | N/A | N/A | N/A | 100
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #1 | Margin - Margin Task Name #1 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #2 | Margin - Margin Task Name #2 | 2026-08-20 |  | 2026-08-20
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #3 | Margin - Margin Task Name #3 | 2026-08-26 |  | 2026-08-26
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #4 | Margin - Margin Task Name #4 | N/A |  | 2026-08-18
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #5 | Margin - Margin Task Name #5 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #6 | Margin - Margin Task Name #6 | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Margin - Margin Task Name #7 | Margin - Margin Task Name #7 | N/A |  | N/A

## NASA-Metrics-Performance-Perf18
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon) | Performance - Baseline_Bow Wave_BEI, HMI, CEI (GRAPH 2, Snapshot_Ribbon)
BEI - Value Task Starts - Cumulative | BEI - Value Task Finishes - Cumulative | HMI - Value Task Starts - by Status Dates | HMI - Value Task Finishes - by Status Dates | CEI - Value Task Starts - by Status Dates | CEI - Value Task Finishes - by Status Dates | FEI - Value Task Starts - Cumulative | FEI - Value Task Finish - Cumulative | To Go - BEI - Value Task Starts - Cumulative (SEM07) | To Go - BEI - Value Task Finishes - Cumulative (SEM07) | To Go - Planned Task Starts - Count (SEM07) | To Go - BEI - Task Finishes - Count (SEM07) | To Go - Baselined Task Starts - Count (SEM07) | To Go - BEI - Value Task Starts - Cumulative (SEM07) | Score
0.33 | 0.27 | 0.33 | 0.27 | 0.33 | 0.27 | 1.11 | 1.11 | 1.11 | 1.11 | 78 | 79 | 78 | 1.11 | 55
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Starts - Cumulative | BEI - Value Task Starts - Cumulative | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Task Finishes - Cumulative | BEI - Value Task Finishes - Cumulative | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 1 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | 1 |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 1 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | 1.35 |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 27 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Starts - by Status Dates | HMI - Value Task Starts - by Status Dates | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for task starts. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Task Finishes - by Status Dates | HMI - Value Task Finishes - by Status Dates | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for task finishes. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Starts - by Status Dates | CEI - Value Task Starts - by Status Dates | 0.33 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Task Finishes - by Status Dates | CEI - Value Task Finishes - by Status Dates | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FEI - Value Task Starts - Cumulative | FEI - Value Task Starts - Cumulative | 1.11 |  | 1
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FEI - Value Task Finish - Cumulative | FEI - Value Task Finish - Cumulative | 1.11 |  | 1
Future Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline for activities that have not yet started.
Excluded | DurationRatio | Notes | Id | Description | Project | Original Duration | Remaining Duration | Actual Duration | Actual Start | Actual Finish | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | 0.6 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 9 | 2026-08-05 |  | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | 0 |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | 0 |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | 0 |  | 180 | Online support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | 0 |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | 0 |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | 0 |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | 0 |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE | 0 |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 0 |  |  | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE | 0 |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 0 |  |  | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | 0 |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | 0 |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | 0 |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 0 |  |  | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | 0 |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | 0 |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | 0 |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | 0 |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | 0 |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | 0 |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 0 |  |  | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | 0 |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 0 |  |  | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 0 |  |  | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Finishes - Cumulative | To Go - BEI - Value Task Finishes - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - Planned Task Starts - Count | To Go - Planned Task Starts - Count | 78 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Task Finishes - Count | To Go - BEI - Task Finishes - Count | 79 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - Baselined Task Starts - Count | To Go - Baselined Task Starts - Count | 78 |  | 85
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
To Go - BEI - Value Task Starts - Cumulative | To Go - BEI - Value Task Starts - Cumulative | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Baseline Start | Start | Actual Start | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
94 | 2026-07-23 | 2026-08-12 |  | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | 2026-07-23 | 2026-08-17 |  | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | 2026-08-17 | 2026-08-17 |  | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | 2026-08-17 | 2026-08-17 |  | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | 2026-07-31 | 2026-08-17 |  | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | 2026-07-31 | 2026-08-17 |  | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | 2026-08-18 | 2026-08-18 |  | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | 2026-08-17 | 2026-08-18 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | 2026-08-18 | 2026-08-18 |  | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | 2026-08-03 | 2026-08-18 |  | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | 2026-08-19 | 2026-08-19 |  | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | 2026-08-03 | 2026-08-19 |  | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | 2026-08-19 | 2026-08-19 |  | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | 2026-08-19 | 2026-08-19 |  | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | 2026-08-04 | 2026-08-19 |  | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | 2026-08-04 | 2026-08-20 |  | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | 2026-08-20 | 2026-08-20 |  | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | 2026-08-27 | 2026-08-20 |  | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | 2026-08-20 | 2026-08-20 |  | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | 2026-08-18 | 2026-08-21 |  | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | 2026-08-21 | 2026-08-21 |  | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | 2026-09-22 | 2026-08-21 |  | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | 2026-08-22 | 2026-08-22 |  | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | 2026-08-24 | 2026-08-24 |  | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | 2026-08-24 | 2026-08-24 |  | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | 2026-08-24 | 2026-08-24 |  | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | 2026-08-25 | 2026-08-25 |  | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | 2026-08-25 | 2026-08-25 |  | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | 2026-08-25 | 2026-08-25 |  | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | 2026-08-26 | 2026-08-26 |  | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | 2026-08-26 | 2026-08-26 |  | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | 2026-08-27 | 2026-08-27 |  | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | 2026-08-28 | 2026-08-28 |  | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | 2026-08-28 | 2026-08-28 |  | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | 2026-08-31 | 2026-08-31 |  | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | 2026-09-07 | 2026-09-07 |  | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | 2026-09-08 | 2026-09-08 |  | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | 2026-09-09 | 2026-09-09 |  | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | 2026-09-10 | 2026-09-10 |  | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | 2026-09-11 | 2026-09-11 |  | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | 2026-09-14 | 2026-09-14 |  | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | 2026-09-15 | 2026-09-15 |  | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | 2026-09-16 | 2026-09-16 |  | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | 2026-09-17 | 2026-09-17 |  | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | 2026-09-22 | 2026-09-22 |  | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | 2026-09-23 | 2026-09-23 |  | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | 2026-09-24 | 2026-09-24 |  | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | 2026-09-25 | 2026-09-25 |  | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | 2026-09-28 | 2026-09-28 |  | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | 2026-09-29 | 2026-09-29 |  | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | 2026-09-30 | 2026-09-30 |  | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | 2026-10-01 | 2026-10-01 |  | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | 2026-10-02 | 2026-10-02 |  | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | 2026-10-02 | 2026-10-02 |  | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | 2026-10-03 | 2026-10-03 |  | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | 2026-10-03 | 2026-10-03 |  | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | 2026-10-03 | 2026-10-03 |  | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | 2026-10-05 | 2026-10-05 |  | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | 2026-10-05 | 2026-10-05 |  | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | 2026-10-06 | 2026-10-06 |  | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | 2026-10-07 | 2026-10-07 |  | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | 2026-10-08 | 2026-10-08 |  | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | 2026-10-09 | 2026-10-09 |  | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | 2026-10-14 | 2026-10-14 |  | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | 2026-10-15 | 2026-10-15 |  | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | 2026-10-16 | 2026-10-16 |  | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | 2026-10-19 | 2026-10-19 |  | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | 2026-10-20 | 2026-10-20 |  | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | 2026-10-23 | 2026-10-23 |  | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | 2026-10-23 | 2026-10-23 |  | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | 2026-10-26 | 2026-10-26 |  | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | 2026-10-26 | 2026-10-26 |  | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | 2026-10-29 | 2026-10-29 |  | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | 2026-10-30 | 2026-10-30 |  | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | 2026-10-30 | 2026-10-30 |  | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | 2026-11-02 | 2026-11-02 |  | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | 2026-11-02 | 2026-11-02 |  | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | 2026-11-03 | 2026-11-03 |  | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned

## NASA-Metrics-Performance-BEI--4
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values | BEI, HMI, CEI - Values
BEI - Value Tasks | HMI - Value Tasks | CEI - Value Tasks | BEI - Value Milestones | HMI - Value Milestones | CEI - Value Milestones | Score
0.27 | 0.27 | 0.27 | 0.33 | 0.33 | 0.33 | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Milestones | BEI - Value Milestones | 0.33 |  | N/A
Baseline Execution Index (BEI) calculation for milestones. A cumulative measure of IMS milestone performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Milestones | HMI - Value Milestones | 0.33 |  | N/A
Hit or Miss Index (HMI) calculation for milestones. A monthly measure of IMS milestone performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Milestones | CEI - Value Milestones | 0.33 |  | N/A
Current Execution Index (CEI) calculation for milestones. A monthly measure of schedule milestone performance against the monthly forecast.

## NASA-Metrics-Performance-BEI--5
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics-Performance -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path | BEI, HMI, CEI - Critical Path
BEI - Value Tasks | BEI - Complete Tasks | BEI - Incomplete Tasks | BEI - CP Tasks - Planned Cumulative | BEI - CP Value Tasks | HMI - Value Tasks | HMI - Complete Tasks | HMI - Incomplete Tasks | HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Value Tasks | CEI - Value Tasks | CEI - Complete Tasks | CEI - Incomplete Tasks | CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Value Tasks | Score
0.27 | 3 | 8 | 0 | N/A | 0.27 | 3 | 8 | 0 | N/A | 0.27 | 3 | 8 | 0 | N/A | 100
| 27% | 73% |  |  |  | 27% | 73% |  |  |  | 27% | 73%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Value Tasks | BEI - Value Tasks | 0.27 |  | N/A
Baseline Execution Index (BEI) calculation for tasks. A cumulative measure of IMS task performance against the baseline.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Complete Tasks | BEI - Complete Tasks | 3 | 27% | N/A
The total number (cumulative) tasks that were baselined to complete and actually completed on or before time now (i.e., IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - Incomplete Tasks | BEI - Incomplete Tasks | 8 | 73% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete.
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE | FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | FALSE | FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | FALSE | FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | FALSE | FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | FALSE | FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE | FALSE | FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | FALSE | FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | FALSE | FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - CP Tasks - Planned Cumulative | BEI - CP Tasks - Planned Cumulative | 0 |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI - CP Value Tasks | BEI - CP Value Tasks | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Value Tasks | HMI - Value Tasks | 0.27 |  | N/A
Hit or Miss Index (HMI) calculation for tasks. A monthly measure of IMS task performance against the baseline for a given status period (e.g., within a month).
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Complete Tasks | HMI - Complete Tasks | 3 | 27% | N/A
The total number of tasks that were baselined to complete and actually completed within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - Incomplete Tasks | HMI - Incomplete Tasks | 8 | 73% | N/A
The total number (cumulative) of tasks that were baselined to complete but did not complete within the current status period (i.e., from previous IMS status date to current IMS status date).
Excluded | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - CP Tasks - Planned to be Completed this Month | HMI - CP Tasks - Planned to be Completed this Month | 0 |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
HMI - CP Value Tasks | HMI - CP Value Tasks | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Value Tasks | CEI - Value Tasks | 0.27 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Complete Tasks | CEI - Complete Tasks | 3 | 27% | N/A
The number of tasks completed in the current month's schedule (based on the current schedule's status date) that were forecasted to complete in the current month per the previous month's schedule forecast (based on the prior schedule's status date).
Excluded | Previous_Critical | Critical | Notes | DRM | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE | FALSE |  | 1 | 97 | Identify typical product usage scenarios | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 100 | 0
FALSE | FALSE | FALSE |  | 1 | 96 | Identify typical customer types | Hard_File_updated | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 100 | 0
FALSE | FALSE | FALSE |  | 1.35 | 95 | Identify anticipated product problem points | Hard_File_updated | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 100 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - Incomplete Tasks | CEI - Incomplete Tasks | 8 | 73% | N/A
The number of tasks that were forecast to complete in the month (time between prior schedule's status date and current schedule's status date) but did not complete.
Excluded | Previous_Critical | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE | FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE | FALSE | FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE | FALSE | FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE | FALSE | FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | FALSE | FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE | FALSE | FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | FALSE | FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE | FALSE | FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - CP Tasks - Planned to be Completed this Month | CEI - CP Tasks - Planned to be Completed this Month | 0 |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CEI - CP Value Tasks | CEI - CP Value Tasks | N/A |  | N/A
Current Execution Index (CEI) calculation for tasks. A monthly measure of schedule task performance against the monthly forecast.

## NASA-Metrics-Schedule-Errors
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors | Schedule Errors
Wrong Status | Invalid Forecast Dates | Expected Finish | Missing WBS | Milestones with Duration>0 | Activities with Duration=0 | Estimated Duration | Missing Logic | Missing Predecessors | Missing Successors | Open Start | Open Finish | Unsatisfied Constraints | Summary Links | Hard Constraints | Critical w/Hidden Duration | Negative Float | Status Date | Score
0 | 0 | 0 | 0 | 0 | 1 | 65 | 8 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-11 | 48
0% | 0% | 0% | 0% | 0% | 1% | 82% | 8% | 0% | 7% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Wrong Status | Wrong Status | 0 | 0% | 0
Number of activities that have been statused into the future.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Invalid Forecast Dates | Invalid Forecast Dates | 0 | 0% | 0 | 0%
All activities with planned work in the past. There should not be any invalid dates in the schedule.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Expected Finish | Expected Finish | 0 | 0% | 0 | 0%
In-progress activities that are 100% complete.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing WBS | Missing WBS | 0 | 0% | 0 | 0%
Number of activities that are missing WBS values.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Milestones with Duration>0 | Milestones with Duration>0 | 0 | 0% | 0 | 0%
Milestones with a duration greater than 0 days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities with Duration=0 | Activities with Duration=0 | 1 | 1% | 1 | 1%
Activities that have an original duration of 0 days.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Estimated Duration | Estimated Duration | 65 | 82% | 68 | 80%
Tasks with estimated duration in Microsoft Project. This condition occurs when an original duration has not been entered by the user.
Excluded | Created | Notes | Id | Description | Project | Baseline Duration | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE |  |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 0 | 2
FALSE |  |  | 157 | Document product review results | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 0 | 3
FALSE |  |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE |  |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 0 | 3
FALSE |  |  | 180 | Online support | Hard_File_updated | 1 | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE |  |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE |  |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE |  |  | 179 | Phone support | Hard_File_updated | 1 | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 0 | 12
FALSE |  |  | 178 | On-site support | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 0 | 11
FALSE |  |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE |  |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 0 | 11
FALSE |  |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE |  |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE |  |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE |  |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 1
FALSE |  |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE |  |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 1
FALSE |  |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE |  |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Logic | Missing Logic | 8 | 8% | 7 | 6%
Total number of activities that are missing a predecessor, a successor, or both. This number should not exceed 5%.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 0 | 1 |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE | Deadline | TRUE | 1 | 0 |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Predecessors | Missing Predecessors | 0 | 0% | 1 | 1%
Number of activities that are missing a predecessor.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Missing Successors | Missing Successors | 7 | 7% | 6 | 5%
Number of normal activities that are missing a successor.
Excluded | Primary Constraint | Critical | Number of Predecessors | Number of Successors | Created | Percent Complete | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
FALSE | None | FALSE | 1 | 0 |  | 0 |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 10
FALSE | Deadline | TRUE | 1 | 0 |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Start | Open Start | 0 | 0% | 0 | 0%
Activities where only the predecessor(s) are either Finish-to-Finish or Start-to-Finish resulting in an open start to the activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Open Finish | Open Finish | 0 | 0% | 0 | 0%
Activities where the only successors(s) are either Start-to-Finish or Start-to-Start resulting in an open finish to the activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Unsatisfied Constraints | Unsatisfied Constraints | 0 | 0% | 0 | 0%
Activities where the constraint date cannot be met
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Summary Links | Summary Links | 0 | 0% | 0 | 0%
Number of summary activities that have logic links.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hard Constraints | Hard Constraints | 0 | 0% | 0 | 0%
Number of activities with hard or two-way constraints.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical w/Hidden Duration | Critical w/Hidden Duration | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Status Date | Status Date | 2026-08-11 |  | 2026-07-07
Current Status Date (Time Now) for the schedule.

## NASA-Metrics-Schedule-Warnings
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings | Schedule Warnings
High Float 10% | High Float 44d | Zero Days Float | Negative Float | Hidden Duration (Planned) | Critical Logic Hotspot™ | Critical Merge Hotspot | Merge Hotspot w/Predecessor Lags | Critical Diverge Hotspot | Diverge Hotspot w/Successor Lags | Riding Data Date | Deadlines | Score
17 | 6 | 74 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 88
17% | 6% | 72% | 0% | 0% | 0% | 0% | ( N/A ) | 0% | ( N/A ) | 0% | 0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Float 10% | High Float 10% | 17 | 17% | 20 | 18%
Number of activities that have a total float value higher than 10% of the total duration of the project. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 180 | Online support | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 0 | 13
FALSE | FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 37
FALSE | FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 37
FALSE | FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 22
FALSE | FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 37
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 0 | 22
FALSE | FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 38
FALSE | FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 39
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
FALSE | FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 38
FALSE | FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-06 | 2026-10-06 | 2026-10-08 | 2026-10-08 | Milestone | Planned | 0 | 22
FALSE | FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 14
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
High Float 44d | High Float 44d | 6 | 6% | 2 | 2%
Number of activities with total float greater than 2 months. This number should not exceed 5%.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 53
FALSE | FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 54
FALSE | FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Milestone | Planned | 0 | 54
FALSE | FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 50
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Zero Days Float | Zero Days Float | 74 | 72% | 78 | 71%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Hidden Duration (Planned) | Hidden Duration (Planned) | 0 | 0% | 0 | 0%
Number of activities that contain a lag on a predecessor relationship that is bigger than 35% of its original duration
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Logic Hotspot™ | Critical Logic Hotspot™ | 0 | 0% | 0 | 0%
Number of activities with a high number of predecessors as well as a high number of successors.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Merge Hotspot | Critical Merge Hotspot | 0 | 0% | 0 | 0%
The total number of activities with a high number of predecessor links that are also critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Merge Hotspot w/Predecessor Lags | Merge Hotspot w/Predecessor Lags | N/A |  | N/A
Number of activities with a high number of predecessor links with lags on the predecessor relationships.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Diverge Hotspot | Critical Diverge Hotspot | 0 | 0% | 1 | 1%
Number of activities with a high number of successor links that are also critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Diverge Hotspot w/Successor Lags | Diverge Hotspot w/Successor Lags | N/A |  | N/A
Number of activities with a high number of successor links and critical.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Riding Data Date | Riding Data Date | 0 | 0% | 0 | 0%
Number of planned activities that have a start date that is the same as the project data date (Time Now)
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Deadlines | Deadlines | 0 | 0% | 0 | 0%
Number of activities with a hard (two-way) constraint that forces the activity to finish on a specific date, overriding CPM calculations.

## NASA-Metrics-Critical-Path
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | NASA-Metrics -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path | Critical Path
Longest Path (Normal Tasks) | Longest Path (Tasks & Milestones) | Critical Milestone-to-Task Ratio (To-Go) | Critical Milestones (To-Go) | Longest Path (Milestones) | Normal Tasks | Normal Tasks (To-Go) | Critical Tasks (To-Go) | Critical Tasks (In Progress) | Zero Days Float | Negative Float | CP Logic Density™ | Newly Critical Activities (SN05) | Activities No Longer Critical (SN06) | Score
27 | 33 | 1:05 | 6 | 6 | 85 | 79 | 27 | 0 | 74 | 0 | 2.12 | 0 | 1 | 1
68% | 83% | 0.22 | 25% | 15% | 60% | 59% | 34% | 0% | 72% | 0% |  | 0% | 1%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Normal Tasks) | Longest Path (Normal Tasks) | 27 | 68% | 27 | 63%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Tasks & Milestones) | Longest Path (Tasks & Milestones) | 33 | 83% | 34 | 79%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestone-to-Task Ratio (To-Go) | Critical Milestone-to-Task Ratio (To-Go) | 1:05 | 0.22 | 1:04 | 0.26
Ratio of the number of milestones to the number of normal activities. This number should not be less than 1:20.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Milestones (To-Go) | Critical Milestones (To-Go) | 6 | 25% | 7 | 28%
Number of critical milestones to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Longest Path (Milestones) | Longest Path (Milestones) | 6 | 15% | 7 | 16%
Activities that together form the longest path through to project completion.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 0 |  | 260 | Content Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0
FALSE |  | 0 |  | 410 | Program Deployment COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0
FALSE |  | 0 |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0
FALSE |  | 0 |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
FALSE |  | 0 |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | Standard | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks | Normal Tasks | 85 | 60% | 85 | 60%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 100 |  | 97 | Identify typical product usage scenarios | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0
FALSE |  | 100 |  | 96 | Identify typical customer types | Hard_File_updated | Standard | 1 | 0 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0
FALSE |  | 100 |  | 95 | Identify anticipated product problem points | Hard_File_updated | Standard | 27 | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | Normal | Complete | 0
FALSE |  | 100 |  | 400 | Build customer service programs | Hard_File_updated | Standard | 1 | 0 | 2026-07-28 | 2026-07-29 | 2026-08-18 | 2026-08-19 | Normal | Complete | 0
FALSE |  | 100 |  | 399 | Perform subject matter expert review | Hard_File_updated | Standard | 5 | 0 | 2026-07-29 | 2026-07-31 | 2026-08-19 | 2026-08-21 | Normal | Complete | 0
FALSE |  | 100 |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | Standard | 8 | 0 | 2026-07-31 | 2026-08-06 | 2026-08-21 | 2026-08-27 | Normal | Complete | 0
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Normal Tasks (To-Go) | Normal Tasks (To-Go) | 79 | 59% | 85 | 60%
Number of normal activities within a grouping.
Excluded | Created | Percent Complete | Notes | Id | Description | Project | Calendar | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Total Float
FALSE |  | 60 |  | 187 | Determine required skill sets for various support options | Hard_File_updated | Standard | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 0
FALSE |  | 0 |  | 94 | Determine solutions for product points | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | Normal | Planned | 2
FALSE |  | 0 |  | 157 | Document product review results | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | Normal | Planned | 3
FALSE |  | 0 |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0
FALSE |  | 0 |  | 384 | Determine business objectives of support services | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 53
FALSE |  | 0 |  | 211 | Review output of product review phase | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | Normal | Planned | 3
FALSE |  | 0 |  | 180 | Online support | Hard_File_updated | Standard | 1 | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | Normal | Planned | 13
FALSE |  | 0 |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0
FALSE |  | 0 |  | 385 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-17 | 2026-08-18 | Normal | Planned | 53
FALSE |  | 0 |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-18 | 2026-08-19 | Normal | Planned | 37
FALSE |  | 0 |  | 179 | Phone support | Hard_File_updated | Standard | 1 | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | Normal | Planned | 12
FALSE |  | 0 |  | 99 | Estimate resource requirements | Hard_File_updated | Standard | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0
FALSE |  | 0 |  | 178 | On-site support | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 131 | Estimate effort to hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 321 | Determine technology budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-21 | 2026-08-19 | 2026-08-21 | Normal | Planned | 37
FALSE |  | 0 |  | 189 | Identify types of problems to be solved | Hard_File_updated | Standard | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | Normal | Planned | 11
FALSE |  | 0 |  | 188 | Identify service delivery options | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | Normal | Planned | 11
FALSE |  | 0 |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0
FALSE |  | 0 |  | 402 | Revise programs and related processes | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-27 | 2026-08-27 | Normal | Planned | 22
FALSE |  | 0 |  | 200 | Determine product-specific training needs | Hard_File_updated | Standard | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0
FALSE |  | 0 |  | 386 | Determine cost efficiency standards | Hard_File_updated | Standard | 1 | 1 | 2026-08-21 | 2026-08-21 | 2026-08-18 | 2026-08-18 | Normal | Planned | 54
FALSE |  | 0 |  | 241 | Determine methods for delivering training | Hard_File_updated | Standard | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 403 | Acquire executive sign-off | Hard_File_updated | Standard | 4 | 4 | 2026-08-21 | 2026-10-06 | 2026-09-22 | 2026-10-08 | Normal | Planned | 22
FALSE |  | 0 |  | 249 | Determine form factor for training content | Hard_File_updated | Standard | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0
FALSE |  | 0 |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0
FALSE |  | 0 |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 38
FALSE |  | 0 |  | 254 | Determine training course topics | Hard_File_updated | Standard | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 301 | Determine number of training courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 1
FALSE |  | 0 |  | 282 | Design student materials | Hard_File_updated | Standard | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0
FALSE |  | 0 |  | 398 | Test technology infrastructure | Hard_File_updated | Standard | 2 | 2 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 | Normal | Planned | 39
FALSE |  | 0 |  | 255 | Draft description of training program/courses | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 1
FALSE |  | 0 |  | 303 | Draft content development budget | Hard_File_updated | Standard | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0
FALSE |  | 0 |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | Standard | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0
FALSE |  | 0 |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0
FALSE |  | 0 |  | 408 | Deploy technology infrastructure | Hard_File_updated | Standard | 1 | 1 | 2026-08-28 | 2026-08-31 | 2026-08-28 | 2026-08-31 | Normal | Planned | 38
FALSE |  | 0 |  | 290 | Review expertise of potential vendors | Hard_File_updated | Standard | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0
FALSE |  | 0 |  | 291 | Review cost | Hard_File_updated | Standard | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0
FALSE |  | 0 |  | 295 | Review service levels | Hard_File_updated | Standard | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0
FALSE |  | 0 |  | 296 | Review customer references | Hard_File_updated | Standard | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0
FALSE |  | 0 |  | 292 | Determine time required to ready external trainers | Hard_File_updated | Standard | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0
FALSE |  | 0 |  | 294 | Make outsourcing decision | Hard_File_updated | Standard | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0
FALSE |  | 0 |  | 261 | Create training delivery schedule | Hard_File_updated | Standard | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0
FALSE |  | 0 |  | 281 | Determine training delivery locations | Hard_File_updated | Standard | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0
FALSE |  | 0 |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | Standard | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0
FALSE |  | 0 |  | 267 | Develop training delivery budget | Hard_File_updated | Standard | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0
FALSE |  | 0 |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | Standard | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0
FALSE |  | 0 |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | Standard | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0
FALSE |  | 0 |  | 276 | Draft Overall Budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0
FALSE |  | 0 |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | Standard | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0
FALSE |  | 0 |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | Standard | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0
FALSE |  | 0 |  | 223 | Assemble content development team | Hard_File_updated | Standard | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0
FALSE |  | 0 |  | 222 | Define roles and responsibilities | Hard_File_updated | Standard | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0
FALSE |  | 0 |  | 253 | Create content development schedule | Hard_File_updated | Standard | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 244 | Review existing intellectual property | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0
FALSE |  | 0 |  | 257 | Develop beta content | Hard_File_updated | Standard | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 228 | Perform SME review of training content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 258 | Revise and update content | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0
FALSE |  | 0 |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | Standard | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0
FALSE |  | 0 |  | 229 | Acquire final content approval | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0
FALSE |  | 0 |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | Standard | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0
FALSE |  | 0 |  | 264 | Create proficiency exams | Hard_File_updated | Standard | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0
FALSE |  | 0 |  | 262 | Train additional trainers | Hard_File_updated | Standard | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0
FALSE |  | 0 |  | 269 | Prepare training venues | Hard_File_updated | Standard | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0
FALSE |  | 0 |  | 270 | Create communications plan | Hard_File_updated | Standard | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0
FALSE |  | 0 |  | 272 | Provide new hires with information on training program | Hard_File_updated | Standard | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0
FALSE |  | 0 |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | Standard | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0
FALSE |  | 0 |  | 49 | Hire new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0
FALSE |  | 0 |  | 34 | Train new resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0
FALSE |  | 0 |  | 389 | Certify new resources | Hard_File_updated | Standard | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0
FALSE |  | 0 |  | 409 | Deploy new customer service programs | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0
FALSE |  | 0 |  | 13 | Determine success metrics | Hard_File_updated | Standard | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | Standard | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0
FALSE |  | 0 |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | Aspose.Tasks.Calendar | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0
FALSE |  | 0 |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | Standard | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0
FALSE |  | 0 |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | Standard | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0
FALSE |  | 0 |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | Standard | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0
FALSE |  | 0 |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | Standard | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Tasks (To-Go) | Critical Tasks (To-Go) | 27 | 34% | 27 | 32%
Number of critical activities to-go.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Critical Tasks (In Progress) | Critical Tasks (In Progress) | 0 | 0% | 0 | 0%
Number of critical activities to-go.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Zero Days Float | Zero Days Float | 74 | 72% | 78 | 71%
Total number of activities with 0 days float.
Excluded | Critical | Notes | Id | Description | Project | Original Duration | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Type | Status | Percent Complete | Total Float
FALSE | FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 15 | 6 | 2026-08-05 | 2026-08-17 | 2026-08-05 | 2026-08-14 | Normal | InProgress | 60 | 0
FALSE | FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-17 | 2026-08-17 | 2026-08-14 | 2026-08-14 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 0 | 2026-08-19 | 2026-08-19 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 1 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 1 | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2 | 2026-08-21 | 2026-08-22 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 1 | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 1 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 1 | 2026-08-27 | 2026-08-27 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 1 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 5 | 2026-08-31 | 2026-09-04 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 1 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-11 | 2026-09-11 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 1 | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 1 | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 4 | 2026-09-17 | 2026-09-22 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 1 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 0 | 2026-09-24 | 2026-09-24 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 1 | 2026-09-24 | 2026-09-25 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 1 | 2026-09-25 | 2026-09-28 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 1 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 0 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE | FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 1 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 1 | 2026-09-30 | 2026-10-01 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 1 | 2026-10-01 | 2026-10-02 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 257 | Develop beta content | Hard_File_updated | 1 | 1 | 2026-10-02 | 2026-10-03 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 258 | Revise and update content | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-03 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 1 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 1 | 2026-10-05 | 2026-10-06 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 4 | 2026-10-06 | 2026-10-07 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE | FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 1 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 1 | 2026-10-08 | 2026-10-09 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 270 | Create communications plan | Hard_File_updated | 3 | 3 | 2026-10-09 | 2026-10-13 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 49 | Hire new resources | Hard_File_updated | 1 | 1 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 34 | Train new resources | Hard_File_updated | 1 | 1 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 389 | Certify new resources | Hard_File_updated | 3 | 3 | 2026-10-20 | 2026-10-22 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 1 | 2026-10-23 | 2026-10-26 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 1 | 2026-10-26 | 2026-10-29 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 1 | 2026-10-29 | 2026-10-30 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 0 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 1 | 2026-10-30 | 2026-11-02 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 1 | 2026-11-02 | 2026-11-03 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 6 | 2 | 2026-11-03 | 2026-11-05 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE | TRUE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE | TRUE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 0 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Negative Float | Negative Float | 0 | 0% | 0 | 0%
Number of activities with total finish float less than 0 working days.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
CP Logic Density™ | CP Logic Density™ | 2.12 |  | 2.21
The average number of logic links per activity.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Newly Critical Activities | Newly Critical Activities | 0 | 0% | 0 | 0%
How many remaining activities were added to the critical path this period
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Activities No Longer Critical | Activities No Longer Critical | 1 | 1% | 0 | 0%
How many remaining activities are no longer on the critical path this period.
Id | Description | Critical | Previous_Critical | Original Duration | Remaining Duration | Start | Finish | Type | Status | Percent Complete | Total Float | Project
147 | Product Review COMPLETE | FALSE | TRUE | 0 | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 3 | Hard_File_updated

## Advanced
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | Advanced
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Advanced
Baseline Compliance
Ribbons | Hard_File | 0
Ribbons | Hard_File_updated | 1
|  | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance
|  | Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Score
Ribbons | Hard_File | 2026-07-07 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | N/A | 0
Ribbons |  |  | 0% | N/A | N/A | N/A |  | 0% | N/A | N/A | N/A
Ribbons | Hard_File_updated | 2026-08-11 | 11 | 2 | 1 | 8 | 18% | 12 | 4 | 0 | 8 | 33% | 1
Ribbons |  |  | 13% | 18% | 9% | 73% |  | 14% | 33% | 0% | 67%

## Advanced-Baseline-Compliance
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | Advanced -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance | Baseline Compliance
Time Now | Forecast to be Finished | Completed On Time | Completed Late | Not Completed | Baseline Finish Compliance | Forecast to be Started | Started On Time | Started Late | Not Started | Baseline Start Compliance | Score
2026-08-11 | 11 | 2 | 1 | 8 | 18% | 12 | 4 | 0 | 8 | 33% | 1
| 13% | 18% | 9% | 73% |  | 14% | 33% | 0% | 67%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Time Now | Time Now | 2026-08-11 |  | 2026-07-07
Current Project Time Now
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Forecast to be Finished | Forecast to be Finished | 11 | 13% | 0 | 0%
Forecast to be finished before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
97 | Identify typical product usage scenarios | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-08-11 | Normal | Complete | 100
96 | Identify typical customer types | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 2026-08-11 | Normal | Complete | 100
95 | Identify anticipated product problem points | Hard_File_updated | 0 | 2026-07-09 | 2026-07-09 | 2026-07-28 | 2026-07-23 | 2026-08-11 | Normal | Complete | 100
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-07-23 | 2026-08-12 | 2026-07-23 | 2026-08-11 | Normal | Planned | 0
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-07-23 | 2026-08-17 | 2026-07-24 | 2026-08-11 | Normal | Planned | 0
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-01 | 2026-08-11 | Normal | Planned | 0
180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-03 | 2026-08-19 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-03 | 2026-08-19 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-04 | 2026-08-20 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-04 | 2026-08-20 | 2026-08-05 | 2026-08-11 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed On Time | Completed On Time | 2 | 18% | 0
Activities actually completed on time, by their baseline finish date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
97 | Identify typical product usage scenarios | Hard_File_updated | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete
96 | Identify typical customer types | Hard_File_updated | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | Normal | Complete
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Late | Completed Late | 1 | 9% | 0
Activities actually completed but late, after their baseline finish date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-09 | 2026-07-09 | 2026-07-28 | 2026-07-23 | Normal | Complete
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Not Completed | Not Completed | 8 | 73% | 0
Activities that were planned to be complete by now that are not complete.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-07-23 | 2026-08-12 | 2026-07-23 | Normal | Planned
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-07-23 | 2026-08-17 | 2026-07-24 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-01 | Normal | Planned
180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-03 | Normal | Planned
179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-03 | 2026-08-19 | 2026-08-03 | Normal | Planned
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-03 | 2026-08-19 | 2026-08-04 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-04 | 2026-08-20 | 2026-08-04 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-04 | 2026-08-20 | 2026-08-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baseline Finish Compliance | Baseline Finish Compliance | 18% |  | N/A
Percentage of those activities forecast to be finished before time now that were finished on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
95 | Identify anticipated product problem points | Hard_File_updated | 0 | 2026-07-09 | 2026-07-28 | 2026-07-09 | 2026-07-23 | 2026-08-11 | Normal | Complete | 100
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | 2026-08-11 | Normal | Planned | 0
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | 2026-08-11 | Normal | Planned | 0
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | 2026-08-11 | Normal | Planned | 0
180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | 2026-08-11 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Forecast to be Started | Forecast to be Started | 12 | 14% | 0 | 0%
Forecast to be started before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
97 | Identify typical product usage scenarios | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-08-11 | Normal | Complete | 100
96 | Identify typical customer types | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | 2026-08-11 | Normal | Complete | 100
95 | Identify anticipated product problem points | Hard_File_updated | 0 | 2026-07-09 | 2026-07-09 | 2026-07-28 | 2026-07-23 | 2026-08-11 | Normal | Complete | 100
187 | Determine required skill sets for various support options | Hard_File_updated | 6 | 2026-08-05 | 2026-08-05 | 2026-08-17 | 2026-08-14 | 2026-08-11 | Normal | InProgress | 60
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-07-23 | 2026-08-12 | 2026-07-23 | 2026-08-11 | Normal | Planned | 0
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-07-23 | 2026-08-17 | 2026-07-24 | 2026-08-11 | Normal | Planned | 0
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-01 | 2026-08-11 | Normal | Planned | 0
180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-03 | 2026-08-19 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-03 | 2026-08-19 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-04 | 2026-08-20 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-04 | 2026-08-20 | 2026-08-05 | 2026-08-11 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started On Time | Started On Time | 4 | 33% | 0
Activities actually started on time, by their baseline start date.
Id | Description | Project | Start | Baseline Start | Finish | Baseline Finish | Type | Status
97 | Identify typical product usage scenarios | Hard_File_updated | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-07-08 | Normal | Complete
96 | Identify typical customer types | Hard_File_updated | 2026-07-08 | 2026-07-08 | 2026-07-09 | 2026-07-09 | Normal | Complete
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-09 | 2026-07-09 | 2026-07-28 | 2026-07-23 | Normal | Complete
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-05 | 2026-08-05 | 2026-08-17 | 2026-08-14 | Normal | InProgress
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Late | Started Late | 0 | 0% | 0
Activities actually started but late, after their baseline start date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Not Started | Not Started | 8 | 67% | 0
Activities that were planned to be start by now that are not started.
Id | Description | Project | Remaining Duration | Start | Baseline Start | Finish | Baseline Finish | Type | Activity Status
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-07-23 | 2026-08-12 | 2026-07-23 | Normal | Planned
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-07-23 | 2026-08-17 | 2026-07-24 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-01 | Normal | Planned
180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 | 2026-08-18 | 2026-08-03 | Normal | Planned
179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-03 | 2026-08-19 | 2026-08-03 | Normal | Planned
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-03 | 2026-08-19 | 2026-08-04 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-04 | 2026-08-20 | 2026-08-04 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-04 | 2026-08-20 | 2026-08-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Baseline Start Compliance | Baseline Start Compliance | 33% |  | N/A
Percentage of those activities forecast to be started before time now that were started on time.
Id | Description | Project | Remaining Duration | Start | Finish | Baseline Start | Baseline Finish | Project Time Now | Type | Status | Percent Complete
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-08-12 | 2026-07-23 | 2026-07-23 | 2026-08-11 | Normal | Planned | 0
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | 2026-07-23 | 2026-07-24 | 2026-08-11 | Normal | Planned | 0
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-01 | 2026-08-11 | Normal | Planned | 0
180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | 2026-07-31 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-19 | 2026-08-03 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-19 | 2026-08-03 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-20 | 2026-08-04 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-20 | 2026-08-04 | 2026-08-05 | 2026-08-11 | Normal | Planned | 0

## Industry-Standards
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | Industry Standards
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Industry Standards
|  | Schedule Execution Metrics (SEM) | Half Step Delay Analysis
Ribbons | Hard_File | 60 | 0
Ribbons | Hard_File_updated | 50 | 0
|  | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM)
|  | Completed Activities (1) | Workoff Burden (SEM01) | BRI Current (SEM02) | BRI Cumulative (SEM03) | BPI Current (SEM04) | BEI Current (SEM05) | BEI Cumulative (SEM06) | TC-BEI (SEM07) | FRI Current (SEM08) | Delta (BEI vs TC-BEI) (SEM09) | Score
Ribbons | Hard_File | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | N/A | -1 | 60
Ribbons |  |  | N/A
Ribbons | Hard_File_updated | 6 | 0 | 0.11 | 0.27 | 0.11 | 0.11 | 0.27 | 1.11 | 0.11 | -0.67 | 50
Ribbons |  |  | 0%
|  | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis
|  | Time Now (HSD01) | Label (HSD02) | Forecast to be Started but not Started yet (HSD03) | Started Late (HSD04) | Forecast to be Finished but not Finished yet (HSD05) | Finished Late (HSD06) | Total days delay in the half step (Days) (HSD06) | Total days delay in the full update (Days) (HSD07) | Total days ahead in the half step (Days) (HSD08) | Total days ahead in the full update (Days) (HSD09) | Cumulative Finish Impact (Days) (HSD10) | Net Finish Impact (Days) (HSD10) | Project Finish (HSD20) | Score
Ribbons | Hard_File | 2026-07-07 | N/A | 0 | 0 | 0 | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 2026-11-05 | 0
Ribbons |  |  |  | 0% | N/A | 0% | N/A
Ribbons | Hard_File_updated | 2026-08-11 | N/A | 8 | 0 | 8 | 1 | N/A | 190 | N/A | 73 | -117 | 0 | 2026-11-05 | 0
Ribbons |  |  |  | 9% | 0% | 9% | 9%

## Industry-Standards-Schedule-Ex
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | Industry-Standards -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM) | Schedule Execution Metrics (SEM)
Completed Activities (1) | Workoff Burden (SEM01) | BRI Current (SEM02) | BRI Cumulative (SEM03) | BPI Current (SEM04) | BEI Current (SEM05) | BEI Cumulative (SEM06) | TC-BEI (SEM07) | FRI Current (SEM08) | Delta (BEI vs TC-BEI) (SEM09) | Score
6 | 0 | 0.11 | 0.27 | 0.11 | 0.11 | 0.27 | 1.11 | 0.11 | -0.67 | 50
0%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Completed Activities | Completed Activities | 6 |  | N/A
Total count of completed activities to date.
Id | Description | Project | ProjectTimeNowMinus30Days | Baseline Finish | Actual Finish | Project Time Now | Type
97 | Identify typical product usage scenarios | Hard_File_updated | 2026-07-12 | 2026-07-08 | 2026-07-08 | 2026-08-11 | Normal
96 | Identify typical customer types | Hard_File_updated | 2026-07-12 | 2026-07-09 | 2026-07-09 | 2026-08-11 | Normal
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-12 | 2026-07-23 | 2026-07-28 | 2026-08-11 | Normal
400 | Build customer service programs | Hard_File_updated | 2026-07-12 | 2026-08-19 | 2026-07-29 | 2026-08-11 | Normal
399 | Perform subject matter expert review | Hard_File_updated | 2026-07-12 | 2026-08-21 | 2026-07-31 | 2026-08-11 | Normal
401 | Perform user acceptance testing with customers | Hard_File_updated | 2026-07-12 | 2026-08-27 | 2026-08-06 | 2026-08-11 | Normal
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Workoff Burden | Workoff Burden | 0 | 0% | N/A
Workoff 30 Day Window
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BRI Current | BRI Current | 0.11 |  | N/A
Current Baseline Realism Index (BRI) - Is the contractor executing the plan?
Id | Description | Project | Baseline Finish | Finish | Actual Finish | ProjectTimeNowMinus30Days | Project Time Now | Type | Status
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-23 | 2026-07-28 | 2026-07-28 | 2026-07-12 | 2026-08-11 | Normal | Complete
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BRI Cumulative | BRI Cumulative | 0.27 |  | N/A
Current Baseline Realism Index (BRI) - Is the contractor executing the plan?
Id | Description | Project | Baseline Finish | Finish | Actual Finish | Project Time Now | Type | Status
97 | Identify typical product usage scenarios | Hard_File_updated | 2026-07-08 | 2026-07-08 | 2026-07-08 | 2026-08-11 | Normal | Complete
96 | Identify typical customer types | Hard_File_updated | 2026-07-09 | 2026-07-09 | 2026-07-09 | 2026-08-11 | Normal | Complete
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-23 | 2026-07-28 | 2026-07-28 | 2026-08-11 | Normal | Complete
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BPI Current | BPI Current | 0.11 |  | N/A
Current Baseline Progress Index (BPI) - Is the contractor keeping up with planned work?
Id | Description | Project | Baseline Finish | Finish | Actual Finish | Project Time Now | Type | Status
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-23 | 2026-07-28 | 2026-07-28 | 2026-08-11 | Normal | Complete
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI Current | BEI Current | 0.11 |  | N/A
Current Baseline Execution Index (BEI)
Id | Description | Project | ProjectTimeNowMinus30Days | Baseline Finish | Actual Finish | Project Time Now | Type | Status
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-12 | 2026-07-23 | 2026-07-28 | 2026-08-11 | Normal | Complete
94 | Determine solutions for product points | Hard_File_updated | 2026-07-12 | 2026-07-23 |  | 2026-08-11 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-07-12 | 2026-07-24 |  | 2026-08-11 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-07-12 | 2026-08-01 |  | 2026-08-11 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-07-12 | 2026-08-03 |  | 2026-08-11 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-07-12 | 2026-08-03 |  | 2026-08-11 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-07-12 | 2026-08-04 |  | 2026-08-11 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-07-12 | 2026-08-04 |  | 2026-08-11 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-07-12 | 2026-08-05 |  | 2026-08-11 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
BEI Cumulative | BEI Cumulative | 0.27 |  | N/A
Cumulative Baseline Execution Index (BEI)
Id | Description | Project | ProjectTimeNowMinus30Days | Baseline Finish | Actual Finish | Project Time Now | Type | Status
97 | Identify typical product usage scenarios | Hard_File_updated | 2026-07-12 | 2026-07-08 | 2026-07-08 | 2026-08-11 | Normal | Complete
96 | Identify typical customer types | Hard_File_updated | 2026-07-12 | 2026-07-09 | 2026-07-09 | 2026-08-11 | Normal | Complete
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-12 | 2026-07-23 | 2026-07-28 | 2026-08-11 | Normal | Complete
94 | Determine solutions for product points | Hard_File_updated | 2026-07-12 | 2026-07-23 |  | 2026-08-11 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-07-12 | 2026-07-24 |  | 2026-08-11 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-07-12 | 2026-08-01 |  | 2026-08-11 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-07-12 | 2026-08-03 |  | 2026-08-11 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-07-12 | 2026-08-03 |  | 2026-08-11 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-07-12 | 2026-08-04 |  | 2026-08-11 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-07-12 | 2026-08-04 |  | 2026-08-11 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-07-12 | 2026-08-05 |  | 2026-08-11 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
TC-BEI | TC-BEI | 1.11 |  | 1
To-Complete Baseline Execution Index (TC-BEI)
Id | Description | Project | Project Time Now | Baseline Finish | Actual Finish | Finish | Type | Status
187 | Determine required skill sets for various support options | Hard_File_updated | 2026-08-11 | 2026-08-14 |  | 2026-08-17 | Normal | InProgress
94 | Determine solutions for product points | Hard_File_updated | 2026-08-11 | 2026-07-23 |  | 2026-08-12 | Normal | Planned
157 | Document product review results | Hard_File_updated | 2026-08-11 | 2026-07-24 |  | 2026-08-17 | Normal | Planned
323 | Service Planning & Design COMPLETE | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
384 | Determine business objectives of support services | Hard_File_updated | 2026-08-11 | 2026-08-17 |  | 2026-08-17 | Normal | Planned
211 | Review output of product review phase | Hard_File_updated | 2026-08-11 | 2026-08-01 |  | 2026-08-18 | Normal | Planned
180 | Online support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-18 | Normal | Planned
98 | Estimate demand for customer support (all options) | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
385 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-18 | Normal | Planned
379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
179 | Phone support | Hard_File_updated | 2026-08-11 | 2026-08-03 |  | 2026-08-19 | Normal | Planned
99 | Estimate resource requirements | Hard_File_updated | 2026-08-11 | 2026-08-19 |  | 2026-08-19 | Normal | Planned
178 | On-site support | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-19 | Normal | Planned
131 | Estimate effort to hire new resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
321 | Determine technology budget | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-11 | 2026-08-04 |  | 2026-08-20 | Normal | Planned
188 | Identify service delivery options | Hard_File_updated | 2026-08-11 | 2026-08-05 |  | 2026-08-20 | Normal | Planned
210 | Review anticipated skill sets of support resources | Hard_File_updated | 2026-08-11 | 2026-08-20 |  | 2026-08-20 | Normal | Planned
402 | Revise programs and related processes | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-21 | Normal | Planned
200 | Determine product-specific training needs | Hard_File_updated | 2026-08-11 | 2026-08-21 |  | 2026-08-21 | Normal | Planned
386 | Determine cost efficiency standards | Hard_File_updated | 2026-08-11 | 2026-08-18 |  | 2026-08-21 | Normal | Planned
241 | Determine methods for delivering training | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
403 | Acquire executive sign-off | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-06 | Normal | Planned
249 | Determine form factor for training content | Hard_File_updated | 2026-08-11 | 2026-08-22 |  | 2026-08-22 | Normal | Planned
251 | Identify internal resources that can review training materials | Hard_File_updated | 2026-08-11 | 2026-08-24 |  | 2026-08-24 | Normal | Planned
396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
254 | Determine training course topics | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
301 | Determine number of training courses | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
282 | Design student materials | Hard_File_updated | 2026-08-11 | 2026-08-25 |  | 2026-08-25 | Normal | Planned
398 | Test technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
255 | Draft description of training program/courses | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
303 | Draft content development budget | Hard_File_updated | 2026-08-11 | 2026-08-26 |  | 2026-08-26 | Normal | Planned
199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 2026-08-11 | 2026-08-27 |  | 2026-08-27 | Normal | Planned
268 | Determine whether additional trainers will be needed | Hard_File_updated | 2026-08-11 | 2026-08-28 |  | 2026-08-28 | Normal | Planned
408 | Deploy technology infrastructure | Hard_File_updated | 2026-08-11 | 2026-08-31 |  | 2026-08-31 | Normal | Planned
290 | Review expertise of potential vendors | Hard_File_updated | 2026-08-11 | 2026-09-04 |  | 2026-09-04 | Normal | Planned
291 | Review cost | Hard_File_updated | 2026-08-11 | 2026-09-07 |  | 2026-09-07 | Normal | Planned
295 | Review service levels | Hard_File_updated | 2026-08-11 | 2026-09-08 |  | 2026-09-08 | Normal | Planned
296 | Review customer references | Hard_File_updated | 2026-08-11 | 2026-09-09 |  | 2026-09-09 | Normal | Planned
292 | Determine time required to ready external trainers | Hard_File_updated | 2026-08-11 | 2026-09-10 |  | 2026-09-10 | Normal | Planned
294 | Make outsourcing decision | Hard_File_updated | 2026-08-11 | 2026-09-11 |  | 2026-09-11 | Normal | Planned
261 | Create training delivery schedule | Hard_File_updated | 2026-08-11 | 2026-09-14 |  | 2026-09-14 | Normal | Planned
281 | Determine training delivery locations | Hard_File_updated | 2026-08-11 | 2026-09-15 |  | 2026-09-15 | Normal | Planned
289 | Review outsourcing options - event logistics | Hard_File_updated | 2026-08-11 | 2026-09-16 |  | 2026-09-16 | Normal | Planned
267 | Develop training delivery budget | Hard_File_updated | 2026-08-11 | 2026-09-22 |  | 2026-09-22 | Normal | Planned
278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 2026-08-11 | 2026-09-23 |  | 2026-09-23 | Normal | Planned
302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 2026-08-11 | 2026-09-24 |  | 2026-09-24 | Normal | Planned
276 | Draft Overall Budget | Hard_File_updated | 2026-08-11 | 2026-09-25 |  | 2026-09-25 | Normal | Planned
275 | Acquire executive sign-off on budget | Hard_File_updated | 2026-08-11 | 2026-09-28 |  | 2026-09-28 | Normal | Planned
307 | Acquire executive sign-off on training plans | Hard_File_updated | 2026-08-11 | 2026-09-29 |  | 2026-09-29 | Normal | Planned
223 | Assemble content development team | Hard_File_updated | 2026-08-11 | 2026-09-30 |  | 2026-09-30 | Normal | Planned
222 | Define roles and responsibilities | Hard_File_updated | 2026-08-11 | 2026-10-01 |  | 2026-10-01 | Normal | Planned
253 | Create content development schedule | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
244 | Review existing intellectual property | Hard_File_updated | 2026-08-11 | 2026-10-02 |  | 2026-10-02 | Normal | Planned
257 | Develop beta content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
228 | Perform SME review of training content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
258 | Revise and update content | Hard_File_updated | 2026-08-11 | 2026-10-03 |  | 2026-10-03 | Normal | Planned
140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 2026-08-11 | 2026-10-04 |  | 2026-10-04 | Normal | Planned
229 | Acquire final content approval | Hard_File_updated | 2026-08-11 | 2026-10-05 |  | 2026-10-05 | Normal | Planned
274 | Create additional "train the trainer" learning materials | Hard_File_updated | 2026-08-11 | 2026-10-06 |  | 2026-10-06 | Normal | Planned
264 | Create proficiency exams | Hard_File_updated | 2026-08-11 | 2026-10-07 |  | 2026-10-07 | Normal | Planned
262 | Train additional trainers | Hard_File_updated | 2026-08-11 | 2026-10-08 |  | 2026-10-08 | Normal | Planned
269 | Prepare training venues | Hard_File_updated | 2026-08-11 | 2026-10-09 |  | 2026-10-09 | Normal | Planned
270 | Create communications plan | Hard_File_updated | 2026-08-11 | 2026-10-13 |  | 2026-10-13 | Normal | Planned
272 | Provide new hires with information on training program | Hard_File_updated | 2026-08-11 | 2026-10-14 |  | 2026-10-14 | Normal | Planned
310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 2026-08-11 | 2026-10-15 |  | 2026-10-15 | Normal | Planned
49 | Hire new resources | Hard_File_updated | 2026-08-11 | 2026-10-16 |  | 2026-10-16 | Normal | Planned
34 | Train new resources | Hard_File_updated | 2026-08-11 | 2026-10-19 |  | 2026-10-19 | Normal | Planned
389 | Certify new resources | Hard_File_updated | 2026-08-11 | 2026-10-22 |  | 2026-10-22 | Normal | Planned
409 | Deploy new customer service programs | Hard_File_updated | 2026-08-11 | 2026-10-23 |  | 2026-10-23 | Normal | Planned
13 | Determine success metrics | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
7 | Create method for tracking common problems and solutions | Hard_File_updated | 2026-08-11 | 2026-10-26 |  | 2026-10-26 | Normal | Planned
14 | Create method to track support issues vs. product aspects | Hard_File_updated | 2026-08-11 | 2026-10-29 |  | 2026-10-29 | Normal | Planned
141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
36 | Monitor customer support issues - look for common problems | Hard_File_updated | 2026-08-11 | 2026-10-30 |  | 2026-10-30 | Normal | Planned
9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 2026-08-11 | 2026-11-02 |  | 2026-11-02 | Normal | Planned
145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 2026-08-11 | 2026-11-03 |  | 2026-11-03 | Normal | Planned
146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2026-08-11 | 2026-11-05 |  | 2026-11-05 | Normal | Planned
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
FRI Current | FRI Current | 0.11 |  | N/A
Forecast Realism Index (FRI)
Id | Description | Project | PreviousFinish | Finish | Actual Finish | Project Time Now | Type | Status | ProjectTimeNowMinus30Days
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-23 | 2026-07-28 | 2026-07-28 | 2026-08-11 | Normal | Complete | 2026-07-12
94 | Determine solutions for product points | Hard_File_updated | 2026-07-23 | 2026-08-12 |  | 2026-08-11 | Normal | Planned | 2026-07-12
157 | Document product review results | Hard_File_updated | 2026-07-24 | 2026-08-17 |  | 2026-08-11 | Normal | Planned | 2026-07-12
211 | Review output of product review phase | Hard_File_updated | 2026-08-01 | 2026-08-18 |  | 2026-08-11 | Normal | Planned | 2026-07-12
180 | Online support | Hard_File_updated | 2026-08-03 | 2026-08-18 |  | 2026-08-11 | Normal | Planned | 2026-07-12
179 | Phone support | Hard_File_updated | 2026-08-03 | 2026-08-19 |  | 2026-08-11 | Normal | Planned | 2026-07-12
178 | On-site support | Hard_File_updated | 2026-08-04 | 2026-08-19 |  | 2026-08-11 | Normal | Planned | 2026-07-12
189 | Identify types of problems to be solved | Hard_File_updated | 2026-08-04 | 2026-08-20 |  | 2026-08-11 | Normal | Planned | 2026-07-12
188 | Identify service delivery options | Hard_File_updated | 2026-08-05 | 2026-08-20 |  | 2026-08-11 | Normal | Planned | 2026-07-12
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Delta (BEI vs TC-BEI) | Delta (BEI vs TC-BEI) | -0.67 |  | -1
Change in efficiency needed to achieve the forecast

## Industry-Standards-Half-Step-D
Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report | Fuse® Summary Metric Report
Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities | Hard_File_Fuse - 282 Activities
Program-Summary -> | Industry-Standards -> | Hard_File_updated: Detailed View
Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026 | Created on: 7/8/2026
Created by: dpolitte | Created by: dpolitte | Created by: dpolitte | Created by: dpolitte
Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View | Hard_File_updated: Detailed View
Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis | Half Step Delay Analysis
Time Now (HSD01) | Label (HSD02) | Forecast to be Started but not Started yet (HSD03) | Started Late (HSD04) | Forecast to be Finished but not Finished yet (HSD05) | Finished Late (HSD06) | Total days delay in the half step (Days) (HSD06) | Total days delay in the full update (Days) (HSD07) | Total days ahead in the half step (Days) (HSD08) | Total days ahead in the full update (Days) (HSD09) | Cumulative Finish Impact (Days) (HSD10) | Net Finish Impact (Days) (HSD10) | Project Finish (HSD20) | Score
2026-08-11 | N/A | 8 | 0 | 8 | 1 | N/A | 190 | N/A | 73 | -117 | 0 | 2026-11-05 | 0
|  | 9% | 0% | 9% | 9%
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Time Now | Time Now | 2026-08-11 |  | 2026-07-07
Current Project Time Now
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Label | Label | N/A |  | N/A
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Forecast to be Started but not Started yet | Forecast to be Started but not Started yet | 8 | 9% | 0 | 0%
Forecast to be started before time now
Id | Description | Project | Remaining Duration | Start | Baseline Start | Actual Start | Project Time Now | Type | Status | Percent Complete
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-07-23 |  | 2026-08-11 | Normal | Planned | 0
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-07-23 |  | 2026-08-11 | Normal | Planned | 0
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 |  | 2026-08-11 | Normal | Planned | 0
180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-07-31 |  | 2026-08-11 | Normal | Planned | 0
179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-03 |  | 2026-08-11 | Normal | Planned | 0
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-03 |  | 2026-08-11 | Normal | Planned | 0
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-04 |  | 2026-08-11 | Normal | Planned | 0
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-04 |  | 2026-08-11 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Started Late | Started Late | 0 | 0% | 0
Activities actually started but late, after their baseline start date.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Forecast to be Finished but not Finished yet | Forecast to be Finished but not Finished yet | 8 | 9% | 0 | 0%
Forecast to be finished before time now
Id | Description | Project | Remaining Duration | Finish | Baseline Finish | Project Time Now | Type | Status | Percent Complete
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-07-23 | 2026-08-11 | Normal | Planned | 0
157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-07-24 | 2026-08-11 | Normal | Planned | 0
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-18 | 2026-08-01 | 2026-08-11 | Normal | Planned | 0
180 | Online support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
179 | Phone support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-03 | 2026-08-11 | Normal | Planned | 0
178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-20 | 2026-08-04 | 2026-08-11 | Normal | Planned | 0
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-05 | 2026-08-11 | Normal | Planned | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Finished Late | Finished Late | 1 | 9% | 0
Activities actually completed but late, after their baseline finish date.
Id | Description | Project | Baseline Finish | Finish | FinishDelay | Type | Status
95 | Identify anticipated product problem points | Hard_File_updated | 2026-07-23 | 2026-07-28 | 5 | Normal | Complete
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total days delay in the half step (Days) | Total days delay in the half step (Days) | N/A |  | N/A
The total number of days activities are delayed due to the progress update in the half step.
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total days delay in the full update (Days) | Total days delay in the full update (Days) | 190 |  | 0
The total number of days activities are delayed due to the updated information on the fully updated schedule.
Id | Description | Project | Remaining Duration | PreviousFinish | Finish | DelayDays | Type | Status | FullStepLabel
95 | Identify anticipated product problem points | Hard_File_updated | 0 | 2026-07-23 | 2026-07-28 | 5 | Normal | Complete | Compared to previous snapshot
187 | Determine required skill sets for various support options | Hard_File_updated | 6 | 2026-08-14 | 2026-08-17 | 3 | Normal | InProgress | Compared to previous snapshot
94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-07-23 | 2026-08-12 | 20 | Normal | Planned | Compared to previous snapshot
157 | Document product review results | Hard_File_updated | 1 | 2026-07-24 | 2026-08-17 | 24 | Normal | Planned | Compared to previous snapshot
184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 2026-08-14 | 2026-08-17 | 3 | Milestone | Planned | Compared to previous snapshot
148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 2026-08-14 | 2026-08-17 | 3 | Milestone | Planned | Compared to previous snapshot
147 | Product Review COMPLETE | Hard_File_updated | 0 | 2026-07-31 | 2026-08-17 | 17 | Milestone | Planned | Compared to previous snapshot
211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-01 | 2026-08-18 | 17 | Normal | Planned | Compared to previous snapshot
180 | Online support | Hard_File_updated | 1 | 2026-08-03 | 2026-08-18 | 15 | Normal | Planned | Compared to previous snapshot
385 | Determine success metrics | Hard_File_updated | 1 | 2026-08-18 | 2026-08-18 | 0 | Normal | Planned | Compared to previous snapshot
179 | Phone support | Hard_File_updated | 1 | 2026-08-03 | 2026-08-19 | 16 | Normal | Planned | Compared to previous snapshot
178 | On-site support | Hard_File_updated | 1 | 2026-08-04 | 2026-08-19 | 15 | Normal | Planned | Compared to previous snapshot
189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-04 | 2026-08-20 | 16 | Normal | Planned | Compared to previous snapshot
181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 2026-08-04 | 2026-08-19 | 15 | Milestone | Planned | Compared to previous snapshot
188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-05 | 2026-08-20 | 15 | Normal | Planned | Compared to previous snapshot
386 | Determine cost efficiency standards | Hard_File_updated | 1 | 2026-08-18 | 2026-08-21 | 3 | Normal | Planned | Compared to previous snapshot
387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 2026-08-18 | 2026-08-21 | 3 | Milestone | Planned | Compared to previous snapshot
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total days ahead in the half step (Days) | Total days ahead in the half step (Days) | N/A |  | N/A
The number of days an activity is ahead due to progress on the half step scenario
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Total days ahead in the full update (Days) | Total days ahead in the full update (Days) | 73 |  | 0
The total number of days activities are ahead due to the updated information on the fully updated schedule.
Id | Description | Project | Remaining Duration | PreviousFinish | Finish | AccelerationDays | Type | Status | FullStepLabel
400 | Build customer service programs | Hard_File_updated | 0 | 2026-08-19 | 2026-07-29 | 21 | Normal | Complete | Compared to previous snapshot
399 | Perform subject matter expert review | Hard_File_updated | 0 | 2026-08-21 | 2026-07-31 | 21 | Normal | Complete | Compared to previous snapshot
401 | Perform user acceptance testing with customers | Hard_File_updated | 0 | 2026-08-27 | 2026-08-06 | 21 | Normal | Complete | Compared to previous snapshot
402 | Revise programs and related processes | Hard_File_updated | 1 | 2026-08-27 | 2026-08-21 | 6 | Normal | Planned | Compared to previous snapshot
403 | Acquire executive sign-off | Hard_File_updated | 4 | 2026-10-08 | 2026-10-06 | 2 | Normal | Planned | Compared to previous snapshot
404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 2026-10-08 | 2026-10-06 | 2 | Milestone | Planned | Compared to previous snapshot
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Cumulative Finish Impact (Days) | Cumulative Finish Impact (Days) | -117 |  | 0
Sum of the finish delays - the finish acceleration in days
Excluded | Notes | Id | Description | Project | Remaining Duration | Start | Finish | Type | Status | AccelerationDays | DelayDays
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 0 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 0 | 2026-07-09 | 2026-07-28 | Normal | Complete | 0 | 5
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 0 | 2026-07-28 | 2026-07-29 | Normal | Complete | 21 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 0 | 2026-07-29 | 2026-07-31 | Normal | Complete | 21 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 0 | 2026-07-31 | 2026-08-06 | Normal | Complete | 21 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 6 | 2026-08-05 | 2026-08-17 | Normal | InProgress | 0 | 3
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-08-12 | Normal | Planned | 0 | 20
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 3
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 3
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 17
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 17
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 15
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 16
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 15
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 16
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 2026-08-19 | 2026-08-19 | Milestone | Planned | 0 | 15
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 15
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 2026-08-20 | 2026-08-21 | Normal | Planned | 6 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 2026-08-21 | 2026-08-21 | Normal | Planned | 0 | 3
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 2026-08-21 | 2026-10-06 | Normal | Planned | 2 | 0
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 3
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 2026-10-06 | 2026-10-06 | Milestone | Planned | 2 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Net Finish Impact (Days) | Net Finish Impact (Days) | 0 |  | 0
Finish delay to the project
Excluded | Notes | Id | Description | Project | Remaining Duration | Start | Finish | Type | Status | AccelerationDays | DelayDays
FALSE |  | 97 | Identify typical product usage scenarios | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | Normal | Complete | 0 | 0
FALSE |  | 412 | Read the note for an explanation of the purpose of the template | Hard_File_updated | 0 | 2026-07-08 | 2026-07-08 | Milestone | Complete | 0 | 0
FALSE |  | 96 | Identify typical customer types | Hard_File_updated | 0 | 2026-07-08 | 2026-07-09 | Normal | Complete | 0 | 0
FALSE |  | 95 | Identify anticipated product problem points | Hard_File_updated | 0 | 2026-07-09 | 2026-07-28 | Normal | Complete | 0 | 5
FALSE |  | 400 | Build customer service programs | Hard_File_updated | 0 | 2026-07-28 | 2026-07-29 | Normal | Complete | 21 | 0
FALSE |  | 399 | Perform subject matter expert review | Hard_File_updated | 0 | 2026-07-29 | 2026-07-31 | Normal | Complete | 21 | 0
FALSE |  | 401 | Perform user acceptance testing with customers | Hard_File_updated | 0 | 2026-07-31 | 2026-08-06 | Normal | Complete | 21 | 0
FALSE |  | 187 | Determine required skill sets for various support options | Hard_File_updated | 6 | 2026-08-05 | 2026-08-17 | Normal | InProgress | 0 | 3
FALSE |  | 94 | Determine solutions for product points | Hard_File_updated | 1 | 2026-08-12 | 2026-08-12 | Normal | Planned | 0 | 20
FALSE |  | 157 | Document product review results | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 24
FALSE |  | 184 | Customer Service Level Design COMPLETE | Hard_File_updated | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 3
FALSE |  | 148 | Design of Support Services COMPLETE | Hard_File_updated | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 3
FALSE |  | 323 | Service Planning & Design COMPLETE | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 384 | Determine business objectives of support services | Hard_File_updated | 1 | 2026-08-17 | 2026-08-17 | Normal | Planned | 0 | 0
FALSE |  | 147 | Product Review COMPLETE | Hard_File_updated | 0 | 2026-08-17 | 2026-08-17 | Milestone | Planned | 0 | 17
FALSE |  | 211 | Review output of product review phase | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 17
FALSE |  | 180 | Online support | Hard_File_updated | 1 | 2026-08-17 | 2026-08-18 | Normal | Planned | 0 | 15
FALSE |  | 98 | Estimate demand for customer support (all options) | Hard_File_updated | 1 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 385 | Determine success metrics | Hard_File_updated | 1 | 2026-08-18 | 2026-08-18 | Normal | Planned | 0 | 0
FALSE |  | 379 | Build technology infrastructure plan (separate project plan required) | Hard_File_updated | 1 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 179 | Phone support | Hard_File_updated | 1 | 2026-08-18 | 2026-08-19 | Normal | Planned | 0 | 16
FALSE |  | 99 | Estimate resource requirements | Hard_File_updated | 0 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 0
FALSE |  | 178 | On-site support | Hard_File_updated | 1 | 2026-08-19 | 2026-08-19 | Normal | Planned | 0 | 15
FALSE |  | 131 | Estimate effort to hire new resources | Hard_File_updated | 1 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 321 | Determine technology budget | Hard_File_updated | 1 | 2026-08-19 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 189 | Identify types of problems to be solved | Hard_File_updated | 1 | 2026-08-19 | 2026-08-20 | Normal | Planned | 0 | 16
FALSE |  | 181 | Design of customer service contact scenarios COMPLETE | Hard_File_updated | 0 | 2026-08-19 | 2026-08-19 | Milestone | Planned | 0 | 15
FALSE |  | 188 | Identify service delivery options | Hard_File_updated | 1 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 15
FALSE |  | 149 | Resource Planning COMPLETE | Hard_File_updated | 0 | 2026-08-20 | 2026-08-20 | Milestone | Planned | 0 | 0
FALSE |  | 210 | Review anticipated skill sets of support resources | Hard_File_updated | 1 | 2026-08-20 | 2026-08-20 | Normal | Planned | 0 | 0
FALSE |  | 402 | Revise programs and related processes | Hard_File_updated | 1 | 2026-08-20 | 2026-08-21 | Normal | Planned | 6 | 0
FALSE |  | 200 | Determine product-specific training needs | Hard_File_updated | 1 | 2026-08-20 | 2026-08-21 | Normal | Planned | 0 | 0
FALSE |  | 386 | Determine cost efficiency standards | Hard_File_updated | 1 | 2026-08-21 | 2026-08-21 | Normal | Planned | 0 | 3
FALSE |  | 381 | Technology infrastructure planning COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 388 | Service Delivery Planning COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 216 | Training Needs Assessment COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 0
FALSE |  | 241 | Determine methods for delivering training | Hard_File_updated | 2 | 2026-08-21 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 403 | Acquire executive sign-off | Hard_File_updated | 4 | 2026-08-21 | 2026-10-06 | Normal | Planned | 2 | 0
FALSE |  | 387 | Business Performance Planning COMPLETE | Hard_File_updated | 0 | 2026-08-21 | 2026-08-21 | Milestone | Planned | 0 | 3
FALSE |  | 249 | Determine form factor for training content | Hard_File_updated | 1 | 2026-08-22 | 2026-08-22 | Normal | Planned | 0 | 0
FALSE |  | 251 | Identify internal resources that can review training materials | Hard_File_updated | 1 | 2026-08-24 | 2026-08-24 | Normal | Planned | 0 | 0
FALSE |  | 396 | Design and develop technology solution (separate schedule required) | Hard_File_updated | 1 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 254 | Determine training course topics | Hard_File_updated | 1 | 2026-08-24 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 301 | Determine number of training courses | Hard_File_updated | 1 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 282 | Design student materials | Hard_File_updated | 1 | 2026-08-25 | 2026-08-25 | Normal | Planned | 0 | 0
FALSE |  | 398 | Test technology infrastructure | Hard_File_updated | 2 | 2026-08-25 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 255 | Draft description of training program/courses | Hard_File_updated | 1 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 303 | Draft content development budget | Hard_File_updated | 1 | 2026-08-26 | 2026-08-26 | Normal | Planned | 0 | 0
FALSE |  | 300 | Content Development Planning COMPLETE | Hard_File_updated | 0 | 2026-08-26 | 2026-08-26 | Milestone | Planned | 0 | 0
FALSE |  | 199 | Identify internal resources that can serve as potential trainers | Hard_File_updated | 1 | 2026-08-27 | 2026-08-27 | Normal | Planned | 0 | 0
FALSE |  | 405 | Technology Infrastructure Development COMPLETE | Hard_File_updated | 0 | 2026-08-27 | 2026-08-27 | Milestone | Planned | 0 | 0
FALSE |  | 268 | Determine whether additional trainers will be needed | Hard_File_updated | 1 | 2026-08-28 | 2026-08-28 | Normal | Planned | 0 | 0
FALSE |  | 408 | Deploy technology infrastructure | Hard_File_updated | 1 | 2026-08-28 | 2026-08-31 | Normal | Planned | 0 | 0
FALSE |  | 290 | Review expertise of potential vendors | Hard_File_updated | 5 | 2026-08-31 | 2026-09-04 | Normal | Planned | 0 | 0
FALSE |  | 291 | Review cost | Hard_File_updated | 1 | 2026-09-07 | 2026-09-07 | Normal | Planned | 0 | 0
FALSE |  | 295 | Review service levels | Hard_File_updated | 1 | 2026-09-08 | 2026-09-08 | Normal | Planned | 0 | 0
FALSE |  | 296 | Review customer references | Hard_File_updated | 1 | 2026-09-09 | 2026-09-09 | Normal | Planned | 0 | 0
FALSE |  | 292 | Determine time required to ready external trainers | Hard_File_updated | 1 | 2026-09-10 | 2026-09-10 | Normal | Planned | 0 | 0
FALSE |  | 294 | Make outsourcing decision | Hard_File_updated | 1 | 2026-09-11 | 2026-09-11 | Normal | Planned | 0 | 0
FALSE |  | 297 | Outsourcing Review COMPLETE | Hard_File_updated | 0 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 298 | Trainer Needs Assessment COMPLETE | Hard_File_updated | 0 | 2026-09-11 | 2026-09-11 | Milestone | Planned | 0 | 0
FALSE |  | 261 | Create training delivery schedule | Hard_File_updated | 1 | 2026-09-14 | 2026-09-14 | Normal | Planned | 0 | 0
FALSE |  | 281 | Determine training delivery locations | Hard_File_updated | 1 | 2026-09-15 | 2026-09-15 | Normal | Planned | 0 | 0
FALSE |  | 289 | Review outsourcing options - event logistics | Hard_File_updated | 1 | 2026-09-16 | 2026-09-16 | Normal | Planned | 0 | 0
FALSE |  | 267 | Develop training delivery budget | Hard_File_updated | 4 | 2026-09-17 | 2026-09-22 | Normal | Planned | 0 | 0
FALSE |  | 278 | Training Delivery Logistics COMPLETE | Hard_File_updated | 1 | 2026-09-22 | 2026-09-23 | Normal | Planned | 0 | 0
FALSE |  | 302 | Create training plan with outputs of Content Development & Training Delivery Phases | Hard_File_updated | 1 | 2026-09-23 | 2026-09-24 | Normal | Planned | 0 | 0
FALSE |  | 305 | Training Delivery Planning Complete | Hard_File_updated | 0 | 2026-09-24 | 2026-09-24 | Milestone | Planned | 0 | 0
FALSE |  | 276 | Draft Overall Budget | Hard_File_updated | 1 | 2026-09-24 | 2026-09-25 | Normal | Planned | 0 | 0
FALSE |  | 275 | Acquire executive sign-off on budget | Hard_File_updated | 1 | 2026-09-25 | 2026-09-28 | Normal | Planned | 0 | 0
FALSE |  | 307 | Acquire executive sign-off on training plans | Hard_File_updated | 1 | 2026-09-28 | 2026-09-29 | Normal | Planned | 0 | 0
FALSE |  | 256 | Training Planning COMPLETE | Hard_File_updated | 0 | 2026-09-29 | 2026-09-29 | Milestone | Planned | 0 | 0
FALSE |  | 223 | Assemble content development team | Hard_File_updated | 1 | 2026-09-29 | 2026-09-30 | Normal | Planned | 0 | 0
FALSE |  | 222 | Define roles and responsibilities | Hard_File_updated | 1 | 2026-09-30 | 2026-10-01 | Normal | Planned | 0 | 0
FALSE |  | 253 | Create content development schedule | Hard_File_updated | 1 | 2026-10-01 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 244 | Review existing intellectual property | Hard_File_updated | 1 | 2026-10-02 | 2026-10-02 | Normal | Planned | 0 | 0
FALSE |  | 257 | Develop beta content | Hard_File_updated | 1 | 2026-10-02 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 228 | Perform SME review of training content | Hard_File_updated | 1 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 258 | Revise and update content | Hard_File_updated | 1 | 2026-10-03 | 2026-10-03 | Normal | Planned | 0 | 0
FALSE |  | 140 | Create "cheat sheets" and additional learning resources for customer support | Hard_File_updated | 1 | 2026-10-03 | 2026-10-04 | Normal | Planned | 0 | 0
FALSE |  | 229 | Acquire final content approval | Hard_File_updated | 1 | 2026-10-05 | 2026-10-05 | Normal | Planned | 0 | 0
FALSE |  | 274 | Create additional "train the trainer" learning materials | Hard_File_updated | 1 | 2026-10-05 | 2026-10-06 | Normal | Planned | 0 | 0
FALSE |  | 260 | Content Development COMPLETE | Hard_File_updated | 0 | 2026-10-05 | 2026-10-05 | Milestone | Planned | 0 | 0
FALSE |  | 264 | Create proficiency exams | Hard_File_updated | 4 | 2026-10-06 | 2026-10-07 | Normal | Planned | 0 | 0
FALSE |  | 404 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 2026-10-06 | 2026-10-06 | Milestone | Planned | 2 | 0
FALSE |  | 262 | Train additional trainers | Hard_File_updated | 1 | 2026-10-07 | 2026-10-08 | Normal | Planned | 0 | 0
FALSE |  | 269 | Prepare training venues | Hard_File_updated | 1 | 2026-10-08 | 2026-10-09 | Normal | Planned | 0 | 0
FALSE |  | 270 | Create communications plan | Hard_File_updated | 3 | 2026-10-09 | 2026-10-13 | Normal | Planned | 0 | 0
FALSE |  | 272 | Provide new hires with information on training program | Hard_File_updated | 1 | 2026-10-14 | 2026-10-14 | Normal | Planned | 0 | 0
FALSE |  | 310 | Send out communication to existing support resources regarding new training plan | Hard_File_updated | 1 | 2026-10-15 | 2026-10-15 | Normal | Planned | 0 | 0
FALSE |  | 150 | Training Delivery Engine Development COMPLETE | Hard_File_updated | 0 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 406 | Training/Readiness Development COMPLETE | Hard_File_updated | 0 | 2026-10-15 | 2026-10-15 | Milestone | Planned | 0 | 0
FALSE |  | 49 | Hire new resources | Hard_File_updated | 1 | 2026-10-16 | 2026-10-16 | Normal | Planned | 0 | 0
FALSE |  | 34 | Train new resources | Hard_File_updated | 1 | 2026-10-19 | 2026-10-19 | Normal | Planned | 0 | 0
FALSE |  | 389 | Certify new resources | Hard_File_updated | 3 | 2026-10-20 | 2026-10-22 | Normal | Planned | 0 | 0
FALSE |  | 407 | Resource Readiness Training COMPLETE | Hard_File_updated | 0 | 2026-10-22 | 2026-10-22 | Milestone | Planned | 0 | 0
FALSE |  | 409 | Deploy new customer service programs | Hard_File_updated | 1 | 2026-10-23 | 2026-10-23 | Normal | Planned | 0 | 0
FALSE |  | 13 | Determine success metrics | Hard_File_updated | 1 | 2026-10-23 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 410 | Program Deployment COMPLETE | Hard_File_updated | 0 | 2026-10-23 | 2026-10-23 | Milestone | Planned | 0 | 0
FALSE |  | 7 | Create method for tracking common problems and solutions | Hard_File_updated | 1 | 2026-10-26 | 2026-10-26 | Normal | Planned | 0 | 0
FALSE |  | 14 | Create method to track support issues vs. product aspects | Hard_File_updated | 1 | 2026-10-26 | 2026-10-29 | Normal | Planned | 0 | 0
FALSE |  | 141 | Create method for distributing common solutions to all support resources | Hard_File_updated | 1 | 2026-10-29 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 156 | Post Launch Preparation COMPLETE | Hard_File_updated | 0 | 2026-10-30 | 2026-10-30 | Milestone | Planned | 0 | 0
FALSE |  | 36 | Monitor customer support issues - look for common problems | Hard_File_updated | 1 | 2026-10-30 | 2026-10-30 | Normal | Planned | 0 | 0
FALSE |  | 9 | Aggregate best practices (solutions) - distribute to support services | Hard_File_updated | 1 | 2026-10-30 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 144 | Review support data, determine which product aspects cause the most support incidents | Hard_File_updated | 1 | 2026-11-02 | 2026-11-02 | Normal | Planned | 0 | 0
FALSE |  | 145 | Review resource performance, determine which ones are the most effective | Hard_File_updated | 1 | 2026-11-02 | 2026-11-03 | Normal | Planned | 0 | 0
FALSE |  | 146 | Revise training materials based on data collected from customer service program | Hard_File_updated | 2 | 2026-11-03 | 2026-11-05 | Normal | Planned | 0 | 0
FALSE |  | 411 | Post Launch Activities COMPLETE | Hard_File_updated | 0 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
FALSE |  | 155 | Customer Service Program Development COMPLETE | Hard_File_updated | 0 | 2026-11-05 | 2026-11-05 | Milestone | Planned | 0 | 0
Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Current Period (Time Now: 8/11/2026) | Hard_File (Time Now: 7/7/2026) | Hard_File (Time Now: 7/7/2026)
Project Finish | Project Finish | 2026-11-05 |  | 2026-11-05